2019-2023 National Strategy of the Labour and Employment Policy of Georgia

LOGICAL FRAMEWORK

Sector Priority 1: Support to Employment

| Aim 1 | Impact Indicator | Baseline Data | Target/Results to be Achieved | Implementation Period | Source of Verification | Compliance with the UN Sustainable Development Goals |
| --- | --- | --- | --- | --- | --- | --- |
| # Reducing discrepancies between supply and demand | Indicators for the unemployment rate among the persons with higher and vocational education | Unemployment rate indicator among the persons with higher education for 2017 - 15.5% | 13% | 2023 | GeoStat LFS data |  |
|  |  | Unemployment rate indicator among the graduates of the vocational institutions for 2017.-12.2% | 10% | 2023 | Geostat LFS data |  |

| Aim 1 | Specific Objectives | Results Indicator | Baseline Data | Target/Results to be achieved | Implementation Period | Source of Verification | Risks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # Reducing discrepancies between supply and demand | 1.1 Support to create jobs, among them throughout highly productive sectors | The number of new jobs in business sector (among them in highly productive sectors) | The number of the people employed in the business sector by 2018 - 660 875 | The number of the people employed in the business increase by 15%. | 2023 | GeoStat business statistics |  |
|  | 1.2 Support to develop market oriented highly qualified human resources | The number of vocational educational programs with work based learning approach | 29 vocational education programs launched with the work based learning approach | 40 vocational education programs launched with the work based learning approach | 2023 | # Ministry of Education, Science, Culture and Sport |  |
|  |  | The share of adult population (25 -64 y.o.) participating in life-long learning programs | 2017 – 1.6% | 1.9% | 2023 | Geostat LFS data |  |
|  |  | The share of young population (15-24 y.o.) participating in vocational educational programs | 2017 - 4.5% | 8% | 2023 | Ministry of Education, Science, Culture and Sport |  |
|  |  | A mechanism for the recognition of informal education is implemented | 2018- The number of qualifications recognizing informal education ა-0 | At least 2 qualifications | 2023 | Ministry of Education, Science, Culture and Sport |  |
|  | 1.3 Support to innovation and entrepreneurship | The number of applicants participating in programs offered by the Georgian Innovation and Technology Agency | 2018 – The number of applicants 620 The number of small grants - 294, Funding grants - 132, The number of participants in Start Your Business with FabLab 194 | The total number of applicants increased by 5% | 2023 | Ministry of Economy and Sustainable Development |  |
|  |  | The renewed module for entrepreneurship integrated into the VET and general education modular programs which are in compliance with the European Frame for Entrepreneurial Competence | 2018 – Work in progress to renew the module for entrepreneurship | Renewed module of entrepreneurship integrated into the program | 2023 | Ministry of Education, Science, Culture and Sport |  |
|  |  | The number of vocational education and school teachers that have undergone trainings in how to teach entrepreneurship | 2018 about 40 vocational education teachers | 200 vocational education teachers | 2023 | Ministry of Education, Science, Culture and Sport |  |

| Aim 2 | Impact Indicator | Baseline Data | Target /Results to be Achieved | Implementation Period | Source of Verification | Compliance with the UN Sustainable Development Aims |
| --- | --- | --- | --- | --- | --- | --- |
| Enhancing Active Labour Market Policy (ALMP) | Improvement of programs and institutional development of the body implementing the program | 2018 State Program Budget 2 950 000 | Increasing the budget for services supporting employment assistance services by 30% | 2023 | Ministry |  |
|  | Unemployment Indicator | 2018- 12.7% | <12% | 2023 | GeoStat |  |

| Aim 2 |  | Specific Objectives | Results indicator | Baseline Data | Target/Results to be Achieved | Implementation Period | Source of Verification | Risks |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enhancing Active Labour Market Policy (ALMP) |  | 2.1. Adoption of Employment Law | Draft Employment Law discussed with state bodies and social partners, initiatied to and adopted by the Parliament of Georgia | Initial draft of Employment Law | Legal basis governing ALMP and implementation in place | 2023 | Ministry |  |  |
|  |  | 2.2. Establishment of a state body implementing employment assistance programs | State Body implementing employment assistance programs operating throughout the country, offering different ALMP services | Employment Program Department under LEPL Social Service Agency | State body (LEPL) implementing ALMP services | 2023 | Ministry |  |  |
|  |  | 2.3 Improving services and activities supporting employment | The number of persons participating in ALMP services in terms of different characteristics: Region, age, gender, level of education, profession | The total number of participant by 2018 was 25 171, among them 14 611 women and 739 young people below 29. | The number of persons participating in the ALMP services increased by 15% |  |  |  |  |
|  |  |  | The share of job seekers participating in the ALMP service as compared to the total number | Total number of persons registered in Worknet by 2018 - 194 296. The share of job seekers engaged in the ALMP services makes up to 12.9% of the total number of the persons registered in the network | The share of job seekers engaged in ALMP services as compared to the total number increase by 17% | 2023 | State body implementing employment support programs |  |  |
|  |  |  | The number of regions that have already launched the new module of employment | 2018 - 2 | 7 | 2023 | State body implementing employment support programs |  |  |
|  |  |  | Percentage of the individuals registered in the data base for job seekers | Total number of persons registered in Worknet by 2018 - 194 296. The share of job seekers who became employed is 1% of the total number of the registered individuals | The indicator for the employed increased by 6% | 2023 | State body implementing employment support programs |  |  |
|  |  | 2.3 Enhancement of job seeker preparatory and training programs | Percentage of the individuals who became employed after they have undergone the job seeker preparatory-training programs | 2017 – 14% | 20%- | 2023 | State body implementing employment support programs |  |  |
|  |  |  | Percentage of job seekers participating in preparatory-training programs as compared to the total number of job seekers | 2018 - 1.5% | The share increased by 5% | 2023 | State body implementing employment support programs |  |  |
|  |  | 2.4 Enhancement of Labour Market Information System | The labour market information system is renewed visual -, program- and content wise. | 2018 labour market information system is on. | The date is renewed and the capacity is increased | 2023 | The Ministry of Economy and Sustainable Development |  |  |

| Aim 3 | Impact Indicator | Baseline Data | Target/Results to be Achieved | Implementation Period | Source of Verification | Compliance with the UN Sustainable Development Aims |
| --- | --- | --- | --- | --- | --- | --- |
| ## Support with targeted social and inclusive employment policy to encourage women and vulnerable groups to participate in labour market | The share of women participating in the labour market (%) | 2018-55,6% | >63.2% | 2023 | GeoStat LFS data |  |
|  | The share of NEET youth (15-24 y.o.) (%) | 2017-24,8% | <22.8% | 2023 | GeoStat LFS data |  |
|  | Discussion of feasibility of intoducting unemployment benefits, minimum wage and economic advisability of salary subsidies for the low-income employees | 2018- minimum wage 20 GEL | Regulatory impact assessment conducted, Related issues discussed in frames of social partnership, relevant decisions/plans made | 2023 | Ministry |  |
|  | Gini Coefficient (according to total consumer expenditure) | 2017 -0,37% | <0,35 | 2023 | GeoStat consumer expenditure data |  |

| Aim 3 | Objective | Results indicator | Baseline Data | Target/Results to be Achieved | Implementation Period | Source of Verification | Risks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Support with targeted social and inclusive employment policy to encourage women and vulnerable groups to participate in labour market | 3.1 Improvement of the link between employment and targeted social benefits | Employment indicator for employable socially unprotected persons who found employment through employment services | Job seekers with the Socially Unprotected status or job seekers who found employment through employment supporting services - 349 by 2018 | Employable socially unprotected people who found employment through employment supporting services increased by 45% | 2023 | LEPL Social Service Agency State body implementing employment support programs |  |
|  | 3.2 Support to gender equality and participation of women in labour market | Women Employment Rate | 2018 - 49,3% | 55% | 2023 | GeoStat |  |
|  | 3.3 Support integration of youth in labour market | Indicator for youth participating in employment support services | 765 young people (below 29) found employment in 2018 | At least 1000 young people (below 29 ) becomes employed every year through the agency | 2023 | State body implementing employment support programs |  |
|  |  | Employment indicator for young people between 15-29 y.o. with vocational education | 2017- 51.3% - | 56.4% | 2023 | GeoStat LFS data Geostat LFS data |  |
|  | 3.4 Support to senior citizen (over 55) employment | Percentage of the employed senior citizens | 2017 – Employment rate for people between 55-65 - 66.8%, 65+ - 38% | The indicator for senior citizen employment is increase by 3% | 2023 | GeoStat LFS data |  |
|  | 3.5. Support to low-qualified work force employment | The share of adults (25-64 y.o.) participating in life-long learning programs | 2017 - 1.6% | 1.9 % | 2023 | Geostat LFS data |  |
|  |  | The percentage of vocational educational institutions carrying out the LLL courses | 2018- 0 | 50% | 2023 | Ministry of Education, Science, Culture and Sport |  |
|  | 3.6 Support to Persons with Disabilities (PWDs) and Persons with Special Educational Needs (PSED) | Employment indicator for PWDs and PSEDs participating in state services | 2018 - 99 PWDs employed | Every year 120 PWDs and PSED are employed | 2023 | State body implementing employment support programs |  |
|  | 3.7 Support to ethnic minorities | Providing access to the Georgian language courses and expanding of target groups in order to support the engagement process of the representatives of the ethnic minorities living in compact settlements | 2018 target groups: youth, students, mobile groups and etc. | Continuity of the service: at least 2 target groups added | 2023 | State body implementing employment support programs Office of the state minister for reconciliation and civic equality |  |
|  | 3.8 Support to increase accessibility of the Internally Displaced People (IDPs) to livelihood |  |  |  |  |  |  |
|  |  | Beneficiaries’ access to the programs of the means of livelihood | In 2018 means of livelihood programs were used by 442 IDPs | Accessibility increased by 5% | 2023 | Ministry |  |
|  |  | IDP unemployment rate | 2014 – 32% | 25% | 2023 | GeoStat |  |

Sector Priority 2: Ensuring effective functioning of the labour market

| Aim 1 | Impact Indicator | Baseline Data | Target/Results to be Achieved | Implementation Period | Source of Verification | Compliance with the UN Sustainable Development Aims |
| --- | --- | --- | --- | --- | --- | --- |
| Advancement of the system for occupational safety and labour rights | Independent state body – Work Safety Inspection supervises the process of due enforcement of the labour legislation | The mandate of the Department of the Working Environment Inspection expands only over specific spheres determined by the Georgian legislation | An independent state body supervising the process of due enforcement of the labour legislation is established The mandate covers labour rights | 2023 | Ministry | Aim 8 |
|  | Reduction of occupational accidents at workplaces | The indicator of frequency of occupational traumas - 2.4; non lethal occupational trauma - 4.7 / As a result of occupational accidents 59 people died and 199 people were injured (in total 258) in 2018. | The number of occupational deaths and injuries is reduced by 30%- | 2023 | Ministry of Internal Affairs of Georgia |  |

| Aim 1 | Objective | Results indicator | Baseline Data | Target/Results to be Achieved | Implementation Period | Source of Verification | Risks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| # Advancement of system for enforcement of occupational health ands safety at work and labour rights | 1.1 Ensure that labour rights are upheld in accordance with international standards | Improvement of labour rights protection (freedom to establish unions s and collective agreements) based on the documents of the ILO and local legislation | Remarks and conclusions of the experts committee of the ILO regarding the compliance of the Georgian legislation with ILO conventions 2015 – collective agreements signed - 8 (articles 1, 2, 3, 4); freedom to establish unions - (Articles 2, 3) | The number of positive remarks from the experts committee of the ILO increased | 2023 | Ministry |  |
|  |  | The legislation reflects the labour norms determined by the Association Agreement | 19.02.2019 - Amendments made to the Georgian legislation according to 3 out 14 directives (2000/43/EC ; 2000/78/EC; 2004/113/EC)determined in the Annex XXX | 14 directives determined in the Annex XXX are extensively reflected in the legislation | 2023 | Ministry |  |
|  | 1.2 Enhancement of labour inspection | Number of inspections | 2018- 224 locations within the program; 90 companies within the legislation | Number of inspections per year - 1000 | 2023 | Ministry |  |
|  |  | Number of inspectors in relation to the number of employees | 2018 - 1 inspector per 44.584 employees | 1 inspector per 20,000 employees | 2023 | Ministry |  |
|  | 1.3 Enhancement of social dialogue and partnership | Improvement of the quality of the three-party dialogue on the national and regional levels on the decisions made or/and enforced. | In 2018 the three-party commission conducted 2 meetings and made 2 decisions in 2018 A social partnership three-party commission of the Autonomous Republic of Adjure is established , 1 meeting conducted | Minimum of 2 meetings per year | 2023 | Ministry |  |
|  | 1.4 Enhancement of labour mediation | The number of labour mediations and advancement of their qualification | 2018 - 11 mediators. 1 training conducted | The number of mediators - 15; 2 trainings per year | 2023 | Ministry |  |

| Aim 2 | Impact Indicator | Baseline Data | Target/Results to be Achieved | Implementation Period | Source of Verification | Compliance with the UN Sustainable Development Aims |
| --- | --- | --- | --- | --- | --- | --- |
| Improvement of labour migration management | Making amendments to the legislation regulating labour migration in response to the needs of the effective management of the labour market and the Georgian economy | Regulatory legal acts: The law of Georgia on Labour Migration; Ordinance of the government of Georgia N417 | Labour migration regulating legislation is compliant with international standards | 2023 | Ministry | Aim 8 |

| Aim 2 | Objective | Results indicator | Baseline Data | Target/Results to be Achieved |  | Implementation Period | Source of Verification |  | Risks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Improvement of labour migration management | 2.1 Support to circular migration | A multi-sided, trustworthy and constantly renewing data base about migrants is in operation | The number of persons willing to obtain temporary legal employment abroad registered in the data-base | At least 1 circular migration scheme is in operation | 2023 |  |  | Ministry Joint analytical system for migration |  |
|  |  | The number of cooperation agreements made by Georgia with other countries with the aim to obtain legal employment opportunities abroad | An agreement on the issue of granting residence to and supporting circular migration of the qualified specialists between the government of Georgia and and the French Republic is entered into force. | At least 3 Agreements | 2023 |  |  | Ministry |  |
|  |  | The share of the returned migrants who managed to obtain employment, become self-employed or launched their businesses by engaging into the state employment programs | 584 returned migrants were registered in the Reintegration Program for the Returned Migrants in 2018, among them 395 used reintegration assistance services | The number increased by 20% | 2023 |  |  | Ministry |  |
|  | 2.3 Support to integrate persons with international protection, and foreign citizens | Accessibility of various programs for persons with international protection and foreign citizens | 2017 – The reintegration program is available for everyone (in Georgia 110 beneficiaries participated in the reintegration program for persons with international protection, (23 women and 87 men) | Continuity of state services | 2023 |  |  | Ministry as the coordinator of the SCMI WG on integration, which unifies Ministries of: education, finances, economy, justice, internal affairs, state security, as well as invited agencies: ministry of foreign affairs, agriculture and UNHCR with respective NGOs. |  |