Review of Sector Reform Performance Contract - Skills Development and Matching for Labour Market Needs

Second Instalment Conclusive/Final Review Mission

May 11-29, 2020

Evaluation Team suggests to conduct the mission on May 11-29, 2020 (alternatively 18 May – 5 June). Main precondition for the start of the mission is that the basic documents to meet the requirements for compliance are provided prior to the mission i) end-April reporting requirements; b) associated reporting on developments surrounding the indicators; and c) documents associated with the General Public Policy Condition.

Main activities planned for the mission to be conducted on distance:

- Review of the documents to define the compliance with the BS requirements;

- Exchanges through emails and possible follow up E-meetings with following persons:

- Giorgi Gamkrelidze, Tsisnami Sabadze at MoESD, cc Ekaterine Mikabadze;

- Lika Klimiashvili at MoIDPLHSA, cc Tamila Barkalia, possibly also Marina Bezarashvili of the SSA (depending on the reporting provided);

- Irina Tserodze of VEDD at MoESCS, cc Tamar Kitiashvili, possibly also Dimitri Beridze of EMIS (depending on the nature of reporting provided);

- Nino Elbakidze of TPDC, cc Irina Tserodze and Tamar Kitiashvili

- Make a decision on compliance;

- Draft summary of conclusions;

- Communicating conclusions to the EUD and line Ministries;

- Conduct if necessary, video conference;

- Draft full Aide Memoire;

- Share Aide Memoire with EUD:

- Receive feedbacks and provide answers

Documents to be reviewed:

- Government self-assessment report(s) - MoESCS/MoIDPLHSA/MoESD;

- Labour Market Report on LMIS website (Indicator 1.1);

- SSA/ESS report on SESSA or SSA website (Indicator 2.1);

- VET student socioeconomic background analysis report (Indicator 3.1);

- Report on VET teachers' completion of pedagogic courses plus detailed attendance etc. evidence (Indicator 3.2);

- Reports on progress during 2019 for the Public Policy General Condition on

- - the VET Reform Strategy 2013-2020;

- - the State Strategy for the Formation of the Georgian Labour Market 2015-2018, and updates on the status of new follow-on strategy;

- Evidence of relevant budgetary allocations for and expenditure in 2019 and budget allocations for 2020-2023.

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Indicative Working Days |  |  | HB/F |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TL | KE2 | KE3 |  |
| Tasks & activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Second Instalment Final Review | May 11-29, 2020 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Review of the documents to assess compliance with the BS requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 2 | 2 | HB |
| - Determine need for clarification; explore through email exchanges and possible follow up E-meetings* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2.5 | 2.5 | 2.5 | HB |
| - Make a decision on compliance; draft summary of conclusions and share with EUD/Line Ministries |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 1 | 1 | HB |
| - Conduct if necessary, video debriefing conference |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.5 | 0.5 | 0.5 | HB |
| - Draft full Aide Memoire and share with EUD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 | 3 | 3 | HB |
| - Respond to feedback |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 | 0.5 | 0.5 | HB |
| Total w/d |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 10 | 9.5 | 9.5 |  |

note: *durationwill be dependent on speed and nature of responses from line ministries, and hence activities 2,3, and 5 may be conducted concurrently.