ROLLING WORK-PLAN No 2. TO TWINNING GRANT CONTRACT Twinning Project “Improving the standards of employment conditions/relations as well as health and safety at work in Georgia“ Twinning number: GE 17 ENI OT 02 19 WORK-PLAN AND BUDGET FOR THE PERIOD: 1 May – 31th October 2020

Contracting Authority

Delegation of the European Union to Georgia

64b Chavchavadze Avenue

0179 Tbilisi, Georgia

General remark:

This 2nd Rolling Work Plan issues from the Twinning Proposal “Improving the standards of employment conditions/relations as well as health and safety at work in Georgia”, which is an Annex 02b of the Twinning Grant Contract No. ENI/2019/409 - 668, taking into consideration rules of the Twinning Manual (revision 2017 - update 2018) and its Annex C15: Template for rolling work-plan.

According to the Twinning Manual (revision 2017 - update 2018), Section 5.2, the key initial task of the Project is elaboration of the initial work-plan, which is considered the first rolling work-plan covering at least the first six months. This initial rolling work-plan is the basis for the effective and timely implementation of the whole project. It stipulates detailed description of particular project activities, methods of their implementation, indicators, human resources and timing saturation.

ARTICLE 1: Objective

The Member State Project Leader Mr. Branislav Ondruš and the Beneficiary Project Leader Mrs. Tamila Barkalaia hereby notify the Contracting Authority of the detailed work-plan and budget of the above-mentioned Twinning Grant Contract for the 6 -month period from 1st May to 31th October 2020.

ARTICLE 2: Tasks (Inputs)

Budget Heading - RTA and related expenses

Indicators and benchmarks agreed:

-  timely and correct implementation of project activities in accordance to initial work plan

ensured

-  administrative management and mission backstopping, as well as translation and

interpretation services ensured by RTA assistants

Budget Heading – Horizontal costs

Sub-heading Steering Committee Meetings

Indicators and benchmarks agreed:

- 2nd Rolling WP is prepared and signed

- SCM is conducted to TW regulations

The first Project Steering Committee meeting was held on 28th November 2019 in accordance with the instructions of the actual Twinning Manual. This initial rolling work-plan was be discussed and approved at the PSC meeting on the same date.

The second PSC meeting was planned in March 2020, presenting the results of quarterly period 28th November – 27th February 2020 including reporting the period from 7th October – 28th November, and approving the extended work-plan of the next 3 months. During the reporting period it has been specified by EUD and agreed to follow 3 months reporting cycle. The Steering Committee to be organised in May will deal with 2 Interim Quarterly Reports, covering period 7th October, 2019 - 6th January, 2020 and 7th January 2020 - 6th April, 2020.

Activity 0.2. Steering Committee meeting

Method:

The MS Project Leader and Junior MS Project Leaders will dedicate at least 2 days per quarter for the management of the project during 24 months of the implementation period. This will include the SC meetings on a quarterly basis. This approach will guarantee the implementation is overseen and any difficulties are resolved immediately without any delay in timing.

During the period covered by the 2nd Rolling work-plan the third Steering Committee meeting will be organised in July/August, 2020, promote effective management and monitoring of the project activities. Progress in the areas of the project’s interventions will be discussed with the beneficiary and the members of the SC.

Apart from these meetings, it is planned that the Project Leaders, RTA and RTA counterpart, on both sides, will carry out the necessary preparatory activities essential for the proper functioning of the SC.

Resources

- Member State human resources needed: 3 MS experts, 6 WDs / 1 mission

Mr Branislav Ondrus, Mr Jose Ignacio Martin Fernandez, Ms Ulla Saar

- Beneficiary administration human resources: SC members: EUD, PAO, BC PL, RTA Counterpart, invited staff of the Labour and Employment Policy and Collective Labour Disputes Division of MoIDPHLSA, Labour Conditions Inspecting Department,

- Other resources: 0

Communication and Information

Indicator(s) and benchmark(s) agreed: Work plan plus Communication and Visibility plan preparation

Budget Heading - Mandatory Results / Components

Component 1/Mandatory result 1: Approximation of primary and secondary legislation related to Labour Law, Gender Equality, and Occupational Safety and Health in accordance with the Union acquis

Indicators of achievement:

Status of the legal basis allowing for a labour inspection system covering standard labour rights and working conditions;

Baseline: Legal basis is incomplete, in need of further  elaboration

Target: The legal basis allowing for a labour inspection system covering standard labour rights and working conditions elaborated;

Status of amendments in the field of Labour Law, Gender Equality, and Occupational Safety and Health as per Union acquis, with an inclusive and evidence-based approach.

Baseline: Delay in harmonisation of the legal framework  covering standard labour rights and working conditions reflected in amendments of the relevant laws

Target: Legal amendments prepared in the field of Labour Law, Gender Equality, and Occupational Safety and Health as per Union acquis, with an inclusive and evidence-based approach

.

Sub-result 1.1: Legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis

Number of the Tables of Concordance prepared for the Labour Law acquis, including aspects of labour inspection system

Baseline: 7

Target: 8 Directives

List of amendments to be made in the  Georgian primary and secondary labour legislation specified with explanatory notes

Baseline: 3

Target: 8 Directives

Activity 1.1.1: Aligning Georgian legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis

Method

The objective of this activity is providing support of the BC staff and relevant stakeholders to the transposition of the provisions of the relevant EU Directives in the field of labour legislation into a national legislation.

During a previous period, harmonisation of the labour code with “labour directives” has been finalised. Proposals for amendments of the primary and secondary legislation were  submitted, explained and discussed with the representatives of the MoIDPLHSA (Ms Irma Geliashvili and advisors of the Ministry) as well as with the team of ILO and Mr Tskitishvili. Taking into consideration the current state of play, the amendments of the Labour Code were prepared and submitted to start the legislation process.  2 versions of the Assessment of the amendments were prepared based on the package of 8 EU Directives (to be adopted in 2018 – 2020 as per AA/DCFTA) which has not been transposed yet.

This activity in this reporting period will be focused on the last update of the assessment based on a version submitted to the Parliament,  on assisting in elaboration of the relevant documents focused on application practise following the adoption of the Labour Code, providing expertise, consultation and training based on the request of the beneficiary.

Due to an outbreak of COVID - 19 and restriction measures applied we propose:

- 2 experts Mr Jozef Toman - 7 WD and Mr Maros Palik – 7 WD will be working from home in May to complete the assessment of the Labour Code based on its last version submitted to the Parliament. The beneficiary will use the assessment for the clarification and explanation of the amendments in the legislative process of the adoption of the Labour Code.

- 1 expert Mr Branislav Ondrus – 10 WD will work from home in July, August  to provide expertise on  application practise regarding the Chapter VIII. Labour remuneration of the Amendments of the Labour Code as well as related articles in terms of the minimum wage.

- 1 expert Mr Jose Ignacio Martin Fernandez 2 WD will work home based in July – consultation and exchange of a good practise on the implementation of the Labour Code

- At this stage of the planning it is not foreseen to apply home work for more experts. If this is a case during the implementation a separate justification agreed with the beneficiary will be provided to EUD by exchanging the emails among a Program Manager and RTA.

During the whole transposition process the participation of following departments, institutions and partners are considered essential in the implementation of this activity: MoIDPLHSA - Labour and Employment Policy and Collective Labour Disputes Division; Labour Conditions Inspecting Department; representatives of social partners; representatives of donors; the Tripartite Social Partnership Commission (TSPC);

Activities to be delivered will cover the following EU Directives to be adopted in 2018, 2019 and 2020 as per AA/DCFTA:

- 91/533/EEC on an employer's obligation to inform employees of the conditions applicable to the contract or employment relationship

- 1999/70/EC concerning the framework agreement on fixed-term work concluded by ETUC, UNICE and CEEP

- 97/81/EC concerning the Framework Agreement on part-time work concluded by UNICE, CEEP and the ETUC - Annex: Framework agreement on part-time work

- 2002/14/EC establishing a general framework for informing and consulting employees in the European Community - Joint declaration of the European Parliament, the Council and the Commission on employee representation

- 2001/23/EC on the approximation of the laws of the Member States relating to the safeguarding of employees' rights in the event of transfers of undertakings, businesses or parts of undertakings or businesses

- 98/59/EC on the approximation of the laws of the Member States relating to collective redundancies

- 2003/88/EC concerning certain aspects of the organisation of working time

Resources

- Member State human resources allocated: 8 MS experts, 53 WDs / 10 missions:

Kristina Balenovic 7 WD/1 misison; Jozef Toman 7 WD/1 misison home based, Maros Palik 7WD/1 misison home based; Seili Suder 5WD/1mission, Marillis Proos 5WD/1 mission; Jose Ignacio Martin Fernandez 7WD/2 missions; Gabriela Beltran Fernández  5WD/1 mission; Branislav Ondrus 10/2 mission (5WD/1 mission home based)

- Beneficiary administration human resources: all together around 20; staff of the Labour and Employment Policy and Collective Labour Disputes Division of MoIDPHLSA, Labour Conditions Inspecting Department, Technical working group members; social partners and other relevant stakeholders; specialists/ experts from the relevant institutions on the topic

- Other resources: Translation of amendments of the Labour Code, 100 pages

Provisional timeschedule of the missions:

First 2 weeks of May: Jozef Toman 7 WD home based, Maros Palik 7WD home based;

Last 2 weeks of July : Mr Branislav Ondrus 5WD home based, Mr Jose Ignacio Martin Fernandez 2 WD home based

Last 2 weeks of August: Mr Branislav Ondrus 5 WD/1 mission,

First 2 weeks of September: Seili Suder 5WD/1mission, Marillis Proos 5WD/1 mission, Kristina Balenovic 5WD/1 mission,

Last 2 weeks of Qctober: Jose Ignacio Martin Fernandez 5WD/1 mission; Gabriela Beltran Fernández  5WD/1 mission;

- Beneficiary administration human resources: all together around 20; staff of the Labour and Employment Policy and Collective Labour Disputes Division of MoIDPHLSA, Labour Conditions Inspecting Department, Technical working group members; social partners and other relevant stakeholders; specialists/ experts from the relevant institutions on the topic

- Other resources: Translation of amendments of the Labour Code, 100 pages

Activity 1.2.1: Analysis / Assessment of current legal framework on non-discrimination and gender equality including aspects of Labour Inspection System, in order to amend it in compliance with the EU aquis

Method

The objective of this activity is providing support of the BC staff and relevant stakeholders to the transposition of the provisions of the relevant EU Directives in the field of labour legislation into a national legislation.

Taking into consideration the current state of play, the amendments of the Labour Code have been prepared and submitted to start the legislation process.  Assessment of the amendments were prepared based on the package of 8 EU Directives (to be adopted in 2018 – 2020 as per AA/DCFTA) which has not been transposed yet.

This activity will be focused on assisting in elaboration of the relevant documents focused on application practise following to the Georgian legislative rules and/or consultation, training based on the request of the beneficiary.

Due to an outbreak of COVID - 19 and restriction measures applied we propose:

- 1 expert Mr Jose Ignacio Martin Fernandez - 5 WD will be working from home in the period of  May - June to complete the Table of Concordance 2004/113/EC implementing the principle of equal treatment between men and women in the access to and supply of goods and services  and Directive 79/7/EEC on the progressive implementation of the principle of equal treatment for men and women in matters of social security

- At this stage of the planning it is not foreseen to apply home work for more experts. If this is a case during the implementation a separate justification agreed with the beneficiary will be provided to EUD by exchanging the emails among a Program Manager and RTA.

During the whole transposition process the participation of following departments, institutions and partners are considered essential in the implementation of this activity: MoIDPLHSA - Labour and Employment Policy and Collective Labour Disputes Division; Labour Conditions Inspecting Department; representatives of social partners; representatives of donors; the Tripartite Social Partnership Commission (TSPC);

Activities to be delivered will cover the following EU Directives to be adopted in 2018, 2019 and 2020 as per AA/DCFTA:

- 2000/43/EC implementing the principle of equal treatment between persons irrespective of racial or ethnic origin

- 2000/78/EC establishing a general framework for equal treatment in employment and occupation

- 2006/54/EC on the implementation of the principle of equal opportunities and equal treatment of men and women in matters of employment and occupation

- 92/85/EEC on the introduction of measures to encourage improvements in the safety and health at work of pregnant workers and workers who have recently given birth or are breastfeeding (tenth individual Directive within the meaning of Article 16(1) of Directive 89/391/EEC).

- 2004/113/EC implementing the principle of equal treatment between men and women in the access to and supply of goods and services

- 79/7/EEC on the progressive implementation of the principle of equal treatment for men and women in matters of social security

Resources

- Member State human resources allocated: 2 MS Experts, 10WD/2 missions

Jose Ignacio Martin Fernandez 5 WD/1 mission home based; Gabriela Beltran Fernández  5WD/1 missions

Provisional timeschedule of the missions:

Last 2 weeks of May: Jose Ignacio Martin Fernandez 5 WD home based

First 2 weeks of September: Gabriela Beltran Fernandez 5 WD/1 mission

- Beneficiary administration human resources: all together around 20; staff of the Labour and Employment Policy and Collective Labour Disputes Division of MoIDPHLSA, Labour Conditions Inspecting Department, Technical working group members; social partners and other relevant stakeholders; specialists/ experts from the relevant institutions on the topic

- Other resources: 0

Activity 1.3.1: Aligning Georgian legal framework on Occupational Health and Safety, including aspects of Labour Inspection System, amended in compliance with the Union acquis:

Method

The objective of this activity is providing support of the BC staff and relevant stakeholders to the transposition of the provisions of the relevant EU Directives in the field of non-discrimination and gender equality legislation into a national legislation.

Based on the original planning 4 missions were planned to be conducted in the 2nd reporting period but were postponed to March and April, 2020. Due to a restriction measures of pandemic the missions weren’t implemented during a previous reporting periods, but were re planned into this period.

Taking into consideration the current state of play, there are 4 EU Directives from the package of 15 EU Directives (to be adopted in 2019 – 2020 as per AA/DCFTA) which have been identified as a priority to be transposed and will be dealt with during the implementation of the 2nd  work plan:

- 89/656/EEC on minimum safety and health requirements for the use of personal protective equipment – postponed from a previous work plan

- 92/58/EEC on minimum requirements for the provision of safety and health and/or health sign at work – postponed from a previous workplan

- 89/654/EEC on minimum safety and health requirements for the workplace

- 2009/104/EC on minimum safety and health requirements for the use of work equipment by workers at work

Moreover, during a previous reporting period the additional task was requested by the Beneficiary’s Project Partner the Makhviladze  Scientific - Research Institute of Occupational Medicine and Ecology with the consent of the BI-  to provide an expertise on the functioning the System of the Occupational Medicine in a selected  member states, focused on medical examinations (prior and periodic) in relation to work; diagnosis and treatment of occupational diseases, work-related illnesses and the consequences of accidents at work as well as identifying factors of work and working environment, performing their measurement, qualification and evaluation.

Due to an outbreak of COVID - 19 and restriction measures applied we propose:

- 3 experts Mr Ivan Majer - 15 WD,  Ms Ulla Saar  - 5 WD  and Ms Eva Poldis – 5 WD will be working from home in the period of  May - July to complete harmonisation of Directive 89/656/EEC on minimum safety and health requirements for the use of personal protective equipment and 92/58/EEC on minimum requirements for the provision of safety and health and/or health sign at work

- 2 experts Mr Michal Nemec 10 WD home based and Mr Slavomir Stastny 10 WD homebased will be working in the period of May  to provide an expertise on  functioning the System of the Occupational Medicine in a selected  member states for the Makhviladze  Scientific - Research Institute of Occupational Medicine and Ecology with the consent of the BI.

- At this stage of the planning it is not foreseen to apply home work for more experts. If this is a case during the implementation a separate justification agreed with the beneficiary will be provided to EUD by exchanging the emails among a Program Manager and RTA.

This activity will be focused on applying the general concept of transposition process, in accordance with the following pattern:

- The process of setting up of formal or non-formal Technical Working Group (standardised or flexible approach) will be discussed at the first working group meeting focused on the alignment of the first directive to be implemented. The STE will join the working groups proposed by the beneficiary and will support them in any phase of the process.

- Survey of Georgian legislation comparing if there are any provisions similar to those of the respective EU Directive.

  - Research of national legislation, comparing if there are any provisions similar to the relevant Directive, recording the findings into the Initial Comparative Table, which enable to analyse wording of particular provisions of EU Directive with text of various up-to-date national regulations and analyse the compliance (concordance).

  - Developing the list of primary and secondary legislation related to labour and other laws that should be revised.

  - Assessing the degree of compliance of existing primary and secondary legislation of Georgia with EU standards and requirements in the relevant field of law. According to the structure of missing provisions, it can be recommended to ensure transposition of the respective directive either through revision and amendment of existing national regulation or through development of a new regulation.

- Introductory meeting of TWG – provided technical and legal information for WG members on the topic of respective directive, and introduction of EU best practice. During this meeting also the structure, concept and content of new Regulation (if needed) proposed by the TW expert is discussed. Drafting the first proposal of the text of Regulation on the basis of comparative analysis of current legislation, a discussion at the 1st meeting and implementing good practice. This introductory workshop of the Technical Working Group will be focused on:

  - Providing basic information on the procedure of transposing process, principles of the respective EU non-discrimination and gender equality directive, technical and legal base of the topic of directive, results of comparative analysis and a proposal of the concept, structure and content of a new regulation (if needed), or amendments of the current law.

  - Based on the assessment, in the 2nd TWG meeting the text of the first draft - article by article in Georgian language would be verified. The development of the amended text or a new regulation will be discussed, fine-tuned and completed by the TWG during the 2nd or 3rd TWG meeting ensuring the inclusive progress and in agreement with corresponding stakeholders. Finalisation of the text, verification from the technical point of view and terminology. The English final version shall be fine-tuned by the twinning experts.

  - Team of BC experts will assist in elaboration of the accompanying documents, such as explanatory notes, regulatory and fiscal impact assessments, ‘Table of Concordance’, compliance with international legal standards, and other documents according to the Georgian legislative rules.

- STE will provide support throughout the consultation and approval process of the relevant legislation in the Georgian Parliament (e.g. assessment of new proposals and changes, suggestions of alternatives).

- During the whole transposition process the participation of the following departments, institutions and partners are considered essential in the implementation of this activity: MoIDPLHSA - Labour and Employment Policy and Collective Labour Disputes Division; Labour Conditions Inspecting Department; Technical and Construction Supervision Agency (TCSA), MoESD; The Tripartite Social Partnership Commission (TSPC); Representatives of social partners;

Resources

- Member State human resources needed: 7 MS experts, 70 WDs /14 missions

Ivan Majer  25 WD/5 missions (15 WD home based), Seili Sudder 5 WD/1 mission, Tomas Criado Navamuniel 5WD /1 mission, Eva Poldis 5WD /1mission (home based), Ulla Saar 10 WD/2 mission (5 WD home based),  Michal Nemec 10 WD/2 missions home based, Slavomir Stastny 10 WD/2 missions home based

Provisional timeschedule of the missions:

Last two weeks of May:  Ivan Majer  5 WD home based, Ulla Saar 5 WD home based,  Michal Nemec 5 WD home based, Slavomir Stastny 5 WD home based

First 2 weeks of June: Ivan Majer 5 WD home based, Eva Poldis 5 WD home based, Michal Nemec 5 WD home based, Slavomir Stastny 5 WD home based

First 2 weeks of July: Ivan Majer 5 WD home based,

September – October: Ivan Majer 10 WD/2 missions, Seili Sudder 5 WD/1 mission, Tomas Criado Navamuniel 5WD /1 mission, Ulla Saar 5WD/1 mission

- Beneficiary administration human resources: around 30; Staff of the Labour Conditions Inspecting Department of MoIDPHLSA, Technical working group members; social partners and other relevant stakeholders

- Other resources: Translation of Directives and relevant texts, 40 pages

Outputs:

- 4 Tables of Concordance prepared for the OSH acquis, including aspects of labour inspection system;

- 4 regulations prepared for further legislation specified with explanatory notes;

- 4 Quality checked translation of the OSH acquis with clear technical terminology (if necessary) completed;

Budget Heading - Mandatory Results / Component 2

Component 2: Capacity building, inter-institutional cooperation, and awareness raising of relevant state authorities and private sector for full implementation of amended legislation in labour law, gender equality and OSH

Indicator/benchmark agreed

- Functional review of the relevant state authorities to implement changes, including human and financial resources, administrative structures and equipment needed;

- Training needs analysis and plan of the whole staff of beneficiary department and representatives from other relevant institutions listed;

- Share of BA staff who received training to implement necessary changes and the representatives from other relevant institutions listed;

- Number of labour inspectors who are trained more to become ‘trainers’ with full knowledge and competency in implementing the new laws;

- Plan for improving institutional operations and procedures of the relevant state authorities to support their pilot implementation, each with clear competences and coordination roles;

- Number of written operational guidelines, manuals and procedures required to implement all changes, explaining all steps of implementation to the relevant staff;

- Number of OSH online Glossary and Risk Assessment checklists and their dissemination to relevant parties;

- Number of elaborated promotional materials and public information campaigns in printed and online media, TV and other tools;

- Share of private companies (i.e. both employers and workers) which are informed and number of citizens reached out on the new rules and changes made in labour legislation;

- Proposal for a structure of inter-institutional cooperation and working procedures, with a review of existing options;

- Working groups operational with team members from relevant institutions with a clear mandate and their continuous involvement in the “Technical Working Group” and “Coordination Group”.

Activity 2.1.1. Assessment of the administrative structures and institutional capacities of the beneficiary and relevant stakeholders and improvement of their inter-institutional operation

Activity was completed in 2nd reporting period and the days not spent will be reallocated to another activity.

Activity 2.1.2. Training needs analysis and strengthening the institutional capacity of the beneficiary and relevant stakeholders

Method

By signing the AA/DCFTA Georgia has to adapt to an enormous number of changes in a very short time. Civil servants are faced with the constantly changing or new regulatory framework which needs implementation and enforcement, as well as new demand from the growing private sector. These challenges can only be met if the staff (civil servants) are highly qualified and constantly updating their qualification.

The functional review conducted within activity 2.1.1. was complemented by the training need analysis (TNA), focused on defining the performance gap. This is what has to be filled by training and enables beneficiary to make informed decisions regarding the training and develop programs for both the management and staff in order to meet any organizational needs and requirements in the execution tasks related to full implementation of the (to be) amended legislation.

During the implementation of this activity the methodology of training for 3 target groups will be further elaborated, structure of the training modules will be further developed and the  training plan will be  adjusted to the  based on the current state of play in hiring of new labour inspectors. The training plan covering the beneficiary staff and representatives of the relevant key stakeholders will be developed for each individual institution.

Due to an outbreak of COVID - 19 and restriction measures applied we propose:

- 3 experts  Silja Soon -  WD6/1 misison home based,  Ms Consuelo Manchon Garcia   - 10 WD  and Ms Tamas Berky – 5 WD will be working from home in the period of  May - June to complete the training methodology and the  training plan.

- At this stage of the planning it is not foreseen to apply home work for more experts. If this is a case during the implementation a separate justification agreed with the beneficiary will be provided to EUD by exchanging the emails among a Program Manager and RTA.

Outputs:

- Training methodology and training plan completed

Resources

- Member State human resources needed: 3 MS Experts, 21WD/ 4 missions

Silja Soon 6 WD/1 mission,  Ms. Consuelo Manchón García 10 WD/2 missions,  Mr Tamas Berky 5/1 mission

Provisional timeschedule of the missions:

Last 2 weeks of May: Silja Soon 6 WD/1 mission home based,  Ms. Consuelo Manchón García 5 WD/1 mission home based,  Mr Tamas Berky 5/1 mission home based

Last 2 week of June: Ms. Consuelo Manchón García 5 WD/1 mission home based,

- Beneficiary administration human resources: Staff of the Labour Conditions Inspecting Department of MoIDPHLSA, social partners and other relevant stakeholders

- Other resources: translation of the directives (to be calculated)

Activity 2.1.3

Delivery of Training of Trainers of the labour inspectors

Method

- The activity is focused on the development of a specific Training Programme for labour inspectors to cover the immediate current need for enforcement of new legislation and implementation of new working methods and instructions. The developed training programme will be based on the principle of Training of Trainers and follow-up training for labour inspectors. Good practice examples confirm that inspectors shall be trained in their mother language, by local trainers to ensure better understanding which finally will contribute to the sustainability of the project outcomes after the completion of the project.

- The rationale of this ToT is to train general trainers for all presented themes, nevertheless it is a possibility to continue in specialisation on selected topics, according to the interest and experiences of particular inspectors-trainers.

- Missions were planned to start in March but based on agreement with ILO it has been postponed until September, 2020.

The following tentative training modules for initial/refreshment training could cover the following topics:

- General skills:

Communication skills

Time management skills

- Regulatory framework:

Labour Inspection performance on OSH Enforcement

Workplace, Work equipment, PPE

Construction sides, Asbestos, Signs

Chemicals, Carcinogens, ATEX, Biological agents

Manual handling, Noise, Vibration

Psychosocial aspects, Working conditions

- Sectors to be covered:

    - Construction

    - Service

    - Mining and heavy industry

    - Light industry

    - Medical

- The candidates for trainers will be identified through the preliminary screening process using some broad criteria for their selection. The success of the Training of Trainers will depend on the candidates’ professional and social skills, and their readiness for training. The following set of criteria for the selection process might be proposed for consideration: a) Qualifications and experience, b) Technical knowledge, c) Personal characteristics and skills.

- Trainers of labour inspector will obtain training materials for delivering their training (curricula and PPTs).

- The course will be complemented by examinations of Trainers of Inspectors, and awarding by certificates.

- At least 8 initial follow-up training courses for labour inspectors, delivered by the new trainers will be mentored by trainers of trainers.

- MS trainers will train a group of selected of maximum 10 labour inspectors. The course will consist of at least 30 days in the period of 8 months), covering training skills, technical issues, legislation issues, and organisational issues, as well as practical exercises and case studies of OSH procedures (the training model can be modified according to the recommendations and the needs of beneficiary). The training courses will be complemented by individual study of related documents and legislative acts.

Due to an outbreak of COVID - 19 and restriction measures applied we propose:

- 4 experts  Ivan Majer -  5 WD/1 missison home based,  Mr Marios Charalambous  5 WD/1 missison home based,  Ms Consuelo Manchon Garcia   - 5 WD  and Jose Ignacio Martin Fernandez – 5 WD/1 mission home based  will be working from home in the period of  July to develop training modules.

- At this stage of the planning it is not foreseen to apply home work for more experts. If this is a case during the implementation a separate justification agreed with the beneficiary will be provided to EUD by exchanging the emails among a Program Manager and RTA.

Outputs:

Following Training modules fully developed:

- Labour Inspection performance on OSH Enforcement

- Workplace, Work equipment, PPE

- Construction sites, Asbestos, Signs

- Delivery of one of the training modules - 3 days training/max 10 inspectors

Resources

- Member State human resources allocated: 4 MS Experts, 45WD/ 9 missions

Mr Ivan Majer  10/2 missions, Mr Marios Charalambous  10/2 missions, Consuelo Manchon Garcia 15/3 missions, Jose Ignacio Martin Fernandez 10/2 missions,

Provisional time schedule of the missions:

First 2 weeks of July: Mr Ivan Majer  5/1 mission home based, Mr Marios Charalambous  5/1 mission,

Last 2 weeks of July: Consuelo Manchon Garcia 5/1 mission home based, Jose Ignacio Martin Fernandez 5/1 mission home based,

Last 2 weeks of October: Mr Ivan Majer  5/1 mission home based, Mr Marios Charalambous  5/1 mission, Consuelo Manchon Garcia 5/1 mission, Jose Ignacio Martin Fernandez 5/1 mission,

Last 2 weeks of October: Consuelo Manchon Garcia 5/1 mission,

- Beneficiary administration human resources: 10 trainers; Staff of the Labour Conditions Inspecting Department of MoIDPHLSA, social partners and other relevant stakeholders

- Other resources: 0

Activity 2.1.4. Delivery of comprehensive training programmes to improve the institutional capacities of the beneficiary and relevant

Method

- New harmonised OSH legislation, new methodologies and guidelines, as well as new challenges for acting of beneficiaries’ staff involved in the approximation process as well as for labour inspectors require to provide specific broadly designed training with the aim of equal implementation, performance and enforcement.

- The activity should have been originally conducted in the period of February – May 2020 but the recruitment process of new inspectors was delayed and the initial training for at least 60 new inspectors and advanced training for 15 inspectors already working as inspectors was postponed as well. If the original assumption will be fulfilled and new labour inspectors hired both types of trainings can start to be implemented in September, October. On request of the beneficiary, the methodology of the training will be based on face to face training, not for alternative e-learning methods.

Based on the training needs analysis and the request of the beneficiary the TW team propose two key training programmes:

- An intensive induction training for newly hired inspectors

- A refresher and advanced training for existing inspectors

A detailed content of both training will be further elaborated during the preparation of the training modules:

Training of new inspectors

- Module 1: Introduction – LI and it’s duties and working internally

- Module 2:  Inspector’s safety

- Module 3 : OSH management at different level starting at LI role and basic principles for employer

- Module 4: Different occupational hazards at workplace

- Module 5: Procedures. How to fill the documents, how to do written ordinance, fines, suspend work etc

- Module 6: Investigation of occupational accidents and occupational diseases

Training for current staff – labour  inspectors (“refreshment”)

The training course will consist of 5 consecutive parts:

- The role of the LI

The first part of the training aims to provide attendants with a comparative view of European Labour Inspectorates and the model Georgia LI has selected to build up its LI on

2)	LI functions with a view to OSH enforcement

This second part of the training aims to provide LI with the references on how EU LIs deal with this new role based upon the structure of the Framework Directive and the Georgia OSH Law.

3)  Individual directives within the meaning of Article16 (1) of Council Directive 89/391/EEC

Directive is a legislative act that requires EU countries to achieve a certain result but leaves them free to choose how to do so. The Directives themselves gave rise to enforcement problems, inter alia, unclear or non-specific requirements, which were open to different interpretations, which may result in interpretation problems at the stage of enforcement as well. This part of the TR aims to share experiences on how EU Labour Inspectorates cope with this legal uncertainty.

4) Identify occupational hazards and preventive measures LI

LIs are expected to some extent to be able to rapidly identify situations that may compromise the safety and health of workers and judge if the measures implemented by the employers to avoid the risks are sufficient and appropriate. LI are also expected to develop their advisory functions on the best means of compliance with the law.  This part of the training aims to cover those needs.

5) Identify risks and preventive measures in different sectors

This part of the training aims to exercise the knowledge from the previous part on risk and preventative measure identification while operation in specific sectors

Sectors to be covered:

    - Construction

    - Service

    - Mining and heavy industry

    - Light industry

    - Medical

Due to an outbreak of COVID - 19 and restriction measures applied we propose:

- 6 experts  Ivan Majer -  5 WD/1 mission home based,  Mr Marios Charalambous  5 WD/1 mission home based,  Ms Consuelo Manchon Garcia   - 5 WD  and Jose Ignacio Martin Fernandez – 5 WD/1 mission,  Silja Soon - 5 WD, Laurencia Jancurova – 5 WD  home based  will be working from home in the period of  June to develop training modules.

- At this stage of the planning it is not foreseen to apply home work for more experts. If this is a case during the implementation a separate justification agreed with the beneficiary will be provided to EUD by exchanging the emails among a Program Manager and RTA.

Outputs:

- 4 training modules for newly hired Labour inspectors fully developed:

- Module 1: Introduction – LI and it’s duties and working internally

- Module 2:  Inspector’s safety

- Module 3 : OSH management at different level starting at LI role and basic principles for employer

- Module 4: Different occupational hazards at workplace

- Delivery of training for newly hired inspectors: 32 days of training delivered for 40 newly hired inspectors

- 3 training modules for senior inspectors developed:

- Modul 1 LI functions with a view to OSH enforcement

- Modul 2 The role of the LI

- Modul 3 Identify occupational hazards and preventive measures LI

- Delivery of training for senior inspectors: 8 days of training delivered for 14 inspectors

Resources

- Member State human resources needed: 8 MS experts, 95 WD / 19 missions

Consuelo Manchón García 10 WD / 2 missions,  José Ignacio Martín Fernández 15 WD / 3 missions, Gabriela Beltran Fernández  15 WD/3 missions,  Ms. Laurencia Jancurova 15 WD / 3 missions, Jaume ADMETLLA 5WD/1 mission, Ivan Majer 10/2 missions, Marios Charalambos 10 WD/2 mission, Silja Soon 15 WD/3 missions

Provisional timeschedule of the missions:

Last 2 weeks of June: Ms Consuelo Manchon Garcia   - 5 WD home based,  Jose Ignacio Martin Fernandez – 5 WD/1 mission home based,  Silja Soon - 5 WD, 5 WD/1 mission home based

First 2 weeks of July: Ivan Majer -  5 WD/1 mission home based,  Mr Marios Charalambous  5 WD/1 mission home based,  Laurencia Jancurova – 5 WD  home based

First 2 weeks of  August: Gabriela Beltran Fernández  5 WD/1 mission home based,

First 2 weeks of September: : Ms Consuelo Manchon Garcia   - 5 WD/1 mission,  Jose Ignacio Martin Fernandez – 5 WD/1 mission, Silja Soon - 5 WD, 5 WD/1 mission

Last 2 weeks of September: Ms Consuelo Manchon Garcia   - 5 WD/1 mission,  Jose Ignacio Martin Fernandez – 5 WD/1 mission, Silja Soon - 5 WD, 5 WD/1 mission

First 2 weeks of October - Ivan Majer -  10 WD/1 mission,  Mr Marios Charalambous  10 WD/1 mission,  Laurencia Jancurova – 5 WD

Last 2 weeks of October Gabriela Beltran Fernández  10 WD/1, Jaume ADMETLLA 5WD/1 mission

- Beneficiary administration human resources: Staff of the Labour Conditions Inspecting Department of MoIDPHLSA,

- Other resources: 0

Activity 2.2.1. Development of the relevant guidelines, labour inspection manuals, checklists and other tools to improve the institutional operations and procedures focused on precise implementation of newly adopted legislation

Method

The success of labour inspection performance depends on a good management, clear instructions, strict rules and standardised procedures. All processes shall be described and available for all inspectors and other relevant staff involved in the implementation of the newly adopted legislation. Therefore, suitable manuals and guidelines are essential.

Implementation of this activity is related to act. 1.3.1. Due to the harmonisation hasn’t started yet, this activity was postponed into a current period.

During these implementation period we will focus on development of operational guidelines and the check lists of the prioritised OSH Directives to be implemented and adapted to Georgian legal framework:

- 89/656/EEC on minimum safety and health requirements for the use of personal protective equipment

- 92/58/EEC on minimum requirements for the provision of safety and health and/or health sign at work

- 89/654/EEC on minimum safety and health requirements for the workplace

- 2009/104/EC on minimum safety and health requirements for the use of work equipment by workers at work

- During the implementation of the workplan 4 operational guidelines, 4 risks assessment checklists and the structure of OSH online glossary will be developed.

Due to an outbreak of COVID - 19 and restriction measures applied we propose:

- 4 experts  Ulla Saar -  5 WD/1 mission home based,  Mr Tomas Criado Navamuiel  5 WD/1 mission home based,  Ms Eva Poldis   - 5 WD  and Laurencia Jancurova – 5 WD/1 mission home based  will be working from home in the period of June to August develop requested guidelines.

- At this stage of the planning it is not foreseen to apply home work for more experts. If this is a case during the implementation a separate justification agreed with the beneficiary will be provided to EUD by exchanging the emails among a Program Manager and RTA.

Output:

- Operational guidelines for personal protective equipment and relevant checklists developed

- Operational guidelines for safety and health and/or health sign at work and relevant checklists developed

- Additional guidelines on the request of the beneficiary

Resources

- Member State human resources allocated: 6 MS experts, 55 WD / 11 missions

Ivan Majer 5 WD/1 mission, Seili Sudder  10 WD/2 missions, Tomas Criado Navamuniel 10WD /2 missions, Eva Poldis 10WD /2missions, Ulla Saar 10 WD/2 missions, Laurencia Jancurova 10 WD/2 missions

Provisional timeschedule of the missions:

Last 2 weeks of June:  Ulla Saar -  5 WD/1 mission home based,

First 2 weeks of August: Ms Eva Poldis  5 WD  home based, Mr Tomas Criado Navamuiel  5 WD/1 mission home based,  Laurencia Jancurova – 5 WD/1 mission home based

Last 2 weeks of September: Ivan Majer 5 WD/1 mission, Seili Sudder  5 WD/1 missions, Tomas Criado Navamuniel 5WD /1 mission, Eva Poldis 5WD /1mission,

First 2 weeks of October :Ulla Saar 5 WD/1 mission, Laurencia Jancurova 5 WD/1 mission

- Beneficiary administration human resources: Staff of the Labour Conditions Inspecting Department of MoIDPHLSA, social partners and other relevant stakeholders

- Other resources: 0

Activity 2.2.2. Preparing and implementing public information campaign aiming to raise awareness among the project among key stakeholders, public, private sector and civil society

Method

- Public awareness raising campaigns are an effective tool for increasing awareness of the private sector and citizens (companies, employers and workers) about legal changes, new requirements and practices, promoting occupational safety and health at the workplaces, increasing of awareness and motivation of employers and employees, as well as building a positive attitude of public. The project team attaches significance to this activity due to its comprehensive coverage and possibility of effective influence.

- During the previous 2 quarters a campaign on World OSH Day was prepared with the assistance of STE experts but due to a State of Emergency in Georgia printing of leaflets, posters and Opening Conference was postponed. An alternative short video was produced.

- During this period when the restrictive measures will be lifted, we will continue with all the messages proposed in the previously designed campaign.  Evaluation of the questionnaires will be completed in the beginning of the quarter.

- Second campaign will be prepared for the OSH week which will start in October. The campaign programme will be developed in cooperation with a working group nominated by the LCID, involving also social partners and other stakeholders. It is an intention to combine a topic of the official EU OSHA Campaign with presentation of new Georgian harmonised legislation, promotion of work culture and positive attitude to safety and health at work.

- The campaign programme will be proposed in the following areas:

- Information about legal changes, new requirements and good practice for different target groups - companies, employers and workers

- Delivering of the OSHA campaign materials (hangers, leaflets, brochures, posters)

- OSH Week promotion in October, 2020

- Organizing debates in TV and Radio

- Development of leaflets and brochures on promotion OSH and their dissemination

- Visits of at least 3 companies as a good OSH practice – with media

- Press releases

- The activities will be coordinated with the ILO and social partners.

Resources

- Member State human resources needed: 3 MS Experts, 30WD/ 6 missions

- Ms. Maria Mercedes Tejedor Aibar 5 WD/1 missions, Ms. Marta Zimmerman Verdejo 10 WD/2 missions, Ivan Majercak 5WD/ 1 mission, Branislav Ondrus 10 WD/2 misisons

- Beneficiary administration human resources: Staff of the Labour Conditions Inspecting Department of MoIDPHLSA, social partners and other relevant stakeholders

- Other resources: 4 500,- Eur (design, printing, purchasing the broadcasting time on TV, radio)

Activity 2.2.3. Conducting study visits to Member states, focused for transfer of good practices on organisation and management of labour inspection

Method

- Any organised study visits are always the most effective forms of transfer of good practice and experiences. Planned study visit to an EU Member State is aimed at bringing new ideas and challenges for those who are building the Labour Conditions Inspecting Department.

- Study visit was planned to be organised in May during the 1st workplan but the SV was postponed due to a pandemic to the 2nd workplan. We plan to organize 2 study visit:

- Estonia September, 2020 for a group of 5 representatives of the  beneficiary and 1 RTA language Assistant

- Slovakia, Czech Republic – in October, 2020 for a group of 7 representatives of the beneficiary and 1 RTA Language Assistant

- The aim of the study visit will be to introduce them the system and organisation of Labour inspectorates in Estonia, Slovakia and Czech Republic especially their inspection policies, organisational structures, management methods, human resources policy, methods of planning, inspection methods, information system, training system, implementation of ESAW/EODS, and other issues interested by beneficiary.

- The complex programme of the study visit will be drafted together with the Georgian partners and agenda of the study visit will be discussed and agreed with LCID.

- After the study visit an evaluation in a form of “Study Visit Report” will be prepared and follow up exercise will be conducted by all participants.

Resources

Member State human resources needed:

- Beneficiary administration human resources: 5 BC experts, 1 interpreter to Estonia, 7 BC experts, 1 interpreter to Slovakia, Czech Republic

- Other resources: 0

Activity 2.3.1.

Supporting inter-institutional cooperation in the process of approximation and implementation of the relevant EU acquis

Method

The inter-institutional cooperation is in the process of approximation and implementation of the relevant EU acquis one of the key elements which should ensure that developed policies and legislation (law making process) are implementable and meet government objectives.  Although the government regulations define the role and policy responsibilities of individual ministries (including their respective departments) they do not define the process or requirements for consultation, involvement of the different stakeholders in the policy development and level of cooperation.

During the initial phase of the project implementation the current institutional cooperation settings were reviewed, shortcomings were analysed and discussed with some members of the Technical Work Group (technical expertise staff including representatives of relevant stakeholders) who were involved regularly in the process of Directive´s transposition. A similar process will be done for the current members of the Coordination Group as well with the aim to ensure that inclusive, evidence-based policy and legislative development enables the achievement of intended policy objectives.

Several rounds of meetings will be focused on designing the appropriate proposal for a structure of inter-institutional cooperation and working procedures, with a review of existing options.

The proposal of the inter-institutional cooperation will be supported by the set of documents covering: description of the structure, clear mandate of the working group member, nomination of the working group member, description of the responsibilities, functions, professional requirements, guideline establishing clear relations and forms of cooperation.

Capacity building programme designed and implemented in the previous activities will be applied for these members as well, supported through the team building and other forms of participatory training.

Resources

- Member State human resources needed: 2 MS experts, 20 working days/4 missions will be allocated for the 2nd rolling work plan.

- Mr Branislav Ondrus 10/2 missions, Michal Nemec 10 WD/2 missions

- Provisional time schedule of the mission:

- First 2 weeks of September: Mr Branislav Ondrus 5WD/1 mission, Michal Nemec 5 WD/1 mission

- First 2 weeks of October: Mr Branislav Ondrus 5WD/1 mission, Michal Nemec 5 WD/1 mission

- Beneficiary administration human resources: Staff of the Labour Conditions Inspecting Department of MoIDPHLSA, social partners and other relevant stakeholders

- Other resources: 0

ARTICLE 3: Risks

Specify/update the internal conditions related to the project that must be fulfilled to guarantee efficient and timely implementation and achievement of results.

| Risk | Corrective measures/ Mitigation |
| --- | --- |
| Unexpected national and international policy or jurisdiction changes affecting the objectives of the project, e.g. slowdown of structural reforms | Continuous policy monitoring in order to react early in project governance. Close and regular exchange between project partners. |
| Inadequate commitment and support from decision making level in particular with regard to adoption of amended legislation, draft acts, guidelines and procedures | Close and regular exchange between project partners, in particular PL, JPL and RTA. Involvement of (MoIDPHLSA) decision-makers in workshops, consultations and presentations of output. |
| Unsuccessful beneficiary administration´s reorganization | Close and regular cooperation and communication between project partners. Regular Project Steering Committee meetings to inform on upcoming changes and if needed agree on actions to be taken. |
| Delay in implementation of project activities | Sufficient human and technical resources allocated in BC and MS administrations. Sound and joint planning of initial work plan. |

ARTICLE 4: Schedule

| Project Month 2020 | May | June | July | August | September | October |
| --- | --- | --- | --- | --- | --- | --- |
| Horizontal costs |  |  |  |  |  |  |
| Steering Committee |  |  |  |  |  |  |
| Component 0 |  |  |  |  |  |  |
| Activity 0.1 Kick-off |  |  |  |  |  |  |
| Activity 1.1.1 |  |  |  |  |  |  |
| Activity 1.1.2 |  |  |  |  |  |  |
| Activity 1.1.3 |  |  |  |  |  |  |
| Component 2 |  |  |  |  |  |  |
| Activity 2.1.1. |  |  |  |  |  |  |
| Activity 2.1.2. |  |  |  |  |  |  |
| Activity 2.1.3. |  |  |  |  |  |  |
| Activity 2.1.4. |  |  |  |  |  |  |
| Activity 2.2.1. |  |  |  |  |  |  |
| Activity 2.2.2. |  |  |  |  |  |  |
| Activity 2.2.3. |  |  |  |  |  |  |
| Activity 2.3.1. |  |  |  |  |  |  |

ARTICLE 5: Human Resources

| Member State or Beneficiary | Name | Present position | Employer | Years of experience | Education | Specialist knowledge | BC experience | Languages |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Slovakia 1 | JOSEF TOMAN | Director of the Legal department of the MoLSAF | Ministry of Labour, Social Affairs and Family, Slovakia | 17 | Comenius University of Bratislava | - Expert in industrial relations policy and practice; - Labour law and employment legislation, social dialog and collective bargaining; - Long-lasting experience with the transposition and implementation of the EU and the EP regulations and directives in the field of employment and social policy, social dialog and collective bargaining into the Slovak legislation | Slovak, English German | Serbia, Croatia, Romania, |
| Slovakia 2 | MAROS PALIK | Chief lawyer for labour relations | Regional Development Agency Senec-Pezinok, Slovakia | 16 | Faculty of Law, Comenius University, Bratislava, Slovak Republic | - Legal assistance in the field of labour law, labour law relations, individual and collective, anti-discrimination law - Legal analysis of labour legislation, anti-discrimination legislation and its alignment with the EC Directives related to labour relations acquis - Analysis of the labour code, occupational health and safety, employment, antidiscrimination, wage regulations and commitments arising from collective agreements, undeclared work - Member of the working group for amendment of the labour legislation in terms of undeclared work ( employment contract, fixed term part-time contract, atypical form of contracts, and development of the deterrence measures) | Slovak, English German | Georgia, Serbia |
| Slovakia 3 | IVAN MAJER | Advisor and Trainer | National Labour Inspectorate | 40 | Technical University, Faculty of Mechanical Engineering Kocise | - Profound knowledge, skills and experiences on occupational safety and health, prevention principles, risk assessment, - safety management, organisation of safety and health services, implementation of OSH legislation, OSH policies and OSH expertise | Slovak, English, Russian | Serbia, Croatia, Albania, Romania, Albania, Croatia, Kosovo, Turkish Cypriot Community, Turkey, Ukraine, Tunisia |
| Slovakia 4 | LAURENCIA JANCUROVA | Senior Inspector and the representative of Focal Point for European Agency for Health and Safety at Work | National Labour Inspectorate | 25 | Technical University, Faculty of Mining Engineering, Slovakia | - Profound experience in safety and health at work, prevention protection, risk management - unifying and rationalising of working methods of the labour inspectorates, - preparation of conceptual materials, programme materials and draft measures for improving the situation in the area of labour protection - development inspection manuals and instructions - implementation of OSHA activities at the national level | Slovak, English, Russian | Croatia, Albania, Romania, Albania, Croatia, Turkish Cypriot Community, Turkey, Ukraine, Tunisia |
| Slovakia 5 | Luba Pavlovova | Director/trainer | Regional Development Agency, Slovakia | 29 | Master in Engineering | - Highly experienced in implementing activities related to raising public awareness, management of several public campaigns - public awareness campaigns – preparation and implementation - development of the radio and TV spots, short documentary films, professional debate, round tables - training of trainers | English French Bulgarian Russian Serbian Croatian Czech Macedonian | Jordan, Croatia, Serbia, North Macedonia, BiH Romania Bulgaria Azerbaijan Albania Turkey Georgia |
| Slovakia 6 | Lubica turner | Trainer/methodologist | Regional Development Agency, Slovakia | 25 | Academic diploma MA in Education and Linguistics | - Extraordinary knowledge and professional skills in elaboration of training methodologies and evidence-based learning - Excellent trainer recognised at EU-level - Proven twinning experience in ToT in Serbia | English Serbian Croatian/Bosnian Russian French Macedonian | North Macedonia Croatia Monte Negro Jordan Serbia, Georgia |
| Croatia 7 | KRISTINA BALENOVIC | Legal Counsellor Specialist | Ministry of Labour and Pension System, Zagreb | 10 | Faculty of Law, Zagreb | - Knowledge and experience in necessary administrative structures and institutional capacities for the implementation of the relevant acquis | Croatian (native), English, Bosnian, Serbian, Slovene ,Spanish | Serbia, Montenegro Ukraine Portugal Slovenia |
| Croatia 8 | TOMISLAV MARKOTA | Legal Counsellor | National Labour Inspectorate, Zagreb | 10 | Faculty of Law, Zagreb | - Knowledge and practical experience in working in the EU approximation field | Croatian (native), English, Italian | Serbia, Montenegro |
| Hungary 9 | TAMAS BERKY | Management Counsellor | Regional Development Agency Senec-Pezinok, Slovakia | 19 | Corvinus University, School of Management, | - Extensive experience in training needs analysis (TNA), development of competency systems and competency based training and education programmes, as well as development of curricula, training methodology support, training delivery and evaluation | English Spain | Georgia Serbia Croatia Romania |
| Croatia 10 | ZDRAVKO MURATTI | Dep. Director of OSH Department | Ministry of Labour and Pension System, Zagreb | 32 | Faculty of Mechanical Engineering and Naval Architecture, Zagreb | - Proven working experience in alignment of the Croatian OSH legislation with EU acquis, - Knowledge and experience of drafting OSH legislation, including regulatory impact assessment, costing and inter-institutional coordination, - preparation of conceptual materials, programme materials and draft measures for improving the situation in the area of labour protection, developing good practice solutions for strengthening capacities to protect workers’ health, reducing of work relate accidents, - Member of the Focal Point EU-OSHA, - drafting opinion on legal OSH provisions; provide explanations to workers, employers, trade unions and employers association; monitoring judicial practice in OSH issue; providing opinion on drafts and proposed regulations form other government bodies. | English | Croatia |
| SPAIN 11 | concepción pascual lizana | Team Leader Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency.(Ministry of Labour, Migrations and Social Security) | 34 | Law degree | - Transposition of EU Directives on OSH. - Occupational Safety and Health. - Labour relations. - Social Partners. - 2008 – 2012 Director National Institute Safety and Health at Work (INSST) of Spain. - EU OSHA governing board member. - ACSH member. | English French | Ecuador |
| SPAIN 12 | consuelo manchón garcía | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. (Ministry of Labour, Migrations and Social Security) | 20 | Political Science and Sociology | - Occupational Safety and Health. - Labour relations. - Social Partners. - 2007 – 2019, Chief OSH Unit Labour and Social Security Inspectorate, Albacete. - 2005 – 2007, Associate professor, Law Universidad Castilla – La Mancha. Teacher LSSI School. - 2009, external consultor ILO, “enhancing LI effectiveness”, FYR Macedonia. - 2010, SLIC exchange, OSH, Romania. - 2011, Speaker “OSH inspection visit”, ITC ILO, Turin Italy. - 2014-2015, project coordinator, ILO “increasing workplace compliance through LI”, Vietnam. - 2015, Speaker “risks assessment OSH”. - 2016, OSH and LI, Panama | English | Sweden. Cape Verde Mexico |
| SPAIN 13 | JUAN MARTÍN GARCÍA ALLOZA | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. (Ministry of Labour, Migrations and Social Security) | 34 | - Law degree - Postgraduate courses. - Superior Technician on OSH. | - Occupational Safety and Health. - Labour relations. - Social Partners. - 1990 -1996, 2015 – 2016, Associate professor, Law Valencia University - Teacher LSSI School - 1987, training LI. Bolivia - 1996, Training OSH LI, Bolivia. - 1997, training OSH LI, Bolivia. - 2000, TU worker’s, Guatemala. - 2005, Labour mediation and conciliation, ILO, Bolivia | English | Colombia El Salvador Bolivia |
| SPAIN 14 | MARÍA MERCEDES TEJEDOR AIBAR | Head International Relations Department | National Institute Safety and Health at Work (INSST) of Spain. Ministry of Labour, Migrations and Social Security. | 23 | Industrial engineer. Ecomonics degree. Master in OSH. Auditor in OSH. | - Transposition of EU Directives on OSH. - Occupational Safety and Health. - Labour relations. - Social Partners. - EU OSHA governing board alternate member. - ACSH alternate member. - PEROSH. | English French | EU OSHA governing board alternate member |
| SPAIN 15 | marta zimmermann verdejo | Head Research and Information Department. | National Institute Safety and Health at Work (INSST) of Spain. Ministry of Labour, Migrations and Social Security. | 33 | Degree in Medicine and Surgery Postgraduate specialization Epidemiology and Public Health. Master degree in Public health Degree in design and statistics methodology for health sciences. Master degree in field of Epidemiology Training programs | - Transposition of EU Directives on OSH. - Occupational Safety and Health. - Labour relations. - Social Partners. - Spanish strategy for safety and health at work. - Surveys on working conditions. - Work relates accidents, occupational diseases. - Epidemiological reports. - Scientific steering group PEROSH. - External expert EUROFOUND. | English | EUROFOUND. |
| SPAIN 16 | RAQUEL CALVERAS AUGÉ | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. Generalitat Cataluña. | 31 | Law degree | - Occupational Safety and Health. - Labour relations. - Social Partners. | English French | STE TW Romania, |
| SPAIN 17 | JAIME ADMETLLA RIBALTA | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. Generalitat Cataluña | 34 | Law degree | - Occupational Safety and Health. - Labour relations. - Social Partners. | English | Czech Republic, Romania, |
| SPAIN 18 | Gabriela Beltran Fernandez | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. (Ministry of Labour, Migrations and Social Security) | 37 | Degree in Law | - In accordance to European acquis and Spanish Legal framework, on site Labour and Social Security Subinspector activities, task of control at the working sites in all areas with relevant competences - Occupational Health and Safety OHS (Factories, Entreprises,Building construction sector, on-site inspectionvisits, campaigns sector ),talks with representatives of social agents, workers, workers’ representatives, Trade Unions, employers’ associations, within the occasion of labour conflicts, strikes, layoffs, etc. - Antidiscrimination, gender equality, Gender Pay Gap | English French Italian Arab | EU ILO |
| SPAIN 19 | Tomas Criado Navamuniel | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. (Ministry of Labour, Migrations and Social Security) | 10 | Law degree Universidad Complutense de Madrid, Madrid (Spain) | - Compliance with social legislation, advising, reporting, assessment, mediation or interaction with workers and entrepreneurs’ representatives, - Good command and deep knowledge of the European Acquis in the fields of OSH, Labour Law, Social Security, Labour Migration, Equality, Undeclared Work and Labour Relations. | English French Romanian | Romania Albania Panama |
| SPAIN 20 | JOSÉ IGNACIO MARTÍN FERNÁNDEZ | Labour and Social Security Inspector. International Relations Unit. | Labour and Social Security Inspectorate of Spain State Agency. (Ministry of Labour, Migrations and Social Security) | 20 | Law degree Jean Monnet Course on European legal Culture | - Transposition of EU Directives on OSH. - ILO Conventions and Regulations. - Technical counsellor ILC 2018 ILO “ending violence and harassment in the world of work”. - ILO legal officer, CEACR 2016. - Occupational Safety and Health. - Labour relations, Social Partners, EU Strategy on OSH. - Spanish strategy for safety and health at work. - SLIC European Campaigns. - SLIC working groups. - SLIC LI exchange programs. - Psychosocial risks. - IMI system. Posting of workers. - ECPW, EPAUW, working groups. - EUROFOUND governing board alternate member. - Teacher LSSI School. - Teacher National Institute Public Administration. - Teacher master access to legal practice. | English French Portuguese Italian Russian | see CV. |
| Estonia 21 | Eva Põldis | Adviser in Working Life Development Department, Work Environment Unit | Ministry of Social Affairs of Estonia | 4 years in the field of OSH | Master´s degree in economics | - Knowledge and experience of drafting labour legislation (with focus on OSH), including regulatory impact assessment and inter-institutional coordination. - Experience in developing strategy documents and implementation guidelines. - Knowledge and experience working on legal approximation issues, particularly Union acquis. - Knowledge and experience of developing public consultations, information campaigns and awareness raising. - Good command of written and spoken English. - Good computer literacy (word, excel, power point). | English | Member of the Advisory Committee on Safety and Health, Member of Baltic Sea Network of Occupational Health and Safety |
| Estonia 22 | Silja soon | Head of Supervisory Department | Labour Inspectorate of Estonia | Since 1995 | Medical doctor | - Occupational health and safety - Occupational hazards and their effect to the health | English | Member of SLIC working groups (Chemex, Long Latency, Enforcement) |
| Estonia 23 | Seili Suder | Working Life Development Department, Head of Work Environment | Ministry of Social Affairs of Estonia | Since 2005 | Magister Juris degree in law at the University of Tartu, where she is currently also pursuing a doctorate degree. | - 14 years of professional experience in the field of labour legislation (both individual and collective labour law and OSH), 2 years of it in the Labour Inspectorate of Estonia - knowledge and experience of drafting labour legislation (labour law, OSH) - knowledge of relevant EU legislation and other international instruments (European Social Charter and ILO conventions, labour law, OSH) - working experience on EU legislation and practical law enforcement issues in Member States - experience in developing strategy documents, implementation guidelines, operational/ procedural manuals and instruction handbooks - Knowledge and experience of developing public consultations, information campaigns and awareness raising. - Good command of written and spoken English. - Good computer literacy (word, excel, power point). - Member of the working party on Occupational Safety and Health Signs Directive 92/58/EEC (special working party in the Advisory Committee on Safety and Health at Work). | English | Finland, Ireland |
| Estonia 24 | Mariliis Proos | Working Life Development Department, Head of Employment Relations | Ministry of Social Affairs of Estonia | Since 2002 | Degree equal to bachelor’s degree in law | - 17 years of professional experience in the field of labour legislation (both individual and collective labour law and labour dispute resolution), 4,5 years of it in the Labour Inspectorate of Estonia and 4,5 years in trade union - knowledge and experience of drafting labour legislation - knowledge of relevant EU legislation and other international instruments (European Social Charter and ILO conventions) - working experience on EU legislation, ILO instruments and practical law enforcement issues in Member States - experience in developing strategy documents, implementation guidelines, operational/ procedural manuals and instruction handbooks - experience in industrial relations (industrial actions, collective bargaining) - knowledge and experience of developing public consultations, information campaigns and awareness raising. - Member of the Advisory group for the European Labour Authority - Member of the European Commission Committee of Experts on Posting of workers and subgroup on the transposition of directive 2018/957/EU. | English | Participation experience in the working group meetings of the Council of European Union. Presidency of EU. |
| Austria 25 | Manuela HARGASSNER-DELPOS | Senior Specialist | Austrian Federal Ministry of Labour, Social Affairs, Health and Consumer Protection | 25 | University of Vienna/Social Sciences Faculty (Vienna, Austria) | Training methodologist, Training of trainers Soft skills Gender Mainstreaming implementation | English German | Czech Republic Azerbaijan |
| Greece 26 | Marios Charalambous | Senior advisor | Regional Development Agency, Professional Adult Trainer | 27 | Higher Technical Institute, Nicosia, Cyprus | Development of working tools for labour inspectors Training of Trainers of State Labour Inspectorate on Effective Labour Inspection Performance Safety and Health on construction sites | English | Kosovo, Saudi Arabia Serbia |

ARTICLE 6: Budget

We hereby provide you with Budget including details of the activities according to the Initial Work-plan.

I. BUDGET HEADING: Resident Twinning Advisor and related cost” and “

II. BUDGET HEADING: Horizontal activities related Costs” are kept as in original budget included in the Twinning contract because these costs are foreseen and known for the entire implementation of the Twinning project (24months).

III. BUDGET HEADING: Components Mandatory Results” is further updated with the Activities foreseen in the period covered by the Initial Work-plan.

| Annex A3 - WorkPlan 1 (incl. SL1) |  |  |  |  | Annex A3 - WorkPlan 1 after SL2 |  |  | Annex A3 - WorkPlan 2 after SL2 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Action to be undertaken under the Twinning project "Improving the standards of employment conditions/relations as well as health and safety at work in Georgia" Twinning Number: GE 17 ENI OT 02 19 (GE) |  |  |  | Note | Unit cost | Number of Units | Total MS costs | Unit cost | Number of Units | Total MS costs |
| General provision |  |  |  |  |  |  |  |  |  |  |
| I. BUDGET HEADING: Resident Twinning Advisor and related cost |  |  |  |  |  |  |  |  |  |  |
| Compensation wage and non wage |  |  |  | 2 | 5 500,00 | 24 | 132 000,00 | 5 500,00 | 24 | 132 000,00 |
| Compensation Daily Subsistence |  |  |  | 3 | 148,50 | 731 | 108 553,50 | 148,50 | 731 | 108 553,50 |
| Removal |  |  |  | 4 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0,00 |
| Travel |  |  |  |  |  |  |  |  |  |  |
| Taking up duty |  |  |  | 5 | 457,00 | 2 | 914,00 | 457,00 | 2 | 914,00 |
| Accompanying Family |  |  |  | 6 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0,00 |
| Annual Return Trip |  |  |  | 7 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0,00 |
| Annual Return Trip spouse and family |  |  |  | 8 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0,00 |
| Monthly Travel |  |  |  | 9 | 457,00 | 23 | 10 511,00 | 457,00 | 23 | 10 511,00 |
| School Fees |  |  |  | 10 | 1,00 | 0 | 0,00 | 1,00 | 0 | 0,00 |
| RTA Training Brussels |  |  |  |  |  |  |  |  |  |  |
| Travel Costs |  |  |  | 11 | 550,00 | 1 | 550,00 | 550,00 | 1 | 550,00 |
| Daily Subsistence Allowance |  |  |  | 12 | 232,00 | 2 | 464,00 | 232,00 | 2 | 464,00 |
| RTA Assistants contracts |  |  |  |  |  |  |  |  |  |  |
| Assistant(s) |  |  |  | 13 | 1 600,00 | 24 | 38 400,00 | 1 600,00 | 24 | 38 400,00 |
| Interpreter/translator salary |  |  |  | 14 | 1 600,00 | 24 | 38 400,00 | 1 600,00 | 24 | 38 400,00 |
| I. Total Resident Twinning Advisor Related Cost |  |  |  |  |  |  | 329 792,50 |  |  | 329 792,50 |
| II. BUDGET HEADING: Horizontal activities related Costs |  |  |  |  |  |  |  |  |  |  |
| Short term staff: MS PL and other Support staff / Component Leaders |  |  |  |  |  |  |  |  |  |  |
| Work Plan preparation* |  |  |  | 23 | 350,00 | 13 | 4 550,00 | 350,00 | 13 | 4 550,00 |
| Steering Committees* |  |  |  | 23 | 350,00 | 42 | 14 700,00 | 350,00 | 42 | 14 700,00 |
| Communication/Visibility programme* |  |  |  | 23 | 350,00 | 0 | 0,00 | 350,00 | 0 | 0,00 |
| Twinning Project Support Cost |  |  |  |  | 136% |  | 26 180,00 | 136% |  | 26 180,00 |
| Compensation for Daily Subsistence |  |  |  | 12 | 198,00 | 79 | 15 642,00 | 198,00 | 79 | 15 642,00 |
| Travel Costs Bratislava (PL 7xSCM) |  |  |  | 11 | 457,00 | 7 | 3 199,00 | 457,00 | 7 | 3 199,00 |
| Travel Costs Madrid (JPL 1xWP, 7xSCM) |  |  |  | 11 | 565,00 | 8 | 4 520,00 | 565,00 | 8 | 4 520,00 |
| Travel Costs Albacete (CL2 1xWP, will be based on real costs) |  |  |  | 11 | 616,00 | 1 | 616,00 | 616,00 | 1 | 616,00 |
| Travel Costs Tallinn (JPL 1xWP, 7xSCM)*** |  |  |  | 11 | 399,00 | 8 | 3 192,00 | 399,00 | 8 | 3 192,00 |
| PC PL and/or RTA Counterpart Training Brussels |  |  |  |  |  |  |  |  |  |  |
| Travel Costs |  |  |  | 11 | 550,00 | 1 | 550,00 | 550,00 | 1 | 550,00 |
| Compensation for Daily Subsistence |  |  |  | 12 | 232,00 | 2 | 464,00 | 232,00 | 2 | 464,00 |
| Communication/Visibility programme |  |  |  |  |  | Up to |  |  | Up to |  |
| Maximum amount for all components |  |  |  | 15 | 15 000,00 | 1 | 15 000,00 | 15 000,00 | 1 | 15 000,00 |
| Purchase of Goods |  |  |  | 16 | 0,00 | 1 | 0,00 | 0,00 | 1 | 0,00 |
| Expenditure Verification / Audit costs |  |  |  | 21 | 5 000,00 | 1 | 5 000,00 | 5 000,00 | 1 | 5 000,00 |
| II. Total Horizontal Related Costs |  |  |  |  |  |  | 93 613,00 |  |  | 93 613,00 |
| III. BUDGET HEADING: Components Mandatory Results |  |  |  |  |  |  |  |  |  |  |
| Component 0: Kick-off meeting and Closing event |  |  |  |  |  |  |  |  |  |  |
| Activity 0.1 Kick-off meeting |  |  |  |  |  |  |  |  |  |  |
| JPL Jose Ignacio Martin Fernandez x 2WDs/1mission |  |  |  |  |  |  |  |  |  |  |
| Flat Daily Allowance |  |  |  |  | 350,00 | 2 | 700,00 | 350,00 | 2 | 700,00 |
| Twinning Project Support Cost |  |  |  |  | 136% |  | 952,00 | 136% |  | 952,00 |
| Compensation for Daily Subsistence |  |  |  | 12 | 198,00 | 4 | 792,00 | 198,00 | 4 | 792,00 |
| Travel Costs Madrid |  |  |  | 11 | 565,00 | 0 | 0,00 | 565,00 | 0 | 0,00 |
| Other Costs (interpretation, translation, venue costs) |  |  |  | 18 | 0,00 | 1 | 0,00 | 0,00 | 1 | 0,00 |
| Activity 0.1 |  |  |  |  |  |  | 2 444,00 |  |  | 2 444,00 |
| Component 0 |  |  |  |  |  |  | 2 444,00 |  |  | 2 444,00 |
| Component 1: Approximation of primary and secondary legislation related to Labour Law, Gender Equality, and Occupational Safety and Health in accordance with the Union acquis |  |  |  |  |  |  |  |  |  |  |
| Activity 1.1.1 Aligning Georgian legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis |  |  |  |  |  |  |  |  |  |  |
| 8 MS experts, 85WDs / 17 missions - Zagreb: Kristina Balenovic 11 WD/3 missions, - Bratislava: Jozef Toman 17 WD/3 missions, Maros Palik 12WDs/2 missions, Branislav Ondrus 10WD/2 missions - Tallin: Saili Suder 10WD/2 missions, Marilis Proos 10WD/2 missions, - Madrid: Jose Ignacio Martin Fernandez 10 WD/2 missions, - Donostia / San Sebastian: Gabriela Beltran Fernández 5WD/1 missions, - Valencia: Juan Martin Garcia Alloza 5WD/1 missions, |  |  |  |  |  |  |  |  |  |  |
| Flat Daily Allowance |  |  |  |  | 350,00 | 85 | 29 750,00 | 350,00 | 85 | 29 750,00 |
| Twinning Project Support Cost |  |  |  |  | 136% |  | 40 460,00 | 136% |  | 40 460,00 |
| Compensation for Daily Subsistence |  |  |  | 12 | 198,00 | 102 | 20 196,00 | 198,00 | 102 | 20 196,00 |
| Travel Costs Bratislava |  |  |  | 11 | 457,00 | 7 | 3 199,00 | 457,00 | 7 | 3 199,00 |
| Travel Costs Madrid |  |  |  | 11 | 565,00 | 2 | 1 130,00 | 565,00 | 2 | 1 130,00 |
| Travel Costs Valencia** |  |  |  | 11 | 616,00 | 0 | 0,00 | 616,00 | 0 | 0,00 |
| Travel Costs Donostia / San Sebastian (will be based on real costs) |  |  |  | 11 | 616,00 | 1 | 616,00 | 616,00 | 1 | 616,00 |
| Travel Costs Tallin*** |  |  |  | 11 | 399,00 | 4 | 1 596,00 | 399,00 | 4 | 1 596,00 |
| Travel Costs Zagreb (will be based on real costs) |  |  |  | 11 | 500,00 | 3 | 1 500,00 | 500,00 | 3 | 1 500,00 |
| Translation |  |  |  | 18 | 12,00 | 100 | 1 200,00 | 12,00 | 100 | 1 200,00 |
| Activity 1.1.1 |  |  |  |  |  |  | 99 647,00 |  |  | 99 647,00 |
| Activity 1.2.1 Analysis / Assessment of current legal framework on non-discrimination and gender equality including aspects of Labour Inspection System, in order to amend it in compliance with the EU aquis |  |  |  |  |  |  |  |  |  |  |
| 3 MS experts, 25WDs / 5missions - Valencia: Mr. Juan Martín GARCÍA ALLOZA 5WD/1 missions, - Madrid: Jose Ignacio Martin Fernandez 15 WD/3 missions, Gabriela Beltran Fernández 5WD/1 mission, |  |  |  |  |  |  |  |  |  |  |
| Flat Daily Allowance |  |  |  |  | 350,00 | 25 | 8 750,00 | 350,00 | 25 | 8 750,00 |
| Twinning Project Support Cost |  |  |  |  | 136% |  | 11 900,00 | 136% |  | 11 900,00 |
| Compensation for Daily Subsistence |  |  |  | 12 | 198,00 | 31 | 6 138,00 | 198,00 | 31 | 6 138,00 |
| Travel Costs Madrid |  |  |  | 11 | 565,00 | 4 | 2 260,00 | 565,00 | 4 | 2 260,00 |
| Travel Costs Valencia** |  |  |  | 11 | 616,00 | 1 | 616,00 | 616,00 | 1 | 616,00 |
| Translation |  |  |  | 18 | 12,00 | 0 | 0,00 | 12,00 | 0 | 0,00 |
| Activity 1.2.1 |  |  |  |  |  |  | 29 664,00 |  |  | 29 664,00 |
| Activity 1.3.1 Aligning Georgian legal framework on Occupational Health and Safety, including aspects of Labour Inspection System, amended in compliance with the Union acquis |  |  |  |  |  |  |  |  |  |  |
| 7 MS experts, 70WDs / 14 missions - Bratislava: Michal Nemec 10WD/2 missions, Slavomir Stastny 10WD/2 missions, - Kosice: Ivan Majer 25WD/5 missions - Zagreb: Zdravko Muratti 15WD/3 missions, - Tallin: Seili Sudder 5WD/1 mission, Eva Poldis 5WD/1 mission, Ulla Saar 10WD/2 missions - Madrid: Tomas Criado Navamuniel 5WD/1 mission, |  |  |  |  |  |  |  |  |  |  |
| Flat Daily Allowance |  |  |  |  | 350,00 | 80 | 28 000,00 | 350,00 | 70 | 24 500,00 |
| Twinning Project Support Cost |  |  |  |  | 136% |  | 38 080,00 | 136% |  | 33 320,00 |
| Compensation for Daily Subsistence |  |  |  | 12 | 198,00 | 96 | 19 008,00 | 198,00 | 84 | 16 632,00 |
| Travel Costs Bratislava |  |  |  | 11 | 457,00 | 4 | 1 828,00 | 457,00 | 4 | 1 828,00 |
| Travel Costs Kosice (will be based on real costs) |  |  |  | 11 | 500,00 | 3 | 1 500,00 | 500,00 | 5 | 2 500,00 |
| Travel Costs Madrid |  |  |  | 11 | 565,00 | 3 | 1 695,00 | 565,00 | 1 | 565,00 |
| Travel Costs Tallin*** |  |  |  | 11 | 399,00 | 6 | 2 394,00 | 399,00 | 4 | 1 596,00 |
| Travel Costs Zagreb (will be based on real costs) |  |  |  | 11 | 500,00 | 0 | 0,00 | 500,00 | 0 | 0,00 |
| Translation |  |  |  | 18 | 12,00 | 40 | 480,00 | 12,00 | 40 | 480,00 |
| Activity 1.3.1 |  |  |  |  |  |  | 92 985,00 |  |  | 81 421,00 |
| Component 1 |  |  |  |  |  |  | 222 296,00 |  |  | 210 732,00 |
| Component 2: Capacity building, inter-institutional cooperation, and awareness raising of relevant state authorities and private sector for full implementation of amended legislation in labour law, gender equality and OSH |  |  |  |  |  |  |  |  |  |  |
| Activity 2.1.1 Assessment of the administrative structures and institutional capacities of the beneficiary and relevant stakeholders and improvement of their inter-institutional operation |  |  |  |  |  |  |  |  |  |  |
| 4 MS experts, 35WD/8 missions - Tallin: Ms. Slija Soon 5WD/2 missions (1 mission cancelled force majeure), - Albacete: Ms. Consuelo Manchón García 10WD/2 missions, - Valencia: Mr. Juan Martín Garcia Alloza 5WD/1 mission, - Budapest: Mr Tamas Berky 15WD/3 missions, |  |  |  |  |  |  |  |  |  |  |
| Flat Daily Allowance |  |  |  |  | 350,00 | 55 | 19 250,00 | 350,00 | 35 | 12 250,00 |
| Twinning Project Support Cost |  |  |  |  | 136% |  | 26 180,00 | 136% |  | 16 660,00 |
| Compensation for Daily Subsistence |  |  |  | 12 | 198,00 | 66 | 13 068,00 | 198,00 | 42 | 8 316,00 |
| Travel Costs Valencia** |  |  |  | 11 | 616,00 | 1 | 616,00 | 616,00 | 0 | 0,00 |
| Travel Costs Barcelona** |  |  |  | 11 | 616,00 | 1 | 616,00 | 616,00 | 0 | 0,00 |
| Travel Costs Albacete (will be based on real costs) |  |  |  | 11 | 616,00 | 3 | 1 848,00 | 616,00 | 2 | 1 232,00 |
| Travel Costs Tallin*** |  |  |  | 11 | 399,00 | 2 | 798,00 | 399,00 | 2 | 798,00 |
| Travel Costs Budapest (will be based on real costs) |  |  |  | 11 | 500,00 | 3 | 1 500,00 | 500,00 | 3 | 1 500,00 |
| Translation |  |  |  | 18 | 12,00 | 0 | 0,00 | 12,00 | 0 | 0,00 |
| Activity 2.1.1 |  |  |  |  |  |  | 63 876,00 |  |  | 40 756,00 |
| Activity 2.1.2 Training needs analysis and strengthening the institutional capacity of the beneficiary and relevant stakeholders |  |  |  |  |  |  |  |  |  |  |
| 5 MS experts, 35 WD / 7 missions - Tallin: Ms. Silia Soon 10WD/2 mission, - Albacete: Ms. Consuelo Manchón García 15WD/3 missions, - Valencia: Mr. Juan Martín GARCIA ALLOZA 0WD/0 mission, - Budapest: Mr Tamas Berky 10WD/2 missions, - Barcelona: Raquel CALVERAS AUGÉ 0WD/0 mission, |  |  |  |  |  |  |  |  |  |  |
| Flat Daily Allowance |  |  |  |  | 350,00 | 35 | 12 250,00 | 350,00 | 35 | 12 250,00 |
| Twinning Project Support Cost |  |  |  |  | 136% |  | 16 660,00 | 136% |  | 16 660,00 |
| Compensation for Daily Subsistence |  |  |  | 12 | 198,00 | 42 | 8 316,00 | 198,00 | 42 | 8 316,00 |
| Travel Costs Valencia** |  |  |  | 11 | 616,00 | 0 | 0,00 | 616,00 | 0 | 0,00 |
| Travel Costs Barcelona** |  |  |  | 11 | 616,00 | 0 | 0,00 | 616,00 | 0 | 0,00 |
| Travel Costs Albacete (will be based on real costs) |  |  |  | 11 | 616,00 | 3 | 1 848,00 | 616,00 | 3 | 1 848,00 |
| Travel Costs Tallin*** |  |  |  | 11 | 399,00 | 2 | 798,00 | 399,00 | 2 | 798,00 |
| Travel Costs Budapest (will be based on real costs) |  |  |  | 11 | 500,00 | 2 | 1 000,00 | 500,00 | 2 | 1 000,00 |
| Translation |  |  |  | 18 | 12,00 | 0 | 0,00 | 12,00 | 0 | 0,00 |
| Activity 2.1.2 |  |  |  |  |  |  | 40 872,00 |  |  | 40 872,00 |
| Activity 2.1.3 Delivery of Training of Trainers of the labour inspectors |  |  |  |  |  |  |  |  |  |  |
| 4 MS experts, 45 WD/ 9 missions Madrid: Jose Ignacio Martin Fernandez 10 WD/2 missions - Albacete: Ms. Consuelo Manchón García 15WD/3 missions, - Kosice: Mr Ivan Majer 10WD/2 missions, - Cyprus: Mr Marios Charalambous 10WD/2 missions, |  |  |  |  |  |  |  |  |  |  |
| Flat Daily Allowance |  |  |  |  | 350,00 | 45 | 15 750,00 | 350,00 | 45 | 15 750,00 |
| Twinning Project Support Cost |  |  |  |  | 136% |  | 21 420,00 | 136% |  | 21 420,00 |
| Compensation for Daily Subsistence |  |  |  | 12 | 198,00 | 54 | 10 692,00 | 198,00 | 54 | 10 692,00 |
| Travel Costs Madrid |  |  |  | 11 | 457,00 | 3 | 1 371,00 | 565,00 | 2 | 1 130,00 |
| Travel Costs Albacete (will be based on real costs) |  |  |  | 11 |  |  |  | 616,00 | 3 | 1 848,00 |
| Travel Costs Kosice (will be based on real costs) |  |  |  | 11 | 500,00 | 3 | 1 500,00 | 500,00 | 2 | 1 000,00 |
| Travel Costs Cyprus (will be based on real costs) |  |  |  | 11 | 500,00 | 3 | 1 500,00 | 500,00 | 2 | 1 000,00 |
| Translation |  |  |  | 18 | 12,00 | 0 | 0,00 | 12,00 | 0 | 0,00 |
| Activity 2.1.3 |  |  |  |  |  |  | 52 233,00 |  |  | 52 840,00 |
| Activity 2.1.4 Delivery of comprehensive training programmes to improve the institutional capacities of the beneficiary and relevant |  |  |  |  |  |  |  |  |  |  |
| 8 MS experts, 100 WD / 20 missions - Albacete: Ms. Consuelo Manchón García 15 WD/3 missions, - Madrid: Mr. José Ignacio Martín Fernández 15 WD/3 missions, - Donostia / San Sebastian: Gabriela Beltran Fernández 15WD/3 missions, - Kosice: Ms. Laurencia Jancurova 15 WD/3 missions, Mr. Ivan Majer 10 WD/2 missions - Barcelona: Jaume ADMETLLA 5WD/1 mission, - Tallin: Ms. Silia Soon 15WD/3 missions, - Cyprus: Mr. Marios Charalambous 10WD/2 missions, |  |  |  |  |  |  |  |  |  |  |
| Flat Daily Allowance |  |  |  |  | 350,00 | 65 | 22 750,00 | 350,00 | 100 | 35 000,00 |
| Twinning Project Support Cost |  |  |  |  | 136% |  | 30 940,00 | 136% |  | 47 600,00 |
| Compensation for Daily Subsistence |  |  |  | 12 | 198,00 | 78 | 15 444,00 | 198,00 | 120 | 23 760,00 |
| Travel Costs Madrid |  |  |  | 11 | 565,00 | 3 | 1 695,00 | 565,00 | 3 | 1 695,00 |
| Travel Costs Barcelona** |  |  |  | 11 | 616,00 | 1 | 616,00 | 616,00 | 1 | 616,00 |
| Travel Costs Albacete (will be based on real costs) |  |  |  | 11 | 616,00 | 3 | 1 848,00 | 616,00 | 3 | 1 848,00 |
| Travel Costs Donostia / San Sebastian (will be based on real costs) |  |  |  | 11 | 616,00 | 3 | 1 848,00 | 616,00 | 3 | 1 848,00 |
| Travel Costs Kosice (will be based on real costs) |  |  |  | 11 | 500,00 | 3 | 1 500,00 | 500,00 | 5 | 2 500,00 |
| Travel Costs Tallin*** |  |  |  | 11 |  |  |  | 399,00 | 3 | 1 197,00 |
| Travel Costs Cyprus (will be based on real costs) |  |  |  | 11 |  |  |  | 500,00 | 2 | 1 000,00 |
| Translation |  |  |  | 18 | 12,00 | 0 | 0,00 | 12,00 | 0 | 0,00 |
| Activity 2.1.4 |  |  |  |  |  |  | 76 641,00 |  |  | 117 064,00 |
| Activity 2.2.1 Development of the relevant guidelines, labour inspection manuals, checklists and other tools to improve the institutional operations and procedures focused on precise implementation of newly adopted legislation |  |  |  |  |  |  |  |  |  |  |
| 6 MS experts, 60 WD / 12 missions - Zagreb: Zdravko Muratti 5WD/1 mission, - Kosice: Ivan Majer: 5WD/1 missions, Laurencia Jancurova 10 WD/2 missions, - Tallin: Seili Sudder 10 WD/2 missions, Eva Poldis 10WD/2 missions, Ulla Saar 10 WD/2 missions, - Madrid: Tomas Criado Navamuniel 10WD /2 missions, |  |  |  |  |  |  |  |  |  |  |
| Flat Daily Allowance |  |  |  |  | 350,00 | 40 | 14 000,00 | 350,00 | 60 | 21 000,00 |
| Twinning Project Support Cost |  |  |  |  | 136% |  | 19 040,00 | 136% |  | 28 560,00 |
| Compensation for Daily Subsistence |  |  |  | 12 | 198,00 | 48 | 9 504,00 | 198,00 | 72 | 14 256,00 |
| Travel Costs Madrid |  |  |  | 11 | 565,00 | 2 | 1 130,00 | 565,00 | 2 | 1 130,00 |
| Travel Costs Tallin*** |  |  |  | 11 | 399,00 | 4 | 1 596,00 | 399,00 | 6 | 2 394,00 |
| Travel Costs Kosice (will be based on real costs) |  |  |  | 11 | 500,00 | 1 | 500,00 | 500,00 | 3 | 1 500,00 |
| Travel Costs Zagreb (will be based on real costs) |  |  |  | 11 | 500,00 | 1 | 500,00 | 500,00 | 1 | 500,00 |
| Translation |  |  |  | 18 | 12,00 | 0 | 0,00 | 12,00 | 0 | 0,00 |
| Activity 2.2.1 |  |  |  |  |  |  | 46 270,00 |  |  | 69 340,00 |
| Activity 2.2.2 Preparing and implementing public information campaign aiming to raise awareness among the project among key stakeholders, public, private sector and civil society |  |  |  |  |  |  |  |  |  |  |
| 5 MS experts, 75 WD/15 missions - Bratislava: Ms. Luba Pavlovova 20 WD/4 missions, Mr. Ivan Majercak 5 WD/1 mission, Mr Branislav Ondrus 10 WD/2 missions - Madrid: Ms. Maria Mercedes Tejedor Aibar 20 WD/4 missions, Ms. Marta Zimmerman Verdejo 20 WD/4 missions, |  |  |  |  |  |  |  |  |  |  |
| Flat Daily Allowance |  |  |  |  | 350,00 | 65 | 22 750,00 | 350,00 | 75 | 26 250,00 |
| Twinning Project Support Cost |  |  |  |  | 136% |  | 30 940,00 | 136% |  | 35 700,00 |
| Compensation for Daily Subsistence |  |  |  | 12 | 198,00 | 78 | 15 444,00 | 198,00 | 90 | 17 820,00 |
| Travel Costs Bratislava |  |  |  | 11 | 457,00 | 5 | 2 285,00 | 457,00 | 7 | 3 199,00 |
| Travel Costs Madrid |  |  |  | 11 | 565,00 | 8 | 4 520,00 | 565,00 | 8 | 4 520,00 |
| TV, radio broadcasting Public awareness campaign |  |  |  | 18 | 5 000,00 | 1 | 5 000,00 | 5 000,00 | 1 | 5 000,00 |
| Translation |  |  |  | 18 | 12,00 | 0 | 0,00 | 12,00 | 0 | 0,00 |
| Activity 2.2.2 |  |  |  |  |  |  | 80 939,00 |  |  | 92 489,00 |
| Activity 2.2.3 Conducting study visits to Member states, focused for transfer of good practices on organisation and management of labour inspection |  |  |  |  |  |  |  |  |  |  |
| Study visit for 5 participants + Interpreter to Estonia for 5days/6nights |  |  |  |  |  |  |  |  |  |  |
| Compensation for Daily Subsistence Estonia |  |  |  | 22 | 181,00 | 36 | 6 516,00 | 181,00 | 36 | 6 516,00 |
| Travel Costs*** |  |  |  | 11 | 399,00 | 6 | 2 394,00 | 399,00 | 6 | 2 394,00 |
| Travel Costs within Member States |  |  |  | 11 | 0,00 | 0 | 0,00 | 0,00 | 0 | 0,00 |
| Activity 2.2.3 |  |  |  |  |  |  | 8 910,00 |  |  | 8 910,00 |
| Activity 2.3.1 Supporting inter-institutional cooperation in the process of approximation and implementation of the relevant EU acquis |  |  |  |  |  |  |  |  |  |  |
| 2 MS experts, 20 WD/4 missions - Bratislava: Branislav Ondrus 10 WD/2 missions, Michal Nemec 10 WD/2 missions, |  |  |  |  |  |  |  |  |  |  |
| Flat Daily Allowance |  |  |  |  | 350,00 | 0 | 0,00 | 350,00 | 20 | 7 000,00 |
| Twinning Project Support Cost |  |  |  |  | 136% |  | 0,00 | 136% |  | 9 520,00 |
| Compensation for Daily Subsistence |  |  |  | 12 | 198,00 | 0 | 0,00 | 198,00 | 24 | 4 752,00 |
| Travel Costs Bratislava |  |  |  | 11 | 457,00 | 0 | 0,00 | 457,00 | 4 | 1 828,00 |
| Translation |  |  |  | 18 | 12,00 | 0 | 0,00 | 12,00 | 0 | 0,00 |
| Activity 2.3.1 |  |  |  |  |  |  | 0,00 |  |  | 23 100,00 |
| Component 2 |  |  |  |  |  |  | 369 741,00 |  |  | 445 371,00 |
| III. Total Components |  |  |  |  |  |  | 594 481,00 |  |  | 658 547,00 |
| IV. Direct Costs Overall Amount Reserve Funds |  |  |  |  |  |  |  |  |  |  |
| Total Direct Costs (I-III) |  |  |  |  |  |  | 1 017 886,50 |  |  | 1 081 952,50 |
| V. Reserves |  |  |  |  |  |  |  |  |  |  |
| Total Reserve Funds [2,5% x IV] |  |  |  |  |  |  | 25 447,16 |  |  | 27 048,81 |
| VI. Provision for Indirect Costs |  |  |  |  |  |  |  |  |  |  |
| Total Provision for Indirect Costs (6% x IV) |  |  |  |  |  |  | 61 073,19 |  |  | 64 917,15 |
| VII.Overall Cost of Twinning |  |  |  |  |  |  |  |  |  |  |
| Total Overall Cost (IV-VI) |  |  |  |  |  |  | 1 104 406,85 |  |  | 1 173 918,46 |
| ** Rate for Spain is subject to the Addendum, after which the flat rate Madrid-Tbilisi-Madrid might be fixed at EUR 565, and other destinations in Spain as well as those unforseen before signing the contract might be charged based on the real costs. |  |  |  |  |  |  |  |  |  |  |
| *** Flat Rate for route Tallinn - Tbilisi – Tallinn in amount 399Eur is subject to the Addendum where current flat rate might be changed to 450Eur. |  |  |  |  |  |  |  |  |  |  |

The Member State PL

[signature]________________________________

[date]____________________________________

The Beneficiary Country PL

[signature]________________________________

[date]____________________________________