## ANNEX C4: Twinning interim quarterly report

EUROPEAN COMMISSION

TWINNING PROJECTS

INTERIM QUARTERLY REPORT

TWINNING INTERIM QUARTERLY REPORT number:1

Project Title: “Improving the standards of employment conditions/relations as well as health and safety at work in Georgia“

Partners:     Lead Partner:
Ministry of Labour, Social Affairs and Family of the Slovak Republic 
(MoLSAF SR)

Junior Partner:
Ministry of Labour, Migrations and Social Security (MITRAMISS). Labour and Social    Security Inspectorate of State Agency

Ministry of Social Affairs of the Republic of Estonia

Back stopping body:
Regional Development Agency SP, Slovak Republic (RDA)

FIIAPP F.S.P. (Fundación Internacional y para Iberoamerica de Admisnistración    y

Polítocas Públicas

Beneficiary Country
                      Ministry of Internally Displaced Persons from the Occupied Territories,

Labour, Health and Social Affairs of Georgia, (MoIDPLHSA) , Labour

Conditions Inspecting Department

Date:         February 28, 2020

Twinning Grant Contract number: 	ENI/2019/409-668

1.	Overview

The Interim Quarterly Report/Final Report for the project comprises the following parts:

Section 0	Executive summary listing decisions needed to be taken by the Project Steering Committee

Section 1	Basic data on the project

Section 2	Content: progress achieved in the implementation of the Twinning project during the reporting period and schedule for the remaining period

Section 3	Expenditure: actual expenditure in relation to budgeted expenditure

2.

Twinning Grant Contract number: ENI/2019/409-668  GE - 17 - ENI - OT – 02 19

Section 0

Executive summary

1. Provide a max 2 pages executive summary

Information provided in this Interim Quarterly Report covers the period from 7th October, 2019 – 6 th January, 2020.

The Twinning Grant Contract ENI/2019/409-668;  GE - 17 - ENI - OT – 02 19 entered  into force on 27th September, 2019 and the conditions for starting the TW project implementation were fulfilled.  On 7th October, 2019 the Resident Twinning Advisor arrived to Georgia and the TW project implementation “Improving the standards of employment conditions/relations as well as health and safety at work in Georgia “started.  The same day, on 7th October, 2019 the Introductory meeting of the RTA with BC PL, RTA Counterpart, EUD Programme Manager, the representatives of PAO as well as selected staff of the LCID was held. The institutional, operational and project management issues such as a work plan preparation, communication and visibility plan, SCM, Side letters, visibility and opening event preparation, coordination issues were discussed during the meeting as well priorities related to the development of the work plan and information about the current legislation process were shared with RTA.  A round of the introductory meetings were conducted with the representatives of the Beneficiary – Mr Beka Peradze, the RTA Counterpart, Mr Levan Abashidze, Head of Monitoring and Supervision Division and Ms Lika Klimiashvili, Head of the Labour Relations and Social Partnership Division, too. The current state of play in approximation of labour law, equal treatment and antidiscrimination as well as the health and safety policy fields in a comparison with the Twinning Project Fiche were discussed and priorities for the development of the work plan were outlined.

In November 2018, European Commission and the Government of Georgia signed an agreement to support the programme "Skills Development and Matching for Labour Market Needs" (Skills4Jobs - Phase 2), with a total EU contribution of € 48.85 million. To launch formally activities under this new programme, a high-level event was held on 29 October, 2019 with participation of key stakeholders from the Government of Georgia, EU Delegation to Georgia, ETF, young people and other stakeholders, total of 100 participants. It also included a high-level panel where reforms skills promoting for jobs in the country were discussed. Mr Jose Ignacio Martin Fernandez, JPL and a Component Leader I. participated in the Launching event and delivered the presentation about objectives, activities and outputs of the project. The TW team used the opportunity of this event and were introduced to the representatives of the social partners and other stakeholders of the project and used this gathering for getting involved and discussed the current state of play in the sector.

First mission started 2 weeks after the start of the project, 20 – 25 October, 2019 and was focused on preparation of the work plan. 2 Junior Project Leaders - Mr Jose Ignacio Martin Fernandez (5WD) and Ms Ulla Saar (3WD) (from Spain and Estonia), and 1 ST expert Ms Consuelo Manchon Garcia (5WD), Component Leader II. took part in the round of meetings with the relevant key representatives of the BA to ensure the common understanding of initial activities of the project and clarification of needs from the side of the BA for the next 6 months. The STE have contributed to the Communication and Visibility Plan as well.

Before the first mission started the 1st Side letter was prepared and submitted due to the urgency to conduct a comprehensive assessment of proposed amendments of the Labour Code of Georgia focused on their alignment to the relevant EU acquis. The draft amendments were available in Georgian language and with support of donor community the public discussions were launched on 22 October 2019. A substantiated feedback from the EU side was needed urgently, even before the approval of the initial work-plan in the first Steering Committee meeting which was planned to take place at the end of November.

During the initial period selection of both the RTA Assistants was completed and both of them were contracted and started working in November 2019.

On 28th November, 2019 the 1st Steering Committee meeting was held and the Initial Work Plan, Communication and Visibility plan was approved.

Coordination of different donor’s activities focused on the same/similar issues was one of the most important management approaches applied during the first months of the project implementation to avoid overlapping in capacity building (training, operational guidelines, manuals and procedures) and in implementation of the public awareness campaign as well.  Very good and professional relations and coordination mechanism was set up at the beginning with the representatives of the ILO, Mr Kinan Albahnasi and his team, in charge of the ILO project “Inclusive Labour Market for Job Creation in Georgia”, funded by the Danish Government.

Since 20th October 2019, activities were implemented smoothly, based on the work plan. In total 11 experts have participated in 9 missions and spent 80 working days (out of 487). Taking into account the initial 3 months of the project implementation including the Christmas (Catholic and Orthodox) holidays the spending of the Initial Workplan was adequate, taking into account the current absorption capacity of the BA.

One of the important outputs of the activities delivered is the Initial Assessment of proposed amendments of the Labour Code of Georgia focused on their alignment to the relevant EU acquis. As a general remark, it should be noted that it is obvious, that a lot of work has been done with the labour code to incorporate all the relevant EU directives into Georgian law. In our opinion, the effort has paid off. The labour code is well crafted, the most important obligations from the directives have been correctly reflected in the labour code.  However, due to the tight timeline, it was difficult to give a thorough review. From initial research it seems that there are still several articles from different directives that are not yet correctly transposed or have been left out.

In December, 2019 Mr Dimitri Tskitishvili, member of Parliament leading and coordinating the initiative to improve Labor Relations in Georgia   and creating the new legal and institutional mechanisms has resigned  and the until the end of the reporting period it was not clear who will overtake the initiative of the previous MP and will keep working on further amendments as well as who will submit the Labour Code amendments to the legislation process.

The list of the outputs delivered during the reporting period is attached.

2. List decisions needed to be taken by the Steering Committee

- 1st Interim Quarterly Report

Section 1:

Project data

| Twinning Grant Contract Number | ENI/2019/409-668 |
| --- | --- |
| Project Title: | Improving the standards of employment conditions/relations as well as health and safety at work in Georgia |
| Twinning Partners (Member State(s) and Beneficiary) | Lead Partner: Ministry of Labour, Social Affairs and Family of the Slovak Republic (MoLSAF SR) Junior Partner: Ministry of Labour, Migrations and Social Security (MITRAMISS).Labour and Social Security Inspectorate of State Agency Ministry of Social Affairs of the Republic of Estonia Back stopping body: Regional Development Agency SP, Slovak Republic (RDA) FIIAPP F.S.P. (Fundación Internacional y para Iberoamerica de Admisnistración y Polítocas Públicas Beneficiary Country Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia, (MoIDPLHSA) , Labour Conditions Inspecting Department |
| Report Number: | 1 |
| Period covered by the report: | 7th October, 2019 – 6th January 2020 |
| Duration of the project: | 24 months |
| Reported by: | Branislav Ondrus, MS PL Tamila Barkalaia, BC PL Jose Ignacio Fernandez Martin, JPL Ulla Saar, JPL Valeria Kubalova, RTA, Beka Peradze, RTA Counterpart |

Section 2:

Content

2A – BACKGROUND

2B – ACHIEVEMENT OF MANDATORY RESULTS/OUTPUTS:

2C – ACTIVITIES IN THE REPORTING PERIOD

2D – TIMING AND DELAYS

2E – ASSESSMENT

.

2A - BACKGROUND

Overall objectives

| Overall Objective and indicators of achievement (as in Log frame) | State of achievement/ problems encountered |
| --- | --- |
| The overall objective of the project is to support higher standards in employment relationship and working conditions in Georgia through improving legal framework and enforcing implementation. |  |
| - employment relations and health and safety standards at work for Georgian employees and enterprises - number of inspected facilities implementing preventive measures focused on creation of safe and healthy working conditions Baseline: 708 Target: 1 050 - Number of employees effected by implemented OSH preventive measures increased Baseline: 210 390 Target: 300 000 | The state of achievement is in line with the implementation of the Initial Work Plan – activities have started during the reporting period without significant results to be compared. The state of achievement is in line with the implementation of the Initial Work Plan – activities have started during the reporting period without significant results to be compared. The state of achievement is in line with the implementation of the Initial Work Plan – activities have started during the reporting period without significant results to be compared. |

Specific Objectives

| Specific Objectives and indicators of achievement (as in Log frame) | State of achievement/ problems encountered |
| --- | --- |
| To assist the MoIDPLHSA, together with other relevant stakeholders, to draft the legal and administrative provisions and establish the institutional mechanisms to improve employment conditions/ relations and Occupational Safety and Health, including a labour inspection system. Additionally, to strengthen the capacity of the national institutions to implement and adopt the best European practices. |  |
| - Degree of compliance of the relevant Georgian legislation with the Union acquis increased - Legal and administrative procedures, and institutional mechanisms for improved employment relations and health and safety standards at work | The state of achievement is in line with the implementation of the Initial Work Plan – activities just have started during the reporting period without significant results to be compared. The state of achievement is in line with the implementation of the Initial Work Plan – activities just have started during the reporting period without significant results to be compared. |

Policy and sector Developments

Recent development in the legal framework

During the reporting period, the MoIDPLHSA was very active and fully involved in further approximation of the Union acquis included in the EU-Georgia Association Agreement in the field of labour law, anti-discrimination and gender equality as well as health and safety at work. Newly adopted the  Organic Law of Georgia on Occupational Health and Safety has created the conditions based on which the country took responsibility to transform the Labour Conditions Inspection Department of the Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia into the Legal Entity under Public Law and specify the regulatory framework for the activities  the newly created legal entity should perform.

Based on the political agreement, the initiative for preparation of the legislative package (amendments of the Labour Code, Draft Labour Inspection Law and other amendments to the related laws) was taken and led by the Member of the Parliament Mr Dimitri Tskitishvili supported by the MoIDPLHSA and different international donors. In October, 2019 a large consultation process has started involving relevant ministries, social partners of different economic sectors, EUD representatives including the TW project and participated international donors, relevant NGO and platforms through organizing 3 round tables focused on different topics of the Labour Code Reform and one Round table focused on Draft Labour Inspection Law were organized to approximate the positions of different stakeholders to the proposed amendments taking into account the minimal requirements of the individual EU Directives.  RTA and 3 STE were invited to participate in all round tables and have shared the experience on application practice applied in the different MS.  Moreover, the Initial Assessment of the Amendments of the Labour Code was prepared by TW experts and shared to the team of Mr Dimitri Tskitishvili for further clarification of the process of harmonization.

Project Assumptions

All assumptions as specified in the Logframe related to Mandatory results were achieved during the reporting period.

| Assumption | Fulfilment |
| --- | --- |
| Government commitment on the fulfilment of AA/ DCFTA requirements continued | YES |
| Strong support and commitment from the senior management of the MoIDPLHSA | YES |
| Availability of local staff | YES |
| Good communication between the Beneficiary and other stakeholders | YES |
| Strong support and commitment from twinning partner(s) | YES |
| Relevant staff of the MoIDPLHSA and other stakeholder representatives available and involved in the process | YES |

Description of the actions/activities which contributed to fulfilment of the assumptions and influenced a smooth implementation of the project:

- On 7th October, 2019 the Resident Twinning Advisor to Georgia arrived and the TW project implementation has started. The introductory meetings with Beka Peradze, the RTA Counterpart, Mr Levan Abashidze, Head of Monitoring and Supervision Division as well as Ms Lika Klimiashvili, Head of the Labour Relations and Social Partnership Division was conducted during the same day. The introductory information about the current state of play in approximation of labour law, equal treatment and antidiscrimination as well as the health and safety policy fields in a comparison with the Twinning Project Fiche were discussed and clarified during those meetings.

- On 7th October, 2019 the Introductory meeting of the RTA with BC PL, RTA Counterpart, EUD Programme Manager, the representatives of PAO as well as selected staff of the LCID was held. The institutional, operational and project management issues such as a work plan preparation, communication and visibility plan, SCM, Side letters, invoicing, visibility and opening event preparation, coordination issues were discussed. Priorities related to the development of work plan were briefly discussed as well and information about the current legislation process were shared with RTA.

- On 23rd October, 2019  1st Side letter was prepared and submitted due to the urgency to conduct a comprehensive assessment of proposed amendments of the Labour Code of Georgia focused on their alignment to the relevant EU acquis. The draft amendments were available in Georgian language and with support of donor community the public discussions were launched on 22 October 2019. The substantiated feedback from the EU side was needed urgently, even before the approval of the initial work-plan in the first Steering Committee meeting which was planned to take place at the end of November.  Therefore, for Ms. Kristina Balenovic, Ms Seili Suder, Ms Mariliis Proos and Mr Jose Ignacio Martin Fernandez   in total 20 working days, 24 per diems and 4 units for travel were incorporated into initial work-plan.

- Since 20 – 25 October, 2019, 2 weeks after arrival of the RTA to a BA a mission focused on preparation of the work plan was conducted. 2 Junior Project Leaders - Mr Jose Ignacio Martin Fernandez (5WD) and Ms Ulla Saar (3WD) (from Spain and Estonia), and 1 ST expert Ms Consuelo Manchon Garcia (5WD), Component Leader II. have participated in the round of meetings with the relevant key representatives of the BA to ensure the common understanding of initial activities of the project and clarification of needs from the side of the BA for the next 6 months. The STE have discussed and commented the Communication and Visibility Plan as well.

- On 29th October, 2019 the new EU Programme on Skills Development and Matching for Labour Market Needs - Skills4Jobs which was launched. Mr Jose Ignacio Martin Fernandez, JPL and a Component Leader I. has participated in the Launching event and   delivered the presentation about objectives, activities and outputs of the project.

- Since 1st November, 2019 RTA Assistant was hired and since 18th November, 2019 the RTA language assistant started working as well.

- On 28th November, 20191 the 1st Steering Committee meeting was held and the Initial Work Plan was approved

- Since November, 2019 several meetings have been organised with the representatives of ILO, Mr Kinan Albahnasi and his team, in charge of the ILO project “Inclusive Labour Market for Job Creation in Georgia”, funded by the Danish Government. ILO yearly working plan was discussed as well as  coordination of activities were set up in order to avoid overlapping in capacity building (training, operational guidelines, manuals and procedures) and in implementation of the public awareness campaign.

- On 13th December, 2020 a Coordination meeting with donors engaged in the OSH and labour relations (incl. antidiscrimination and gender equality issues) was held.  During a meeting the detailed information on activities each donor performs in the OSH & labour relations areas were shared and an overview of activities focused on awareness raising and information on OSH in the country was mapped in order to avoid overlapping during the implementation of the public awareness campaign.

- Since 20th October 2019, 11 experts have participated in 9 missions and spent 80 working days.

Operational issues

Initial problems with the appropriate room for RTA and RTA Assistants were solved in January 2020 and the TW team has moved to a room with adequate space and equipment for the TW project staff responsible for the organisation and implementation of the activities. RTA assistant and Language assistant were selected in the first month of the project implementation and hired in November, 2019.

Activities performed

All activities were performed in time.

Benchmarks

The state of achievement is in line with the current work plan implementation.

Relationship

The cooperation between the Twinning partners is very professional and very intensive. The BC staff (Labour Conditions Inspecting Department and Labour and Employment Policy and Collective Labour Disputes Division) are highly involved into the topics and highly motivated. All stakeholders including the social partners are fully committed and they confirmed their active participation in the implementation of the project’s components. EUD manager and PAO representatives are very helpful and very operational in dealing with daily issues. There are no difficulties in communication/cooperation with all involved twinning parties.

2B - ACHIEVEMENT OF MANDATORY RESULTS/OUTPUTS

Results under components:

| Results and indicators of achievement (as in Log frame) |  | State of achievement/ problems encountered |
| --- | --- | --- |
| Result 1 Approximation of primary and secondary legislation related to labour law, gender equality and OSH in accordance with the Union acquis |  |  |
| Sub-result 1.1. Legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis |  |  |
| - Number of the Tables of Concordance prepared for the Labour Law acquis, including aspects of labour inspection system Baseline: 7 Target: 8 Directives - List of amendments to be made in the Georgian primary and secondary labour legislation specified with explanatory notes Baseline: 3 Target: 8 Directives |  | - 1 Table of Concordance of the Council Directive 91/383/EEC of 25 June 1991 supplementing the measures to encourage improvements in the safety and health at work of workers with a fixed- duration employment relationship or a temporary employment relationship was developed and completed. - 2nd version of the Compliance Report of Amendments to the draft Organic Law of Georgia the Labour Code with 8 Directives in the field of the Labour Law was prepared during the reporting period. First version was submitted to the BA as well as to the representatives of the Parliament, the initiators of the amendments. Both reports have included main findings, recommendations for the amendments, good practise and the recent CJEU law. |
| Sub-result 1.2: Legal framework on non-discrimination and gender equality, including aspects of labour inspection system, amended in compliance with the Union acquis |  |  |
| - List of amendments to be made in the Georgian primary and secondary legislation on Gender Equality acquis specified with explanatory notes Baseline: 4 Target: 2 Directives - Share of staff from relevant public institutions who are fully informed on regulatory and fiscal impact of changes in labour law and gender equality acquis Baseline: 0 Target: 90% of staff in LCID and LEPD | - The state of achievement is in line with implementation of the work plan – 2 missions were conducted focused on discussion of the Council Directive 2004/113/EC implementing the principle of equal treatment between men and women in the access to and supply of goods and services and Council Directive 79/7/EEC on the progressive implementation of the principle of equal treatment for men and women in matters of social security. - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. |  |
| Sub-result 1.3: Legal framework on OSH, including aspects of labour inspection system, amended in compliance with the Union acquis |  |  |
| - Availability of quality checked translation of the OSH acquis with clear technical terminology (if necessary) Baseline: 9 Target: 15 Directives - Availability of the Tables of Concordance prepared for the OSH acquis, including aspects of labour inspection system Baseline: 5 Target: 15 Directives - Availability of the list of amendments to be made in the Georgian primary and secondary OSH legislation specified with explanatory notes Baseline: 2 Target: 15 Directives - Share of staff from relevant public institutions who are fully informed on regulatory and fiscal impact of changes in OSH acquis Baseline: 0 Target: 90% of staff in LCID and LEPD | - Activities to contribute to fulfilment of the Indicator were not planned during this reporting period. - Activities to contribute to fulfilment of the Indicator were not planned during this reporting period. - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. |  |

| Result 2 Capacity building, inter-institutional cooperation, and awareness raising of relevant state authorities and private sector for full implementation of amended legislation in labour law, gender equality and OSH |  |
| --- | --- |
| Sub-result 2.1: Analysis for strengthening state authorities’ capacity for implementation of the EU best practices performed and required strategies developed |  |
| - Functional review of the relevant state authorities to implement changes, including human and financial resources, administrative structures and equipment needed Baseline: 0 Target: 1 - Training needs analysis and plan of the whole staff of beneficiary department and representatives from other relevant institutions listed Baseline: 0 Target: 1 - Share of BA staff who received training to implement necessary changes and the representatives from other relevant institutions listed Baseline: 10% Target: 90% of staff in BA and others - Number of labour inspectors who are trained more to become ‘trainers’ with full knowledge and competency in implementing new laws Baseline: 0 Target: 5 | - During the reporting period 1 mission focused on the development of the functional review was conducted, detailed mapping and assessment of the interinstitutional relationships between the various state and non-governmental actors dealing with the occupational health and labour relations were conducted. Functional review will be completed in the next reporting period. - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. - Delivery of targeted training for newly hired inspectors have been postponed due to a delay in the recruitment process - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. |
| Sub-result 2.2: Implementation of the EU best practices regarding the amended legislation piloted and awareness of the citizens and private sector on the topic increased |  |
| - Number of written operational guidelines, manuals and procedures required to implement all changes, explaining all steps of implementation to the relevant staff Baseline: 0 Target: At least 15 documents(*) - Number of OSH online Glossary and Risk Assessment checklists and their dissemination to relevant parties Baseline: 0 Target: At least 20 (*) - Number of elaborated promotional materials and public information campaigns in printed and online media, TV and other tools Baseline: 5 Target: 20 short written materials + 2 public campaigns (*) - Share of private companies (i.e. both employers and workers) which are informed and number of citizens reached out on the new rules and changes made in labour legislation Baseline: 50 Target: 90% of registered companies | - The state of achievement is in line with the implementation of the Initial Work Plan – activities just have started during the reporting period without significant results to be compared. - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. - The state of achievement is in line with the implementation of the Initial Work Plan – activities just have started during the reporting period. Public awareness campaign is under preparation including other communication tools. - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. |
| Sub-result 2.3: Organisation of working group(s) on labour law, gender equality and OSH comprising line ministries and social partners completed and functional |  |
| - Proposal for a structure of inter-institutional cooperation and working procedures, with a review of existing options Baseline: 0 Target: 1 - Working groups operational with team members from relevant institutions with a clear mandate and their continuous involvement in the ‘Technical Working Group’ and ‘Coordination Group’ Baseline: 0 Target: 2 (*) - Number of meetings facilitated for effective functioning of working groups through team building, training and expert inputs Baseline: 0 Target: at least 4 meetings a year (*) | - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. |

2C - ACTIVITIES IN THE REPORTING PERIOD

Budget Heading II. Horizontal Costs

Work Plan Preparation

2 weeks after arrival of the RTA to a BA a mission focused on preparation of the work plan was conducted. 2 Junior Project Leaders - Mr Jose Ignacio Martin Fernandez (5WD) and Ms Ulla Saar (3WD) (from Spain and Estonia), and 1 ST expert Ms Consuelo Manchon Garcia (5WD), Component Leader II. have participated in the round of meetings with the relevant key representatives of the BA to ensure a common understanding of initial activities of the project and clarification of need from the side of the BA for the next 6 months. The STE have discussed and commented the Communication and Visibility Plan as well.

Output: Initial work plan

| Name of MS Experts | Mr Jose Ignacio Martin Fernandez, JPL, Component Leader I. Ms Consuelo Manchon Garcia, Component Leader II. Ms Ulla Saar, JPL |
| --- | --- |
| Number of experts from BA experts/dpt. | 7 experts in total - Mr Beka PERADZE, Head of Labour Conditions Inspecting Department. - Ms Lika KLIMIASHVILI, Head of the Labour Relations and Social Partnership Division. - Mr Levan ABASHIDZE, Head of Monitoring and Supervision Division of the Labour Conditions Inspection Department (LCID). - Ms Irma GELASHVILI, Legal counsellor at the Head of Labour Relations and Social Partnership Division. - Ms Shorena KUBANEISHVILI, Labour Conditions Inspecting Department - Mr Dimitri Tskitishvili, MP of Georgia - Mr Zakaria Shvelidze, ILO consultant |
| Duration of activity | 21 - 25/10/2019, 2 experts/2 missions x 5 WD, in total 10 WD 22 - 24/10/2019, 1 expert/1 mission, 3 WD |

Communication and Visibility Programme

Communication and Visibility Plan was prepared by the RTA, Ms Valeria Kubalova during the mission focused on the preparation of the workplan. The draft of the Communication and Visibility Plan was discussed and consulted with all presented STE experts and the representatives of the BA.

Output: Communication and Visibility Plan

| Number of experts from BA experts/dpt. | - 4 BA experts in total - Mr Beka PERADZE, Head of Labour Conditions Inspecting Department. - Ms Lika KLIMIASHVILI, Head of the Labour Relations and Social Partnership Division. - Mr Levan ABASHIDZE, Head of Monitoring and Supervision Division of the Labour Conditions Inspection Department (LCID). - Ms Shorena KUBANEISHVILI, Labour Conditions Inspecting Department |
| --- | --- |

Activity 01. Kick-off meeting (Opening event)

Launching of new EU Programme on Skills Development and Matching for Labour Market Needs - Skills4Jobs which was held on 29th October, 2019 was considered as a Kick-off meeting of the TW Project. Mr Jose Ignacio Martin Fernandez, JPL and a Component Leader I. has participated in the Launching event and   delivered the presentation about objectives, activities and outputs of the project.

| Name of MS Experts | Mr Jose Ignacio Martin Fernandez, JPL, Component Leader I. |
| --- | --- |
| Number of experts from BA experts/dpt. | - 7 BA experts in total - Ms Tamila BARKALAIA, Deputy Minister, MoIDPLHSA - Mr Beka PERADZE, Head of Labour Conditions Inspecting Department, MoIDPLHSA - Ms Lika KLIMIASHVILI, Head of the Labour Relations and Social Partnership Division, MoIDPLHSA - Mr Levan ABASHIDZE, Head of Monitoring and Supervision Division of the Labour Conditions Inspection Department (LCID). - Ms Shorena KUBANEISHVILI, Labour Conditions Inspecting Department |
| Duration of activity | 28-29/10/2019, 1 experts/1 missions x 2 WD |

Activity 0.2. Steering Committee meeting

Steering Committee Meeting was held on 28th October, 2019 at the premises of the MoIDPLHSA. Initial working plan and Communication and Visibility Plan was approved during the SCM.

2 MS experts - Mr Branislav Ondrus, Deputy Minister, MS PL and Mr Jose Ignacio Martin Fernandez, JPL, Component Leader I. participated in the SCM. EUD was represented by Ms. Jurate Juodsnukyte, Attachée - Programme Officer in charge of Labour Market, Migration, Gender and Mr. Vincent Rey Head of Cooperation Section.

In total 7 BA experts participated in the SCM.

Output: Initial Work Plan, Communication and Visibility Plan, updated Logframe

| Name of MS Experts | Mr Branislav Ondrus, Deputy Minister, MS PL Mr Jose Ignacio Martin Fernandez, JPL, Component Leader I. |
| --- | --- |
| Number of experts from BA experts/dpt. | - 5 BA experts in total - Ms Tamila Barkalaia, Deputy Minister, MoIDPLHSA - Ms Lika KLIMIASHVILI, Head of the Labour Relations and Social Partnership Division, MoIDPLHSA - Ms Shorena KUBANEISHVILI, Labour Conditions Inspecting Department Ms. Nino Grdzelishvili (Head of EU Assistance Coordination Division/PAO EU Assistance Coordination and Sectoral Integration Department, Ministry of Foreign Affairs of Georgia); - Ms. Nino Mujiri (Expert on EU External Assistance Coordination, AA Facility II, PAO Support) |
| Duration of activity | 28-29/10/2019, 2 experts/2 missions x 2 WD, in total 4 WD |

Component 1 Approximation of primary and secondary legislation related to Labour Law, Gender Equality, and Occupational Safety and Health in accordance with the Union acquis

Activity 1.1.1: Aligning Georgian legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis

| Component 1 Approximation of primary and secondary legislation related to Labour Law, Gender Equality, and Occupational Safety and Health in accordance with the Union acquis |  |  |
| --- | --- | --- |
| Ref. number | Title of activity/State of play/Name of involved MS Experts | Duration of the activity |
| Activity 1.1.1: | Aligning Georgian legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis | October 2019 – April 2020 |
|  | State of play: 4 missions were carried out during the reporting period as follows: 1st mission 29/11/2019 – 01/12/2019 Ms Karolina Balenovic (4 WD) was focused on: - Compliance of the Draft Labour Code of Georgia with Council Directive 2001/23/EC on the approximation of the laws of the Member States relating to the safeguarding of employees' rights in the event of transfers of undertakings, businesses or parts of undertakings or businesses (hereinafter: Directive 2001/23/EC) and Council Directive 98/59/EC on the approximation of the laws of the Member States relating to collective redundancies Key findings: - Labour Code of Georgia is namely in compliance with both Directives 2001/23/EC transfer of undertaking & Directive 98/59/EC on collective redundancy. Certain proposals have been made for further improvements and timely implementation of the ECJ interpretation of the Directives. Notice have been given to possibility of more extensive integration of workers representation (Directive 2002/14/EC). Recommendations: - Directive 2001/23/EC - wider definition of the ‘transfer’ of undertaking, business or part of an undertaking or business needed by ECJ case law. Proposal for implementing ‘any’ transfer instead of simple wording transfer in definition of the transfer in Labour Code Georgia. Directive 2002/14/EC establishing a general framework for informing and consulting employees in the European Community may be taken in consideration in transposing the Directive 2001/23/EC. Namely, Art 6/4, when the undertaking, business or part of an undertaking or business does not preserves its autonomy, the continuum of workers representation will be preserved during the period necessary for the reconstitution or reappointment of the representation of employees in accordance with national law or practice. - Directive 98/59/EC - Art 1/1 (i) vs LC Georgia Art 49/1 - contracts of employment concluded for limited periods of time or for specific tasks (part time contracts) should be in calculation - for ‘establishments normally employing’ (number, percentage of workers) Art. 1/1 (i). - Art 3/2 – workers association/representatives – comments/proposals to the Minister (Art 49/4 LC Georgia – not clear enough, they can write not only to the employer but to the public authority (in LC Georgia –Minister) too and they should both be looking for solutions (and Minister to have tool for such), for example to have the right to write an opinion and to receive the timely answer from the employer Output: - Compliance and the List of amendments related to Directive 98/59/EC, Directive 2001/23/EC 2nd mission 04/11/2019 – 08/11/2019 Ms Seili Suder (5 WD),Ms Mariliis Proos (5 WD) was focused on: - Assessment of compliance of the draft Labour Code of Georgia with the following EU directives: Council Directives 1999/70/EC, 97/81/EC, 2002/14/EC, 2003/88/EC, - Participation and discussion in the 3rd Round Table focused on amendments of the draft Labour Code of Georgia: 1) Grounds for terminating labour contracts (LCG article 47) 2) Internship (draft LCG Article 18), 3) Procedure for terminating labour contracts (LCG article 48), 4) Information and Consultation, Strikes and mediation - Clarification meeting with Ms Irma Geliashvili and Mr Jose Ignacio Martin Fernandez, STE focusing on questions that came up during the analysis of the directives. The questions mainly concerned the specifics of the LCG and the current regulations in force. These questions were discussed with the representative of Labour Conditions Inspection Department. The topics on the table concerned mainly working time (e.g maximum working hours, working in shifts, minimum rest, possible derogations etc), conclusion of the employment contract (e.g fixed-term contracts), collective agreements. Main findings and recommendations: - Findings, CJEU case law examples, best practise and recommendations are developed in the Assessment Report Output: - Assessment Report on Compliance of the amendments of the Labour Code of Georgia with the relevant EC Directives 3rd mission 07/11/2019 – 11/11/2019 Jose Ignacio Fernandez Martin (3 WD) was focused on : - Participation in the fourth meetingss of the tripartite round table meeting of the LCG Reform which was devoted to the draft of the Labour Inspectorate Law and the necessary amendments in other texts of the legal framework of Georgia as well as taking part in further aassessment of compliance of the draft Labour Code of Georgia with the the EU directives being dealt in the mission above Main findings and recommendations: - Concerning the Labour Code of Georgia Reform, and the new Labour Inspectorate Law, a great deal of work has been done by the BC in order to adapt to international standards on the matter. The attendance to the meeting of the tripartite round table meeting of the LCG Reform. Devoted to the draft of the Labour Inspectorate Law and the necessary amendments in other texts of the legal framework of Georgia, give a thorough knowledge of the state of play that is key for Component 1. - A clearer contractual framework with good differentiation between labour contracts and service provider’s contract would mean a great advantage for the whole system 4th misison 02/12/2019 – 06/12/2019 Jozef Toman (5 WD), Maros Palik (5 WD) was dealt with: - Presentation of the council Directive 91/383/EEC of 25 June 1991 supplementing the measures to encourage improvements in the safety and health at work of workers with a fixed- duration employment relationship or a temporary employment relationship; - Preparation of Table of Concordance on the directive 91/383/EEC (comparison of current legal provisions of Labour Code of Georgia and Organic Law of Georgia on Occupational Health and Safety with provisions of the directive); - Finalization of the Assessment on ccompliance of the draft Labour Code of Georgia with 8 Council Directives Main findings and recommendations: - In Georgian legislation there are no specific provisions on occupational health and safety related to fixed-term workers. There are only general provision in Labour Code (e.g. article 12 of draft) and Organic Law of Georgia on Occupational Health and Safety. - There is no legal framework on temporary agency work in Georgia. For example, subjects established/based on Law on Labour Migration are in fact intermediators, without existence of labour relationship between such subject and an employee. Such intermediator signs an employment contract with employee in name and in favour of foreign employer. Such relationship is not temporary agency work under EU law - Large part of discussion was focused on functioning and regulation, licensing of agencies in the Slovak Republic including legal framework and practice. STE´s gave practical examples for possible further development of this issue in Georgia - Draft of LCG can be seen as a big step forward in approximation of EU law to Georgian labour law. There are still however some problematic provisions of draft LCG in connection to EU law (some provision are not very clear and therefore it is not possible to come to conclusion of their conformity with EU law, there are some omission or missing parts). Assessment of draft law contains: 1) short description of basic scope and purpose of directives, 2) analysis on positive parts – transposed parts of directive and on problematic issues (by using best practices of EU members states and provide BC with relevant proposals and suggestions) Outputs: - Draft Table of Concordance council Directive 91/383/EEC of 25 June 1991 supplementing the measures to encourage improvements in the safety and health at work of workers with a fixed-duration employment relationship or a temporary employment relationship | 1st mission: 29/11/2019 – 01/12/2019 2nd mission: 04/11/2019 – 08/11/2019 3rd mission 07/11/2019 – 11/11/2019 4th misison 02/12/2019 – 06/12/2019 |
| Number of experts from BA experts/dpt. | - 4 BA experts in total - Ms Lika KLIMIASHVILI, Head of the Labour Relations and Social Partnership Division, MoIDPLHSA - Ms Irma Gelashvili, Head of the Labour Relations and Social Partnership Division, MoIDPLHSA - Ms Shorena KUBANEISHVILI, Labour Conditions Inspecting Department - Nino Gvetadze, Social Protection Policy Division |  |
| Ref. number | Title of activity/State of play/Name of involved MS Experts | Duration of the activity |
| Act.1.2.1. | Analysis / Assessment of current legal framework on non-discrimination and gender equality including aspects of Labour Inspection System, in order to amend it in compliance with the EU aquis | December 2019 – April 2020 |
|  | State of play: 1 mission was carried out during the reporting period as follows: 1st mission 02 - 06/12/2019 Mr Jose Ignacio Martin Fernandez (5 WD), Mr Juan Martin Garcia Alloza (4 WD) Mission was focused on assessment of the 2 directives: - 2004/113/EC implementing the principle of equal treatment between men and women in the access to and supply of goods and services - 79/7/EEC on the progressive implementation of the principle of equal treatment for men and women in matters of social security State of Play Mission was focused on initial discussion and assessment of the relevant Georgian laws and its alignment to the EU acquis. 2 meetings with the representatives were held and the topics were clarified. The ToC were drafted, but completed in the next reporting period. | 1st mission 02 - 06/12/2019 2nd mission 24 -28/02/2020 |
| Number of experts from BA experts/dpt. | - 4 BA experts in total - Ms Lika KLIMIASHVILI, Head of the Labour Relations and Social Partnership Division, MoIDPLHSA - Ms Irma Gelashvili, Head of the Labour Relations and Social Partnership Division, MoIDPLHSA - Ms Shorena KUBANEISHVILI, Labour Conditions Inspecting Department - Nino Gvetadze, Social Protection Policy Division - Mr Beka PERADZE, Head of Labour Conditions Inspecting Department, MoIDPLHSA - Mr Levan ABASHIDZE, Head of Monitoring and Supervision Division of the Labour Conditions Inspection Department (LCID). |  |

| Component 2: Capacity building, inter-institutional cooperation, and awareness raising of relevant state authorities and private sector for full implementation of amended legislation in labour law, gender equality and OSH |  |  |
| --- | --- | --- |
| Ref. number | Title of activity/State of play/Name of involved MS Experts | Duration of the activity |
| Act. 2.1.1. | Assessment of the administrative structures and institutional capacities of the beneficiary and relevant stakeholders and improvement of their inter-institutional operation | December 2019 – March 2020 |
|  | State of play: 1 mission was carried out during the reporting period as follows: 1st mission 09 - 13/12/2019 Ms Consuelo Manchon Garcia (5 WD), Mr Tamas Berky (5WD ), Mr Juan Martin Garcia Alloza (5 WD) was focused on: - focused on mapping and assessment of the administrative structures and the institutional capacities of the beneficiary including relevant stakeholders with the aim to improve their inter-institutional cooperation and capacity building for full implementation of (to be) amended legislation. - as a first steps in conducting the functional analysis, aims to gain an overall understanding of the public administration reform process in Georgia so that we could place our analysis and recommendations in an appropriate context Key findings: - The mission focused on collecting initial data on the status of labour inspection, determining the scope of necessary further data and partner meetings for further missions, including the elaboration of a need’s assessment survey. - The initial profound findings are: a) the inspection authority is in place for 3 years. While it is important to assess current conditions at the department, it is essential that we look at inspection, and improvement of OSH and labour relation as a system, including other actors and future regional affiliates. b) we consider that is is important to look for the future objectives of the Ministry and assess the situation in particular sectors in order to establish future institutional capabilities and capacities required as well as the adequacy of the current system. c) we assess that the staff of the inspectorate consists of motivated persons, who have a practical experience in field inspection, however, according to their assessment, sector and hazard specific training, as well as training in measurement and other technical aspects is needed. - Also, the current practice focuses on the sectors where there is a high rate of accidents and fatal accidents, but in the future it will be necessary to cover further fields in the service, care, tourism sector, where risks do not pose an immediate threat to human health but are significant in a longer term and which concern greater number of employees with regard to the whole economy. Recommendations: - Questionnaire on the training needs analysis completed to be filled in by labour inspectors - Structure of the Functional Review Report | 1st mission 09 - 13/12/2019 |
| Number of experts from BA experts/dpt. | - 24 BA experts in total - Ms Shorena KUBANEISHVILI, Labour Conditions Inspecting Department - Badri Ugulava, LCID - Mikheil Imerlishvili, LCID - Monika Chania, LCID - 10 staff of the Makhviladze Research Institute of Labour Medicine and Ecology - 5 staff of the Tbilisi municipality - 3 staff of the Technical and Construction Supervision Agency - 2 staff of the Georgian Association of Employers |  |
| Ref. number | Title of activity/State of play/Name of involved MS Experts | Duration of the activity |
| Activity 2.2.2. | Preparing and implementing public information campaign aiming to raise awareness among the project among key stakeholders, public, private sector and civil society | December 2019 – May 2020 |
|  | State of play: 3 missions were carried out during the reporting period as follows: 1st mission 09 - 13/12/2019 Ms Luba Pavlovova (5 WD) was focused on: - mapping the situation regarding the preparation of the public awareness campaign aiming at increasing awareness and understanding of new legal rules / amendments related to the labour relations (Labour Code) and occupational health and safety at work by key target groups – employers and employees as well by key representatives of these target groups (social partners), other key stakeholders and by the Georgian public - during the mission the current stage of play regarding LCID capacity for planning, preparing, implementing and evaluating a nationwide campaign was checked - any activities already done by any donors operational in the country and on ILO works towards awareness raising actions and campaign preparation in order to ensure mutual cooperation and avoid overlapping of any events/activities were checked - input for the next missions to be conducted by STEs involved in this activity was prepared Key findings and recommendations: - There are number of donors who are also dealing with communication and information activities in the OSH area incl. on gender matters and equal opportunities - Both ILO and GIZ are working on specialised animations (videos); while ILO is focused on more “general” adds, the GIZ is focused on a concrete sector – construction – and the planned videos are of technical nature, i.e. directly aiming at concrete topics and targeting employers and workers in the sector; these videos are to be ready in January 2020 - UN Women are dealing with gender issues and antidiscrimination, as well with flexible working hours, social protection, etc – later possible cooperation can be of benefit for the both sides – LCID and UN Women - No survey/s was conducted so far neither on employers perception on OSH awareness raising and information on new legal rules/requirements, etc, nor on the employees’ side. The recent information/communication and campaigning activities were based mainly on initiatives of the LCID upon some evidence from the field. None of the donors did such survey/s - In line with above and taking into account the content of act. 2.2.2 it will be necessary to get the real view of both key target groups – employers and employees (workers) on OSH awareness raising and information on new legal rules/requirements, etc; this will be served as good basis for the campaign preparation - Taking into consideration the fact that TWP has to launch the campaign on 28.4.2020 all planning must be done in the course of Jan-March 2020 and the list of Conducting surveys – employers + employees (workers), evaluation of results and based on this set /adjust the campaign plan. The list of actions was sett up: - Set clear Concept – most important is to BE CLEAR WHAT WE WOULD LIKE TO ACHIEVE AND WHY, SET THE MAIN MESSAGE/S ACCORDINGLY and elaborate on the plan - Coordinate the above-activities with other donors/organisations, specifically with GIZ & ILO, possibly with UN Women to make a common Concept and Action Plan for not only opening of the campaign on 28.4.2020 but also on the months after this OSH Day. - The training of LCID staff on campaign planning and realisation, focused on planning, implementing and evaluation of campaign and awareness-raising activities aiming at changing the OSH culture in the country after TWP ends and be the owner of all these actions Outputs: - OSH Questionnaire for employers elaborated and delivered to LCID for any further commenting | 1st mission 09 - 13/12/2019 |
| Number of experts from BA experts/dpt. | 16 BA experts in total were involved in the activity - Ms Tamila Barkalaia, Deputy Minister, MoIDPLHSA - Mr Beka PERADZE, Head of Labour Conditions Inspecting Department, MoIDPLHSA - Mr Levan ABASHIDZE, Head of Monitoring and Supervision Division of the Labour Conditions Inspection Department (LCID). - Ms Shorena KUBANEISHVILI, Labour Conditions Inspecting Department - Maia Mikkaia, Head of Labour Inspection Division of the L Labour Conditions Inspection Department - Nick Nanuashvili, BAG - Tamar Kapianidze, ICCA - Nino Ushirishvili, EBA - Lasha Labadze, GEA - Elene Makharashvili, GEA - Giga Bekauri, GIUC - Kinan Albahnasi, ILO - Tamar Kheladze, ILO - Ekaterine Karchkhadze, ILO - Tatia Tsereteli, PR Department, MoIDPLHSA - Nino Talakhadze, PR Department, MoIDPLHSA - Irina Sikharulidze, PR Department, MoIDPLHSA |  |

2D - TIMING AND DELAYS

Adherence to time schedule

| Project Month 2019/20 | October | Nov | Dec | Jan |
| --- | --- | --- | --- | --- |
| Horizontal costs |  |  |  |  |
| Steering Committee |  | X |  |  |
| Workplan | X |  |  |  |
| Component 0 |  |  |  |  |
| Activity 0.1 Kick-off | X |  |  |  |
| Activity 1.1.1 |  | X | X |  |
| Activity 1.2.1 |  |  | X |  |
| Activity 1.3.1 |  |  |  |  |
| Component 2 |  |  |  |  |
| Activity 2.1.1. |  |  | X | X |
| Activity 2.1.2. |  |  |  |  |
| Activity 2.1.3. |  |  |  |  |
| Activity 2.1.4. |  |  |  |  |
| Activity 2.2.1. |  |  |  | X |
| Activity 2.2.2. |  |  | X | X |
| Activity 2.2.3. |  |  |  |  |
| Activity 3.1.1. |  |  |  |  |

Activity/action Planned

X		Activity/action Performed

Activity/action Delayed by more than three months

Recuperation of delays

During the 1st reporting period there is no delay in implementation of the project.

2E - ASSESSMENT

Overall Assessment of progress

The progress made is in line with the given timeframe.

Concrete time schedule – dates for each activity and mission were prepared and consulted with the beneficiary and MS ST experts. Taking into consideration the beneficiary, different stakeholders and planned activities, it was necessary to keep some flexibility in the planning as majority of events are to be implemented in close cooperation with all involved into the twinning project.

During the reporting period the beneficiary has shown a high level of involvement.

The cooperation with BA as well as with other stakeholders is efficient and discussions are constructive thus the benchmarks are expected to be met as stated in the contract.

All stakeholders including the social partners are fully committed and they confirmed their active participation in the implementation of the project’s components. CFCA managers are very helpful, quick and very operational in dealing with daily issues. There are no difficulties in communication/cooperation with all involved twinning parties.

At the end of reporting period one political resignation of the MPs might has influence to the further implementation of activity 1.1.1. Aligning Georgian legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis. Mr Dimitri Tskitishvili, member of Parliament leading and coordinating the initiative the Labor Code Reform in Georgia   and creating the new legal and institutional mechanisms has resigned. Until the end of the reporting period it was not clear who will overtake the initiative of the previous MP and will keep working on further amendments as well as who will submit the Labour Code amendments to the further legislation process.

Overall evaluation of the progress achieved during the reporting period.

Component 0

Within the component 0 the following outputs were delivered during the reporting period:

- Initial Work plan

- Communication and visibility Plan

- Facts sheet

Component 1

Within the component 1 the following outputs were delivered during the reporting period:

- 1st Draft of the Initial Assessment on the proposed amendments of the Labour Code of Georgia

- Assessment of compliance of the amendments of the Labour Code of Georgia with 8 EC Directives related to the labour law including the selected Case Law of CJ EU to each of selected Directives

- Table of Concordance of the Council Directive 91/383/EEC of 25 June 1991 supplementing the measures to encourage improvements in the safety and health at work of workers with a fixed-duration employment relationship or a temporary employment relationship

Component 2

Within the component 2 the following outputs were delivered during the reporting period:

- Electronic questionnaire for the Training needs Analysis

- OSH Questionnaires for private employers

Other Issues

No problems in the management of the Twinning Project have occurred until now. All project partners handle unforeseen issues in the project in a very cooperative and flexible way. Any partial issues were resolved on the grounds of good communication and cooperation among the twinning partners.

List of Annexes

Annex 1	1st  Interim Quaterly Financial Report

Annex 2	First Draft of the Initial Assessment on the proposed amendments of the Labour Code of Georgia

Annex 3	Assessment of the compliance of the amendments of the Labour Code of Georgia with 8 EC Directives related to the labour law including the selected Case Law of CJ EU to each of selected Directives

Annex 4	Table of Concordance of the Council Directive 91/383/EEC of 25 June 1991 supplementing the measures to encourage improvements in the safety and health at work of workers with a fixed-duration employment relationship or a temporary employment relationship in both languages

Annex 5	Questionnaire for Training Needs Analysis

Annex 6 	Questionnaire for Private Sector Employers

Section 3: Expenditures

Provide total figures of disbursement in the reporting period broken down on budget headings and for the key groups of costs under each budget heading - as per Annex A3 to the Twinning Grant Contract.

| Section No./Activity | Name of services/ goods purchased or direct costs | Date(s) of service | Invoice No. | Date of invoice | Breakdown and clarification | Amount paid in local currency (if applicable) | Info EURO exch. Rate | Amount paid in EUR | Amount foreseen in original budget | Amount introduced by side letter/amendment | Amount charged to contingencies |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I. | I. BUDGET HEADING: Resident Twinning Advisor and related cost |  |  |  |  |  |  |  |  |  |  |
|  | Compensation wage and non wage | 07.10.2019-31.10.2019 01.11.2019-30.11.2019 01.12.2019-31.12.2019 01.01.2020-06.01.2020 | RfP Nr. 1, 2, 3, 4 | 25.11.2019, 23.12.2019, 16.01.2020, 14.02.2020, | October 2019 (5500Eur/31days)* 25days = 4435,48Eur November 2019: 5500Eur December 2019: 5500Eur January 2020 (5500Eur/31days)* 6days = 1064,52 Eur |  |  | 16,500.00 € | 132,000.00 € | 132,000.00 € |  |
|  | Compensation Daily Subsistence | 07.10.2019-31.10.2019 01.11.2019-30.11.2019 01.12.2019-31.12.2019 01.01.2020-06.01.2020 | RfP Nr. 1, 2, 3, 4 | 25.11.2019, 23.12.2019, 16.01.2020, 14.02.2020, | October: 148,50Eur x 25days = 3712,50Eur November: 148,50Eur x 30days = 4455,00Eur December: 148,50Eur x 31days = 4603,50Eur January: 148,50Eur x 6days = 891,00Eur |  |  | 13,662.00 € | 108,553.50 € | 108,553.50 € |  |
|  | Removal |  |  |  |  |  |  |  | 0.00 € | 0.00 € |  |
|  | Travel |  |  |  |  |  |  |  |  |  |  |
|  | Taking up duty | 07/10/2019 | RfP Nr. 1 | 25/11/2019 | RTA travel Bratislava-Tbilis reimbursed at the real costs for economy flight ticket: 458,31Eur |  |  | 457.00 € | 914.00 € | 914.00 € | 1.31 € |
|  | Accompanying Family |  |  |  |  |  |  |  | 0.00 € | 0.00 € |  |
|  | Annual Return Trip |  |  |  |  |  |  |  | 0.00 € | 0.00 € |  |
|  | Annual Return Trip spouse and family |  |  |  |  |  |  |  | 0.00 € | 0.00 € |  |
|  | Monthly Travel | 01.11.2019-30.11.2019 01.12.2019-31.12.2019 01.01.2020-06.01.2020 | RfP Nr. 2, 3, 4 | 23.12.2019, 16.01.2020, 14.02.2020, | November 2019: 457Eur December 2019: 457Eur January 2020: (457/31) x 6days = 88,45Eur |  |  | 1,002.45 € | 10,511.00 € | 10,511.00 € |  |
|  | School Fees |  |  |  |  |  |  |  | 0.00 € | 0.00 € |  |
|  | RTA Training Brussels |  |  |  |  |  |  |  |  |  |  |
|  | Travel Costs |  |  |  |  |  |  |  | 550.00 € | 550.00 € |  |
|  | Daily Subsistence Allowance |  |  |  |  |  |  |  | 464.00 € | 464.00 € |  |
|  | RTA Assistants contracts |  |  |  |  |  |  |  |  |  |  |
|  | Assistant(s) | 01.11.2019-30.11.2019 01.12.2019-31.12.2019 01.01.2020-06.01.2020 | Inv. Nr. 01 Machkhaneli Inv. Nr. 02 Machkhaneli Inv. Nr. 03 Machkhaneli | 29.11.2019, 31.12.2019, 31.01.2019, | November 2019: 1600Eur December 2019: 1600Eur January 2020: (1600/31) x 6days = 309,68Eur |  |  | 3,509.68 € | 38,400.00 € | 38,400.00 € |  |
|  | Interpreter/translator salary | 18.11.2019-30.11.2019 01.12.2019-31.12.2019 01.01.2020-06.01.2020 | Inv. Nr. 01 Goisashvili Inv. Nr. 02 Goisashvili Inv. Nr. 03 Goisashvili | 29.11.2019, 31.12.2019, 31.01.2019, | November 2019: (1600/21WDs) x 10days = 761,90Eur December 2019: 1600Eur January 2020: (1600/31) x 6days = 309,68Eur |  |  | 2,671.58 € | 38,400.00 € | 38,400.00 € |  |
|  | Total: Resident Twinning Advisor and related cost |  |  |  |  |  |  | 37,802.71 € | 329,792.50 € | 329,792.50 € | 1.31 € |
| II. | II. BUDGET HEADING: Horizontal activities related Costs |  |  |  |  |  |  |  |  |  |  |
|  | Short term staff: MS PL and other Support staff / Component Leaders |  |  |  |  |  |  |  |  |  |  |
|  | Work Plan preparation* |  |  |  |  |  |  |  | 4,550.00 € | 4,550.00 € |  |
|  | Steering Committees* |  |  |  |  |  |  |  | 14,700.00 € | 14,700.00 € |  |
|  | Communication/Visibility programme* |  |  |  |  |  |  |  | 0.00 € | 0.00 € |  |
|  | Twinning Project Support Cost |  |  |  |  |  |  |  | 26,180.00 € | 26,180.00 € |  |
|  | Compensation for Daily Subsistence |  |  |  |  |  |  |  | 15,642.00 € | 15,642.00 € |  |
|  | Travel Costs Bratislava (PL 7xSCM) |  |  |  |  |  |  |  | 3,199.00 € | 3,199.00 € |  |
|  | Travel Costs Madrid (JPL 1xWP, 7xSCM) |  |  |  |  |  |  |  | 4,520.00 € | 4,520.00 € |  |
|  | Travel Costs Albacete (CL2 1xWP, will be based on real costs) |  |  |  |  |  |  |  | 616.00 € | 616.00 € |  |
|  | Travel Costs Tallinn (JPL 1xWP, 7xSCM) |  |  |  |  |  |  |  | 3,192.00 € | 3,192.00 € |  |
|  | PC PL and/or RTA Counterpart Training Brussels |  |  |  |  |  |  |  |  |  |  |
|  | Travel Costs |  |  |  |  |  |  |  | 550.00 € | 550.00 € |  |
|  | Compensation for Daily Subsistence |  |  |  |  |  |  |  | 464.00 € | 464.00 € |  |
|  | Communication/Visibility programme |  |  |  |  |  |  |  |  |  |  |
|  | Maximum amount for all components |  |  |  |  |  |  |  | 15,000.00 € | 15,000.00 € |  |
|  | Purchase of Goods |  |  |  |  |  |  |  | 0.00 € | 0.00 € |  |
|  | Expenditure Verification / Audit costs |  |  |  |  |  |  |  | 5,000.00 € | 5,000.00 € |  |
|  | Work Plan preparation: Flat Daily Allowance Fernandez | 21.10.2019-25.10.2019 | MC | 25/10/2019 | 350Eur x 5days |  |  | 1,750.00 € |  |  |  |
|  | Twinning Project Support Cost (Fernandez) | 21.10.2019-25.10.2019 |  |  | 1750*136% |  |  | 2,380.00 € |  |  |  |
|  | Compensation for Daily Subsistence Fernandez | 20.10.2019-26.10.2019 | MC | 25/10/2019 | 198Eur x 6nights |  |  | 1,188.00 € |  |  |  |
|  | Travel Costs (Fernandez) | 20.10.2019-30.10.2019 | MC | 25/10/2019 | Flat rate Madrid-Tbilisi-Madrid reimbursed at unit cost for travel fixed in the contract: 565,00Eur Arrival: 20.10.2019, 04:30 Departure: 30.10.2019, 04:15 * Expert continued on Kick-off meeting 28-29.10.2019 |  |  | 565.00 € |  |  |  |
|  | Work Plan preparation: Flat Daily Allowance Garcia | 21.10.2019-25.10.2019 | MC | 25/10/2019 | 350Eur x 5days |  |  | 1,750.00 € |  |  |  |
|  | Twinning Project Support Cost (Garcia) | 21.10.2019-25.10.2019 |  |  | 1750*136% |  |  | 2,380.00 € |  |  |  |
|  | Compensation for Daily Subsistence Garcia | 20.10.2019-26.10.2019 | MC | 25/10/2019 | 198Eur x 6nights |  |  | 1,188.00 € |  |  |  |
|  | Travel Costs (Garcia) | 20.10.2019-26.10.2019 | MC | 25/10/2019 | Travel costs Albacete-Tbilisi-Albacete reimbursed at the real costs for economy treavel and flights: 698,19Eur Arrival: 20.10.2019, 04:30 Departure: 26.10.2019, 04:40 |  |  | 616.00 € |  |  | 82.19 € |
|  | Work Plan preparation: Flat Daily Allowance Saar | 22.10.2019-24.10.2019 | MC | 24/10/2019 | 350Eur x 3days |  |  | 1,050.00 € |  |  |  |
|  | Twinning Project Support Cost (Saar) | 22.10.2019-24.10.2019 |  |  | 1050*136% |  |  | 1,428.00 € |  |  |  |
|  | Compensation for Daily Subsistence Saar | 21.10.2019-25.10.2019 | MC | 24/10/2019 | 198Eur x 4nights |  |  | 792.00 € |  |  |  |
|  | Travel Costs (Saar) | 22.10.2019-25.10.2019 | MC | 24/10/2019 | Flat rate Tallinn-Tbilisi-Tallinn reimbursed at unit cost for travel fixed in the contract: 399,00Eur Arrival: 22.10.2019, 03:30 Departure: 25.10.2019, 04:15 |  |  | 399.00 € |  |  |  |
|  | Steering Committee 1: Flat Daily Allowance Fernandez | 28.11.2019-29.11.2019 | MC | 29/11/2019 | 350Eur x 2days |  |  | 700.00 € |  |  |  |
|  | Twinning Project Support Cost (Fernandez) | 28.11.2019-29.11.2019 |  |  | 700*136% |  |  | 952.00 € |  |  |  |
|  | Compensation for Daily Subsistence Fernandez | 27.11.2019-30.11.2019 | MC | 29/11/2019 | 198Eur x 3nights |  |  | 594.00 € |  |  |  |
|  | Travel Costs (Fernandez) | 27.11.2019-07.12.2019 | MC | 29/11/2019 | Flat rate Madrid-Tbilisi-Madrid reimbursed at unit cost for travel fixed in the contract: 565,00Eur Arrival: 27.11.2019, 04:25 Departure: 07.12.2019, 05:45 * Expert continued on Act 1.2.1 02-06.12.2019 |  |  | 565.00 € |  |  |  |
|  | Steering Committee 1: Flat Daily Allowance Ondruš | 28.11.2019-29.11.2019 | MC | 29/11/2019 | 350Eur x 2days |  |  | 700.00 € |  |  |  |
|  | Twinning Project Support Cost (Ondruš) | 28.11.2019-29.11.2019 |  |  | 700*136% |  |  | 952.00 € |  |  |  |
|  | Compensation for Daily Subsistence Ondruš | 27.11.2019-30.11.2019 | MC | 29/11/2019 | 198Eur x 3nights |  |  | 594.00 € |  |  |  |
|  | Travel Costs (Ondruš) | 27.11.2019-01.12.2019 | MC | 29/11/2019 | Flat rate Bratislava-Tbilisi-Bratislava reimbursed at unit cost for travel fixed in the contract: 457,00Eur Arrival: 27.11.2019, 03:45+1 Departure: 01.12.2019, 04:40 |  |  | 457.00 € |  |  |  |
|  | Total: Horizontal activities related Costs |  |  |  |  |  |  | 21,000.00 € | 93,613.00 € | 93,613.00 € | 82.19 € |
| III. | III. BUDGET HEADING: Components Mandatory Results |  |  |  |  |  |  |  |  |  |  |
| COMPONENT 0: Kick-off meeting and Closing event |  |  |  |  |  |  |  |  |  |  |  |
| 0.1. | Activity 0.1 Kick-off meeting |  |  |  |  |  |  |  |  |  |  |
|  | JPL Jose Ignacio Martin Fernandez x 2WDs/1mission |  |  |  |  |  |  |  |  |  |  |
|  | Flat Daily Allowance |  |  |  |  |  |  |  | 700.00 € | 700.00 € |  |
|  | Twinning Project Support Cost |  |  |  |  |  |  |  | 952.00 € | 952.00 € |  |
|  | Compensation for Daily Subsistence |  |  |  |  |  |  |  | 792.00 € | 792.00 € |  |
|  | Travel Costs Madrid |  |  |  |  |  |  |  | 0.00 € | 0.00 € |  |
|  | Other Costs (interpretation, translation, venue costs) |  |  |  |  |  |  |  | 0.00 € | 0.00 € |  |
|  | Flat Daily Allowance Fernandez | 28.10.2019-29.10.2019 | MC | 29/10/2019 | 350Eur x 2days |  |  | 700.00 € |  |  |  |
|  | Twinning Project Support Cost (Fernandez) | 28.10.2019-29.10.2019 |  |  | 700*136% |  |  | 952.00 € |  |  |  |
|  | Compensation for Daily Subsistence Fernandez | 26.10.2019-30.10.2019 | MC | 29/10/2019 | 198Eur x 4nights |  |  | 792.00 € |  |  |  |
|  | Travel Costs (Fernandez) | 20.10.2019-30.10.2019 | MC | 29/10/2019 | Travel costs covered by Initial workplan preparation (21.10.2019-25.10.2019) Arrival: 20.10.2019, 04:30 Departure: 30.10.2019, 04:15 |  |  | 0.00 € |  |  |  |
|  | Total cost ACT 0.1. |  |  |  |  |  |  | 2,444.00 € | 2,444.00 € | 2,444.00 € | 0.00 € |
| COMPONENT 1 |  |  |  |  |  |  |  |  |  |  |  |
| 1.1. | Sub-Result 1.1: Legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis |  |  |  |  |  |  |  |  |  |  |
| 1.1.1. | Activity 1.1.1 Aligning Georgian legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis |  |  |  |  |  |  |  |  |  |  |
|  | 8 MS experts, 75WDs / 15 missions - Zagreb: Kristina Balenovic 15 WD/3 missions, - Bratislava: Jozef Toman 15 WD/3 missions, Maros Palik 5WD/1 mission, - Tallin: Saili Suder 10WD/2 missions, Marilis Proos 10WD/2 missions, - Madrid: Jose Ignacio Martin Fernandez 10 WD/2 missions, - Donostia / San Sebastian: Gabriela Beltran Fernández 5WD/1 missions, - Valencia: Juan Martin Garcia Alloza 5WD/1 missions, |  |  |  |  |  |  |  |  |  |  |
|  | Flat Daily Allowance |  |  |  |  |  |  |  | 26,250.00 € | 26,250.00 € |  |
|  | Twinning Project Support Cost |  |  |  |  |  |  |  | 35,700.00 € | 35,700.00 € |  |
|  | Compensation for Daily Subsistence |  |  |  |  |  |  |  | 17,820.00 € | 17,820.00 € |  |
|  | Travel Costs Bratislava |  |  |  |  |  |  |  | 1,828.00 € | 1,828.00 € |  |
|  | Travel Costs Madrid |  |  |  |  |  |  |  | 1,130.00 € | 1,130.00 € |  |
|  | Travel Costs Valencia** |  |  |  |  |  |  |  | 616.00 € | 616.00 € |  |
|  | Travel Costs Donostia / San Sebastian (will be based on real costs) |  |  |  |  |  |  |  | 616.00 € | 616.00 € |  |
|  | Travel Costs Tallin*** |  |  |  |  |  |  |  | 1,596.00 € | 1,596.00 € |  |
|  | Travel Costs Zagreb (will be based on real costs) |  |  |  |  |  |  |  | 1,500.00 € | 1,500.00 € |  |
|  | Translation |  |  |  |  |  |  |  | 1,200.00 € | 1,200.00 € |  |
|  | Flat Daily Allowance Balenovic | 29.10.2019-01.11.2019 | MC | 01/11/2019 | 350Eur x 4days |  |  | 1,400.00 € |  |  |  |
|  | Twinning Project Support Cost (Balenovic) | 29.10.2019-01.11.2019 |  |  | 1400*136% |  |  | 1,904.00 € |  |  |  |
|  | Compensation for Daily Subsistence Balenovic | 28.10.2019-02.11.2019 | MC | 01/11/2019 | 198Eur x 5nights |  |  | 990.00 € |  |  |  |
|  | Travel Costs (Balenovic) | 28.10.2019-02.11.2019 | MC | 01/11/2019 | Travel costs Zagreb-Tbilisi-Zagreb reimbursed at the real costs for economy treavel and flights: 525,00Eur Arrival: 28.10.2019, 05:00+1 Departure: 02.11.2019, 05:50 |  |  | 500.00 € |  |  | 25.00 € |
|  | Flat Daily Allowance Suder | 04.11.2019-08.11.2019 | MC | 08/11/2019 | 350Eur x 5days |  |  | 1,750.00 € |  |  |  |
|  | Twinning Project Support Cost (Suder) | 04.11.2019-08.11.2019 |  |  | 1750*136% |  |  | 2,380.00 € |  |  |  |
|  | Compensation for Daily Subsistence Suder | 03.11.2019-09.11.2019 | MC | 08/11/2019 | 198Eur x 6nights |  |  | 1,188.00 € |  |  |  |
|  | Travel Costs (Suder) | 03.11.2019-09.11.2019 | MC | 08/11/2019 | Flat rate Tallinn-Tbilisi-Tallinn reimbursed at unit cost for travel fixed in the contract: 399,00Eur Arrival: 03.11.2019, 04:30+1 Departure: 09.11.2019, 05:15 |  |  | 399.00 € |  |  |  |
|  | Flat Daily Allowance Proos | 04.11.2019-08.11.2019 | MC | 08/11/2019 | 350Eur x 5days |  |  | 1,750.00 € |  |  |  |
|  | Twinning Project Support Cost (Proos) | 04.11.2019-08.11.2019 |  |  | 1750*136% |  |  | 2,380.00 € |  |  |  |
|  | Compensation for Daily Subsistence Proos | 03.11.2019-09.11.2019 | MC | 08/11/2019 | 198Eur x 6nights |  |  | 1,188.00 € |  |  |  |
|  | Travel Costs (Proos) | 03.11.2019-09.11.2019 | MC | 08/11/2019 | Flat rate Tallinn-Tbilisi-Tallinn reimbursed at unit cost for travel fixed in the contract: 399,00Eur Arrival: 03.11.2019, 04:30+1 Departure: 09.11.2019, 05:15 |  |  | 399.00 € |  |  |  |
|  | Flat Daily Allowance Fernandez | 07.11.2019-11.11.2019 | MC | 11/11/2019 | 350Eur x 3days |  |  | 1,050.00 € |  |  |  |
|  | Twinning Project Support Cost (Fernandez) | 07.11.2019-11.11.2019 |  |  | 1050*136% |  |  | 1,428.00 € |  |  |  |
|  | Compensation for Daily Subsistence Fernandez | 07.11.2019-12.11.2019 | MC | 11/11/2019 | 198Eur x 5nights |  |  | 990.00 € |  |  |  |
|  | Travel Costs (Fernandez) | 07.11.2019-12.11.2019 | MC | 11/11/2019 | Flat rate Madrid-Tbilisi-Madrid reimbursed at unit cost for travel fixed in the contract: 565,00Eur Arrival: 07.11.2019, 04:25 Departure: 12.11.2019, 05:30 |  |  | 565.00 € |  |  |  |
|  | Flat Daily Allowance Toman | 02.12.2019-06.12.2019 | MC | 06/12/2019 | 350Eur x 5days |  |  | 1,750.00 € |  |  |  |
|  | Twinning Project Support Cost (Toman) | 02.12.2019-06.12.2019 |  |  | 1750*136% |  |  | 2,380.00 € |  |  |  |
|  | Compensation for Daily Subsistence Toman | 01.12.2019-07.12.2019 | MC | 06/12/2019 | 198Eur x 6nights |  |  | 1,188.00 € |  |  |  |
|  | Travel Costs (Toman) | 01.12.2019-07.12.2019 | MC | 06/12/2019 | Flat rate Bratislava-Tbilisi-Bratislava reimbursed at unit cost for travel fixed in the contract: 457,00Eur Arrival: 01.12.2019, 17:10 Departure: 07.12.2019, 18:50 |  |  | 457.00 € |  |  |  |
|  | Flat Daily Allowance Palik | 02.12.2019-06.12.2019 | MC | 06/12/2019 | 350Eur x 5days |  |  | 1,750.00 € |  |  |  |
|  | Twinning Project Support Cost (Palik) | 02.12.2019-06.12.2019 |  |  | 1750*136% |  |  | 2,380.00 € |  |  |  |
|  | Compensation for Daily Subsistence Palik | 01.12.2019-07.12.2019 | MC | 06/12/2019 | 198Eur x 6nights |  |  | 1,188.00 € |  |  |  |
|  | Travel Costs (Palik) | 01.12.2019-07.12.2019 | MC | 06/12/2019 | Flat rate Bratislava-Tbilisi-Bratislava reimbursed at unit cost for travel fixed in the contract: 457,00Eur Arrival: 01.12.2019, 17:10 Departure: 07.12.2019, 18:50 |  |  | 457.00 € |  |  |  |
|  | Total cost ACT 1.1.1. |  |  |  |  |  |  | 31,811.00 € | 88,256.00 € | 88,256.00 € | 25.00 € |
| 1.2. | Sub-Result 1.2: Legal framework on non-discrimination and gender equality, including aspects of labour inspection system, amended in compliance with the Union acquis. |  |  |  |  |  |  |  |  |  |  |
| 1.2.1. | Activity 1.2.1 Aligning Georgian legal framework on Occupational Health and Safety, including aspects of Labour Inspection System, amended in compliance with the Union acquis |  |  |  |  |  |  |  |  |  |  |
|  | 3 MS experts, 25WDs / 5missions - Valencia: Mr. Juan Martín GARCÍA ALLOZA 10WD/2 missions, - Madrid: Jose Ignacio Martin Fernandez 10 WD/2 missions, Gabriela Beltran Fernández 5WD/1 mission, |  |  |  |  |  |  |  |  |  |  |
|  | Flat Daily Allowance |  |  |  |  |  |  |  | 8,750.00 € | 8,750.00 € |  |
|  | Twinning Project Support Cost |  |  |  |  |  |  |  | 11,900.00 € | 11,900.00 € |  |
|  | Compensation for Daily Subsistence |  |  |  |  |  |  |  | 6,138.00 € | 6,138.00 € |  |
|  | Travel Costs Madrid |  |  |  |  |  |  |  | 1,695.00 € | 1,695.00 € |  |
|  | Travel Costs Valencia** |  |  |  |  |  |  |  | 1,232.00 € | 1,232.00 € |  |
|  | Translation |  |  |  |  |  |  |  | 0.00 € | 0.00 € |  |
|  | Flat Daily Allowance Fernandez | 02.12.2019-06.12.2019 | MC | 06/12/2019 | 350Eur x 5days |  |  | 1,750.00 € |  |  |  |
|  | Twinning Project Support Cost (Fernandez) | 02.12.2019-06.12.2019 |  |  | 1750*136% |  |  | 2,380.00 € |  |  |  |
|  | Compensation for Daily Subsistence Fernandez | 30.11.2019-07.12.2019 | MC | 06/12/2019 | 198Eur x 7nights |  |  | 1,386.00 € |  |  |  |
|  | Travel Costs (Fernandez) | 27.11.2019-07.12.2019 | MC | 06/12/2019 | Travel costs covered by Steering Committee (28-29.11.2019) Arrival: 27.11.2019, 04:25 Departure: 07.12.2019, 05:45 |  |  | 0.00 € |  |  |  |
|  | Flat Daily Allowance ALLOZA | 02.12.2019-06.12.2019 | MC | 06/12/2019 | 350Eur x 5days |  |  | 1,750.00 € |  |  |  |
|  | Twinning Project Support Cost (ALLOZA) | 02.12.2019-06.12.2019 |  |  | 1750*136% |  |  | 2,380.00 € |  |  |  |
|  | Compensation for Daily Subsistence ALLOZA | 01.12.2019-08.12.2019 | MC | 06/12/2019 | 198Eur x 7nights |  |  | 1,386.00 € |  |  |  |
|  | Travel Costs (ALLOZA) | 01.12.2019-14.12.2019 | MC | 06/12/2019 | Flat rate Valencia-Tbilisi-Valencia reimbursed at unit cost for travel fixed in the contract: 616,00Eur Arrival: 01.12.2019, 03:45 Departure: 14.12.2019, 04:40 * Expert continued on Act 2.1.1 09-13.12.2019 |  |  | 616.00 € |  |  |  |
|  | Total cost ACT 1.2.1. |  |  |  |  |  |  | 11,648.00 € | 29,715.00 € | 29,715.00 € | 0.00 € |
| COMPONENT 2 |  |  |  |  |  |  |  |  |  |  |  |
| 2.1. | Sub-Result 2.1: Analysis for strengthening state authorities’ capacity for implementation of the EU best practices performed, and required strategies developed. |  |  |  |  |  |  |  |  |  |  |
| 2.1.1. | Activity 2.1.1 Assessment of the administrative structures and institutional capacities of the beneficiary and relevant stakeholders and improvement of their inter-institutional operation |  |  |  |  |  |  |  |  |  |  |
|  | 5 MS experts, 55WD/11 missions - Tallin: Ms. Slija Soon 10WD/2 missions, - Albacete: Ms. Consuelo Manchón García 15WD/3 missions, - Valencia: Mr. Juan Martín Garcia Alloza 10WD/2 missions, - Budapest: Mr Tamas Berky 15WD/3 missions, - Barcelona: Concepción PASCUAL LIZANA 5WD/1 mission, |  |  |  |  |  |  |  |  |  |  |
|  | Flat Daily Allowance |  |  |  |  |  |  |  | 19,250.00 € | 19,250.00 € |  |
|  | Twinning Project Support Cost |  |  |  |  |  |  |  | 26,180.00 € | 26,180.00 € |  |
|  | Compensation for Daily Subsistence |  |  |  |  |  |  |  | 13,068.00 € | 13,068.00 € |  |
|  | Travel Costs Valencia** |  |  |  |  |  |  |  | 616.00 € | 616.00 € |  |
|  | Travel Costs Barcelona** |  |  |  |  |  |  |  | 616.00 € | 616.00 € |  |
|  | Travel Costs Albacete (will be based on real costs) |  |  |  |  |  |  |  | 1,848.00 € | 1,848.00 € |  |
|  | Travel Costs Tallin*** |  |  |  |  |  |  |  | 798.00 € | 798.00 € |  |
|  | Travel Costs Budapest (will be based on real costs) |  |  |  |  |  |  |  | 1,500.00 € | 1,500.00 € |  |
|  | Translation |  |  |  |  |  |  |  | 0.00 € | 0.00 € |  |
|  | Flat Daily Allowance García | 09.12.2019-13.12.2019 | MC | 13/12/2019 | 350Eur x 5days |  |  | 1,750.00 € |  |  |  |
|  | Twinning Project Support Cost (García) | 09.12.2019-13.12.2019 |  |  | 1750*136% |  |  | 2,380.00 € |  |  |  |
|  | Compensation for Daily Subsistence García | 08.12.2019-14.12.2019 | MC | 13/12/2019 | 198Eur x 6nights |  |  | 1,188.00 € |  |  |  |
|  | Travel Costs (García) | 08.12.2019-14.12.2019 | MC | 13/12/2019 | Travel costs Albacete-Tbilisi-Albacete reimbursed at the real costs for economy treavel and flights: 331,11Eur Arrival: 08.12.2019, 05:25 Departure: 14.12.2019, 04:40 |  |  | 331.11 € |  |  |  |
|  | Flat Daily Allowance Alloza | 09.12.2019-13.12.2019 | MC | 13/12/2019 | 350Eur x 5days |  |  | 1,750.00 € |  |  |  |
|  | Twinning Project Support Cost (Alloza) | 09.12.2019-13.12.2019 |  |  | 1750*136% |  |  | 2,380.00 € |  |  |  |
|  | Compensation for Daily Subsistence Alloza | 08.12.2019-14.12.2019 | MC | 13/12/2019 | 198Eur x 6nights |  |  | 1,188.00 € |  |  |  |
|  | Travel Costs (Alloza) | 01.12.2019-14.12.2019 | MC | 13/12/2019 | Travel costs covered by Act 1.2.1 (02-06.12.2019) Arrival: 01.12.2019, 03:45 Departure: 14.12.2019, 04:40 |  |  | 0.00 € |  |  |  |
|  | Flat Daily Allowance Berky | 09.12.2019-13.12.2019 | MC | 13/12/2019 | 350Eur x 5days |  |  | 1,750.00 € |  |  |  |
|  | Twinning Project Support Cost (Berky) | 09.12.2019-13.12.2019 |  |  | 1750*136% |  |  | 2,380.00 € |  |  |  |
|  | Compensation for Daily Subsistence Berky | 08.12.2019-14.12.2019 | MC | 13/12/2019 | 198Eur x 6nights |  |  | 1,188.00 € |  |  |  |
|  | Travel Costs (Berky) | 08.12.2019-14.12.2019 | MC | 13/12/2019 | Travel costs Budapest-Tbilisi-Budapest reimbursed at the real costs for economy treavel and flights: 321,00Eur Arrival: 08.12.2019, 05:25+1 Departure: 14.12.2019, 04:40 |  |  | 321.00 € |  |  |  |
|  | Total cost ACT 2.1.1. |  |  |  |  |  |  | 16,606.11 € | 63,876.00 € | 63,876.00 € | 0.00 € |
| 2.2. | Sub-Result 2.2: Implementation of the EU best practices regarding the amended legislation piloted and awareness of the citizens and private sector on the topic increased. |  |  |  |  |  |  |  |  |  |  |
| 2.2.2. | Activity 2.2.2 Preparing and implementing public information campaign aiming to raise awareness among the project among key stakeholders, public, private sector and civil society |  |  |  |  |  |  |  |  |  |  |
|  | 3 MS experts, 60 WD/12 missions - Bratislava: Ms. Luba Pavlovova 20 WD/4 missions, - Madrid: Ms. Maria Mercedes Tejedor Aibar 20 WD/4 missions, Ms. Marta Zimmerman Verdejo 20 WD/4 missions, |  |  |  |  |  |  |  |  |  |  |
|  | Flat Daily Allowance |  |  |  |  |  |  |  | 21,000.00 € | 21,000.00 € |  |
|  | Twinning Project Support Cost |  |  |  |  |  |  |  | 28,560.00 € | 28,560.00 € |  |
|  | Compensation for Daily Subsistence |  |  |  |  |  |  |  | 14,256.00 € | 14,256.00 € |  |
|  | Travel Costs Bratislava |  |  |  |  |  |  |  | 1,828.00 € | 1,828.00 € |  |
|  | Travel Costs Madrid |  |  |  |  |  |  |  | 4,520.00 € | 4,520.00 € |  |
|  | TV, radio broadcasting |  |  |  |  |  |  |  | 4,500.00 € | 4,500.00 € |  |
|  | Translation |  |  |  |  |  |  |  | 0.00 € | 0.00 € |  |
|  | Flat Daily Allowance Pavlovova | 09.12.2019-13.12.2019 | MC | 13/12/2019 | 350Eur x 5days |  |  | 1,750.00 € |  |  |  |
|  | Twinning Project Support Cost (Pavlovova) | 09.12.2019-13.12.2019 |  |  | 1750*136% |  |  | 2,380.00 € |  |  |  |
|  | Compensation for Daily Subsistence Pavlovova | 08.12.2019-14.12.2019 | MC | 13/12/2019 | 198Eur x 6nights |  |  | 1,188.00 € |  |  |  |
|  | Travel Costs (Pavlovova) | 08.12.2019-17.12.2019 | MC | 13/12/2019 | Flat rate Bratislava-Tbilisi-Bratislava reimbursed at unit cost for travel fixed in the contract: 457,00Eur Arrival: 08.12.2019, 05:25 Departure: 17.12.2019, 12:05 |  |  | 457.00 € |  |  |  |
|  | Total cost ACT 2.2.2. |  |  |  |  |  |  | 5,775.00 € | 74,664.00 € | 74,664.00 € | 0.00 € |
|  | SUB-TOTAL |  |  |  |  |  |  | 127,086.82 € | 682,360.50 € | 682,360.50 € | 108.50 € |
| IV. | IV. Direct Costs Overall Amount Reserve Funds |  |  |  |  |  |  | 127,086.82 € |  |  |  |
| V. | V. Reserves |  |  |  |  |  |  | 108.50 € |  |  |  |
| VI. | VI. Provision for Indirect Costs |  |  |  |  |  |  | 7,625.21 € |  |  |  |
|  | TOTAL COSTS |  |  |  |  |  |  | 134,820.53 € |  |  |  |

It should be noted that the Member State and Beneficiary country Project Leaders in their own right could agree not to deliver an extensive narrative report to the Steering Committee every quarter but only bi-annually.

Donors and other organisations who attended the meeting: EU (TWP), ILO, GIZ, UN Women, UNDP, IOM, WB, IMPAQ INTERNATIONAL, LLC

Directive 2002/14/EC of the European Parliament and of the Council of 11 March 2002 establishing a general framework for informing and consulting employees in the European Community - Joint declaration of the European Parliament, the Council and the Commission on employee presentation.

‘collective redundancies' means dismissals effected by an employer for one or more reasons not related to the individual workers concerned where, the number of redundancies is:

- at least 10 in establishments normally employing more than 20 and less than 100 workers;

- at least 10 % of the number of workers in establishments normally employing at least 100 but less than 300

workers;

- at least 30 in establishments normally employing 300 workers or more.

Project named: Producing information campaigns to rise awareness about labour safety law in Georgia