## ANNEX C4: Twinning interim quarterly report

EUROPEAN COMMISSION

TWINNING PROJECTS

INTERIM QUARTERLY REPORT

TWINNING INTERIM QUARTERLY REPORT number:2

Project Title: “Improving the standards of employment conditions/relations as well as health and safety at work in Georgia “

Partners:     Lead Partner:
Ministry of Labour, Social Affairs and Family of the Slovak Republic 
(MoLSAF SR)

Junior Partner:
Ministry of Labour, Migrations and Social Security (MITRAMISS).Labour and Social    Security Inspectorate of State Agency

Ministry of Social Affairs of the Republic of Estonia

Back stopping body:
Regional Development Agency SP, Slovak Republic (RDA)

FIIAPP F.S.P. (Fundación Internacional y para Iberoamerica de Admisnistración    y

Polítocas Públicas

Beneficiary Country
                      Ministry of Internally Displaced Persons from the Occupied Territories,

Labour, Health and Social Affairs of Georgia, (MoIDPLHSA) , Labour

Conditions Inspecting Department

Date:         May 6th, 2020

Twinning Grant Contract number: 	ENI/2019/409-668

1.	Overview

The Interim Quarterly Report/Final Report for the project comprises the following parts:

Section 0	Executive summary listing decisions needed to be taken by the Project Steering Committee

Section 1	Basic data on the project

Section 2	Content: progress achieved in the implementation of the Twinning project during the reporting period and schedule for the remaining period

Section 3	Expenditure: actual expenditure in relation to budgeted expenditure

2.

Twinning Grant Contract number: ENI/2019/409-668  GE - 17 - ENI - OT – 02 19

Section 0

Executive summary

Information provided in this Interim Quarterly Report covers the period from 7th January, 2020 – 6th April, 2020.

Since 7th January 2020, part of activities was implemented smoothly as scheduled in the work plan, however, the implementation of some activities was postponed or didn’t started yet due to 3 reasons: a) delay in hiring new labour inspectors: Act. 2.1.4. Delivery of a comprehensive training program to improve the institutional capacities of the beneficiary and relevant stakeholders was planned to be implemented since February, 2020. If hiring of new Labour Inspectors will be completed in May – June the Induction training might start accordingly.

b) outbreak of COVID - 19 and restrictive measures taken: Act. 1.3.1. Aligning Georgian legal framework on Occupational Health and Safety including aspects of Labour Inspection System, in order to amend it in compliance with the EU aquis was planned to be implemented by 3 experts during the period of 16 – 20/03/2020, but due to a COVID – 19 restrictive measures mission was cancelled. Act. 2.1.4 – Refresher training for senior labour Inspectors was planned to be implemented by 2 experts since 9 – 13/03/2020, but due to a restrictive measures a mission was postponed.

c) common agreement of postponement of activity: Act. 2.1.3. Delivery of Training of Trainers of the labour Inspectors. Activity was postponed due to a common agreement between TW, ILO and beneficiary.  Based on the common agreement the ILO will proceed with their training modules and the TW project will complement the ToT with very targeted and field training. Provisional date to be scheduled – September 2020.

On 31st January, 2020 the Amendment No.1 to the Twinning Contract was in forced. The subject of the amendment was to change the originally established unit cost 399.00 EUR for Estonia (Tallinn) at 450.00 EUR,  unit cost per return trip for Madrid-Tbilisi-Madrid was fixed in the amount of 565,- EUR (as an average of three offers) and other destinations in Spain and all other destinations unforeseen before signing of the contract  will be charged on the real costs.

During the second reporting period a level of mutual understanding and of a different approaches of  OSH policies/strategies implementation was recognised and different best practise were  exchanged. In both components the analytical and assessment documents were completed or almost completed (1.1.1. and 2.1.1; 2.1.2.)

In component 1 the assistance of experts was focused on consultation, advise and assessment of the amendments of the Labour Code with the labour EU acquis. There is significant progress with the approximation of all “labour and anti-discrimination” directives into the LCG and other regulations. The Georgian legislator has a deep knowledge of the European Union law and tried to incorporate basics of EU law into a national legislation (in lots of cases almost verbatim). There are elements of each of the relevant directives in LCG. That means that the legislator tried to transpose all of directives. In some cases, the approximation of EU law is not completed. There are some gaps, some parts of draft LCG create a certain unclarity but that is not atypical for non-member states because they are not accustomed to daily function and details of EU law. In some cases, lack of approximation of EU law into national law can be more the matter of current state of Georgian budget (see payment of allowance in case of maternity) or the reality of labour market than the willingness to follow rules of EU law (even if Georgian MoIDPLHSA made the considerable effort to follow a minimal requirements). It has to be taken into account that for further progress, at first Georgian stakeholders have to accept a current changes in draft LCG and then it is possible to achieve further progress. E.g. the concept of transfer of undertaking can be rather marginal and “academical” problem in Georgia where there are much more important issues at labour market connected with protecting the basic rights at work – nevertheless Georgia transposed that regulation in draft LCG. But it will take time to implement it in practise irrespective of perfect or non-perfect transposition of directive. After “acceptation” of this EU concept to be part of Georgian law the regulation can be further improved.

However, the progress in draft of LCG has to be seen as very positive development for the present as well as for the future development of labour relations. Further recommendations are part of the assessment.

In component 2 the basic analytical reports were completed: Functional Review, Training needs analysis, Training programs designed. Evaluation of 3 types of questionnaires: employees, private  and public employers will be  evaluated in a next reporting period.

It is important to note that the complete area of occupational medicine needs to be rebuilt again in order to provide for a regular and obligatory medical check-up, medical suitability assessment, capacity to examine possible cases of occupational origin and assist employers in the preparation of risks assessments and planning of workplaces with regard to specific aspects (such as handling of toxically components or ergonomics). It was raised that the Institute would welcome further assistance in the framework of the current project and in future Twining projects.

Due to the outbreak of COVID – 19 and restrictive measures taken the TW team: RTA and 2 assistants based on the consent with the EUD and Beneficiary are teleworking from home since 16 March, 2020.

During the period of 16 March to the end of reporting period no activities were implemented. TW team and the beneficiary have agreed on the plan and the manner of the implementation of activities in the period of May – July, 2020.

In total 14 experts have participated in 10 missions and 94 working days (out of 405) were spent. The reasons of relatively low spending of working days is explained above.

The list of the outputs delivered during the reporting period is attached.

2. List decisions needed to be taken by the Steering Committee

- Updated Logical Framework Matrix

- 2nd Interim Quarterly Report

- 2nd Rolling Workplan

Section 1:

Project data

| Twinning Grant Contract Number | ENI/2019/409-668 |
| --- | --- |
| Project Title: | Improving the standards of employment conditions/relations as well as health and safety at work in Georgia |
| Twinning Partners (Member State(s) and Beneficiary) | Lead Partner: Ministry of Labour, Social Affairs and Family of the Slovak Republic (MoLSAF SR) Junior Partner: Ministry of Labour, Migrations and Social Security (MITRAMISS).Labour and Social Security Inspectorate of State Agency Ministry of Social Affairs of the Republic of Estonia Back stopping body: Regional Development Agency SP, Slovak Republic (RDA) FIIAPP F.S.P. (Fundación Internacional y para Iberoamerica de Admisnistración y Polítocas Públicas Beneficiary Country Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia, (MoIDPLHSA) , Labour Conditions Inspecting Department |
| Report Number: | 2 |
| Period covered by the report: | 7th January, 2020 – 6th April, 2020 |
| Duration of the project: | 24 months |
| Reported by: | Branislav Ondrus, MS PL Tamila Barkalaia, BC PL Jose Ignacio Fernandez Martin, JPL Ulla Saar, JPL Valeria Kubalova, RTA Beka Peradze, RTA Counterpart |

Section 2:

Content

2A – BACKGROUND

2B – ACHIEVEMENT OF MANDATORY RESULTS/OUTPUTS

2C – ACTIVITIES IN THE REPORTING PERIOD

2D – TIMING AND DELAYS

2E – ASSESSMENT

2A - BACKGROUND

Overall objectives

| Overall Objective and indicators of achievement (as in Log frame) | State of achievement/ problems encountered |
| --- | --- |
| The overall objective of the project is to support higher standards in employment relationship and working conditions in Georgia through improving legal framework and enforcing implementation. |  |
| - employment relations and health and safety standards at work for Georgian employees and enterprises - number of facilities implementing preventive measures to create safe and healthy working conditions Baseline: 708 Target: 1 050 - Number of employees effected by implemented OSH preventive measures increased Baseline: 210 390 Target: 300 000 | The state of achievement is in line with the implementation of the Initial Work Plan – activities have started during the reporting period without significant results to be compared. The state of achievement is in line with the implementation of the Initial Work Plan – activities have started during the reporting period without significant results to be compared. The state of achievement is in line with the implementation of the Initial Work Plan – activities have started during the reporting period without significant results to be compared. |

Specific Objectives

| Specific Objectives and indicators of achievement (as in Log frame) | State of achievement/ problems encountered |
| --- | --- |
| To assist the MoIDPLHSA, together with other relevant stakeholders, to draft the legal and administrative provisions and establish the institutional mechanisms to improve employment conditions/ relations and Occupational Safety and Health, including a labour inspection system. Additionally, to strengthen the capacity of the national institutions to implement and adopt the best European practices. |  |
| - Degree of compliance of the relevant Georgian legislation with the Union acquis increased - Legal and administrative procedures, and institutional mechanisms for improved employment relations and health and safety standards at work are in place and operational. | The state of achievement is in line with the implementation of the Initial Work Plan – activities just have started during the reporting period without significant results to be compared. The state of achievement is in line with the implementation of the Initial Work Plan – activities just have started during the reporting period without significant results to be compared. |

Policy and sector Developments

Recent development in the legal framework

During the reporting period, the MoIDPLHSA was very active and fully involved in further approximation of the Union acquis included in the EU-Georgia Association Agreement in the field of labour law, anti-discrimination and gender equality as well as health and safety at work. Newly adopted the  Organic Law of Georgia on Occupational Health and Safety has created the conditions based on which the country took responsibility to transform the Labour Conditions Inspection Department of the Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia into the Legal Entity under Public Law and specify the regulatory framework for the activities  the newly created legal entity should perform.

In March, 2020 the legislative package (amendments of the Labour Code, Draft Labour Inspection Law and other amendments to the related laws) prepared by the Parliament was finalised and a commenting process was opened before submission to the further legislative procedure.

Furthermore, during the reporting period the following ordinances/orders were developed and approved by the Government/Minister of MoIDPLHSA:

- February 6, 2020, Ordinance of the Government of Georgia №80, On approval of methods for determination of priority branches of economic activity and rule for risk assessment

- February 10, 2020, Ordinance of the Government of Georgia №99, On approval of the rules and conditions to enter and inspect the workplace liable to inspection

- January 30, 2020, Order of the Minister of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs Of Georgia №01-15/ნ, Amended on February 18, 2020 Order №01-21/ნ, On approval of the rule for risk assessment in the working area

- February 14, 2020, Order of the Minister of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs Of Georgia №01-20/ნ, On approval of jobs containing substantial risk and/or threat to the health of pregnant workers, workers who have recently given birth or who are breastfeeding

Project Assumptions

All assumptions as specified in the Logframe related to Mandatory results were achieved during the previous reporting period.

Description of the actions/activities which contributed to fulfilment of the assumptions and influenced a smooth implementation of the project:

- Since 7th January 2020, part of activities was implemented smoothly as scheduled in the work plan, however, the implementation of some activities was postponed or didn’t started yet due to 3 reasons:

- a) delay in hiring new labour inspectors: Act. 2.1.4. Delivery of a comprehensive training program to improve the institutional capacities of the beneficiary and relevant stakeholders was planned to be implemented since February, 2020. If hiring of new Labour Inspectors will be completed in May – June the Induction training might start accordingly.

- b) outbreak of COVID - 19 and restrictive measures taken: Act. 1.3.1. Aligning Georgian legal framework on Occupational Health and Safety including aspects of Labour Inspection System, in order to amend it in compliance with the EU aquis was planned to be implemented by 3 experts during the period of 16 – 20/03/2020, but due to a COVID – 19 restrictive measures mission was cancelled. Act. 2.1.4 – Refresher training for senior labour Inspectors was planned to be implemented by 2 experts since 9 – 13/03/2020, but due to a restrictive measure a mission was postponed.

- c) common agreement of postponement of activity: Act. 2.1.3. Delivery of Training of Trainers of the labour Inspectors. Activity was postponed due to a common agreement between TW, ILO and beneficiary.  Based on the common agreement the ILO will proceed with their training modules and the TW project will complement the ToT with very targeted and field training. Provisional date to be scheduled – September 2020.

- Since 7th January, 2020 in total 14 experts have participated in 10 missions and 94 working days (out of 405) were spent.

- On 31st January 2020 the Amendment No.1 to the Twinning Contract was in forced. The subject of the amendment was to change the originally established unit cost 399.00 EUR for Estonia (Tallinn) at 450.00 EUR,  unit cost per return trip for Madrid-Tbilisi-Madrid was fixed in the amount of 565,- EUR (as an average of three offers) and other destinations in Spain and all other destinations unforeseen before signing of the contract  will be charged on the real costs.

- In January, 2020 the Campaign Focus Group (CFG) and Campaign Organisational Board (COB)  were established composing the experts of TW and ILO project, LCID representatives and social partners focused on common preparation and implementation of a public information campaign aiming to raise awareness of the OSH culture among key stakeholders, public, private sector and civil society. During the reporting period very good cooperation, committed working and creative atmosphere was created during all meetings of the CFG and COB which contributed to the development of many outputs delivered for the Campaign which will start on 28th April, 2020, the World OSH Day. Training of the LCID staff to be dealt with preparation and implementation of the campaign has increased the professional capacity of the LCID staff and has contributed to a very valuable approach in designing the campaign.

- In order to gain a better understanding of occupational safety and health (OSH) awareness among employees (workers) in Georgia in relation to the new changes/amendments of the OSH legal rules and identify the best ways and tools to be used for increasing awareness of and information to be provided to all employees (workers) in Georgia, in both – private and public sector 3 questionnaires were developed and disseminated via channels of the social partners. Despite the involvement of the whole spectrum of the social partners only 628 responses were returned. The evaluation of all questionnaires will be processed in May, 2020.

- In response to the outbreak of COVID-19 worldwide, restrictive measures have been put in place both by the Georgian Government and by the respective EU Member State(s) (Slovakia, Estonia, Spain). Due to the restrictions mentioned above, the Resident Twinning Adviser (RTA) was authorised to telework from outside Georgia and both RTA assistants support the implementation  of the project. Since 16 th March to the end of reporting period no activities were implemented.

2B - ACHIEVEMENT OF MANDATORY RESULTS/OUTPUTS

Results under components:

| Results and indicators of achievement (as in Log frame) |  | State of achievement/ problems encountered |
| --- | --- | --- |
| Result 1 Approximation of primary and secondary legislation related to labour law, gender equality and OSH in accordance with the Union acquis |  |  |
| Sub-result 1.1. Legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis |  |  |
| - Number of the Tables of Concordance prepared for the Labour Law acquis, including aspects of labour inspection system Baseline: 7 Target: 8 Directives - List of amendments to be made in the Georgian primary and secondary labour legislation specified with explanatory notes Baseline: 3 Target: 8 Directives |  | - 1 Table of Concordance of the Council Directive 91/383/EEC of 25 June 1991 supplementing the measures to encourage improvements in the safety and health at work of workers with a fixed- duration employment relationship or a temporary employment relationship was developed and completed. - 3rd version of the Compliance Report of Amendments to the draft Organic Law of Georgia the Labour Code with 8 Directives in the field of the Labour Law was prepared during the reporting period. First 2 versions were submitted to the BA as well as to the representatives of the Parliament, the initiators of the amendments. Both reports have included main findings, recommendations for the amendments, good practise and the recent CJEU law. |
| Sub-result 1.2: Legal framework on non-discrimination and gender equality, including aspects of labour inspection system, amended in compliance with the Union acquis |  |  |
| - List of amendments to be made in the Georgian primary and secondary legislation on Gender Equality acquis specified with explanatory notes Baseline: 4 Target: 2 Directives - Share of staff from relevant public institutions who are fully informed on regulatory and fiscal impact of changes in labour law and gender equality acquis Baseline: 0 Target: 90% of staff in LCID and LEPD | - The state of achievement is in line with implementation of the work plan – 2 missions were conducted focused on discussion of the Council Directive 2004/113/EC implementing the principle of equal treatment between men and women in the access to and supply of goods and services and Council Directive 79/7/EEC on the progressive implementation of the principle of equal treatment for men and women in matters of social security. - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. |  |
| Sub-result 1.3: Legal framework on OSH, including aspects of labour inspection system, amended in compliance with the Union acquis |  |  |
| - Availability of quality checked translation of the OSH acquis with clear technical terminology (if necessary) Baseline: 9 Target: 15 Directives - Availability of the Tables of Concordance prepared for the OSH acquis, including aspects of labour inspection system Baseline: 5 Target: 15 Directives - Availability of the list of amendments to be made in the Georgian primary and secondary OSH legislation specified with explanatory notes Baseline: 2 Target: 15 Directives - Share of staff from relevant public institutions who are fully informed on regulatory and fiscal impact of changes in OSH acquis Baseline: 0 Target: 90% of staff in LCID and LEPD | - Quality of Directive 89/656/EEC on minimum safety and health requirements for the use of personal protective equipment was checked and improved - Quality of Directive 92/58/EEC on minimum requirements for the provision of safety and health and/or health sign at work was checked and improved - Activities to contribute to fulfilment of the Indicator were not planned during this reporting period. - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. |  |

| Result 2 Capacity building, inter-institutional cooperation, and awareness raising of relevant state authorities and private sector for full implementation of amended legislation in labour law, gender equality and OSH |  |
| --- | --- |
| Sub-result 2.1: Analysis for strengthening state authorities’ capacity for implementation of the EU best practices performed and required strategies developed |  |
| - Functional review of the relevant state authorities to implement changes, including human and financial resources, administrative structures and equipment needed Baseline: 0 Target: 1 - Training needs analysis and plan of the whole staff of beneficiary department and representatives from other relevant institutions listed Baseline: 0 Target: 1 - Share of BA staff who received training to implement necessary changes and the representatives from other relevant institutions listed Baseline: 10% Target: 90% of staff in BA and others - Number of labour inspectors who are trained more to become ‘trainers’ with full knowledge and competency in implementing new laws Baseline: 0 Target: 5 | - During the reporting period 2 missions focused on the development of the functional review were conducted, detailed mapping and assessment of the interinstitutional relationships between the various state and non-governmental actors dealing with the occupational health and labour relations were conducted. Functional review will be completed in the next reporting period. - Evaluation of the TNA analysis was completed including the design of the training. - Delivery of targeted training for newly hired inspectors have been postponed due to a delay in the recruitment process - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. |
| Sub-result 2.2: Implementation of the EU best practices regarding the amended legislation piloted and awareness of the citizens and private sector on the topic increased |  |
| - Number of written operational guidelines, manuals and procedures required to implement all changes, explaining all steps of implementation to the relevant staff Baseline: 0 Target: At least 15 documents - Number of OSH online Glossary and Risk Assessment checklists and their dissemination to relevant parties Baseline: 0 Target: At least 20 - Number of elaborated promotional materials and public information campaigns in printed and online media, TV and other tools Baseline: 5 Target: 20 short written materials + 2 public campaigns - Share of private companies (i.e. both employers and workers) which are informed and number of citizens reached out on the new rules and changes made in labour legislation Baseline: 50 Target: 90% of registered companies | - The state of achievement is in line with the implementation of the Initial Work Plan – activities just have started during the reporting period without significant results to be compared. - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. - The state of achievement is in line with the implementation of the Initial Work Plan – activities just have started during the reporting period. Public awareness campaign is under preparation including other communication tools. - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. |
| Sub-result 2.3: Organisation of working group(s) on labour law, gender equality and OSH comprising line ministries and social partners completed and functional |  |
| - Proposal for a structure of inter-institutional cooperation and working procedures, with a review of existing options Baseline: 0 Target: 1 - Working groups operational with team members from relevant institutions with a clear mandate and their continuous involvement in the ‘Technical Working Group’ and ‘Coordination Group’ Baseline: 0 Target: 2 - Number of meetings facilitated for effective functioning of working groups through team building, training and expert inputs Baseline: 0 Target: at least 4 meetings a year | - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. - Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. |

2C - ACTIVITIES IN THE REPORTING PERIOD

| Component 1 Approximation of primary and secondary legislation related to Labour Law, Gender Equality, and Occupational Safety and Health in accordance with the Union acquis |  |  |
| --- | --- | --- |
| Ref. number | Title of activity/State of play/Name of involved MS Experts | Duration of the activity |
| Activity 1.1.1: | Aligning Georgian legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis | October 2019 – April 2020 |
|  | State of play: 1 mission was carried out during the reporting period as follows: 1st mission 17/02 – 21/02/2020 Jozef Toman (5 WD) was focused on: - Providing advice and consultancy in course of amendment of Georgian Labour Code – Council Directive 1999/70/EC, 2003/88/EC, 92/85/EEC - Clarification and discussion with BC representatives on specific problems concerning fixed-term contract, maternity leave, working time and overtime. The presentation of best practises by using Slovak and others experiences. - Finalization of the Assessment on compliance of the draft Labour Code of Georgia with 8 EC Directives related to the labour law Output - Assessment on compliance of the draft Labour Code of Georgia with 8 EC Directives related to the labour law including the selected Case Law of CJ EU to each of selected Directives | 1st mission: 04/11/2019 – 08/11/2019 |
| Number of experts from BA experts/dpt. | - 4 BA experts in total - Ms Lika KLIMIASHVILI, Head of the Labour Relations and Social Partnership Division, MoIDPLHSA - Ms Irma Gelashvili, Head of the Labour Relations and Social Partnership Division, MoIDPLHSA - Ms Shorena KUBANEISHVILI, Labour Conditions Inspecting Department - Nino Gvetadze, Social Protection Policy Division |  |
| Ref. number | Title of activity/State of play/Name of involved MS Experts | Duration of the activity |
| Act.1.2.1. | Analysis / Assessment of current legal framework on non-discrimination and gender equality including aspects of Labour Inspection System, in order to amend it in compliance with the EU aquis | December 2019 – April 2020 |
|  | State of play: 1 mission was carried out during the reporting period as follows: 1st mission 24 -28/02/2020 Mr Jose Ignacio Martin Fernandez (5 WD) Mission was focused on further assessment of the 2 directives: - 2004/113/EC implementing the principle of equal treatment between men and women in the access to and supply of goods and services - 79/7/EEC on the progressive implementation of the principle of equal treatment for men and women in matters of social security State of Play Mission was focused on assessment of the relevant Georgian laws and its alignment to the EU acquis. During a mission a desk research for both directives was conducted. Moreover, the presence of expert was used by the LCID staff and additional consultation, advise and clarification was provided by expert mostly to the accreditation process of the OSH Specialists. ToC will be completed in the next reporting period. | 1st mission 24 -28/02/2020 |
| Number of experts from BA experts/dpt. | - 4 BA experts in total - Ms Lika KLIMIASHVILI, Head of the Labour Relations and Social Partnership Division, MoIDPLHSA - Ms Irma Gelashvili, Head of the Labour Relations and Social Partnership Division, MoIDPLHSA - Ms Shorena KUBANEISHVILI, Labour Conditions Inspecting Department - Nino Gvetadze, Social Protection Policy Division - Mr Beka PERADZE, Head of Labour Conditions Inspecting Department, MoIDPLHSA - Mr Levan ABASHIDZE, Head of Monitoring and Supervision Division of the Labour Conditions Inspection Department (LCID). |  |

| Component 2: Capacity building, inter-institutional cooperation, and awareness raising of relevant state authorities and private sector for full implementation of amended legislation in labour law, gender equality and OSH |  |  |
| --- | --- | --- |
| Ref. number | Title of activity/State of play/Name of involved MS Experts | Duration of the activity |
| Act. 2.1.1. | Assessment of the administrative structures and institutional capacities of the beneficiary and relevant stakeholders and improvement of their inter-institutional operation | December 2019 – March 2020 |
|  | State of play: 2 missions were carried out during the reporting period as follows: 1st mission 20 -24/01/2020 Ms Consuelo Manchon Garcia (5 WD), Mr Tamas Berky (5WD ), Ms Silja Soon (5WD ), was focused on: - This mission consisted of work on the draft of the functional review report in the structure elaborated during the previous mission and conducting further interviews and data collection to understand the interinstitutional relationship in specific aspects of OSH and labour inspection. - Furthermore, on the occasion of the mission Member State experts shared their experiences on the planning of OSH and labour inspections, as well as participated in expert discussions including the head of department and the representative of the ILO with the aim of better coordinating the various efforts to improve labour inspection in Georgia. Key findings The key findings of the interviews are summarized as follows: Technical and Construction Supervision Agency - The agency conducts regular inspection to investigate whether the different economic operators have observed their legal duties in terms of obtaining the necessary product / equipment compliance certificates and re-certificates. In case of non compliance, the agency can impose a fine, suspend works / operation and call for the establishment of the lawful situation. - The Agency is able and cooperates with LCID occasionally in the inspection of worksites should a doubt emerge during the inspection of the LCID. It has been observed however, that the procedure of possible joint inspections, the involvement of TCSA in the examination of OSH cases, and specifically, the involvement of the accredited agencies in such case specific examinations can be better regulated (at a guidance, agreement level only) and arranged. - The Tbilisi Municipality has an inspection department, in which there is a specific unit for construction inspection, with around 70 inspectors. The inspection department obtains the information regarding the start and duration of works based on the building permits and the notification mentioned above (however, it is not automatically provided for them). - The construction inspectors inspect the worksites on a regular basis, which can even be a daily one. - The basis of their inspection is the regulation regulating working at height (decree 477.), and the scope of inspection is the observation of the technical criteria as laid down by that regulation, which includes safety measures. - However, the inspectors do not investigate other OSH related aspects as defined in the organic law on OSH, such as for instance the existence of safety plan (other than the one submitted as part of the construction plan), the OSH training of workers or employment matters. - This is the reason why they conduct joint visits with LCID, whereby the municipality inspectors limit the scope of their activity to decree 477., whereas LCID inspectors focus on OSH and employment matters. There have been joint inspection “campaigns”, however, the joint planning of such visits, the selection of sites specifically for OSH inspection is not clearly laid down. Georgian Association of Employers - In the opinion of the Association, last year’s courses provided an easy access for many participants to a certificate in OSH. The result of this is that the level of service provided by such people either as employed OSH coodinators or external consultants, cannot ensure an adequate level of OSH at an implementation level at worksites. For this reason, they consider it essential to revise the system of both training accreditation and the issuance of professional certificates and introduce deeper level of OSH training or education in addition to shorther continuous professional development courses. - With regard to attitude towards OSH at employers, their view is that OSH is not yet regarded as an asset in the company, rather than as a cost, and the propensity to develop their OSH system is motivated by the state sanctioning mechanisms only, thus the actual application depends on the effectiveness of such a sanctioning mechanism. Makhviladze Research Institute of Labour Medicine and Ecology - The current state of occupational medicine in Georgia is precarious and lacks the capacities to effectively assist in health service provision and ensuring an adequate level of occupational health at workplace level. - Employres at present are not obliged to employ/contract an occupational health service, carry out regular checkups, elaborate workplace health programme, report occupational health diseases and retain related documentation. There is no specific occupational health service which could examine specific cases and establish whether they are of occupational origin, and the absence of related documentation also prevents the proper function of such service, should it exist. Diseases which emerge as a result of occupational factors are diagnosed by non-occupational medical staff and as such their possible occupational origin is not documented. - As regards training, it has become clear that the undifferentiated provision of trainings to a high number of OSH specialist compromised the quality level of training. Possible direction we see in this area are: - Differentiate between different types of OSH / employment relations trainings. It is suggested that employee OSH representatives, enterprise level OSH responsible, and OSH technicians and engineers are trained through separate schemes, complemented by risk and industry specific trainings. - It can also be considered that private agencies could only provide basic OSH training and certificate for employee representatives and enterprise level OSH responsible, but OSH technicians and engineers could be trained separately and at higher level courses, as well as tested by an independent organisation or by a university. - The Ministry of Economy operates an adult education accreditation scheme. Requiring that training courses are accredited under this scheme would probably ensure that the compliance of such courses are inspected through such an adult education accreditation scheme, thereby providing the necessary quality for the training. The MOLHSA could cooperate with the ministry of economy in terms of the content wise accreditation of providers and their programmes. Also, it can be considered whether certain OSH training (e.g. OSH technician) is provided as vocational education course or as higher education course. - As regards the area of occupational medicine, we consider it a critical issue that occupational health is not provided as a regular service at employers, the capacities of the national institute are limited, there is no occupational medicine specialist training at present, no regular medical check-ups and suitability assessments. We consider it important to develop the field both in terms of obligatory requirements in terms of occupational health and providing for the training and material resources for the service. Also, the involvement of the national institute as part of regular procedures in the examination of OSH cases and in subject matter training of both inspectors and OSH specialists would have an added value. Recommendations: - It is important to note that the complete area of occupational medicine needs to be rebuilt again in order to provide for a regular and obligatory medical check-up, medical suitability assessment, capacity to examine possible cases of occupational origin and assist employers in the preparation of risks assessments and planning of workplaces with regard to specific aspects (such as handling of toxically components or ergonomics). It was raised that the Institute would welcome further assistance in the framework of the current project and in future Twining projects. 2nd mission 09 -13/03/2020 Mr Tamas Berky (5WD) was focused on: - Completing the overview of the legal and regulatory framework, with regard to the treatment of workplace safety, health and labour relations in other pieces of legislation than the organic law on OSH, as well as clarifying the application of ILO guidelines, and operational templates. - Assessing the relationship between Public Administration Reform (PAR) and the development of the area of OSH and labour relations, with specific regard to policy planning, regulatory impact assessment and monitoring and evaluation - Assessing the perspectives of regionalisation and decentralisation, as well as possible ovrelaps and synergies between local authorities and the central inspectorate - Assessing the treatment of gender equality in inspecting labour relations Recommendations: - Regionalisation is only a planned direction of institutional development, for which purpose we elaborated certain recommendations. It was also found that certain areas of the institutional development of labour inspection can be better aligned with central government actions foreseen in the PAR action plan for 2019 and 2020 | 1st mission 20 -24/01/2020 2nd mission 09 -13/03/2020 |
| Number of experts from BA experts/dpt. | - 24 BA experts in total - Ms Shorena KUBANEISHVILI, Labour Conditions Inspecting Department - Badri Ugulava, LCID - Mikheil Imerlishvili, LCID - Monika Chania, LCID - 10 staff of the Makhviladze Research Institute of Labour Medicine and Ecology - 5 staff of the Tbilisi municipality - 3 staff of the Technical and Construction Supervision Agency - 2 staff of the Georgian Association of Employers |  |
| Ref. number | Title of activity/State of play/Name of involved MS Experts | Duration of the activity |
| Activity 2.1.2. | Training needs analysis and strengthening the institutional capacity of the beneficiary and relevant stakeholders |  |
|  | State of play: 1 mission was carried out during the reporting period as follows: 1st mission 10 - 14/02/2020 Ms Consuelo Manchon Garcia (5 WD), Mr Tamas Berky (5WD ), 11 – 14/02/2020 Ms Silja Soon (4WD ) was focused on: Training needs analysis which was focused on the development of the most important The aim of this training needs analysis (hereinafter: TNA) is to analyse the training needs and to propose a training plan covering the needs of beneficiary staff as well as representatives of the relevant institutions to contribute to the full implementation and enforcement of the new regulatory labour framework. Based on completed answers of the questionnaire the Training needs analysis was completed including the design of Induction training program for newly hired Labour Inspectors and refresher training program for senior inspectors. Outputs: - Training needs Analysis of the Labour Conditions Inspecting Department including design of training program for both groups | 1st mission 10 - 14/02/2020 |
| Number of experts from BA experts/dpt. | - 4 BA experts in total - Ms Shorena KUBANEISHVILI, Labour Conditions Inspecting Department - Badri Ugulava, LCID - Mikheil Imerlishvili, LCID - Monika Chania, LCID |  |
| Ref. number | Title of activity/State of play/Name of involved MS Experts | Duration of the activity |
| Activity 2.1.4. | Delivery of comprehensive training programmes to improve the institutional capacities of the beneficiary and relevant stakeholders | February 2020 |
|  | State of Play 1 mission was carried out during the reporting period as follows: Ms Consuelo Manchon Garcia 09 -13/03/2020 (5WD) was focused on: - Originally, the mission was focused on delivery of training on Labour Inspection performance in relation to OSH enforcement. However, due to already taken restrictive measures (STE from Spain and has travelled with a STE from Hungary who had a fever) both experts were isolated in the hotel and the training was cancelled - Ms Consuelo Manchon Garcia worked from hotel on development of an appropriate specific Training Programme covering new adopted legislation, daily work method as regards the approximation agenda and inspection working methods. The training programme is based in the previous training needs analysis. Outputs - Design proposal for senior LI training - Theoretical and practical content of the training on LI performance on OSH including PPT | 09-13/03/2020 |
| Number of experts from BA experts/dpt. | No BA experts were involved due to restrictive measures |  |
| Ref. number | Title of activity/State of play/Name of involved MS Experts | Duration of the activity |
| Activity 2.2.1. | Development of the relevant guidelines, labour inspection manuals, checklists and other tools to improve the institutional operations and procedures focused on precise implementation of newly adopted legislation | April 2020 – May 2020 |
|  | State of Play 1 mission was carried out during the reporting period as follows: Mr Zdravko Muratti 7 – 31/01/2010 (5 WD) was focused on: - Proposing measures how to improve the quality of Accredited Training Programme for the OSH Specialists - The Minister’s Order “The Certified Occupational health and safety Specialist Program” dealing with the duration, procedures and conditions for the implementation of Accredited Occupational health and safety Specialist Program has been studied and discussed with the representatives of the LCID Findings and recommendations: - Several options to classify the different levels of OSH specialists/functions was proposed and discussed. A different level of qualifications, training and their scope of work for companies based on NACE assigned to a high, medium and low risk sectors was proposed. - In order to increase the quality of training institutions the requirements for the applicants applied for accreditation as a training institution in delivery of OSH training were discussed and proposed based on the good practise from different MS (Croatia, Slovakia, Spain, etc.) - Different length of professional working experience, training skills for the applicant and trainers delivering training was proposed - The competencies of the Accreditation Committee, Examination Centre, Supervisory body were discussed and some new articles proposed - Based on the above-mentioned discussion as well as the involvement of the Component Leader Mr Jose Ignacio Martin Fernandez the Proposal of the new structure of Decree was prepared, redrafting the purpose, scope, definitions and individual chapters of the decree Output: - Proposal for a new structure of the Decree “The Certified Occupational Health and Safety Specialist Program” - Good practice of OSH Specialists training in Croatia, Slovakia | 1st mission Muratti 7 – 31/01/2010 |
| Number of experts from BA experts/dpt. | - 4 BA experts in total - Mr Beka PERADZE, Head of Labour Conditions Inspecting Department, MoIDPLHSA - Mr Levan ABASHIDZE, Head of Monitoring and Supervision Division of the Labour Conditions Inspection Department (LCID). - Ms Shorena KUBANEISHVILI, Labour Conditions Inspecting Department - Maia Mikaia, Head of Labour Inspection Division of the L Labour Conditions Inspection Department - Maia Mtchedlishvili, Labour Conditions Inspection Department |  |
| Ref. number | Title of activity/State of play/Name of involved MS Experts | Duration of the activity |
| Activity 2.2.2. | Preparing and implementing public information campaign aiming to raise awareness among the project among key stakeholders, public, private sector and civil society | December 2019 – May 2020 |
|  | State of play: 3 missions were carried out during the reporting period as follows: 1st mission 27 – 31/01/2010 Ms Luba Pavlovova (5 WD), Ms Mercedes Tejedor Aibar ( 5 WD), Ms Marta Zimmerman Verdejo ( 5WD) - During a mission the outline of the Campaign – Concept Paper, draft programme for the kick off – 28.4.2020 (OSH World Day), key activities of the campaign, logo and slogan was prepared - the current stage of play regarding LCID capacity for planning, preparing, implementing and evaluating a nationwide campaign was checked - the planned works with other donors – specifically with ILO, GIZ, possibly UN Women and opportunity for common preparation and running of the campaign was coordinated Findings and recommendations: - Social partners representing both key target groups – employers & employees are to be actively involved in the survey conducting and campaign designing, preparation and implementation of planned activities/events - Social partners will nominate their representative/s to the COB - All preparatory work on the campaign and its kick off (28.4.2020) will be done as one team consisting of representatives of the social partners, LCID, EU & ILO experts. The CFG will be of technical nature meaning will be in charge to propose options, documents, etc. and the final decision is to be taken by the COB. Outputs: - All 3 Questionnaires elaborated, revised and ready for online survey (they are part of the project documentation - Concept Paper on “Public OSH Information Campaign 2020” elaborated - PPT “Campaign design & execution – preliminarily concept” elaborated - possible types of logo of the campaign for further discussion with LCID proposed, company to be recruited for elaboration of logo and materials for the kick off of the campaign 2nd mission 10 -14/02/2020 Ms Luba Pavlovova (5 WD), Ms Mercedes Tejedor Aibar (5 WD), Ms Marta Zimmerman Verdejo (5 WD) - The state of play of the online forms of survey questionnaires were distributed timely to the public and private sectors – employers & employees - Agenda of the meeting of the COBS-Campaign Organisational Board Secretariat – and results to be achieved at the end of the meeting was prepared - meeting of COBS (LCID/MoIDPLHSA, ILO, EU TWP) prepared - The opening of the Campaign planned for 28.4.2020 - campaign documents (work on logo, leaflet, poster, slogan, etc.) drafted - training materials for specialised training of the LCID and PR Dept. /MoIDPLHSA on planning and running a OSH campaign - Conduct the training (as mentioned-above) prepared Main findings and Recommendations - Online forms of all 3 Questionnaires were prepared and survey released; there is a need from LCID to check with the social partners whether the latter distributed the Q link to the relevant respondents - It is advisable LCID to ensure Mid-term check on the responses from the both – employers and employees, i.e. to get information that Qs reached the potential recipients! - It was agreed that Campaign Slogan is: “CREATE TOGETHER SAVE WORK SPACES” - Work meeting of the COB shall be organised in the week 24-28.2.2020 to reach agreement on the Logo and other documents, this is very important to be done prior to the next mission of STEs so they can concentrate on finalisation of all materials for the 28.4.2020 – official opening of the Campaign - Agreement on all practicalities regarding opening of the Campaign between members of the COBS (LCID, ILO, EU TWP) was reached and details are in the Minutes of the meeting held on 11.2.2020 at the MoIDPLHSA. Outputs: - Invitation & agenda and minutes of the meeting of the COBS meeting - Check list of tasks and responsibilities between LCID/ILO/EU TWP for the opening of the Campaign - Draft Registration Form for 28.4.2020 - Draft Information for the Prime Minister on the TWP and Campaign - Invitation and agenda for the training on planning and implementing OSH campaign - Training materials for training of the LCID&PR Dept. staff on preparing and implementing OSH campaign - Proposals of: logos, leaflet, flyer, 3 poster design, web design, draft invitation to the opening of the Campaign - Prepared documents with main points of the Campaign - Fact sheets in GE language of OSHA Bilbao 3rd mission 09 -13/03/2020 Ms Luba Pavlovova (5 WD), Ms Mercedes Tejedor Aibar (5 WD) was focused on: - Update on the state of play of the campaign preparation including on the survey and related practicalities specifically for the opening event - Organise 2nd COBS meeting to ensure all tasks are agreed and responsibilities are understood and distributed as per partner – (for details please see the Minutes of the 2nd COBS meeting attached as annex to this report) - Work on the campaign documents – specifically for the opening event – leaflet, banners, poster/s, other materials as agreed by partners to be part of documents given to participants - Agree on the next steps to be taken by partners till opening event on 28.4.2020 Findings and recommendations: - The agreement on programme for 28.4.2020 was agreed – tasks are distributed to each partner (LCID, TWP, ILO) and also financial issues were agreed (see MoM of 11.3.2020 as part of project documentation) - Logo of the campaign is already agreed and is to be used in all promotional materials of the campaign - All COBS members agreed that focus will be put on the campaign as such and not on so much on the projects implemented by EU/TWP and ILO/Danida - It is necessary to have so-called plan “B” for the opening event of the whole campaign due to the current situation and restrictions relating to corona virus in the country and worldwide. It might happen that the opening event of the campaign could be shifted; at present, it is not possible to predict due to the fact that no one can really say what could happen during the upcoming weeks. Therefore, it is necessary to follow the situation and based on it to take decision/s. Outputs - The key promo materials – leaflet, banners (2+1) and poster for the screen are to be ready by 14.4.2020 - Finalised programme of opening event to be held on 28.4.2020 - 13 examples of posters based on the already proposed ones during previous mission; 2 proposals for the banner, 2 proposals for the leaflet (also based on the draft prepared during previous mission) - Document on Dissemination Activities for the campaign - Proposal for photography awards - First feedback (data) from the survey - Minutes of the 2nd work meeting COBS held on 11.3.2020 - Final registration (online) form for the opening event 28.4.2020 | 1st mission 27 – 31/01/2010 2nd mission 10 -14/02/2020 |
| Number of experts from BA experts/dpt. | 16 BA experts in total were involved in the activity - Ms Tamila Barkalaia, Deputy Minister, MoIDPLHSA - Mr Beka PERADZE, Head of Labour Conditions Inspecting Department, MoIDPLHSA - Mr Levan ABASHIDZE, Head of Monitoring and Supervision Division of the Labour Conditions Inspection Department (LCID). - Ms Shorena KUBANEISHVILI, Labour Conditions Inspecting Department - Maia Mikkaia, Head of Labour Inspection Division of the L Labour Conditions Inspection Department - Nick Nanuashvili, BAG - Tamar Kapianidze, ICCA - Nino Ushirishvili, EBA - Lasha Labadze, GEA - Elene Makharashvili, GEA - Giga Bekauri, GIUC - Kinan Albahnasi, ILO - Tamar Kheladze, ILO - Ekaterine Karchkhadze, ILO - Tatia Tsereteli, PR Department, MoIDPLHSA - Nino Talakhadze, PR Department, MoIDPLHSA - Irina Sikharulidze, PR Department, MoIDPLHSA |  |

2D - TIMING AND DELAYS

Adherence to time schedule

| Project Month 2019/20 | Jan | Feb | March | April |
| --- | --- | --- | --- | --- |
| Horizontal costs |  |  |  |  |
| Steering Committee |  |  |  |  |
| Workplan |  |  |  |  |
| Component 0 |  |  |  |  |
| Activity 0.1 Kick-off |  |  |  |  |
| Activity 1.1.1 |  | X |  |  |
| Activity 1.2.1 |  | X |  |  |
| Activity 1.3.1 |  |  |  |  |
| Component 2 |  |  |  |  |
| Activity 2.1.1. | X |  | X |  |
| Activity 2.1.2. |  | X |  |  |
| Activity 2.1.3. |  |  |  |  |
| Activity 2.1.4. |  |  | X |  |
| Activity 2.2.1. | X |  |  |  |
| Activity 2.2.2. | X | X | X |  |
| Activity 2.2.3. |  |  |  |  |
| Activity 3.1.1. |  |  |  |  |

Activity/action Planned

X		Activity/action Performed

Activity/action Delayed by more than three months

Recuperation of delays

There will be a delay more than 3 months in implementation of following activities 1.3.1.;2.1.3 and 2.1.4. Act. 1.3.1 will conducted in May. Based on common agreement with RTA Counterpart, the implementation of activities 2.1.3. and 2.1.4. is postponed to the next period due to a delay in hiring of the new labour inspectors.

2E - ASSESSMENT

Overall Assessment of progress

The progress made is in line with the given timeframe.

Concrete time schedule – dates for each activity and mission were prepared and consulted with the beneficiary and MS ST experts. Taking into consideration the beneficiary, different stakeholders and planned activities, it was necessary to keep some flexibility in the planning as majority of events are to be implemented in close cooperation with all involved into the twinning project.

During the reporting period the beneficiary has shown a high level of involvement and commitment in implementation of activities.

The cooperation with BA as well as with other stakeholders is efficient and discussions are constructive thus the benchmarks are expected to be met as stated in the contract.

All stakeholders including the social partners are fully committed and they confirmed their active participation in the implementation of the project’s components. DEU Program manager and PAO representatives  are very committed and very operational in dealing with daily issues. There are no difficulties in communication/cooperation with all involved twinning parties.

Overall evaluation of the progress achieved during the reporting period.

Component 0

No activities were delivered within the component 0 during this reporting period

Component 1

Within the component 1 the following outputs were delivered during the reporting period:

- Assessment of compliance of the amendments of the Labour Code of Georgia with 8 EC Directives related to the labour law including the selected Case Law of CJ EU to each of selected Directives

Component 2

Within the component 2 the following outputs were delivered during the reporting period:

- Evaluation of the Training Needs Analysis of the Labour Conditions Inspecting Department

- OSH Questionnaire for public employers

- OSH Questionnaires for private employers

- OSH Questionnaires for employees

- Concept Paper on “Public OSH Information Campaign 2020” elaborated

- Electronic Registration Form for 28.4.2020 World OSH Day

- Design of the Induction training for newly hired inspectors and Refresher training for Senior Inspectors

- Delivery of training materials for training of the LCID&PR Dept. staff on preparing and implementing OSH campaign

- A package of proposals of logos, leaflets, flyers, 3 poster design, web design, draft invitation and agenda of the opening of the campaign

Other Issues

No problems in the management of the Twinning Project have occurred until now. All project partners handle unforeseen issues in the project in a very reasonable, cooperative and flexible way. Any partial issues were resolved on the grounds of good communication and cooperation among the twinning partners.

List of Annexes

Annex 1	1st  Interim Quarterly Financial Report (will be completed and submitted after taking the decision on reimbursement of the RTA unit costs)

Annex 2	Assessment of the compliance of the amendments of the Labour Code of Georgia with 8 EC Directives related to the labour law including the selected Case Law of CJ EU to each of selected Directives

Annex 3	Training Needs Analysis of the Labour Conditions Inspecting Department

Annex 4	OSH Questionnaire for Employees

Annex 5	OSH Questionnaire for Public Employers

Section 3: Expenditures

Provide total figures of disbursement in the reporting period broken down on budget headings and for the key groups of costs under each budget heading - as per Annex A3 to the Twinning Grant Contract.

Budget will be submitted after taking a decision of the RTA Unit cost teleworking  outside Georgia .

It should be noted that the Member State and Beneficiary country Project Leaders in their own right could agree not to deliver an extensive narrative report to the Steering Committee every quarter but only bi-annually.

Project named: Producing information campaigns to rise awareness about labour safety law in Georgia