UPDATED LOGICAL FRAMEWORK, Project title: Improving the standards of employment conditions/relations as well as health and safety at work in Georgia

| Intervention logic | Description | Indicators (with relevant baseline and target data) | Sources of verification | Risks | Assumptions (external to project) |
| --- | --- | --- | --- | --- | --- |
| Impact: Overall objective | Overall Objective Support higher standards in employment relationship and working conditions in Georgia through improving legal framework and enforcing implementation. | - Degree of employment relations and health and safety standards at work for Georgian employees and enterprises Baseline: Employment relations and OSH standards at work lacking behind Target: Improved employment relations and OSH standards at work - Number of inspected facilities implementing preventive measures focused on creation of safe and healthy working conditions Baseline: 708 Target: 1 050 - Number of employees effected by implemented OSH preventive measures increased Baseline: 210 390 Target: 300 000 | - Reports, including the EC Progress reports - Comparative international studies - National statistics and Annual Reports of the Labour Conditions Inspecting Department (LCID) |  |  |
| Outcome: Specific objectives | Specific Objective(s) To assist the MoIDPLHSA, together with other relevant stakeholders, to draft the legal and administrative provisions and establish the institutional mechanisms to improve employment conditions/ relations and Occupational Safety and Health, including a labour inspection system. Additionally, to strengthen the capacity of the national institutions to implement and adopt the best European practices. | - Degree of compliance of the relevant Georgian legislation with the Union acquis Baseline: Available policies, strategies and laws not yet harmonised with the EU Directives Target: Available policies, strategies and laws fully developed and harmonised with the relevant EU Directives - Status of legal and administrative procedures, and institutional mechanisms for improved employment relations and health and safety standards at work Baseline: Legal and administrative procedures and institutional mechanism for improved employment relations and health and safety standards at work not drafted yet and lacks of inter-institutional coordination Target: Legal and administrative procedures and institutional mechanism for improved employment relations and health and safety standards at work fully developed and coordinated | Project documentation (list of various meetings, list of participants from various meetings, training programmes, training materials, list of trainees, interim project reports, etc.); Project documentation: legal analysis reports, administrative/ institutional analysis reports, quality and cost assessment reports, training needs assessments, recommendations, etc.); Translated Georgian versions of the all labour legislation acquis covered by the project; Operational plans and procedures, implementation manuals and guidelines; Promotional materials, links to public information tools; Mission reports, participants’ list, and/or training lists; Project interim and final reports. | L/M Decrease of commitment and support of all governmental bodies of the Georgia and other involved stakeholders to the process of fulfilment of AA/DCFTA requirement | Government commitment on the fulfilment of AA/ DCFTA requirements continued; Strong support and commitment from the senior management of the MoIDPLHSA; Strong support and commitment from twinning partner(s); Relevant staff of the MoIDPLHSA and other stakeholder representatives available and involved in the process. |
| Mandatory results/outputs by Components | Mandatory result 1: Approximation of primary and secondary legislation related to labour law, gender equality and OSH in accordance with the Union acquis | - Status of the legal basis allowing for a labour inspection system covering standard labour rights and working conditions; Baseline: Legal basis is incomplete, in need of further elaboration Target: The legal basis allowing for a labour inspection system covering standard labour rights and working conditions elaborated; - Status of amendments in the field of Labour Law, Gender Equality, and Occupational Safety and Health as per Union acquis, with an inclusive and evidence-based approach. Baseline: Delay in harmonisation of the legal framework covering standard labour rights and working conditions reflected in amendments of the relevant laws Target: Legal amendments prepared in the field of Labour Law, Gender Equality, and Occupational Safety and Health as per Union acquis, with an inclusive and evidence-based approach. | Reports of the MoIDPLHSA; Monitoring/assessment reports by international organisations such as ILO; EU-Georgia Association Agenda implementation report. | Inadequate commitment and support from decision making level in particular with regard to adoption of amended legislation, draft acts, guidelines and procedures | Government commitment on the fulfilment of AA/ DCFTA requirements continued; Strong support and commitment from the senior management of the MoLHSA; Availability of local staff; Good communication between the Beneficiary and other stakeholders; Twinning MS partner(s) commitment; All relevant national documentation available. |
|  | Mandatory result 2: Capacity building, inter-institutional cooperation, and awareness raising of relevant state authorities and private sector for full implementation of amended legislation in labour law, gender equality and OSH | - Status of operational plans and administrative procedures of the MoIDPLHSA and other relevant stakeholders to be amended in accordance with the new requirements Baseline: Operational guidelines, manuals and procedures outdated and in need of amendments based on further harmonisation Target: Operational plans and administrative procedures of the MoIDPLHSA and other relevant stakeholders amended in accordance with the new requirements; - Number of participants in capacity building activities Baseline: Staff development needs partially analysed Target: The relevant staff of the MoIDPLHSA and other stakeholder representatives trained for the implementation of new legal framework. | Reports of the MoIDPLHSA; Monitoring/assessment reports by international organisations such as ILO; EU-Georgia Association Agenda implementation report. | L/M No sufficient cooperation among all involved Georgian stakeholders | Government commitment on the fulfilment of AA/ DCFTA requirements continued; Strong support and commitment from the senior management of the MoLHSA; Availability of local staff; Good communication between the Beneficiary and other stakeholders; Twinning MS partner(s) commitment; All relevant national documentation available. |
| Sub-results per component (optional and indicative | Sub-result 1.1: Legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis Sub-result 1.2: Legal framework on non-discrimination and gender equality, including aspects of labour inspection system, amended in compliance with the Union acquis Sub-result 1.3: Legal framework on OSH, including aspects of labour inspection system, amended in compliance with the Union acquis Sub-result 2.1: Analysis for strengthening state authorities’ capacity for implementation of the EU best practices performed and required strategies developed Sub-result 2.2: Implementation of the EU best practices regarding the amended legislation piloted and awareness of the citizens and private sector on the topic increased Sub-result 2.3: Organisation of working group(s) on labour law, gender equality and OSH comprising line ministries and social partners completed and functional | Number of the Tables of Concordance prepared for the Labour Law acquis, including aspects of labour inspection system Baseline: 7 Target: 8 Directives List of amendments to be made in the Georgian primary and secondary labour legislation specified with explanatory notes Baseline: 3 Target: 8 Directives List of amendments to be made in the Georgian primary and secondary legislation on Gender Equality acquis specified with explanatory notes Baseline: 4 Target: 2 Directives Share of staff from relevant public institutions who are fully informed on regulatory and fiscal impact of changes in labour law and gender equality acquis Baseline: 0 Target: 90% of staff in LCID and LEPD Availability of quality checked translation of the OSH acquis with clear technical terminology (if necessary) Baseline: 9 Target: 15 Directives Availability of the Tables of Concordance prepared for the OSH acquis, including aspects of labour inspection system Baseline: 5 Target: 15 Directives Availability of the list of amendments to be made in the Georgian primary and secondary OSH legislation specified with explanatory notes Baseline: 2 Target: 13 Directives Share of staff from relevant public institutions who are fully informed on regulatory and fiscal impact of changes in OSH acquis Baseline: 0 Target: 90% of staff in LCID and LEPD Functional review of the relevant state authorities to implement changes, including human and financial resources, administrative structures and equipment needed Baseline: 0 Target: 1 Training needs analysis and plan of the whole staff of beneficiary department and representatives from other relevant institutions listed Baseline: 0 Target: 1 Share of BA staff who received training to implement necessary changes and the representatives from other relevant institutions listed Baseline: 10% Target: 90% of staff in BA and others Number of labour inspectors who are trained more to become ‘trainers’ with full knowledge and competency in implementing new laws Baseline: 0 Target: 5 Plan for improving institutional operations and procedures of the relevant state authorities to support their pilot implementation, each with clear competences and coordination roles Baseline: 0 Target: 1 Number of written operational guidelines, manuals and procedures required to implement all changes, explaining all steps of implementation to the relevant staff Baseline: 0 Target: At least 15 documents(*) Number of OSH online Glossary and Risk Assessment checklists and their dissemination to relevant parties Baseline: 0 Target: At least 20 (*) Number of elaborated promotional materials and public information campaigns in printed and online media, TV and other tools Baseline: 5 Target: 30 short written materials + 2 public campaigns (*) Share of private companies (i.e. both employers and workers) which are informed and number of citizens reached out on the new rules and changes made in labour legislation Baseline: 50 Target: 90% of registered companies Proposal for a structure of inter-institutional cooperation and working procedures, with a review of existing options Baseline: 0 Target: 1 Working groups operational with team members from relevant institutions with a clear mandate and their continuous involvement in the ‘Technical Working Group’ and ‘Coordination Group’ Baseline: 0 Target: 2 (*) Number of meetings facilitated for effective functioning of working groups through team building, training and expert inputs Baseline: 0 Target: at least 4 meetings a year (*) | Project documentation (list of meetings, training programs and materials, list of participants, recommendations etc); Translated Georgian versions of the all labour law acquis covered by the project; Translated Georgian versions of the all OSH acquis covered by the project; Analysis reports of the relevant Georgian legislation (including by-laws, amendments and administrative regulations); Reports on regulatory and fiscal impact assessments of the legal amendments; Tables of concordance in both areas (labour law, gender equality and OSH acquis); Reports on administrative/ institutional assessments, including legal basis for a modern labour inspection system; Meeting notes and decisions on the topic from the technical working group and/or the Tripartite Social Partnership Commission (TSPC); Legislative amendments made in labour law, gender equality, and OSH; STE mission reports. Project documentation (training programmes and materials, list of participants, recommendations etc); Translated Georgian versions of the all relevant EU Directives; Analysis reports of the relevant Georgian legislation (including by-laws, amendments and administrative regulations); Reports on regulatory and fiscal impact assessments of the legal amendments; Meeting notes and decisions on the topic from the technical working group and/or the Tripartite Social Partnership Commission (TSPC); Legislative amendments in labour law, non-discrimination and gender equality, and OSH); Analysis reports on the training needs of the BA (LCID and LEPD staff) as well as other relevant institutions listed; Short and long-term training plans, training programs and materials; The names and numbers of training participants from all institutions; Study visits’ and mission reports; Plans for improvement of administrative structure and resources; Operational plans and procedures, implementation manuals and guidelines (in English and Georgian); Promotional materials, links to public information campaigns. | L/M Inadequate commitment and support from decision making level in particular with regard to adoption of amended legislation, draft acts, guidelines and procedures | Government commitment on the fulfilment of AA/ DCFTA requirements continued; Strong support and commitment from the senior management of the MoLHSA; Availability of local staff; Good communication between the Beneficiary and other stakeholders; Twinning MS partner(s) commitment; All relevant national documentation available. |

Please consult Annex 5 – “Action Document for Skills Development and Matching for Labour Market Needs” under which this Twinning Project will be operating