DEVELOPMENT OF NATIONAL EMPLOYMENT STRATEGY

GEORGIA

Draft Time Table – 3 August 2018

| Time Period | Activity | Comments |
| --- | --- | --- |
| July – August | - Develop terms of reference for the development of: - National Employment Strategy (NES) (national consultant) - Macro-economic research (international consultant) |  |
| August – September | - ILO Mission to Georgia by consultant undertaking macro-economic research (fact-finding, constituent consultations, consultation with national consultant) | Please include consultations with EU technical assistance project staff; UNICEF; World Bank (WB international experts are visiting Georgia the week of September 15th. Would be great to coordinate their visit with consultations/interviews). |
| September - October | - Inter-agency Working Group meeting to discuss basic concepts related to the development of a NES - Tripartite round table in Tbilisi to discuss basic concepts related to the development of a NES |  |
| October | - First draft macro-economic research - Inter-agency Working Group meeting to discuss basic issues related to the development of a NES specific to Georgia |  |
| Mid-November | - First draft NES presentation to constituents |  |
| Early December | - Final macro-economic research presentation to constituents |  |
| End December | - Finalisation and adoption of NES |  |