## OC Plan and budget
|  |  |  | Budget | Status |  | I QUARTER |  |  | II QUARTER |  |  | III QUARTER |  |  | IV QUARTER
Activities* | Responsible | Support From | Funding allocated in GF approved budget? Y/N | Additional Details | Period | Completion Status
[7 empty] | MAR'20 | APR'20 | MAY'20 | JUN'20 | JUL'20 | AUG'20 | SEP'20 | OCT'20 | NOV'20 | DEC'20 | JAN'21 | FEB'21
Hold an orientation with the new CCM OC members to review their role, inputs required and commitments. | CCM Secretariat | OC Chair | N/A |  | based on need
Set quarterly Oversight Committee meeting dates for dashbioard revision/discussion | CCM Secretariat OC | PR | N/A |  | dates TBD on a quarterly basis
Conduct quarterly dashboard meetings | OC Chair | CCM Secretariat | Yes | budget is indicated in CCM GA meeting | dates TBD on a quarterly basis
Develop dashboard recommendations based on the findings of the dashboard status | OC Chair OC members | CCM Secretariat | N/A |  | week after the dashboard meeting
Agree on site visit dates and locations for the visit together with PR, | CCM Secretariat | OC PR | N/A |  | will be defined after dashboard meeting
Develop site visit questionnaire decide (number of participants depending on issue, frequency, etc). | OC Chair OC members CCM Secretariat | PR/CCM | N/A |  | week before of the site visit
Carry out 2 site visits in Tbilisi | OC CCM Secretariat | PR | No | Two site visits in Tbilisi do not require any funding. | dates TBD after dashboard/CCM/OC meeting based on needs
Carry out 2 site visits in the regions | OC CCM Secretariat | PR | YES | Total number of site visits 4. Approximate # of participants 5 persons. 2 visits in Tbilisi. 2 field visits to regions. Field visit costs include perdiem, transportation and accommodation for the participants | dates TBD after dashboard/CCM/OC meeting based on needs
Report to CCM on OC activities, provide recommendations based on the dashboard meetings and site visits during CCM GA | OC | CCM Secretariat | YES | part of the budget line allocated for the CCM GA and other CCM related meetings. | Each CCM Meetings
Develop OC reports, site visit, dashboard reports | OC CCM Secretariat | CCM | N/A |  | week after OC meetings
Share the reports with all CCM members and to the GF | CCM Secretariat | All CCM | N/A |  | week after OC meetings
NOTE: *Activities can be implemented in online format based on the Covid 19 related status