Draft agenda for 3nd mission from 3nd to 31st May 2020

| Week | Days (28) | Date | Activities |
| --- | --- | --- | --- |
| Week 1 | Sunday | 03.05. | Planning and preparatory work for the mission |
|  | Monday | 04.05. | Planning and preparatory work for the mission |
|  | Tuesday | 05.05. | Assessment on number of by- laws indicated in new draft Law proposals and its content that should be addressed |
|  | Wednesday | 06.05. | Drafting the list of indicated by-laws |
|  | Thursday | 07.05. | Consultation on administrative/technical issues via teleconference with project management team |
|  | Friday | 08.05. | Preparatory work for meeting with local expert group |
|  | Saturday | 09.05. | Local expert team introductory teleconference meeting (job description and assignments) |
| Week 2 | Sunday | 10.05. | Drafting by-law |
|  | Monday | 11.05. | Drafting by-law |
|  | Tuesday | 12.05. | Drafting by-law |
|  | Wednesday | 13.05. | Drafting by-law |
|  | Thursday | 14.05. | Preparatory work for meeting with beneficiary team |
|  | Friday | 15.05. | Consultation with beneficiary team (MoH) via teleconference, on work plans and the mission’s expected outcomes |
|  | Saturday | 16.05. | Teleconference meeting with local experts and exchange of project relevant documentation and RIA templates |
| Week 3 | Sunday | 17.05. | Drafting by-law |
|  | Monday | 18.05. | Drafting by-law |
|  | Tuesday | 19.05. | Drafting by-law |
|  | Wednesday | 20.05. | Drafting by-law |
|  | Thursday | 21.05 | Drafting by-law |
|  | Friday | 22.05 | Drafting by-law |
|  | Saturday | 23.05. | Debriefing meeting on outputs (EU experts) |
| Week 4 | Sunday | 24.05. | Drafting by-law |
|  | Monday | 25.05 | Preparation of the minutes of the meetings and exchange of documentation and feedback information with beneficiary team |
|  | Tuesday | 26.05. | Drafting by-law |
|  | Wednesday | 27.05. | Drafting by-law |
|  | Thursday | 28.05. | Drafting by-law |
|  | Friday | 29.05. | Drafting by-law |
|  | Saturday | 30.05. | Drafting by-law |
|  | Sunday | 31.05. | Debriefing meeting on outputs (EU experts) |