Annex 1. Working plan for the mission to Georgia 14- 20 of April 2019

2 groups with separated agenda:

- Camille, Yannick, Andrei are going to Batoumi, Kutaissi and Borjomi together with AFD team

- Antoine, Taavi, Michel and Alain are staying in Tbilissi with eventual participation in some visits close to Tbilissi (Mental health institutions & IDP camps)

|  | Antoine | Taavi | Michel | Camille, Yannick, Andrei | Alain |
| --- | --- | --- | --- | --- | --- |
| 14/04 | Arrival to Tbilissi | Arrival to Tbilissi |  | Arrival to Tbilissi or Batoumi | Arrival to Tbilissi |
| 15/04 | Organisation of programme in Tbilissi | Meeting with the Ministry (Health insurance) | Arrival to Tbilissi during the night 15 and 16/04 (to check with Michel his availability) | In case of arrival to Tbllissi, departure for Batoumy by plain 9h00 – 10h00 All the day in Batoumi for UNICEF disability piloting Departure for Kutaissi by train | Working on pension project |
| 16/04 | Organisation of programme in Tbilissi | Meeting with WHO (definitions of needs in AMO) | Meeting with WHO (definitions of needs in AMO) | Day in Kutaissi, visit of children with disability institution Departure for Borjomi by train | Working on pension project |
| 17/04 | Eventually Visit of IDP close to Gory | Visit of Mental Health institution (operationalisation of activities A221, A222, A223, A224) | Meeting with IT department of the Ministry | 1/2 Day in Borjomi ½ day in Mental Health institution | Visit of Mental Health institution (operationalisation of activities A221, A222, A223, A224) |
| 18/04 | Drafting of deliverables; Meeting with Levan, Nicolas and Andrei Other meetings if necessary | Drafting of deliverables; Other meetings if necessary | Drafting of deliverables; Meeting with UNICEF Other meetings if necessary | Meeting with Nutsi and UNICEF Tbilisi office in order to discuss the methodology of piloting | Working on pension project Meeting with Levan, Nicolas and Andrei |
| 19/04 | 10h- 12h Debriefing in the Ministry 13h-14h Meeting with French embassy Other meetings if necessary | 10h- 12h Debriefing in the Ministry 13h-14h Meeting with French embassy Other meetings if necessary | 10h- 12h Debriefing in the Ministry 13h-14h Meeting with French embassy Other meetings if necessary | 10h- 12h Debriefing in the Ministry 13h-14h Meeting with French embassy | 10h- 12h Debriefing in the Ministry 13h-14h Meeting with French embassy |
| 20/04 | Departure | Departure | Departure Michel can stay some additional days if he need meet additional peoples | Departure | Departure |

| Expert name | No of working days/ activity | Deliverables |
| --- | --- | --- |
| Camille LAMBINON | 10 WD (including 5 WD in site)/Inception phase | - First draft Inception report; - Methodology for piloting the disability assessment in Samtskhe Javakheti region including detailed workplan and CV of experts to mobilise; |
| Yannick DEIMAT | 7 WD (including 5 WD in site)/A111 | - Development of proposal of module for personal rehabilitation plan to integrate to the piloting; - Contribution for Methodology for piloting the disability assessment in Samtskhe Javakheti region including detailed workplan and CV of experts to mobilise; - Definition of data necessary for Policy impact assessment based on the results of piloting in two Georgian regions (Activity 113) together with Michel. |
| Andrei TRETYAK | 10 WD (including 5 WD in site)/A111 | - Contribution for Methodology for piloting the disability assessment in Samtskhe Javakheti region including detailed workplan and CV of experts to mobilise; |
| Michel VILLAC | 7 WD (including 3 WD in site)/A212 | - First discussion paper on functioning of IT in the health sector (E health) and recommendations for improvement; - Part of inception report for the activity A212 including detailed workplan and CV of experts to mobilise; - Definition of data necessary for Policy impact assessment based on the results of piloting in two Georgian regions (Activity 113) together with Yannick. |
| Taavi LAI | 7 WD (including 5 WD in site)/A211 | - First discussion paper on Standard operating procedures for the implementation of performance-based contracting, especially to primary health care in Georgia; - Part of inception report for the activity A211 including detailed workplan and CV of experts to mobilise; - Participation in the drafting of Part of inception report for the activity A221; A222; A223 & A224 including detailed workplan and CV of experts to mobilise; |
| Alain LEFEBVRE | Covered by pension project | - Part of inception report for the activity A221; A222; A223 & A224 including detailed workplan and CV of experts to mobilise; |
| Antoine POGORZELSKI | 5 WD (including 5 WD in site)/Inception phase | - Part of inception report for the activity A31; A32 & A33 including detailed workplan and CV of experts to mobilise; - Contribution of First draft Inception report and preparation of CVs of experts |

All logistical aspects of EF experts will be managed by Antoine starting from 1/04/2019

Annex 2. List of persons met during the mission to Georgia 14- 20 of April 2019

Ketevan Melikadze, UNICEF
Milena Harizanova, UNICEF
Maguli Shaghashvili, UNICEF
Tinatini Tsertsvadze, UNICEF

Ms Ketevan Gigineishvili, GASW

Dr. Silviu Domente, WHO Representative and Head of WHO Country Office

Ketevan Mezvrishvili, “Human Rights for All” UNDP/EU

Mariam Tutberidze, “Human Rights for All” UNDP/EU

Salome Kusikashvili, Assistant Protection Officer, UNHCR

Vincent Dontot, Country Director, DRC

Nino Khokhobaia, Strategic Partnerships Manager, DRC

Friederike Rochowanski, Programme Director of “Economic Participation of IDPs in the Caucasus”, GIZ

Ekaterine Berdznishvili, Head of outpatient mental health services of Rustavi MH Center

Manana Eliashvili, Director, Rustavi MH Center

Irma Khabazi, Open Society Foundation

Lela Sulaberidze, Junior Researcher, Curation International Foundation

Eka Chkonia, Professor of Psychiatry at Tbilisi State Medical University, President of the Society of Georgian Psychiatrists