Technical Assistance 
to the Social Welfare system in Georgia

Inception report

May 2019

Human capital & Social development Department

Social Protection & Decent Work Unit

# Table of content

Introduction	5

Section 1. Progress made during inception phase	7

1.1 Pillar 1: Enhancing social support to Persons With Disabilities	8

1.2 Pillar 2 : Ensure affordable and quality-driven healthcare	16

1.3 Pillar 3: Reinforcing the efficiency of resources allocated to IDP needs	20

Section 2. First recommendations	18

2.1 Pillar 1: Enhancing social support to Persons With Disabilities	18

2.2 Pillar 2: Ensure affordable and quality-driven healthcare	20

2.3 Pillar 3 : Supporting the Ministry in identifying and passing the IDP allowance reform	22

Section 3. Next steps of the project	24

3.1 Pillar 1: Enhancing social support to People With Disabilities	24

3.2 Pillar 2 : Quality healthcare	25

3.3 Pillar 3 : Supporting the Ministry in identifying and passing the IDP allowance reform	26

ANNEXES	27

Annex 1. Working plan for the mission to Georgia 14- 20 of April 2019

Annex 2. List of persons met during the mission to Georgia 14- 20 of April 2019

Annex 3. Planning of working days per activity

Annex 4. Methodology for piloting the disability assessment in Samtskhe Javakheti region

Annex 5. Detailed minutes of the meetings

# List of Acronyms

| AFD | Agence Française de Développement |
| --- | --- |
| IDP | Internally Displaced Person |
| CSO | Civil Society Organisation |
| GASW | Georgian Association of Social Workers |
| GEL | Georgian Lari |
| NGO | Non-Governmental Organization |
| MOLSHA | Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs |
| OOP | Out-of-Pocket |
| PHC | Primary Health Care |
| PWD | Persons with Disabilities |
| SSA | Social Service Agency |
| TA | Technical Assistance |
| TSA | Targeted Social Assistance |
| UHC | Universal health coverage |
| WHO | World Health Organization |

# Introduction

The Georgian Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs (MOLSHA) has started an international cooperation with support of AFD and implemented by Expertise France since 1 of April 2019. The purpose of this project which will last two years is to strengthen the Georgian social welfare system through technical assistance to three following pillars:

- Pillar 1: Enhancing social support to Persons With Disabilities (PWD)

- Pillar 2: Ensuring affordable and quality healthcare

- Pillar 3: Support to optimizing resources allocated to IDP needs

This inception report was prepared after the first mission organised in Georgia from 15th to 19th of April, 2019 in order to present the first diagnosis made by a team of international experts as well as to present the project and its approach to key stakeholders in order to ensure their active participation. This report greatly benefited from the contributions of Georgian representatives from the Ministry of IDPs from the Occupied Territories, Labour, Health and Social Affairs, from UNICEF, from the Georgian Association of Social Workers and other stakeholders (detailed list of persons met is presented in Annex 1 and 2). Project team is grateful to all participants of the meetings for their availability and for the information and feedback they have provided during the inception phase. The efficiency of meetings and the quality of exchanges between Georgian and international partners have allowed to define precisely the type of services, the content of expertise and the timeframe expected by the MOLSHA.

This inception report first describes the overall progress made by TA during inception phase (Section 1); which recommendations the TA team can provide at this stage (Section 2). This report finally describes the next steps to be undertaken, including activities and proposed timetable, and taking into account MOLHSA’s feedback (Section 3).

# Section1. Progress made during inception phase

The inception phase of this project is based on the meetings which took place during the experts’ mission trough 15th to 19th of April, 2019. It is also based on the analysis of the documents which were kindly provided by Georgian stakeholders prior and around this mission. Furthermore, inception phase has benefited from the exchanges which took place by emails, Skype and phone calls both before and after the mission.

During the inception phase, project proposal was fine-tuned listing the key areas for technical assistance (TA) based on the discussions of national counterparts in Georgia, desk review of available national documents and review of the experts pool of Expertise France who could be employed in provision of TA in Georgia as requested by the national authorities.

The inception mission to Georgia was conducted to fine-tune the needs of the MOLSHA, collect additional information on the status and development plans in Georgia, to discuss detailed focus of the project efforts with the national counterparts in order to ensure maximum impact of the TA, and to design and agree the final timeline as well as expert support activities for the project. Overview of the background information, planned project activities with approximate timeline as detailed during the inception mission, is presented in this sections.

The approach described in the initial project methodology remains globally confirmed after the inception phase. However, a progressive better understanding of actual challenges, expectations and opportunities, as well as preliminary elements of analysis, refines our approach for the implementation of the next activities.

## 1.1 Pillar 1: Enhancing social support to Persons With Disabilities (PWD)

One of the objectives of the project is to propose a methodology for piloting the testing phase of new functional assessment instruments in the pilot region Samtskhe Javakheti. As the results in Samtskhe Javakheti will have to be compared with results from the pilot region of Adjara, processes and samples shall be similar in the two pilot regions. The preparatory exchanges and meetings have been held with the MOLSHA, local public authorities in Adjara (Batumi) and Samtskhe Javakheti (Akhaltsikhe), UNICEF and key civil society actors involved in the process. Various meetings were organized between Georgian and French partners. These meetings helped fine-tuning the project methodology regarding assessment of handicap (see annex 5 for detailed minutes). The purpose of these discussions was also to present to each stakeholder the role of AFD and Expertise France and the testing of the new functional approach to evaluation for adults and children with disabilities.

Granting a disability status in Georgia

The disability diagnosis is based on the law on social protection of persons with disabilities (Law of Georgia No 959) and two directives of the MOLSHA. These directives stipulate a list of sicknesses which allows the granting of status of PWD. The granting of status also depends on the level of seriousness of the sickness.

There are three groups of disability for adults: serious (Group 1), average (Group 2) and slight (Group 3). The statute related to Group 1 and 2 opens the right to disability benefit which is ranking between GEL 80 and GEL 150. For less severe handicaps (Group 3), the disability benefits are attributed only if the person is recognised as PWD since its childhood.

A part from monetary benefits, the peoples getting status of disability have some reductions in terms of medical treatment. For example, they pay less for medical exams. Retired people pay 30 % of medical exams. When they are both retired and PWD, 90% of the costs of medical exams is covered by the State.

For most severe handicaps, people are assessed once and the disability status is given for whole their life. Whereas for average disability (Group 2), 50% of persons are subject of revaluation: the status is given for 5 years, but every years a re-evaluation can cause the change in status. If their handicap does not go worst, they stay in this category after the 5 years have passed. If it goes worst, they switch to the higher category.

For the children there is no groups of disability. Children are reassessed every two years. At 18 years old, everyone needs to be reassessed because it is a change from a child status to an adult status. Unlike adults who need a disability status in order to enjoy some social services, children do not necessarily need a status.

As a part of medical institutions reform, in 2006 Georgian authorities gave the rights for disability assessment for all kind of institutions (mainly privates). The public disability assessment bodies were closed or transformed. In the beginning there was a lot of difficulties because the right of delivery of disability status was given to all medical staffs and too many statuses were delivered. Therefore, a certification of specialised bodies was organized and out of the 300 institutions only 69 got authorized to deliver statuses nowadays.

Piloting functional assessment in Adjara

In Adjara autonomous republic the evaluation of handicap is realized by 6 medical centres. Four of them are general assessment centres and two are specialized centres (in oncology and mental health). These medical centres used to hold a public status before the 2006 reform. They have been private for a few years. An agency ensures that the handicap status is delivered in application of the legislation. Some mobile monitoring teams go to medical centres and proceeds to controls. In case the law was not respected, medical centres receive a fine.

The main challenge for the region is to support PWD in getting access to work. Adjara region develops some rehabilitation programs for children, including for children with autism or suffering from dysphasia. There are also semi-private centres where a child and her/his mother can live for some periods of time.

The project which aiming at testing the new functional assessment questionnaire was launched Adjara in January 2018 by UNICEF with active participation of Georgian Association of Social Workers (GASW). For that purpose, the functional questionnaire that was developed by the World Health Organization has been translated in Georgian. In October 2018, the project was presented to various stakeholders, namely to beneficiaries, municipalities and NGOs in Adjara. The profiles needed for the testing phase have been identified: Functional Evaluation Specialist and Case Manager. Beforehand only Doctors were involved in the evaluation process of handicap.

In each medical evaluation centre, a Medical Coordinator has been identified. He/she is the first level in the evaluation process as he/she has the first contact with the public. A professional (Functional Evaluation Specialist) who will conduct a functional evaluation was identified as necessary to the process. A third professional was identified: A Case Manager who will coordinate the work of the Coordinator Doctor and the Functional Evaluation Specialist and ensure the coordination with the patients.

The evaluation specialists have been trained 3 days per week for 3 month which made 23 training days in total. The professionals who have prepared and delivered the training sessions are Occupational Therapists and Psychologists who have analysed the questionnaires from the WHO.

The testing phase has actually started at the beginning of April 2019. It is a one-year project which was supposed to start in August 2018 and to finish in August 2019. Because of some delay, it will last until December 2019. There are 14 000 people with disability status in Adjara region. GASW provided experts with the technical information needed to replicate the recruitment of candidates. The job advertisement was made on UNICEF and GASW Facebook pages and on the website Jobs.ge. The recruitment committee included representatives from MOLSHA, UNICEF, GASW and from the training team.

In the functional questionnaire, there is no mention of the patient’s medical situation. The professional who fills in the functional question has no information about the patient’s medical situation. Experts suggest that it could be interesting to compare medical and functional evaluations. At this stage of the project, no medical assessment from a doctor was reviewed based on the results of a functional assessment.

During a visit of a medical centre specialized in oncology in Batumi, experts had the opportunity to meet a team composed of a Coordinator Doctor, a Functional Evaluation Specialist and a Case Manager. The Functional Evaluation Specialist was a psychologist and the Case manager was a medical background. This team was receiving two persons per day since the beginning of the experiment. There are in total between 60 and 80 requests per month for disability status based on oncologic issues.

Situation with disability in Samtskhe Javakheti

In Samtskhe Javakheti region, there are 3 medical centres which realize disability assessments (2 in Akhaltsikhe and one in Akhalkalaki). On March 2019 there are 4684 PWD where a majority is in the second group:

| # Adigeni | # 39 | # 142 | # 373 | # 70 | # 624 |
| --- | --- | --- | --- | --- | --- |
| # Aspindza | # 27 | # 72 | # 197 | # 37 | # 333 |
| # Akhalkalaki | # 79 | # 209 | # 611 | # 110 | # 1,009 |
| # Akhaltsikhe -city | # 39 | # 109 | # 261 | # 36 | # 445 |
| # Akhaltsikhe – munic. | # 53 | # 174 | # 392 | # 61 | # 680 |
| # Borjomi | # 74 | # 233 | # 604 | # 153 | # 1,064 |
| # Ninotsminda | # 53 | # 100 | # 330 | # 46 | # 529 |
| Smtskhe-Javakheti | 364 Child | 1,039 - I gr. | 2,768 – II gr. | 513 – III gr. | 4,684 - Total |

Information from Social Service Agensy:  March 2019

In the last statistics, these institutions assessed 1131 persons (around 629 are reassessments and 502 of first assessments).

# Adigeni 42 4 26 3 9 21 21

# Aspindza 29 2 12 3 0 14 15

# Akhalkalaki 180 10 130 3 10 75 105

# Akhaltsikhe 573 73 438 13 49 242 331

# Borjomi 217 37 156 10 15 110 107

# Ninotsminda 90 8 73 1 8 40 50

Smtskhe-Javakheti 1131-Total 134 - I gr. 834- II gr. 33- III gr. 91 - Child 502- at first 629 - Verify

This Information  is from     State Regulation Agency for  Medical Activities and Includes the number of established  dis.st. throughout the year.

Summary of situation

- The collection of information about the experimentation in Adjara, including assessment grids and methodology for evaluation, was made. Meetings were held with project team and pilot medical centre.

- Presentations of the experimentation project to various stakeholders in Samtskhe Javakheti region were realized.

- Two institutions specialized in the handicap field were visited to build project knowledge.

## 1.2 Pillar 2: Ensure affordable and quality-driven healthcare

Effectiveness and efficiency of universal healthcare

As the current activity of the technical assistance project focusses on the health financing in primary health care (PHC) this section covers key aspects of the recent developments in these two areas.

Health financing

Since 2013 Georgia has been making significant improvements in health financing policy by extending population entitlement to publicly financed health care and gradually increasing public funding of the health system. The Social Services Agency (SSA) acts as a single purchasing agency for the health sector and with this approach Georgia follows European and global best practices. As a result, the evidence shows that these reforms have led to progress in meeting the goals of universal health coverage; they have increased access to health services and improved financial protection in areas targeted for expanded coverage.

Since 2013, the Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia (MOLSHA) has introduced new systems and methods to manage the flow of funds to providers. MOLSHA also has introduced several reforms to strengthen the capacity of the SSA to be more strategic in purchasing health care for the population. Remarkable progress has been made so far, but more can be done. Strategic purchasing can enable Georgia’s health system to make the best use of available resources to move towards universal health coverage (UHC) within financial constraints. Strategic purchasing is a complex function where institutional and multiple operational aspects play an important role.

As a result of these developments, a Strategic Purchasing Strategy for Georgia 2019 – 2021 has been developed with the support of World Health Organization (WHO) and will be soon adopted formally. This strategy aims to move from passive to active purchasing which means, the purchaser:

- drawing on information about the health care needs of the population for which it is responsible and aligning the availability of services to these needs (volume of care according to key medical specialties, different levels of care, geographical distribution, distribution according to service providers)

- planning of services according to needs, prospective planning considering long-term needs

- contracting with selected providers who agree to comply with access and quality standards and utilisation controls and are willing to accept specified payment mechanisms and payment rates and to provide information for monitoring purposes

- using its financial power (leverage) to influence the behaviour of providers to be efficient and deliver quality services, particularly through linking provider payment to information on performance, carefully monitoring provider performance and taking action when performance is poor

- using modern payment mechanisms and incentive systems

- design of HBP considering dynamics in need, provision of services and considering financial limitations

This strategy on strategic purchasing will be also the framework in which current technical assistance project shall operate in close collaboration and alignment with the WHO and the MOLSHA. This especially important as this strategy is also the basis of TA provided to Georgian MOLSHA by WHO in the area of health financing.

Primary health care

Georgia is striving to strengthen primary health care. These efforts have resumed with the Georgian Health System State Concept 2014–2020 on universal health coverage following an impasse between 2008 and 2012 created by the privatization of the provision of services.

In 2016, as part of the renewed commitments towards primary health care and in the context of the Health System State Concept 2014–2020, a draft of the Primary Health Care Development Strategy 2016-2023 was prepared by the Global Alliance for Health. This draft Strategy aims at strengthening family medicine and developing responsive, effective and sustainable primary health care

Currently, service delivery model in Georgia is varied using parallel polyclinic and rural doctor system while all professionals are salaried even as the polyclinics themselves are paid using capitation more like general budget. Also, the picture is varied regarding the services themselves as additional financing is allocated using national vertical programmes for priority disease areas. In parallel, role of inpatient care in the health care system is still high while gatekeeping function of the PHC is weak. Additionally, a large proportion of private out-of-pocket (OOP) payments especially for outpatient medication creates barriers to maximizing impact of PHC on population health improvement. As such, potential introduction and results of performance-based contracting in PHC in Georgia is strongly influenced by service delivery and overall health system organization decisions while this can also strongly influence impact of the technical assistance provided in the current project.

Summary of situation

- Universal health coverage (UHC) has improved significantly in recent years and is planned to improve further (target for OOP reduction by 2023 set to 50% in total health expenditure)

- Strategy on strategic purchasing has been developed and awaits formal adoption – set’s key framework for TA provided by the current project

- Situation in current PHC service delivery is varied, introduction on performance-based contracting for PHC is strongly influenced by service delivery and overall health system organisation decisions to be introduced in the framework of the draft of the Primary Health Care Development Strategy 2016-2023

Mental Health Care in Georgia

Following the collapse of the Soviet Union in the 1990s, the Georgian authorities made several efforts in order to promote the deinstitutionalization for people with disabilities and people living with mental disorders. This followed international guidelines and enabled to decrease costs. However deinstitutionalization was enforced at the expense of global mental healthcare: out-patient care was not strengthened adequately to compensate inpatient care. However since 2014, more out-patient care options are being developed by mental health institutions: it is worth noting that mobile teams of interdisciplinary practitioners are increasing).

Offer and Quality of Mental Health Care in Georgia

Mental health care can be divided into two categories: inpatient and outpatient care. However some traits are specific to both types of care, notably:

- Pharmaceutical/medical approach with little psychosocial care and support provided: the global approach to treating mental health is the use of medicines and few psychosocial care and soft therapies. Families and communities are involved but support to families in dealing with mental disorders is scarce.

- Lack of qualified staff trained to deal with mental disorders at different levels :

  - only Ilia University proposes a psychiatric degree in medecine and working in mental health institutions doesn’t attract many students or nurses (meager salary for hard conditions)

  - The psychiatrist-to-patients ratio is low for both inpatient and outpatient care, so is the psychosocial practitioners-to-patients ;

  - Nurses and nurse assistants are trained to be medical nurses and neither to psychiatry nor to psychosocial support; they receive a one-to-two week training regarding their daily tasks in the hospital and how to administer special medical health care (especially drugs) and daily care (bath, toilet, …) but not on the psychosocial side.

Inpatient care suffers from a lack of room/beds for short and long stays of inpatients: 40% of long-term in-patients should be in shelters to free beds for short-term stays, however shelters are

State Program and financing mental health care

Different institutions offer in- and out-patient mental health care in Georgia. Most are private (the mental health hospital with the most numerous beds of Georgia is in fact private) and some are public (like Rustavi Mental Health Center). The State financially support mental health care under State programs. 12 facilities are under the State program for mental health care, out of which 4 are private.

There are different financial instruments under the State program for mental health facilities and funding mental health care:

- global budget financing: the facility sends data monthly regarding the number of beds and short-term stays to the Ministry of health and the Ministry then pays based on a global flat rate price for inpatient stay and treatment of disorders (however, the ministry has no way of monitoring the quality of care effectively provided)

- Separate budget for long-term patients/inpatient and acute care

- Vouchers for outpatient care, in exchange for a restricted range of goods or services. Vouchers tie the receipt of cash to particular goods (such as drugs) or services (such as medical consultations or laboratory tests), provided by particular vendors, at particular times.

Under State programs, care is free of charge for

- First consultations in public mental health facilities;

- Outpatients living with serious mental disorders (bipolar disorder, PTSD, recurrent depression), including services provided by mobile teams;

- Inpatient mental health care for Georgians;

- People requiring the crisis intervention center a multi-disciplinary team and a hotline.

If the first consultation with a psychiatrist in free in some mental health institutions, outpatients need then to pay subsequent consultations (35 GEL) and pharmaceuticals (circa. 100 GEL/month), which many poor patients cannot afford.

Outside the scope of the State programs, all other mental health care items are paid directly by the patient/family/community/individual to the health institution. Insurance products in Georgia do not cover mental health disorders and risks. Out-of-pocket payments by outpatients is therefore high.

Monitoring and evidence-based decision-making regarding mental health care in Georgia

Mental health care has been under the spotlight in Georgia in recent years. The existing situation has drawn attention to the Ministry of Health and to international organizations and CSOs because despite local laws being up-to-date regarding mental health (UNCRPD, laws on disability and mental health in 2004 and 2006), the government lacks monitoring tools to really assess the many different situations and practices of mental health care in Georgia and make evidence-based decisions.  Collection of epidemiological data is not centralized and systematic, making it difficult to really assess the situation of mental health (number of people living with mental health disorders, types of disorders …).

The Ministry receives in fact data and information about mental health in Georgia in two ways, however without systematic collection and storage of data:

- The first way to get mental health data is through payment requests from health institutions (including mental health institutions) under state program and financing: the health institution shares its number of beds/inpatients and diagnosis to the Ministry and gets funds in return

- Civil Society Organizations, the Ombudsman and International Organizations exchange with the ministry regarding different issues in mental health.

## 2.3 Pillar 3: Reinforcing the efficiency of resources allocated to IDP needs

Overall, IDPs in Georgia are a more vulnerable group than the general population despite the fact that the social and economic situations of IDPs are very diverse and cover different vulnerable situations (in housing, livelihoods, employment and/or social integration).

Housing was an issue for many displaced persons, especially from the conflict in Abkhazia in 1992-1993. Most of the displaced persons relocated in collective centers (public and private flats, hotels, …) and livelihood in old collective centers worsened over time. Today, collapsing collective centers are the main housing issue for IPDs and the government is moving forward on this issue, closing collapsing collective centers and relocating IDPs in new collective centers or offering housing. After visiting some collective centers (collapsing and new ones) and discussing the issue with the government and other partners, it was decided that the government doesn’t require a technical assistance on this issue.

Different reforms of the IDP allowance changed the amount of the allowance. The latest reform of the IDP allowance in 2014 set the monthly allowance at 45 GEL/month and introduced conditionality (the 1250 GEL/month threshold) for allowance eligibility. However, there is particular need for reforming the IDP allowance that every IDP earning less than 1250 GEL/month receives : on the long-run, this monthly allowance to every IDP will be a financial burden for the state budget (status is hereditary) without getting the most vulnerable IDPs out of the poverty trap.  There is a consensus among policy makers and major stakeholders (interest groups, NGOs and donors) on the need to reform the IDP allowance, without touching the political status (“right to go back in the occupied territory”). The aim of the new reform is to switch from a status-based IDP allowance to a need-based allowance, in coordination with social services and allowances distributed by the Georgian State and municipalities.

In 2017, the government has identified 4 sceneriis  for reforming IDP status and switch smoothly from a status-based allowance to a needs-based allowance. The “IDP Allowance Reform Draft Document” from the Ministry of Internally Displaced Persons from The Occupied Territories, Accommodation and Refugees of Georgia published in early 2017 displayed for 4 options for reform:

- Reduction of the 1250 GEL margin

This would go further than the 2014 reform, with different options to include or exclude some individuals depending on the overall household revenue;

- Transferring all IDPs to the TSA (and suppressing the IDP allowance)

This would mean cutting the IDP allowance and registering IDPs to the SSA, assess their situation against TSA criteria. One major issue is that it is politically sensible : in its current form, the IDP allowance is an allowance for a lifetime and TSA is subject to reevaluation following an assessment of the vulnerability score.

The following table displays the IDPs receiving the TSA (and therefore refusing the IDP Allowance, because there are incompatible) and thee expenditures. We assume the figures are from 2016. However it is not know to which year(s) “Future Expenditures” are referring to.

Table 1. IDPs evaluated by the Social Service Agency

| Categories per Family Rating Scores | Number of Evaluated IDPs |  | Social Assistance Beneficiary |  | Current Expenditure |  | Future Expenditure |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Social Service Agency Family Evaluation Method | New | Old | New | Old | New | Old | New | Old |
| Below 30,001 scores – 60 GEL/person monthly | 11,319 | 16,451 | 9,313 | 12,680 | 6,705,360 | 7,912,320 | 8,149,680 | 10,265,424 |
| 30,001-57,000 Scores – 50 Gel/person monthly | 12,959 |  | 9,263 |  | 5,557,800 |  | 7,775,400 |  |
| 57,001-60,000 Scores – 40 Gel/person monthly | 1,393 | 3048 | 402 | 0 | 192,960 | 0 | 668,640 | 0 |
| 60,001-65,000 Scores – 30 Gel/person monthly | 2,402 |  | 273 |  | 98,280 |  | 864,720 |  |
| 65,001-100,001 GEL - 10 GEL per Family member under 16 (2,900 persons) | 11,509 |  | 50 |  | 6,000 |  | 310,800 |  |
| 100,001-150,000 scores and no accommodation received | 6,374 | 8,650 | 0 | 0 | 0 |  | 0 |  |
| Total | 45,956 | 28,149 | 19,301 | 12,680 | 12,560,400 | 7,912,320 | 17,769,240 | 10,265,424 |
| All in Total | 74,107 |  | 31,981 |  | 20,472,720 |  | 28,034,664 |  |

Source : IDP Allowance Reform Draft Document, Ministry of Internally Displaced Persons from The Occupied Territories, Accommodation and Refugees Of Georgia

In total, 35% of IDPs applied the social service agency, and 26% of them received the amount of scores necessary to be granted the TSA, but only 11% receives the TSA and the remainder of them prefers to have IDP allowance.

It must be taken into consideration that approximately 80,000 IDPs are removed from the database of socially vulnerable people of the social service agency due to various reasons, with the inclusion of the inability to satisfy the established criteria.

IDPs living in the occupied territories do not have a right to register for the TSA program, because one of the main terms for the participation in the named program is to indicate the address of a permanent residence, where the social address can visit and verify respective data. When we speak about the conditions of the socially vulnerable IDPs, IDPs living in the occupied territories are automatically excluded.

- Dividing IDPs by Generations

Monthly 45 GEL IDP allowance will be maintained for only those IDPs who have personally been internally displaced, and will be removed from the others (i.e. “second generation” IDPs or subsequent). Currently, the number of IDPs of second generation (who have not been personally internally displaced and were granted the status by birth of an IDP parent) is approximately 89,000. Approximately 75,000 of them receive IDP allowance, which costs 40,000,000 GEL annually. Estimates from the Ministry on excluding second-generation IDPs of the IDP allowance and enrolling some of them to the TSA system forecast that 34,000,000 GEL will be saved annually.

- Mixed model

The mixed model is based on IDP’s subjective assessment of their conditions and satisfaction with the social services and allowances provided to them. In this case all IDPs will be evaluated by the Social Service Agency and the scores assigned will be used for the ranking of social assistance based on the fact, whether the IDP family is satisfied with the DHS program.

| IDPs to be Satisfied with Accommodation | Currently Receive | Applied Measures | Will Receive |
| --- | --- | --- | --- |
| I. Below 30,001 scores | 60 GEL | Double | 120 GEL |
| II. 30,001-57,000 scores | 50 GEL | Double | 100 GEL |
| III. 57,001-60,000 scores | 40 GEL | Double | 80 GEL |
| IV. 60,001-65,000 scores | 30 GEL | Double | 60 GEL |
| V. 65,001-100,000 scores | 45 GEL | Maintain | 45 GEL |

Source : IDP Allowance Reform Draft Document, Ministry of Internally Displaced Persons from The Occupied Territories, Accommodation and Refugees Of Georgia

# Section 2. First recommendations

The project presents many opportunities for all stakeholders which have been confirmed during the inception phase. ADF and Expertise France project team are committed and engaged in finding solutions at each step of the process while focusing on achieving project results.

## 2.1 Pillar 1: Enhancing social support to Persons With Disabilities

## Starting point/first recommendation: Using UNICEF / GASW’s experience in training professionals (functional assessment specialist, case-manager and medical coordinator) and adapt a web application in defining methodology for second pilot region.

In order to explore the disability status determination system from the perspective of persons with disabilities, UNICEF conducted the focus groups with PWD and parents of children with disabilities. The results demonstrated that the status determination system does not consider active participation of persons with disabilities or legal representatives of children with disabilities.

UNICEF in strong collaboration with the MOLSHA and national and local partners (Georgian Association of Social Workers and disability activists) will arrange regular meetings with disability community to inform them about the goal and objectives of the pilot and engage them in the pilot. In order to provide the functional assessment of children, they developed a new instrument based on the questionnaire of the WHO – Model Disability Survey with 80-item for assessing the functional ability of children from 2 to 18.

Thus, it is an opportunity to continue and improve these tools and methodology, which will also facilitate the comparison of the results obtained.

Second recommendation: Including needs and life projects in the questionnaires as well as adding compensation and habitation services.

Questionnaires must also enable us to identify the compensation needs that are not or poorly covered and to prioritize them in terms of public policy. Indeed, the paradigm shift must allow the project team to study the answers with regard to the life project and available capacities of an individual. Thus, the solutions must no longer be based exclusively on rehabilitation but also on the empowerment of new skills or abilities to enable effective inclusion.

Third recommendation: Building links between collected data on functional assessment and data already collected by the Ministry through individual identification numbers.

For the impact assessment purpose it is important to compare the data on medical attribution of disability and the data on functional assessment. According to our information, the individual data is collected on the region level about medical attribution. This data is used in order to provide statistical information per region. In Georgia there is an individual identification number which can be used in order to identify a person.

It is essential, in order to understand the impact of the functional evaluation reform, to have impact measurement elements available. These elements of measurement should enable the project team to shed light on the differences in access to the status of a person with a disability.

## 2.2 Pillar 2: Ensure affordable and quality-driven healthcare

Effectiveness and efficiency of universal healthcare

In response to the information collected from various document before and during the inception mission, analysis of the situation and interviews conducted, the following recommendations were presented to the MOLSHA during the mission debrief meeting:

First recommendation: Alignment with ongoing PHC reform efforts and strategy of strategic purchasing is crucial e.g. FM versus rural doctor, overall payment mechanism for PHC, referral mechanisms, prescription rights, overall contracting procedures for strategic purchasing, etc.

Second recommendation: Clear definitions of what is understood as performance i.e. what should be incentivized with contracting in PHC should be developed as a preliminary activity for development of performance-based contracting.

Third recommendation: Ideally, a stepwise introduction of performance-based contracting should be adopted:

  - First, review of potential options for design of performance payment mechanisms and decision e.g. target institutions or professionals, positive or negative incentives, pay for activities or outcomes, specific diseases or general, based on absolute targets or relative improvement etc.

  - Second, data collection and analysis of the performance in place to start performance measurement (link to eHealth and SSA financial data).

  - Third, design contracting mechanism and process for performance-based contracting.

MOLSHA did agree with the situation analysis and recommendations presented in the debrief meeting and above. However, strong suggestion was made to focus on the second step above, especially on review of available data and even more specifically support to development of a potential indicator framework to measure performance of primary care taking into account it’s possible use in a future PHC payment scheme to be developed in the future. This strong suggestion was largely influenced by MOLSHA discussions with WHO on their technical assistance and overall groundwork already done or planned in the context of the national strategy on strategic purchasing.

Improving Mental Healthcare

In response to the information collected from various document before and during the inception mission, analysis of the situation and interviews conducted, the following recommendations were presented to the MOLSHA during the mission debrief meeting:

- Need for a global approach with a planning based on an analysis of the needs for deinstitutionalization and mainstreaming of quality care and soft therapies, and reliable data;

- Strengthen the monitoring mechanisms for the Ministry (improved quantitative data, quality standards for different types of institutions and measurement of outcomes), including human rights

- Bridge the legislative gaps: monitoring clause, psychological therapies, etc… (capitalize on recommendations from the informal coordination group of CSOs and Ministry)

MOLSHA did agree with the situation analysis and recommendations presented in the debrief meeting and above. However, strong suggestion was made to provide the Ministry with an operational and budgeted mental health care strategy (A221) and to give tools to the Ministry to monitor indicators, performance and contracting with mental healthcare suppliers (A222). There are complementary approaches to use with activity A211 (Performance-based contracting) and A212 (e-health and monitoring tools).

## 2.3 Pillar 3: Supporting the Ministry in identifying and passing the IDP allowance reform

In response to the information collected from various document before and during the inception mission, analysis of the situation and interviews conducted, the following recommendations were presented to the MOLSHA during the mission debrief meeting:

- No need of technical assistance in housing and reallocating IDPs from CCC to CC;

- Technical assistance should focus on the IDP allowance reform in 1 )supporting the ministry in identifying the best reform scenario with evidence-based arguments; and 2) supporting the communication of the reform

# Section3. Next steps of the project

## 3.1 Pillar 1: Enhancing social support to People With Disabilities (PWD)

The next steps to be undertaken are presented in Annex 3 “Planning of working days per activity” and Annex 4 “Methodology for piloting the disability assessment in Samtskhe Javakheti region”:

- Delivering information and training to staff:

- One day workshop in Akhaltsikhe divided into three parts:

- Presentation of the pilot project and functional evaluation approach

- Discussion on medical and social programs for PWD

- Presentation of best practices including French experience

- Recruitment of a local expert to assess local needs

- Setting up contract with service provider for training of 4 Functional Evaluation Specialists, 4 Case Managers and 3 Medical Coordinators.

- Advertisement of job descriptions and creation of a recruitment commission

- Interviews of candidates in the pilot region

- Purchase of tablets

- Training to centres staff

Timeline: June – September 2019

Working days: 27 WD for international experts; local experts; Salaries for local staffs

- Mobilizing specialists from Adjara pilot to share experiences with Samtskhe - Javakheti

Timeline: September 2019

- Testing phase for implementation of new assessment instruments

Timeline: October 2019 – October 2020

Working days: 60 WD for international experts; local experts

- 1st evaluation mission

Analysis of three month collected data.

International experts mobilized: Andrei Tretyak, Michel Villac and Yannick Deimat

Working days: 15 WD for international experts; local experts

- 2nd evaluation mission

Mid-term analysis of six month collected data

Timeline: April 2020
International experts mobilized: Andrei Tretyak, Michel Villac and one specialist of disability scaling

Working days: 15 WD for international experts; local experts

- 3nd evaluation mission

Final evaluation and impact assessment

Timeline: November –December 2020 (2 missions)
International experts mobilized: Andrei Tretyak and Michel Villac

Working days: 15 WD for international experts; local experts

In order to complete assessment impact due to the reform of PWD assessment, it seems necessary to collect additional information. This information will allow the measurement of potential impact over individual way of life and costs or priorities of public policies.

## 3.2 Pillar 2: Quality healthcare

Component 2.1 – Improve the effectiveness and efficiency of universal healthcare and other programs

A 2.1.1 – Primary Health Care financing and contracting

The initial next steps to be undertaken that were presented to the MOLSHA during the mission debrief meeting were the following with equal resource allocation for each:

- Clarification and agreement on definitions of performance in PHC,

- Design options for performance-based contracting in PHC,

- Review of available data on PHC performance and list of potential indicators for use in Georgia, and

- Design of contracting mechanisms along with operational standards for performance-based contracting)

However, based on the position and feedback of the MOLSHA, the revised list of activities prioritizes the third proposed step on information and indicators:

- Preparatory work
Defining or review of performance goals for PHC in Georgia along with model of performance-based contracting selected for Georgia and update on current status of the parallel policy developments in health financing and service delivery 
Timeline: August/September 2019
Working days: 3 WD for international expert

- Work with data and indicators
Review of international examples on performance measurement in PHC, review of availability of data for measurement of performance in PHC in Georgia, policy options for additional data collection if necessary
Timeline: August/September 2019
Working days: 10 WD for international expert, 20 WD for local expert

- Implementation support
Support to MOLSHA and SSA on design and implementation of data collection for performance measurement in PHC as well as on use and analysis of the collected data and indicator results
Timeline: January/February 2020
Working days: 5 WD for international expert

Overall deliverable: a summary paper on indicator framework and measurement of performance in PHC

Component 2.2 – Improving mental healthcare

A2.2.1 – Establishing the strategy for comprehensive mental health care and deinstitutionalization

The TA team has identified potential partners for coordinating activities and mobilizing stakeholders (Ilia State University, Curation Foundation, Open Society Foundation), as well as carrying out the epidemiological survey (Geostat, Georgian Opinion Research Business International).

- Mapping existing facilities and services

Timeline: June/July 2019

Working days: 10 WD for international expert; 10 WD for local experts

Interim deliverable: Methodology for epidemiological survey (including questionnaire and test)

- Implementation of the epidemiological survey

Timeline: September to December 2019

Working days: 60 WD for local experts

Interim deliverable: Questionnaires filled and tests run

- Analysis of results and draft of the report (10 IWD; 5 LWD)  report jan/feb 2020

Timeline: February 2020

Working days: 10 WD for international expert; 5 WD for local experts

- Proposition of a range of facilities to meet these needs, and of their repartition on the territory

Timeline: October 2019

Working days: 10 WD for international expert

Interim deliverable: Report on the repartition of patients

- Proposed strategy on planning of the structures according the epidemiological report, including financial impact (InW 20; 25 LWD)

Timeline: April 2020

Working days: 20 WD for international expert ; 25 WD for local experts

Final deliverable: Final report with objectives, action plan, timeline and budget: Strategy for mental health care in Georgia and deinstitutionalization

A2.2.2 – Strengthening Monitoring mechanisms for the Ministry

This activity will be linked with activities A211 (performance-based contracting) and A212 (IT improvement and data collection) and their outcomes, especially regarding monitoring of performance in mental health institutions.

- Mapping of existing practices in Georgia and presentation of international best practices

Experts will assess monitoring tools of the ministry and provide recommendations based international standards (set of indicators regarding performance to be defined together) and best practices. A set of indicators, tools (including a dashboard) and  solutions to collect, store and analyze data from mental health institution can be developed together with the ministry.

Timeline: October/November 2019

Working days: 8 WD for international expert; 9 WD for local experts

Interim deliverable: Presentation to the Ministry

- Preparation of recommendations to the stakeholder group (NGO, donors, Ministry)

The stakeholder group is an informal set of different parties involved in mental health care (Ministry, CSOs, donors, …). They meet on a regular basis of different settings and without meetings being systematic. They are a platform for coordinating, even though quite an informal one and not systematized.

A set of recommendations, including in engaging and strengthening CSOs and other partners in monitoring mental health care in Georgia, will be presented to the stakeholder group.

Timeline: January 2020

Working days: 8 WD for international expert; 9 WD for local experts

Interim deliverable: Presentation to the stakeholder group

- Drafting of final report and presentation

Timeline: March 2020

Working days: 9 WD for international expert; 12 WD for local experts

Final deliverable: Final report on monitoring quality care and human rights. Tools are used by relevant functions in the Ministry.

A2.2.3 – Improving the legal framework

Experts will assess the legal loopholes in the existing legislation and provide the ministry with recommendations.

Timeline: February 2020

Working days: 5 WD for international expert; 15 WD for local experts

Final deliverable: Report on recommendation to the Ministry and stakeholder group

## 433 Pillar 3 : Supporting the Ministry in identifying and passing the IDP allowance reform

A 3.1 – Impact Analysis of the reform scenarii

The mission met with the Ministry, other donors and NGOs active on IDP issues. It was agreed with the Ministry that Expertise France can mobilize expertise in order to make impact assessments (including a policy gap analysis) of the 4 identified reform scenarii (and not ruling out making small amends to them).

The goal of this impact analysis is to assess the number of IDP impacted by the different reform scenario and those who would lose their benefits, be eligible to other social services/allowances and assess the costs of the reform. Based on this impact assessment, decision-makers in the Ministry would be provided with evidence-based data and would have more knowledge to back their decision in reforming the IDP allowance system.

Timeline: January 2020

Working days: 15 WD for international expert; 10 WD for local experts

Deliverable: Impact analysis of the 4 reform scenarii

Activity 3.2 – Elaborate a communication strategy for the IDP reform

Once the Ministry has agreed to a reform scenario and has decided to go along with it, it is important to have a communication strategy for the reform, especially since it’s a very sensible one. Political and social changes meet stark opposition, especially with politically loaded topic such as displacement and social allowances. However, the key to a successful reform, is its transparency and its evidence-based communication.

Policy-makers and decision-makers need to gather allies and momentum to get their bill voted in Parliament. A communication strategy for passing the reform will target different interest groups and the public opinion and will mobilize different means of communication and public relations. It was decided with the Ministry of IDPs, Health, Labor and Social Affairs that Expertise France can assist the Ministry in elaborating the communication strategy for the IDP allowance reform.

Timeline: March 2020

Working days: 10 WD for international expert; 15 WD for local experts

Interim deliverable: Communication strategy

Conclusion

Though the scope of this technical assistance is wide, there are some common features in the different activities of the project: more inclusiveness for people with disabilities and for people suffering from mental disorders; more efficiency and cost-effectiveness in public policies related to health and to internally displaced people in Georgia.

The inception phase was an opportunity for most of the project stakeholders to meet and to agree on strategic objectives, actions and timeframe. The discussions in MOLSHA especially shed the light on Ministry’s priorities. Based on these priorities, project’s activities were fine-tuned and decisions were made about the next steps of the project for the coming year. The main objective of the inception phase was to set a consensus on the final outcomes that Georgian and international partners want to achieve and to establish a realistic yet ambitious agenda for the future activities.

A very positive aspect of the discussions held in the Ministry and in public and private institutions was the participative approach that was used in meetings and written communication. Indeed, at various levels and from different perspectives, stakeholders have brought their input and shared their experiences in order to define precisely the project’ methodology and expected results. This specific process will contribute to reinforce the project’s legitimacy amongst external and internal partners as well as the involvement of politicians, civil servants and the professionals implied in this technical assistance.

-------------------------

Annexes

Approximately 1 psychiatrist for 60 to 70 inpatients

There are only 4 in Georgia (Kutaisi, Batumi, Rustavi, Tbilisi)

Data provided by the Social service agency