## Slide 1: 0
PROGRAMME REVIEW FOR REPRODUCTIVE, MATERNAL, NEWBORN, CHILD AND ADOLESCENT HEALTH
Guidance Document
December 2017

## Slide 2
  I. Introduction
    1.1 What is a programme review for RMNCAH?
    1.2 Objectives of an RMNCAH programme review
    1.3 Scope of RMNCAH programme review
  2
  3
  4
  4
  II. Preparation for RMNCAH programme review
    2.1 Who is involved?
    2.2 Schedule of activities
  5
  5
  6
  III. Information requirements
    3.1 Data collection
    3.2 Data quality
    3.3 Data tool for RMNCAH Programme Review
  7
  7
  9
  9
  IV. Review and analysis of findings
    4.1 Analytical framework
    4.2 Methodology for analysis and recommendations
    4.3 Programme Review Workshop overview
    4.4 Programme Review Workshop process
  10
  10
  11
  12
  13
Contents
  Annexes
    A.1 Action areas of the Global Strategy for Women’s,
    Children’s and Adolescents’ Health
  17
  #
  V. Findings and recommendations
    5.1 Presenting findings and recommendations
    5.2 Documenting findings and recommendations
    5.3 Use of findings and recommendations
  14
  14
  15
  16

## Slide 3
  The purpose of this guide is to assist countries in planning and managing an integrated review of Reproductive, Maternal, Newborn, Child, and Adolescent Health (RMNCAH) programmes and in reviewing the status of implementation of the Global Strategy for Women’s, Children’s and Adolescents’ Health. This guide provides a recommended approach for conducting RMNCAH programme reviews but is not intended to be prescriptive in that the processes should be adapted to suit the needs of the country or programmes where it is being used.
  The guide helps to assess the results that RMNCAH programmes have achieved, identify gaps in intervention implementation, and provide recommendations and solutions to better improve the health status of women, children, and adolescents. It also assists in assessing whether milestones for the implementation of the Global Strategy for Women’s, Children’s and Adolescents’ Health (set for 2016-2017) have been met and to set objectives to achieve the targets proposed.
  The main audience for this guide includes:
  National and sub-national level Programme Managers and Officers from Reproductive, Maternal, Newborn, Child, and Adolescent health who are involved in planning, implementing, and monitoring these programmes within a Ministry of Health;
  Programme Managers and Officers in related programmes in the Ministry of Health or other Ministries;
  Non-governmental, private sector and international partners involved in planning, implementing, and funding RMNCAH programmes.
  To complement this document are a Facilitator’s Guide and Data Tool.
I. Introduction

## Slide 4: Figure 1. Where does the RMNCAH Programme Review fit into planning and management cycles?
The Reproductive, Maternal, Neonatal, Child and Adolescent Health Programme Review is a process for assessing mid- and/or end-term country progress in improving women’s, children’s and adolescents’ health. A Programme Review is conducted on a periodic basis as part of the regular RMNCAH programme planning and implementation cycle.
A Programme Review is conducted regularly (every 2 to 3 years) and is most useful if coordinated with other ongoing health sector review and planning activities; these could include strategic planning, annual reviews of Country Accountability Frameworks, and annual or bi-annual district review or planning exercises. Thus a programme review constitutes an integral part of a programme planning and management cycle occurring periodically as mid-term and end-term activities. Ideally, the programme review should be incorporated into the existing strategic health and annual plans and processes.
1.1 What is a programme review for RMNCAH?
  RMNCAH Programme review as part of end-term review
  Review activities and outputs of programme(s)
  (Every 1-2 years)
  Develop strategic plan
  (Every 5-10 years)
  Develop implementation plan (Every 1-2 years)
  RMNCAH Programme review as mid-term review
Strategic planning cycle (5-10 years)
Implementation planning cycle (1-2 years)
  Manage implementation (Ongoing)
  Evaluate health impact and intervention coverage e.g. DHS, MICS (Every 5-10 years)
  Develop new strategic plan
  (Every 5-10 years)

## Slide 5
  The purpose of the RMNCAH Programme Review is to assess progress towards the goals and objectives of the RMNCAH programme(s).
  Objectives:
To assess how well the RMNCAH programme(s) implemented their plans and identify successes, lessons and good practices;
To identify problems and gaps, facilitating factors, emerging issues, opportunities, lessons, threats, etc. so as to determine solutions;
To align the programmes’ priorities, guidelines with the Sustainable Development Goals (SDGs) and Global Strategy for Women’s, Children’s, and Adolescents’ Health and other regional and global priorities;
To develop recommendations including priority actions to be taken, resources needed and responsible persons/organizations needed to implement them so as to improve implementation;
To decide on the next steps for implementing the recommendations including utilization in revision/development of strategic plans.
1.2 Objectives of an RMNCAH programme review
1.3 Scope of RMNCAH programme review
The Programme Review process is developed based on the following principles:
Focus on proven effective, high impact interventions;
Address all the target populations of RMNCAH: women of reproductive age, pregnant women though childbirth, newborns, infants and children up to age 5 years; adolescents as well as cross cutting and multi-sectoral areas such as nutrition, WASH, etc.
Use a continuum of care approach:
  Life stages: Pre-pregnancy, pregnancy, childbirth, newborn, infancy, childhood, adolescence and post-reproductive;
  Levels of the health system: Household and community, first-level health facilities, referral facilities.
Use the action areas of the Global Strategy for Women’s, Children’s and Adolescents’ Health*
  To access the full Global Strategy for Women’s, Children’s, and Adolescents’ Health (2016-2030): http://globalstrategy.everywomaneverychild.org/

## Slide 6
II. Preparation for RMNCAH programme review
  Planning for a programme review in advance is a key to its success. Preparation includes defining the scope of the review, selecting facilitators and participants, securing funding, preparing the content and logistics. Once resources are secured, it is important to align with other planning events that are ongoing in a country. If relevant RMNCAH data collection processes are being conducted, they should ideally be completed prior to the programme review.
  Key factors for a successful programme review include:
  Strong commitment from the MoH and partners to conducting an RMNCAH programme review
  Existence of reliable data and information on RMNCAH intervention coverage and activity outputs
  Full support of the MoH and partners, including willingness to release staff and adequate funding to cover costs for all steps of the review process
2.1 Who is involved in the programme review?
  The programme review process can benefit from the selection of a Programme Review Coordinator from the Ministry of Health to initiate and follow through on conducting the process. The Coordinator brings together other RMNCAH stakeholders in the country to create a Programme Review Committee (or task force).
  Membership of the Committee ideally includes professionals (from within the MoH and among partner organizations) who are familiar with RMNCAH issues in the country and are able to devote the time needed for the review process. The Committee undertakes preparations for all stages of the programme review process and likely serve as facilitators during the review workshop. Where applicable, an existing Technical Working Group could take up the roles of the Programme Review Committee.
  The Programme Review Workshop brings together a wider group of RMNCAH stakeholders including different cross-cutting and multi-sectoral departments of the MoH, non-health ministries, NGOs, professional associations, academia, and donors.
  Responsibilities of the RMNCAH Programme Review Committee:
Prepare for the programme review including defining the scope of the review, selecting facilitators and participants, preparing the content and logistics
Organize the review workshop
Document the review’s findings and recommendations
During, or immediately after, the workshop, present the findings and recommendations of the review to senior representatives from the MoH and other partners and stakeholders

## Slide 7: Figure 2. Suggested activity flow for RMNCAH Programme Review
2.2 Schedule of activities
  Preparation for RMNCAH programme review
  Data collection
  Analysis and review
  Implementation of recommendations and solutions
  Define the purpose, scope, and objectives of the review
  Identify and mobilize resources
  Select Programme Review Coordinator
  Form Programme Review Committee
  Prepare the content and logistics, including reviewing and updating Data Tool with relevant indicators
  Collect and/or analyze data to meet information requirements for the review:
  Surveys
  Routine data
  Key informant interviews and/or focus groups
  Field visits
  Client perspectives
  Assess data quality
  Confirm and validate information
  Enter data into Data Tool
  Programme Review Workshop
  Review information to prioritize intervention packages for in-depth analysis
  Discussions and group work to identify the main problems of the programme(s)
  Formulate solutions and recommenda-tions on priority actions to take
  Development of report on the findings and recommendations of the Programme Review
  Plan for implementation of recommendations and solutions from the Programme Review
  Preparation for the RMNCAH Programme Review is an important first step during which the scope, objectives and timeline for the process must be well defined. In addition, clarification on who will carry out the review, what information is needed to conduct the review and how it will be collected and analyzed is necessary to inform how the outcomes of the review will be reported and how the recommendations will be implemented. The amount of time necessary to complete the activities in preparing for and conducting a Programme Review will vary based on the country context.

## Slide 8: Figure 3. Examples of Reference documents and data sources for RMNCAH Programme Review
III. Information requirements
  Information gathered for the Programme Review is essential for informing the programmes on how they are performing against their own goals and objectives and against the targets set in the Global Strategy for Women’s, Children’s and Adolescents’ Health. This information will show to what extent the RMNCAH programmes have improved the health status of women, children, and adolescents. It is important to select relevant indicators and use data that reflects service delivery and health status during current period under review. Presentation of the information should be clear and easy to understand.
3.1 Data collection
  Data necessary for an RMNCAH Programme Review comes from a variety of sources. National and global reference documents are necessary for reviewing existing goals and objectives. These should be used together with the most recent quantitative data and qualitative narratives to assess intervention coverage and identify disparities and the most critical needs of women, children, and adolescents. See Figure 4 for key indicators from the Global Strategy for Women’s, Children’s, and Adolescents’ Health.
  REFERENCE DOCUMENTS
  National documents
  Strategic Plans
  RMNCAH Policy statements
  Most recent work plans (from all levels)
  Past programme review reports
  Annual training summaries
  Global documents
  Global Strategy on Women’s, Children’s and Adolescent Health
  Indicator and Monitoring Framework for the Global Strategy
DATA SOURCES
Survey data
Population surveys
Health Facility Assessments
Routine monitoring data
HMIS
LMIS
Qualitative data
Key informant interviews/focus groups
Field visits
Client perspectives

## Slide 9: Figure 4. Key indicators from the Global Strategy
    3.1 Data collection con’t.
  Priority indicators for RMNCAH will vary by country, however inclusion of the key indicators from the Indicator and Monitoring Framework for the Global Strategy for Women’s, Children’s, and Adolescents’ Health (2016-2030)* is important for consideration in the RMNCAH Programme Review.
Objectives | Key Indicators
SURVIVE End preventable deaths THRIVE Ensure health and well-being TRANSFORM Expand enabling environments | Maternal mortality ratio Under-5 mortality rate Neonatal mortality rate Stillbirth rate Adolescent mortality rate Prevalence of stunting among children 5 under years of age Adolescent birth rate (10-14, 15-19) per 1000 women in that age group Coverage index of essential health services, including for infectious diseases, diseases, noncommunicable diseases and RMNCAH: family planning, antenatal care, skilled birth attendance, breastfeeding, immunization, childhood illnesses treatment Out-of-pocket health expenditure as a percentage of total health expenditure Current country health expenditure per capita (including specifically on RMNCAH) financed from domestic sources Laws and regulations that guarantee women aged 15-49 access to sexual and reproductive health care, information and education Proportion of population with primary reliance on clean fuels and technology Proportion of children under 5 years of age whose births have been registered with a civil authority Proportion of children and young people in schools with proficiency in reading and mathematics Proportion of women, children and adolescents subjected to violence Percentage of population using safely managed sanitation services including a hand-washing facility with soap and water
  *To access the full Indicator and Monitoring Framework: www.who.int/life-course/publications/gs-Indicator-and-monitoring-framework.pdf

## Slide 10
3.2 Data Quality
  Programme Reviews rely on existing data sources, but can be complemented by key informant interviews/focus groups, field visits, and client perspectives, which can additionally serve to confirm or complement what is found in the quantitative data. The information used must be as reliable and accurate as possible, which usually depends on the quality of the information systems.
  Key considerations for data quality include:
  Are the data from reputable national and international data sources?
  Have the data been validated through global reporting mechanisms?
  Have data quality assessments been conducted? Are routine data quality audits being done?
  Have the data been validated by national stakeholders?
  Availability and quality of data are themselves important findings of the review process.
3.3 Data Tool for RMNCAH Programme Review
  Data/information collected for the RMNCAH Programme Review should be entered into the Data Tool in advance of the Programme Review Workshop. The Excel-based tool is flexible for country-specific adaptation and linkages to Health Sector Strategic Plan and/or Health M&E Plan that allows space for optional information for analysis and review, such as baseline values, targets or sub-national (e.g. provincial or district) data. The Data Tool is pre-populated with suggested RMNCAH indicators, but should be reviewed and adapted to match country priorities. Indicators that are not relevant in the country may be modified or deleted; indicators that are priority for the country may be added.
  There are six steps to complete and use the tool:
  Adapt indicators (impacts, outcomes, etc.) to country needs
  Populate indicators with available data
  Determine status of intervention packages
  Select intervention packages for in-depth review
  Adapt the in-depth review
  Conduct the in-depth review
  See Data Tool for detailed explanation.

## Slide 11: Figure 5. Suggested Analytical Framework for RMNCAH Programme Review
  The objective of analyzing the information collected and presented in Data Tool for the Programme Review is to understand the performance of the RMNCAH programme(s) and make recommendations for moving forward. Review and analysis will help to answer:
  Which RMNCAH intervention packages were implemented and where? How well were they implemented?
  What are the inputs, outputs, outcomes and impacts and mechanisms in place for intervention implementation over a cyclical period?
  What are the RMNCAH programmes’ most important problems that are causing gaps in implementation?
IV. Review and analysis of findings
  Results
  Gaps and challenges
  Recommendations and solutions
  Programme readiness
  System readiness
  Demand readiness
  Cross-cutting
  Review of the information organized in the Data Tool will help to identify the relative performance of high impact intervention packages. Underperforming (and possible other priority) intervention packages should be analyzed using a more in-depth manner to identify gaps and bottlenecks and to formulate solutions through a well-defined analytical framework.
4.1 Analytical framework
  Programme readiness
  Policy, Standard Treatment Guidelines, Training curriculum, Defined indicators, Essential Medicines/Equipment List, Supervision forms
  System readiness
  Where are packages implemented? Are staff trained; at which levels? Are commodities and/or equipment available; at which levels? Is supervision undertaken; at which levels? What is the quality of the data in the health information system; at which levels?
  Demand readiness
  Communication, Awareness, Advocacy
  Cross-cutting
  Financing, Staff availability, Functional infrastructure
  Results
  Coverage, Utilization, Quality

## Slide 12
    4.2 Methodology for analysis and recommendations
During the RMNCAH Programme Review Workshop, facilitators will guide the participants in reviewing the information collected and presented in the Data Tool. Priority intervention packages (e.g. high impact with poor performance) will be analyzed in sub-groups under the lens of the defined Analytical Framework for the review.
These groups may be split to match how the various programmes that make up RMNCAH are organized in the Ministry of Health. One example of organizing the groups is:
Group 1a: Sexual and Reproductive Health
Group 2a: Maternal and Newborn Health, including PMTCT
Group 3a: Child Health
Group 4a: Adolescent Health
During the course of the Workshop, the groups can be re-organized to facilitate discussions on cross-cutting issues such as:
Group 1b: Human resources
Group 2b: Finances
Group 3b: Supply chain and infrastructure
Group 4b: Strategy
To start, groups can review the available quantitative and qualitative indicators across the respective determinants (e.g. policy, commodity availability, financial access, quality of care, etc.) within each intervention package. Emphasis should be placed on indicators with outstanding gaps to target. The information in the Data Tool is limited in scope, so it acts as a starting point for discussion.
The expertise within each group is critical for synthesis and interpretation of data as well as feasibility in current health system settings. Based on available data, experience and existing implementation challenges, groups will develop feasible recommendations (short- and/or medium-term) for strengthening each of the priority intervention packages.
The groups will discuss their findings in plenary sessions, where other groups may ask questions and contribute to forming recommendations. Plenary sessions also offer an opportunity to analyze cross-cutting and multi-sectoral issues.

## Slide 13
4.3 Programme Review Workshop overview
Participants
Stakeholders from all levels of the health system who are knowledgeable about RMNCAH programmes and issues, and include cross-cutting and multi-sectoral departments of the MoH, non-health ministries, NGOs, professional associations, academia, multilateral and bilateral partners and donors. Ideally, there should be a mix of experts with constituencies from Reproductive, Maternal, Newborn, Child and Adolescent Health and broader health systems from all levels represented in each working group.
Content and process
Participants will review and analyze progress on the health status of women, newborns and children and adolescents; intervention coverage at all levels; and programme implementation at all levels of the health system. Facilitators will lead participants through a structured process to review documents and analyze data (which will be collected and entered into Data Tool prior to the Workshop) in order to identify progress made and areas that need to be strengthened.
Outcomes
Facilitated plenary discussions and structured group work will be used to identify the main problems the programmes are having and suggest solutions and formulate recommendations on priority actions to take at all levels of the health system. These solutions and recommendations will be synthesized into the Programme Review Report.
  For details of preparation and facilitation of Workshop, see Facilitator’s Guide for RMNCAH Programme Review.
  Principles of the RMNCAH Programme Review workshop:
Reviews progress in order to identify the RMNCAH programmes’ most important problems, bottlenecks, gaps and formulate solutions to address them at all levels
Uses available data on health status, intervention coverage and programme outputs at all levels
Is a multi-stakeholder process which actively involves participants in making assessments and recommendations for all levels

## Slide 14: Figure 6. RMNCAH Programme Review Workshop: Key steps
4.4 Programme Review Workshop process
The Programme Review Committee and workshop facilitators will agree upon a detailed agenda for the Programme Review Workshop. While the agenda will be adapted to the structure and needs of the programme(s), the elements in Figure 6 should be addressed throughout the workshop.
Early in the workshop each working group will review data organized in the Data Tool and other information collected in advance to prioritize intervention packages for in-depth analysis.
For each step, it is suggested the workshop facilitators introduce the content in plenary and then break the participants into group work sessions. Following the group work, findings should be shared in plenary.
By the end of the workshop, participants will formulate solutions and recommendations on priority actions to take that will be documented and presented to senior representatives from the MoH during or soon after the workshop.
  1. To what extent have the RMNCAH programmes improved the health status of women, children, and adolescents?
  Review goals, objectives, targets and baselines to identify the most critical needs of women, children, and adolescents
  Outcome: Assess whether RMNCAH programme(s) is/are making positive, negative, or no progress in improving health status
  Review intervention coverage in terms of progress towards achieving target impact
  Outcome: Identify underperforming intervention packages for in-depth analysis.
  2. Which RMNCAH intervention packages were implemented and where? How well were they implemented?
  Review indicators of availability, access, quality and demand – available information plus personal knowledge and experience
  Outcome: Identify achievements and gaps in implementation of each package
  Review availability of packages – geographic areas and levels of health system
  Outcome: Identify areas and levels where packages are implemented and where improvement is needed
  3. What are the RMNCAH programmes’ most important problems that are causing gaps in implementation?
  Outcome: List problems causing implementation gaps and identify most important ones
  4. What are solutions and recommendations for the most important problems?
  Outcome: Propose solutions that address causes of main problems and formulate recommendation on how these solutions should be carried out

## Slide 15
V. Findings and recommendations
Reporting on the findings of the Programme Review is a key step to ensuring that the recommendations are implemented. Actions taken from the review should be high impact, evidence based, concrete, specific, realistic, time bound and achievable. They should also be prioritized, grouped and sequenced in a logical and feasible plan. Using the findings of the Programme Review to inform action requires the report to be endorsed and disseminated by the MoH and shared with wider RMNCAH stakeholders.
5.1 Presenting findings and recommendations
A presentation on the findings and recommendations of the Programme Review should be planned by the Programme Review Committee. The presentation should occur at the end or soon after the Workshop.
This meeting should bring together MoH representatives, partners and other RMNCAH stakeholders.
Ministry of Health Senior Management should be debriefed before all other stakeholder groups so as to gain consensus on what will be shared with a wider group of stakeholders
Programme Review Committee spearheaded by the multi-stakeholder team will prepare a summary in the form of a power point for debriefing each of the stakeholder groups.
The Coordinator and members of the Committee may make the presentations.
The Director(s) of the RMNCAH Programme(s) may also have a role, such as to explain the need for the review.
Next steps to be taken to incorporate steps of the plan of action into work plans and to implement the recommendations should be highlighted in the presentation. It is helpful if the attendees, such as representatives from MOH, other ministries or partners, will make a statement of endorsement of the recommendations.

## Slide 16
5.2 Documenting the findings and recommendations
Soon after the presentation, the Programme Review Committee, workshop facilitators (plus perhaps a few key programme staff, partners or stakeholders who they have identified and invited during the review) should work together to document the analytical findings and recommendations of the review into a Programme Review report.
The report can be drafted as an Aide Memoir that documents the key findings and actions discussed and endorsed by the MoH and RMNCAH stakeholders. Presentation of the Aide Memoire can take place during the workshop or in smaller meetings afterwards. The purpose of the discussion is to ensure that there is consensus and buy-in for the suggested recommendations by all RMNCAH stakeholders. The Aide Memoire should include specific timelines for reviewing and documenting implementation of the recommendations which will be shared with all stakeholders.
  Dissemination of Final Report by Ministry of Health
The Ministry of Health will meet to develop a plan of action, based on the recommendations from the workshop that will be included in the report. The plan should include actions to be taken, which are concrete, specific, realistic, time bound and achievable, grouped and sequenced in a logical and feasible plan.
When the report is complete, the MoH should distribute it to key individuals in the RMNCAH Programme(s) and related programmes and others involved in some way with the review or implementation of the recommendations from other ministries, partners and other stakeholders, including civil society. If possible, a media event could be planned as part of the dissemination of results.

## Slide 17: Figure 7. How does the RMNCAH Programme Review fit into planning and management activities?
    5.3 Use of findings and recommendations
The purpose of the RMNCAH Programme Review is to assess progress towards the goals and objectives of the RMNCAH programmes and improve performance of the programmes. The findings and recommendations should lead to clear actions for follow-up and can be used in several ways.
  Purpose of review type
  Review type
  Role of RMNCAH programme review
  Timing of activity
  Mid-term review
  Review progress towards meeting objectives of programme(s) and re-programme if necessary
  Mid-point of programme cycle
  Assess whether programme(s) are on track to achieve objectives through outputs and outcomes; re-direct programming or re-allocate resources where necessary
  End-term review
  Review performance of programme(s) and develop new strategic plan
  Prior to the end of the programme cycle
  Contribute to assessing what the programme(s) have achieved by reviewing outcomes and impact measures (along with other evaluation activities requires for developing next strategic plan)
  Annual review
  Adjust ongoing implementation activities of the programme(s)
  Annually
  Improve the ongoing implementation of the programme through immediate adjustments to service delivery and addressing bottlenecks to scaling up services

## Slide 18
    A.1 Global Strategy for Women’s, Children’s and Adolescents’ Health – Action areas
  The vision of the Global Strategy is that by 2030, a world in which every woman, child and adolescent in every setting realizes their rights to physical and mental health and well-being, has social and economic opportunities, and is able to participate fully in shaping prosperous and sustainable societies.
  Nine action areas were identified as key to achieving the objectives of the Global Strategy. While the details of each action will differ based on the country setting, the RMNCAH Programme Review should aim to include these action areas in its scope.
  To access the full Global Strategy for Women’s, Children’s, and Adolescents’ Health (2016-2030): http://www.who.int/life-course/partners/global-strategy/en/