## Slide 1: PROGRAMME REVIEW WORKSHOP FOR REPRODUCTIVE, MATERNAL, NEWBORN, CHILD AND ADOLESCENT HEALTH Introductory presentation
Notes: These are a suggested set slides that can be used to facilitate the introductory session of the RMNCAH Programme Review Workshop. These can be modified to match the logistics of the Workshop and should be adapted to the country setting and needs.

## Slide 2: What is a programme review for RMNCAH?
The Reproductive, Maternal, Neonatal, Child and Adolescent Health (RMNCAH) Programme Review is:
  A process for assessing mid- and/or end-term country progress in improving women’s, children’s and adolescents’ health.
  A Programme Review is conducted on a periodic basis as part of the regular programme planning and implementation cycle.
  Most useful if coordinated with other ongoing review and planning activities
  Ideally incorporated into existing strategic and annual plans and processes

## Slide 3: Where does the RMNCAH Programme Review fit into planning and management cycles?
  RMNCAH Programme review as part of end-term review
  Review activities and outputs of programme(s)
  (Every 1-2 years)
  Develop strategic plan
  (Every 5-10 years)
  Develop implementation plan (Every 1-2 years)
  RMNCAH Programme review as mid-term review
Strategic planning cycle (5-10 years)
Implementation planning cycle (1-2 years)
  Manage implementation (Ongoing)
  Evaluate health impact and intervention coverage e.g. DHS, MICS (Every 5-10 years)
  Develop new strategic plan
  (Every 5-10 years)
  A programme review is an integral part of a programme planning and management cycle occurring periodically as mid-term and end-term activities

## Slide 4: Objectives an RMNCAH Programme Review
  Objectives:
To assess how well the programme(s) implemented their plans and identify successes, lessons and good practices;
To identify problems and gaps, facilitating factors, emerging issues, opportunities, lessons, threats to determine solutions;
To align the programmes’ priorities and guidelines with the Sustainable Development Goals (SDGs) and Global Strategy for Women’s, Children’s, and Adolescents’ Health and other regional and global priorities;
To develop recommendations including priority actions to be taken, resources needed and responsible persons/organizations needed to implement them so as to improve implementation and operationalization of the strategic plan;
To decide on the next steps for implementing the review recommendations including inputs to the operational RMNCAH plan
  The purpose of the RMNCAH Programme Review is to assess progress towards the goals and objectives of the RMNCAH programme(s).

## Slide 5: Scope of the RMNCAH Programme Review
The programme review process is developed based on the following principles:
Focus on proven effective, high impact interventions;
Address all the target populations of RMNCAH: women of reproductive age, pregnant women though childbirth, newborns, infants and children up to age 5 years; adolescents as well as cross cutting and multi-sectoral areas such as nutrition, WASH, etc.
Use a continuum of care approach:
  Life stages: Pre-pregnancy, pregnancy, childbirth, newborn, infancy, childhood, adolescence and post-reproductive;
  Levels of the health system: Household and community, first-level health facilities, referral facilities
Use the action areas of the Global Strategy for Women’s, Children’s and Adolescents’ Health

## Slide 6: RMNCAH programme review workshop - Overview
  Principles of the RMNCAH Programme Review workshop:
Reviews progress in order to identify most important problems, bottlenecks, gaps and formulate solutions to address them at all levels
Uses available data on health status, intervention coverage and programme outputs at all levels
Is a multi-stakeholder process which actively involves participants in making assessments and recommendations for all levels
Content and process
Participants will review and analyze:
Progress on the health status of women, newborns and children and adolescents
Programme coverage at all levels
Programme implementation at all levels of the health system
Outcomes
Participants will:
Identify the main problems the programmes are having
Suggest solutions and formulate recommendations on priority actions to take at all levels of the health system.
These findings, solutions and recommendations will be synthesized into a report.

## Slide 7: The programmatic pathway for improving RMNCAH
IMPLEMENTATION OF ACTIVITIES
RMNCAH policies
Advocacy for RMNCAH
Human, material and financial resource mobilization
Human resource capacity development
Communication with families & communities
Health system supports strengthened
Progress tracked
IMPROVED
Availability and access to health care
Quality of care
Demand for care
Knowledge of families and communities
INCREASED POPULATION-BASED COVERAGE
of key effective interventions
IMPROVED SURVIVAL AND HEALTH
Other determinants
Notes: This slide summarizes the programmatic pathway for improving child survival and health. Implementation of programme activities is expected to improve availability, access, demand and quality of health care. They are also expected to improve knowledge of families and communities about optimal child care practices. The outputs are in turn expected to increase population-based coverage of key, effective interventions. Finally, effective coverage with key interventions is expected to result in improved survival and health. While this is one pathway for improved child health and survival, it is noteworthy that there are several other determinants of child health and survival including socio-economic and education factors.

## Slide 8: Step 1 (a & b) To what extent have the RMNCAH programmes improved the health status of women, children, and adolescents?
Step 1a: What are the goals, objectives and targets of the RMNCAH programme(s)?
  Outcome: Assess whether RMNCAH programme(s) is/are making positive, negative, or no progress in improving health status
  Step 1b: To what extent have RMNCAH interventions contributed to achieving impact?
  Outcome: Identify underperforming intervention packages for in-depth analysis.

## Slide 9: Steps 2 (a & b) Which RMNCAH intervention packages were implemented and where? How well were they implemented?
  Step 2b: How well were the RMNCAH intervention packages implemented?
  Outcome: Identify achievements and gaps in implementation of each package
  Step 2a: Which RMNCAH intervention packages were implemented and where?
  Outcome: Identify areas and levels where packages are implemented and where improvement is needed

## Slide 10: Step 3
  Step 3. What are the RMNCAH programmes’ most important problems that are causing gaps in implementation?
  Outcome: List problems causing implementation gaps and identify most important ones.

## Slide 11: Step 4
  4. What are solutions and recommendations for problems?
  Outcome: Propose solutions that address causes of main problems and formulate recommendation on how these solutions should be carried out by the programme(s).

## Slide 12: RMNCAH programme review workshop - Steps
  1. To what extent have the RMNCAH programmes improved the health status of women, children, and adolescents?
  Review goals, objectives and health status indicators to identify the most critical needs of women, children, and adolescents
  Outcome: Assess whether RMNCAH programme(s) is/are making positive, negative, or no progress in improving health status
  Review intervention coverage to identify disparities in coverage
  Outcome: Identify underperforming intervention packages for in-depth analysis.
  2. Which RMNCAH intervention packages were implemented and where? How well were they implemented?
  Review indicators of availability, access, quality and demand – available information plus personal knowledge and experience
  Outcome: Identify achievements and gaps in implementation of each package
  Review availability of packages – geographic areas and levels of health system
  Outcome: Identify areas and levels where packages are implemented and where improvement is needed
  3. What are the RMNCAH programmes’ most important problems that are causing gaps in implementation?
  Outcome: List problems causing implementation gaps and identify most important ones.
  4. What are solutions and recommendations for problems?
  Outcome: Propose solutions that address causes of main problems and formulate recommendation on how these solutions should be carried out by the programme(s).

## Slide 13: Use of findings and recommendations Programme Review
  Purpose of review type
  Review type
  Role of RMNCAH programme review
  Timing of activity
  Mid-term review
  Review progress towards meeting objectives of programme(s) and re-programme if necessary
  Mid-point of programme cycle
  Assess whether programme(s) are on track to achieve objectives through outputs and outcomes; re-direct programming or re-allocate resources where necessary
  End-term review
  Review performance of programme(s) and develop new strategic plan
  Prior to the end of the programme cycle
  Contribute to assessing what the programme(s) have achieved by reviewing outcomes and impact measures (along with other evaluation activities requires for developing next strategic plan)
  Annual review
  Adjust ongoing implementation activities of the programme(s)
  Annually
  Improve the ongoing implementation of the programme through immediate adjustments to service delivery and addressing bottlenecks to scaling up services
The findings and recommendations should lead to clear actions for follow-up and can be used in several ways.