## Slide 1: HCV program progress – decentralization of care and utilization of geneXpert capacity
May, 2019

## Slide 2: Care Cascade - PHC
Chart: 
| Number of persons cured | Number of persons completed treatment | Number of persons initiated treatment | Number of persons diagnosed with positive confirmatory tests who have completed HCV pre-treatment evaluation | FIB≥ 1,45 | FIB | Number of persons with positive HCV confirmatory test results | Number of anti-HCV positive persons tested for hepatitis C using HCV confirmatory testing
Series 1 | 10 | 201 | 206 | 222 | 39 | 318 | 391 | 470

## Slide 3: Care cascade by providers
Chart: 
| Tbilisi-National Center for Family Medicine | Poti -Evex Clinics | Khasuri-New Clinic | Telavi Referral Hospital | Senaki-Ambulatory-Polyclinic Union | Akhaltsikhe Referral Hospital
Number of persons cured | 0 | 0 | 0 | 0 | 10 | 0
Number of persons completed treatment | 0 | 94 | 5 | 50 | 48 | 4
Number of persons initiated treatment | 0 | 95 | 5 | 50 | 52 | 4
Number of persons diagnosed with positive confirmatory tests who have completed HCV pre-treatment evaluation | 2 | 104 | 7 | 52 | 53 | 4
Number of persons with positive HCV confirmatory test results | 11 | 184 | 20 | 64 | 101 | 11
Number of anti-HCV positive persons tested for hepatitis C using HCV confirmatory testing | 17 | 224 | 22 | 67 | 101 | 29

## Slide 4: PHC providers registration / launch dates
 | providers | registration date | program start date
1 | PHC- National Center for Family Medicine | june, 2018 | february, 2019
2 | PHC - "Ambulatory-Polyclinic Union" - Senaki | april, 2018 | may, 2018
3 | PHC - "Evex Clinics" -Poti phc | april, 2018 | september, 2018
4 | PHC - "New Clinic"-Khasuri | june, 2018 | january, 2019
5 | PHC - "Evex Hospitals" - Telavi Referral Hospital | june, 2018 | november, 2018
6 | PHC - "Evex Hospitals" - Akhaltsikhe Referral Hospital | september, 2018 | november, 2018

## Slide 5: Care Cascade - HRC
Chart: 
| Number of persons cured | Number of persons completed treatment | Number of persons initiated treatment | Number of persons diagnosed with positive confirmatory tests who have completed HCV pre-treatment evaluation | FIB≥ 1,45 | FIB | Number of persons with positive HCV confirmatory test results | Number of anti-HCV positive persons tested for hepatitis C using HCV confirmatory testing
Series 1 | 0 | 95 | 96 | 108 | 16 | 145 | 145 | 156

## Slide 6: Care Cascade – by HRC providers
Chart: 
| HRC- ,,Imedi" | HRC - Dependency Medical Management Center | HRC - Younger psychologists and doctors' association Xenon | HRC - "New Vector"
Number of anti-HCV positive persons tested for hepatitis C using HCV confirmatory testing | 39 | 25 | 55 | 37
Number of persons with positive HCV confirmatory test results | 39 | 14 | 55 | 37
Number of persons diagnosed with positive confirmatory tests who have completed HCV pre-treatment evaluation | 18 | 12 | 46 | 32
Number of persons initiated treatment | 18 | 11 | 39 | 28
Number of persons completed treatment | 17 | 11 | 39 | 28
Number of persons cured | 0 | 0 | 0 | 0

## Slide 7: HRC providers registration / launch dates
 | providers | registration date | program start date
1 | HRC - "New Vector"-Tbilisi | september, 2018 | november, 2018
2 | HRC - Dependency Medical Management Center-Tbilisi | november, 2018 | december, 2018
3 | HRC- ,,Imedi" -Batumi | september, 2018 | november, 2018
4 | HRC - Xenon-Zugdidi | september, 2018 | november, 2018

## Slide 8: Providers with zero cases
 | providers | registration date | program start date
1 | PHC - "Evex Hospitals" -Khobuleti | september, 2018 | ***
2 | PHC - "Evex Hospitals" - Akhalkalaki | september, 2018 | ***
3 | PHC-GeoHospitals-Marneuli | january, 2019 | ***
4 | PHC-GeoHospitals-Sagarejo | january, 2019 | ***

## Slide 9: main reasons of declined inclusion
1. the period since launching is not long
2. stigma of patients (they more trust the special clinic and well-known specialists)
3. patients inclusion criteria (depends on FIB4 score, i.e. FIB4 should be <1,45)
4. lack of awareness (of both patients and personnel)

## Slide 10: committee decisions
change inclusion criteria on PHC and HRC level, i.e. raise fib4 score to 3.25
abolish 4 week RNA testing during the monitoring process
Abolish video - monitoring obligation for new providers
continue the decentralization process, include new PHC and HRC (the list will be agreed soon)

## Slide 11: Diagnostic for 12 week treatment monitoring (for special clinics)
Chart: 
| 2015 | 2016 | 2017 | 2018 | 2019
with ribavirin + interferon | 380.8 | 280 | 165.2 | 0
with ribavirin | 374.5 | 273.7 | 155.4 | 155.4 | 81.9
without ribavirin | 0 | 0 | 152.6 | 152.6 | 75.6

## Slide 12: Proposed sites for integration
# | Potential site | Quantity of GX Platform | Modules | Year installed | Running software in GX | Last date of calibration
1 | LSS in Akhaltsikhe | 1 | 4 | 2014-2015 | 4.7b | 28/02/2019
2 | LSS in Telavi | 1 | 4 | 2014-2015 | 4.7b | 26/02/2019
3 | LSS in Poti | 1 | 4 | 2014-2015 | 4.7b | 21/02/2019
4 | LSS in Gori | 1 | 4 | 2014-2015 | 4.7b | 13/02/2019
5 | LSS in Ozurgeti | 1 | 4 | 2014-2015 | 4.7b | 20/02/2019
6 | LSS in Zugdidi | 1 | 4 | 2014-2015 | 4.7b | 
7 | ZDL in Batumi | 2 | 8 | 2013 & 2015 | 4.7b | 21/02/2019 & 12/12/2018
8 | ZDL in Kutaisi | 2 | 8 | 2014 & 2016 | 4.8 | 12/12/2018
9 | Tbilisi Penitentiary | 1 | 4 | 2017 | 4.4 | 21/04/2018
10 | Ksani Penitentiary | 1 | 4 | 2017 | 4.4 | 24/04/2018
11 | Tbilisi TB Center | 6 | 24 |  | 4.7b | 15/03/2018 & 21/12/2018
12 | LLC Med X in Marneuli | 1 | 4 | 2018 | 4.8 | 13/06/2018
13 | Kobuleti Evex –Unimed Adjara | 1 | 2 | 2017 | 4.8 | 22/06/2018
14 | Sagarejo Geo Hospital | 1 | 2 | 2017 | 4.8 | 6/7/2018
15 | Kutaisi “LG and company” | 1 | 4 | 2017 | 4.7b | 27/06/2018

## Slide 13: Integration of HCV diagnostics has started
# | Sites | Training | Date
1 | LSS in Telavi | DONE | 25-Apr-2019
2 | LSS in Poti | DONE | 30-Apr-2019
3 | LSS in Gori | DONE | 01-May-2019
4 | LSS in Zugdidi | DONE | 03-May-2019
5 | ZDL in Batumi | DONE | 01-May-2019
6 | ZDL in Kutaisi | DONE | 02-May-2019

## Slide 14: Workflow of HCV testing in LSS/ZDLs
Samples from the clinics/hospitals
Receiving the samples from the clinics as it is SOC procedure
Outpatients
Blood drawing will be done for Anti HCV + patients / or capillary blood prick
The results entering to the data base (Stop C)
The results will be seen in Elim C data base by clinic personal in 24 hr
Test result is giving to back to the patient in 2 - 24 hr
Performing of HCV confirmatory test on GX
Performing HCV confirmatory test on GX in Lab
The results will be entering to the data base (Stop C)

## Slide 15: THANK YOU FOR YOUR ATTENTION!