## Slide 1: Management of HEP C Elimination program

## Slide 2: Goal
Goal Elimination of HCV by ensuring prevention, diagnostics and treatment of the disease
Targets
90-95-95
By 2020
90% of people living with HCV are diagnosed
95% of those diagnosed are treated
95% of those treated are cured

## Slide 3
Persons* Screened per Month,
Georgia HCV elimination program, January 2015 – April 2019
Chart: Month of Screening
| 42005 | 42036 | 42064 | 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401 | 42430 | 42461 | 42491 | 42522 | 42552 | 42583 | 42614 | 42644 | 42675 | 42705 | 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979 | 43009 | 43040 | 43070 | 43101 | 43132 | 43160 | 43191 | 43221 | 43252 | 43282 | 43313 | 43344 | 43374 | 43405 | 43435 | 43466 | 43497 | 43525 | 43556
Positive | 128 | 214 | 214 | 459 | 2363 | 2142 | 2014 | 1957 | 1996 | 1752 | 1970 | 2028 | 1624 | 2151 | 2164 | 1475 | 1506 | 2425 | 2082 | 1983 | 2021 | 1826 | 3062 | 2764 | 2718 | 3092 | 3086 | 2725 | 2284 | 2737 | 3023 | 2761 | 2626 | 2878 | 2573 | 2464 | 2009 | 2088 | 1878 | 2255 | 2573 | 2433 | 2220 | 2000 | 1912 | 1953 | 1865 | 1733 | 1687 | 1771 | 1902 | 1564
Negative | 1278 | 2277 | 2559 | 1932 | 1840 | 2298 | 2279 | 2407 | 2926 | 2870 | 4193 | 3962 | 4095 | 5700 | 5323 | 3947 | 4001 | 4516 | 4257 | 4596 | 5702 | 7807 | 20127 | 25266 | 23791 | 25475 | 26778 | 26113 | 23466 | 29907 | 34998 | 35081 | 38624 | 44328 | 39987 | 36760 | 30050 | 32403 | 30396 | 46174 | 56780 | 52757 | 58467 | 56441 | 53077 | 60330 | 54819 | 61334 | 62181 | 69405 | 75282 | 72099
Cumulative Persons Screened | 1406 | 3897 | 6670 | 9061 | 13264 | 17704 | 21997 | 26361 | 31283 | 35905 | 42068 | 48058 | 53777 | 61628 | 69115 | 74537 | 80044 | 86985 | 93324 | 99903 | 107626 | 117259 | 140448 | 168478 | 194987 | 223554 | 253418 | 282258 | 308008 | 340652 | 378673 | 416515 | 457768 | 504980 | 547545 | 586776 | 618835 | 653326 | 685600 | 734029 | 793382 | 848572 | 909259 | 967700 | 1022689 | 1084972 | 1141656 | 1204723 | 1268591 | 1339767 | 1416951 | 1490614
* Among all persons with PID. Does not include persons with 15-digit code

## Slide 4
Georgia Hepatitis C Elimination Program Care Cascade,
April 28, 2015 – April 30, 2019
Chart: 
| Cured | Tested for SVR | Eligible for SVR | Completed Treatment | Initiated HCV Treatment | HCV Confirmed Chronic Infection | HCV Confirmatory Testing | Positive Anti- HCV Test (Tx eligible)** | Positive Anti- HCV Test (Total)*
 | 36650 | 37345 | 49865 | 52053 | 56318 | 72060 | 86748 | 108767 | 113951
92.4%
79.8%
83.1%
95.5%
95.8%
74.9%
* Among persons with PID. Does not include persons with 15-digit code
** Age ≥ 12 with no mortality data prior to confirmation
Notes: SLIDE 3
This slide shows the number of people with a positive HCV test results presenting to four pilot provider sites in Tbilisi by week.
For the first four weeks of the program at least 700 people presented to the 4 sites combined, peaking during the second week at a 1000 people.
SLIDE 4
And here are the same trends by month BUT for 12 provider sites enrolled in the program as of October 18th
The peak volume of Hepatitis C –infected persons seeking care occurred in May and thereafter stabilized at approximately 2300 people per month.
SLIDE 5
This slide demonstrates number of persons with current HCV-infection and indications for treatment, who were approved by the committee ,depicted in blue
and those who started treatment depicted in orange, by month
Initially in May and June proportionally a low percentage of patients eligible to start treatment were approved. However as the process was refined, in July and August larger proportion of patients started treatment.
SLIDE 6
Here are the demographic characteristics of 3 722 people who started treatment.
86% of patients were male. Median age was 51.
Available data of Family score was equally distributed among those with less than 70.000 score and those with >70,000
SLIDE 7
Among patients who started treatment the majority resided in Tbilisi followed by Imereti and Adjara regions

## Slide 5: Challenges
Declined enrollment in the treatment program (financial barrier, geographical barrier, etc.)
Limited provider capacity and a scarcity of treatment centers in some geographic and especially in rural areas

## Slide 6
Chart: Month of Treatment Initiation
| 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401 | 42430 | 42461 | 42491 | 42522 | 42552 | 42583 | 42614 | 42644 | 42675 | 42705 | 42736 | 42767 | 42795 | 42826 | 42856 | 42887 | 42917 | 42948 | 42979 | 43009 | 43040 | 43070 | 43101 | 43132 | 43160 | 43191 | 43221 | 43252 | 43282 | 43313 | 43344 | 43374 | 43405 | 43435 | 43466 | 43497 | 43525 | 43556
Patients Initiating Treatment | 0 | 298 | 561 | 1000 | 1125 | 287 | 1135 | 637 | 891 | 15 | 629 | 518 | 1346 | 810 | 1164 | 1263 | 3297 | 4594 | 3691 | 2188 | 2140 | 1966 | 1460 | 1382 | 1262 | 1354 | 1162 | 1164 | 1004 | 1041 | 1023 | 1065 | 908 | 342 | 1026 | 1586 | 121 | 959 | 975 | 729 | 782 | 1085 | 1078 | 807 | 717 | 804 | 924 | 1059 | 944
Cumulative Initiated Treatment | 0 | 298 | 859 | 1859 | 2984 | 3271 | 4406 | 5043 | 5934 | 5949 | 6578 | 7096 | 8442 | 9252 | 10416 | 11679 | 14976 | 19570 | 23261 | 25449 | 27589 | 29555 | 31015 | 32397 | 33659 | 35013 | 36175 | 37339 | 38343 | 39384 | 40407 | 41472 | 42380 | 42722 | 43748 | 45334 | 45455 | 46414 | 47389 | 48118 | 48900 | 49985 | 51063 | 51870 | 52587 | 53391 | 54315 | 55374 | 56318
Patients initiating treatment,
Georgia HCV elimination program, April 2015 – April 2019

## Slide 7: Patients initiating treatment (total vs vulnerable
Chart: 
| 2015 | 2016 | 2017 | 2018
total | 5934 | 21655 | 14791 | 10207
vulnerable | 1499 | 3133 | 3750 | 2250

## Slide 8: Service providers (37*) – current + pilot+1 phase of decentralization
Chart: 
| Tbilisi | Imereti | Adjara | Guria | Shida kartli | Samegrelo | Kvemo kartli | Kakheti
Column1 | 13 | 5 | 4 | 2 | 3 | 5 | 2 | 3
2 PHC
1 HRC
1 PHC
2 PHC
1 PHC
2 HRC
1 PHC
1 HRC

## Slide 9: Care cascade – TOTAL vs PHC/HRC (April, 2019)
Chart: 
| Number of persons cured | Number of persons completed treatment | Number of persons initiated treatment | Number of persons with positive HCV confirmatory test results | Number of anti-HCV positive persons tested for hepatitis C using HCV confirmatory testing
phc/hrc | 0 | 0.095 | 0.096 | 0.145 | 0.156
total | 36.65 | 52.053 | 56.318 | 72.06 | 86.748

## Slide 10: main reasons of declined inclusion in PHC/HRC
the period since launching is not long
stigma of patients (they more trust the special clinic and well-known specialists)
patients inclusion criteria (depends on FIB4 score, i.e. FIB4 should be <1,45)
lack of awareness (of both patients and personnel)

## Slide 11: Cost of Diagnostic before treatment for patient
Chart: 
| 2015 | 2016 | 2017 | 2018-I -II -III-qv | 2018-IV qv
with elastography (GEL) | 336 | 350 | 335.3 | 258.3 | 160.3
without elastography(GEL) | 280 | 294 | 279.3 | 202.3 | 104.3
PHC/HRC | 70.7

## Slide 12: Cost of diagnostic for 12 week treatment monitoring for patient
Chart: 
| 2015 | 2016 | 2017-2018 | 2018 (PHC/HRC)
with ribavirin + interferon | 380.8 | 280 | 165.2 | 0
with ribavirin | 374.5 | 273.7 | 155.4 | 71.4
without ribavirin | 0 | 0 | 152.6 | 52.5

## Slide 13: Cost of Full Diagnostic for patient (12 week treatment)
Chart: 
| 2015 | 2016 | 2017 | 2018 -I-II-III qv | 2018 - IV qv | 2018-PHC/HRC
with elastography (GEL) | 714 | 627 | 495 | 418 | 222 | 189
without elastography(GEL) | 658 | 570 | 440 | 363 | 166 | 133

## Slide 14: program expenditure
Chart: 
| 2015 | 2016 | 2017 | 2018
approved budget (GEL) | 2000 | 21300 | 15000 | 16000
real expenditure (GEL) | 6062 | 8594 | 9514 | 6369

## Slide 15: Program budget -2019
approved budget (GEL)
Chart: 
| screening | diagnostic | treatment | logistics | TOTAL
approved budget (GEL) | 1100 | 7900 | 800 | 1200 | 11000
Anticipated resource (GEL)
Chart: 
| screening | diagnostic | treatment | logistics
approved budget (GEL) | 1100 | 7900 | 800 | 1200
expenditure (GEL) (I qv+ II qv (anticip)) | 600 | 1600 | 400 | 600
resource (GEL) (july-november) | 500 | 6300 | 400 | 600

## Slide 16: committee decisions
change inclusion criteria on PHC and HRC level, i.e. raise fib4 score to 3.25
abolish 4 week RNA testing during the monitoring process
Abolish video - monitoring obligation for new providers
continue the decentralization process, include new PHC and HRC (the list will be agreed soon)
Abolish co-payment ?

## Slide 17: Total cost of diagnostic after abolish 4 week RHA testing
Chart: 
| 12 week - current (2018-2019) | 12 week anticipated (2019) | phc/hrc-current (2018-2019) | phc/hrc-anticipated (2019)
for patient | 288.05 | 0 | 160.65 | 0
for government | 535.75 | 631.5 | 490.65 | 559.5

## Slide 18: TOTAL COST FOR DIAGNOSTIC PER MONTH FOR 2000 PATIENTS (after abolish 4 week RNA testing)
 | NUMBER OF PATIENT (VULNERABLE)PER MONTH | NUMBER OF OTHER PATIENT PER MONTH | COST OF FULL DIAGNOSTIC (FOR 1 PATIENT) GEL | TOTAL COST PER MONTH (GEL)
12 WEEK TREATMENT | 140 |  | 631.5 | 88 410
12 WEEK TREATMENT |  | 1260 | 631.5 | 795 690
PHC/HRC | 60 |  | 559.5 | 33 570
PHC/HRC |  | 540 | 559.5 | 302 130
TOTAL | 200 | 1800 |  | 1 219 800

## Slide 19: TOTAL COST FOR DIAGNOSTIC 10 000 PATIENTS in 5 month (after abolish 4 week RNA testing)
 | NUMBER OF PATIENT for 5 MONTH | COST OF FULL DIAGNOSTIC (FOR 1 PATIENT) GEL | TOTAL COST PER MONTH (GEL)
12 WEEK TREATMENT | 7000 | 631.5 | 4 420 500
PHC/HRC | 3000 | 559.5 | 1 678 500
TOTAL | 10 000 |  | 6 099 000