## GEO6011+GEO6010 Work Plans
AIPS Number | Project No | Level | Description | Component | Fund source | MS funds | EBT/ GCS f/a | EBT distribution of funds | EBT Reserved | EBT Under Impl | EBT Not Initiated (NOT Reserved) | TCF Approved Budget | TCF New Estimates | Reserved (Actual cost) | Under Impl (Funds Not Reserved) | Not Initiated (NOT Reserved) | Total Needed (Not Reserved) | Quarter | City, Country | Event Date | Revised Year | Approved year | End User Institution | Area/TO | Names of Nominees / Proposed Experts | Comments by Counterpart | Comments by TO/PMO | PMO follow up notes | Status: Under Implementation Ongoing Activity Ongoing Supplier Being Delivered Pending Counterpart Pending PMA Pending PMO Pending TO Cancelled Completed | EVT NUMBER | Req. Num. | Req. Approval Date | Procurement Plan Submit Date | RFQ Close Date | Technical Evaluation Request Date | Technical Evaluation Completed Date | PO Num. | PO Approval Date | PO promised Date (Ready to ship by) | Supplier Name | Bollore Collection Date | Delivery date at End user site | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
2061598 | GEO6010 | Outcome | Title: GEO6010 "Creating a Radiation Medicine Education and Training Strategy" Project Objective: To provide Georgian citizens with high quality radiation treatment and diagnostic services. Outcome: Academic education and clinical training programmes in radiation medicine established and a supervision body at the Ministry of Health level created, which as a body will be responsible for the strengthening and implementation of current national standarts and regulations. Performance Indicators: Academic education and clinic training programme established by the country with AEA's support+C440provided through the project. 1. continues medical educational system in radiation medicine is in line with international standards and assure preparation of highly qualified Human Resources in radiation medicine, 2. medical service in radiation medicine are in line with international guidelines and standards and monitoring is supervised by regulatory body (MoH level), Means of Verification: Project periodic achievement reports and review activities at annual basic, progress/outputs is visible. There is an established: 1. center that provides training according to international standards; 2. qualified trainers who can train local staff, 3. supervisory body at MoH level which will provide in QA/QC in medical providers in area of radiation medicine 4. radiation medicine residency program Assumptions: Local resources commitment including staff and budget in the place in line with the work plan, while IAEA's support provided through the project.
2061598 | GEO6010 | Output | 2. National academic educational center for Medical Physicists, radiation medicine technicians, for onco-nurses developed and educational infrastructure created. Performance Indicators: Programme established and trained staff'role function.
2061598 | GEO6010 | Activity | 2.1 Establish curuculums for the national academic educational programmes in field of radiation medicine for medical physicists, technicians, onco-nurses.
2061598 | GEO6010 | Input | 2.1.4 Expert mission 2, to perform teaching course as a training for trainers (For radiation treatment technicians (3px5d) | EM | TCF | 0 | 0 |  |  |  |  | 15000 | 15000 |  |  | 15000 | 15000 | 2Q |  | Aug | 2018 | 2018 |  |  |  |  | EXPERT: Send Job Description proposing dates and duties to PMO, PA, TO, official.mail@iaea.org (Annex 1) | 2 lecturers (2-3 days) Confirm dates | Pending counterpart
2061598 | GEO6010 | Input | 2.1.14 FE/MMP - N11, to sent phisitists to EU Universities (1px2years) | FE | TCF | 0 | 0 |  |  |  |  | 43200 | 43200 |  |  | 43200 | 43200 | 1Q |  | ICTP-ITA (2Y) | 2018 | 2018 |  | MP | GEO16022 Revez Turmanidze |  |  |  | Ongoing | bar: Q1
2061598 | GEO6010 | Input | 2 NTCs in RT: 1. Stereotactic RT- for ROs and MPs (also could be open for RTTs)- 4 exp 2. Breast ca- for RTTs- 3 exp | NTC | TCF | [7 empty] | 0 |  |  |  |  | 2Q |  |  | 2018 | 2018 |  |  |  |  | LECTURER: Send Job Description proposing dates and training programme to PMO, PA, TO, official.mail@iaea.org (Annex 1) |  | Pending counterpart |  | RO: ELENA | bar: Q2
2061598 | GEO6010 | Activity | 2.2 Select the staff and train them as future trainers.
2061598 | GEO6010 | Input | 2.2.3&2.2.7 Fellowships-N7, for relevant staff as a œtraining for trainers in advanced universities or educational centers of Europe practicing in teaching methodology for Medical Physicists (2px2.5m) | FE | TCF | 0 | 0 |  |  |  |  | 24300 | 24300 |  |  | 15000 | 15000 | 2Q |  | 20 April-7 July ICTP (2m15d) University Hospital of Udine (1m) | 2018 | 2018 |  | MP - Gian Luca | *Kakha Shamatava-Medical Physicist in ,,Aversi” Hospital *Giorgi Kharaishvili - Medical Physicist in High technology center |  |  | Medical Physicist (Nuclear Medicine) | Under implementation | EVT1704541 | bar: Q1
2061598 | GEO6010 | Output | 3 Enhanced educational level and skills of team; enforced and amended regulatory documentation. Performance Indicators: Trained staff and unite exist in the wrking place and play their role.
2061598 | GEO6010 | Activity | 3.1 Establish team at the MoH level, who will be responsable for legislative documentation and national standartization.
2061598 | GEO6010 | Input | 3.1.2&3.1.6 SV 2, visit regulatory agencies in EU, to assist local staff in elaboration of national radiation medicine International Standarts (2px5d) | SV | TCF | 0 | 0 |  |  |  |  | 6000 | 6000 |  |  | 6000 | 6000 | 2Q |  | FRA REJECTED! CHANGE TO BELGIUM 1w SV | 2018 | 2018 |  |  | GEO16019 Natia Nogaideli – Ministry of Health, head of medical regulation division; |  |  | Regulatory Aspects 1 week Belgium - Nomination has to be uploaded to AIPS EVT1704643 | Under implementation | EVT1704643 | bar: Q1
2061598 | GEO6010 | Activity | 3.2 To train the staff for knowledgmant of practical standarts QA and development of national quality assurance program.
2061598 | GEO6010 | Output | 4. Clinical/residence programmes for nuclear medicine doctors created, and clinical/residence programme for radiation oncologists improved. Performance Indicators: Creation of the programme and implementation in the country.
2061598 | GEO6010 | Activity | 4.1 To phasilitate training curuculum for residense program in Nuclear medicine and radiotherapy.
2061598 | GEO6010 | Input | 4.1.1 EM by clinical medical physicist to advise on establishing a structured hospital-based clinical training programme | EM | TCF | 0 | 0 |  |  |  |  | 8000 | 8000 |  |  | 8000 | 8000 | 1Q |  |  | 2018 | 2018 |  |  |  |  | EXPERT: Send Job Description proposing dates and duties to PMO, PA, TO, official.mail@iaea.org (Annex 1) |  | Pending counterpart |  | MP- Brendan
2061598 | GEO6010 | Input | 4.1.6&4.1.16 SV 3, for relevant staff as a training for trainers in advanced universities or educational centers of Europe practicing in teaching methodology (NM Doctor) (2px5d) | SV | TCF | 0 | 0 |  |  |  |  | 6000 | 6000 |  |  | 6000 | 6000 | 1Q |  | 11-22 Sept. 2017 Spedali Civili di Brescia; Medicina Nucleare (2w) | 2018 | 2018 |  | NM -Enrique | GEO16012 Nata Shengelia – NM doctor from ,,Aversi” clinic; |  |  | Nuclear Medicine Physician Postponed to 1Q 2018, as requested by candidate shengeln@yahoo.com I would kindly like to ask you if you could ask the the host to postpone my visit to spring 2018 (feb/march/April). Aim of project: development of NM Residence Programme Centres, need 2 certified NM doctors, 5 NM technoloigists Establishment of QA/QC syste (assign one responsible person) Can support 1-2 IEX for training NM techicians and 2 IEX for training NM Physicians | Under implementation | EVT1704554 | bar: Q1
2061598 | GEO6010 | Output | Capacities strenghtened in radiation medicine
2061598 | GEO6010 | Activity | Procurement of equipment
2061598 | GEO6010 | Input | Training course in the country on Quality and Safety in Breast Imaging (for all stakeholders, radiologist, radiographer, medical physicist). | NTC | TCF | [6 empty] | 0 | 0 |  |  | 0 | 0 | 2Q |  |  | 2018 | 2018 |  |  |  |  | LECTURER: Send Job Description proposing dates and training programme to PMO, PA, TO, official.mail@iaea.org (Annex 1) | Harri Delis After receiving Mammography equipment - Training onsite | Pending TO
2061598 | GEO6010 | Input | Short term fellowships for Medical Physicist on Mammography (and radiology in general). | FE | TCF | [6 empty] | 0 | 0 |  |  | 0 | 0 | 2Q |  |  | 2018 | 2018 |  |  |  |  | FE/SV: SEND NOMINATION VIA INTOUCH+ -Refer to Event Number (Column AE). Ensure forms are complete by following the attached application procedure. | Harri Delis After receiving Mammography equipment - Training onsite | Pending TO
2061598 | GEO6010 | Input | 5.1.1 Mammography Equipment | PR-HW | TCF | [6 empty] | 0 | 0 |  |  |  |  | 1Q |  |  | 2018 | 2018 | [5 empty] | Harri Delis | Under Supplier | [7 empty] | 201713200 | 2017-12-14 | 2018-12-29 | Siemens
2061598 | GEO6010 | Input | Procurement of X ray equipment and QA equipment | PR-HW | TCF | [6 empty] | 0 | 200000 | 200000 |  |  |  | 3Q |  |  | 2018 | 2018 | [5 empty] | Estimated value: 200K TCF2017:118.000 TCF2018:82,000 | Under Procurement |  | 61989 | 2017-11-30
2061982 | GEO6011 | Outcome | Title: GEO6011 Improving the Treatment of Oncologic Diseases Project Objective: To decreased mortality and morbidity related to oncological diseases. Outcome: Accessibility to effective treatment of oncological diseases for population in Georgia improved. Performance Indicators: Nnew cases of malignancies per 100 000 in 2022 reduced by 10% Means of Verification: Medical statistic Assumptions: Governments commitment, including allocation of necessary resources
2061982 | GEO6011 | Output | Output 1. Equipment installed and operational for providing radiotherapy services. Radiation Oncology Department in Rukhis hospital enacted on October 1, 2020; Mission report Lack of financial resources
2061982 | GEO6011 | Activity | 1.1 RT: Procurement of equipment for radiotherapy services;
2061982 | GEO6011 | Input | 1.1.1 RT: EQ Procurement of CT-simulation (400-500K), Brachytherapy equipment (400K) | PR-HW | MS | 800000 | [6 empty] | 0 |  |  |  |  | 1Q |  | 1Q | 2019 | 2019 |  | 850K is the real estimated cost for all the mentioned equipment |  |  | PROCUREMENT: Send technical specifications to PMO, PA, TO and official.mail@iaea.org using the corresponding format: Annex 2. Template for Consumables, reagents, etc. (requisition list form). Annex 3 Template for Equipment, Software, Services | Purchase Order could be made in Oct. 2019 | bar: Q4 to Q4
2061982 | GEO6011 | Input | 1.1.2 EQ: Imobilization equipment (70K) | PR-HW | TCF | [6 empty] | 70000 | 70000 |  |  |  |  | 1Q |  | 1Q | 2020 | 2020 |  |  |  |  | PROCUREMENT: Send technical specifications to PMO, PA, TO and official.mail@iaea.org using the corresponding format: Annex 2. Template for Consumables, reagents, etc. (requisition list form). Annex 3 Template for Equipment, Software, Services | IAEA could budget 350,000 in 2019 and 270,000 in 2020 (40% of 1.55M). The funds of 2020 can be used to make the Purchase Order in October 2019, but the shipment of the LINAC can only be made in early 2020. | bar: Q4 to Q3
2061982 | GEO6011 | Input | 1.1.3 RT: EQ Procurement of Accelerator (with treatment planning system and spera parts) | PR-HW | TCF | [6 empty] | 350000 | 350000 |  |  |  |  | 2Q |  | 2Q | 2019 | 2019 |  |  |  |  | PROCUREMENT: Send technical specifications to PMO, PA, TO and official.mail@iaea.org using the corresponding format: Annex 2. Template for Consumables, reagents, etc. (requisition list form). Annex 3 Template for Equipment, Software, Services | bar: Q2 to Q2
2061982 | GEO6011 | Input | 1.1.4 RT: EQ Procurement of Accelerator (with treatment planning system and spera parts) | PR-HW | TCF | [6 empty] | 270350 | 270350 |  |  |  |  | 1Q |  | 1Q | 2020 | 2020 |  |  |  |  | PROCUREMENT: Send technical specifications to PMO, PA, TO and official.mail@iaea.org using the corresponding format: Annex 2. Template for Consumables, reagents, etc. (requisition list form). Annex 3 Template for Equipment, Software, Services | bar: Q4 to Q2
2061982 | GEO6011 | Input | 1.1.5 RT: EQ Procurement of Accelerator (with treatment planning system and spera parts) | PR-HW | GCS |  | 930000 | [5 empty] | 930000 |  |  |  |  | 2Q |  | 2Q | 2019 | 2019 |  |  |  |  | PROCUREMENT: Send technical specifications to PMO, PA, TO and official.mail@iaea.org using the corresponding format: Annex 2. Template for Consumables, reagents, etc. (requisition list form). Annex 3 Template for Equipment, Software, Services | CONSIDER: A) For 1.7M you can buy 1 single energy accelerator (700K) + 1 advanced acelerator (1M), RECOMMENDED SCENARIO or: B) For 1.5M you can buy 2 single energy accelerators (700K each) C) For 1.55 M you can buy 1 most advanced LINAC in the market | bar: Q2 to Q2
2061982 | GEO6011 | Activity | 1.2 RT: Physical infrastructure for radiotherapy in place and operational;
2061982 | GEO6011 | Input | 1.2.1 RT: Equipment installed | PR-HW | MS | 200000 | [6 empty] | 0 |  |  |  |  | 1Q |  | 1Q | 2020 | 2020 |  |  |  |  | PROCUREMENT: Send technical specifications to PMO, PA, TO and official.mail@iaea.org using the corresponding format: Annex 2. Template for Consumables, reagents, etc. (requisition list form). Annex 3 Template for Equipment, Software, Services | bar: Q1 to Q4
2061982 | GEO6011 | Input | 1.2.2 RT: Radiation oncology department infrastructure (wards, mouldroom and etc) ready get to patients | PR-HW | MS | 600000 | [6 empty] | 0 |  |  |  |  | 1Q |  | 1Q | 2020 | 2020 |  |  |  |  | PROCUREMENT: Send technical specifications to PMO, PA, TO and official.mail@iaea.org using the corresponding format: Annex 2. Template for Consumables, reagents, etc. (requisition list form). Annex 3 Template for Equipment, Software, Services | bar: Q1 to Q4
2061982 | GEO6011 | Output | Output 2. Qualified staff available to deliver radiotherapy services. Performance Indicators: Trained staff ratio in 2020 increased by 20% Means of Verification: Mission report Assumptions: Shortage of adequate personnel
2061982 | GEO6011 | Activity | 2.1 RT: Training of radiotherapy services staff (Radiation Oncologist, RTTS, Oncology Nurses) | [24 empty] | (schedule should be moved to 2018 to coincide with budget year)
2061982 | GEO6011 | Input | 2.1.1 RT: Selecting of personal (radiation oncologysts, radiation tecnologysts, nurses) | LOCAL | MS | 1000 | [6 empty] | 0 |  |  |  |  | 1Q |  |  | 2018 | 2018 |  |  |  |  | Local Activity | bar: Q1
2061982 | GEO6011 | Input | 2.1.2 IEX RT: Training of Radiation Therapy Technologist | EM | GEO6010 |  | 5250 | [5 empty] | 5250 |  |  |  |  | 3Q |  |  | 2018 | 2018 |  | Instead of FE conduct 1 expert mission 1 week. Technologists should be trained at a local hosptial with the available facilities |  |  | EXPERT: Send Job Description proposing dates and duties to PMO, PA, TO, official.mail@iaea.org (Annex 1) |  | Pending counterpart | bar: Q3
2061982 | GEO6011 | Input | 2.1.3 IEX RT: Training of Radiation Therapy Technologist | EM | GEO6010 |  | 5250 | [5 empty] | 5250 |  |  |  |  | 4Q |  |  | 2018 | 2018 |  | Instead of FE conduct 1 expert mission 1 week.Technologists should be trained at a local hosptial with the available facilities |  |  | EXPERT: Send Job Description proposing dates and duties to PMO, PA, TO, official.mail@iaea.org (Annex 1) |  | Pending counterpart | bar: Q4
2061982 | GEO6011 | Input | 2.1.4 FE RT: Training of Radiation Therapy Technologist. | FE | GEO6010 |  | 22680 | [5 empty] | 22680 |  |  |  |  | 4Q |  |  | 2018 | 2018 |  |  |  |  | FE/SV: SEND NOMINATION VIA INTOUCH+ -Refer to Event Number (Column AE). Ensure forms are complete by following the attached application procedure. |  | Pending counterpart | EVT1800458 | bar: Q4
2061982 | GEO6011 | Input | 2.1.5-2.1.6 FE RT: Training of Radiation Oncologist (2 persons) | FE | GEO6010 |  | 45360 | [5 empty] | 45360 |  |  |  |  | 2Q |  |  | 2018 | 2018 |  |  |  |  | FE/SV: SEND NOMINATION VIA INTOUCH+ -Refer to Event Number (Column AE). Ensure forms are complete by following the attached application procedure. | 4 months | Pending counterpart | EVT1800334 | bar: Q2 to Q3
2061982 | GEO6011 | Input | 2.1.7 RT:Training of a Oncology Nurses (in the place). | EM | GEO6010 |  | 5250 | [5 empty] | 5250 |  |  |  |  | 3Q |  |  | 2018 | 2018 |  |  |  |  | EXPERT: Send Job Description proposing dates and duties to PMO, PA, TO, official.mail@iaea.org (Annex 1) |  | Pending counterpart | bar: Q3
2061982 | GEO6011 | Activity | 2.2 MP: Training of Medical Physicists for radiotherapy services.
2061982 | GEO6011 | Input | 2.2.1 MP: Selecting of personal (Medical Physicist) | LOCAL | MS | 500 | [6 empty] | 0 |  |  |  |  | 1Q |  |  | 2018 | 2018 |  |  |  |  | Local Activity |  | Pending counterpart | bar: Q1
2061982 | GEO6011 | Input | 2.2.2 MP: MP:Training of a Medical Physicist (for Radiation Therapy) | FE | GEO6010 |  | 45360 | [5 empty] | 45360 |  |  |  |  | 2Q |  |  | 2018 | 2018 |  |  |  |  | FE/SV: SEND NOMINATION VIA INTOUCH+ -Refer to Event Number (Column AE). Ensure forms are complete by following the attached application procedure. | 8 month FE | Pending counterpart | EVT1800337 | bar: Q2 to Q4
2061982 | GEO6011 | Output | Output 3. QA/QC system established in radiotherapy services. Performance Indicators: Since Jenuary 2021 in Rukhis hospital the routine radiological assessment is conducted. Means of Verification: Data of radiological assassment. Assumptions: Lack of appropriate funding.
2061982 | GEO6011 | Activity | 3.1 RT: Develop QA/QC and clinical protocols;
2061982 | GEO6011 | Input | 3.1.1 RT: IEX -RTT to establish treatment protocols and workflow for Radiatiom Medicine Department (2IEX, 1 week) | EM | TCF | 0 | [5 empty] | 7350 | 7350 |  |  |  |  | 3Q |  | 3Q | 2020 | 2020 |  |  |  |  | EXPERT: Send Job Description proposing dates and duties to PMO, PA, TO, official.mail@iaea.org (Annex 1) | see note above regarding NTC 2 IEX, 1 week (schedule should be moved to 2020 to coincide with budget year) | bar: Q3
2061982 | GEO6011 | Input | 3.1.2 RT: IEX -RTT to establish treatment protocols and workflow for Radiatiom Medicine Department | EM | f/a |  | 5250 | [5 empty] | 5250 |  |  |  |  | 4Q |  | 4Q | 2020 | 2020 |  |  |  |  | EXPERT: Send Job Description proposing dates and duties to PMO, PA, TO, official.mail@iaea.org (Annex 1) | bar: Q4
2061982 | GEO6011 | Input | 3.1.3 RT: IEX -Radiation Oncologist to establish clinical protocols and workflow for Radiation Medicine Departament (2IEX, 1 week) | EM | TCF | 0 | [5 empty] | 7350 | 7350 |  |  |  |  | 3Q |  | 3Q | 2020 | 2020 |  |  |  |  | EXPERT: Send Job Description proposing dates and duties to PMO, PA, TO, official.mail@iaea.org (Annex 1) | bar: Q3
2061982 | GEO6011 | Input | 3.1.4 RT: IEX -Radiation Oncologist to establish clinical protocols and workflow for Radiation Medicine Departament (2IEX, 1 week) | EM | f/a |  | 5250 | [5 empty] | 5250 |  |  |  |  | 4Q |  | 4Q | 2020 | 2020 |  |  |  |  | EXPERT: Send Job Description proposing dates and duties to PMO, PA, TO, official.mail@iaea.org (Annex 1) | bar: Q4
2061982 | GEO6011 | Input | 3.1.5 RT: Developing guidelines and protocols for Radiation Medicine Departament | PR-SERV | MS | 5250 | [6 empty] | 0 |  |  |  |  | 4Q |  | 4Q | 2020 | 2020 |  |  |  |  | PROCUREMENT: Send technical specifications to PMO, PA, TO and official.mail@iaea.org using the corresponding format: Annex 2. Template for Consumables, reagents, etc. (requisition list form). Annex 3 Template for Equipment, Software, Services | bar: Q4
2061982 | GEO6011 | Activity | 3.2 MP: Develop QA/QC and clinical protocols;
2061982 | GEO6011 | Input | 3.2.1 MP: IEX -Medical Physicist to establish QA and QC protocols and workflow for Radiation Medicine Department | EM | TCF | 0 | [5 empty] | 7350 | 7350 |  |  |  |  | 4Q |  | 4Q | 2020 | 2020 |  |  |  |  | EXPERT: Send Job Description proposing dates and duties to PMO, PA, TO, official.mail@iaea.org (Annex 1) | 2 IEX, 1 week | bar: Q4
2061982 | GEO6011 | Input | 3.2.2 MP: IEX -Medical Physicist to establish QA and QC protocols and workflow for Radiation Medicine Department | EM | f/a |  | 7350 | [5 empty] | 7350 |  |  |  |  | 3Q |  | 3Q | 2020 | 2020 |  |  |  |  | EXPERT: Send Job Description proposing dates and duties to PMO, PA, TO, official.mail@iaea.org (Annex 1) | bar: Q3
2061982 | GEO6011 | Input | 3.2.3 MP: Developing guidelines and protocols for Radiation Medicine Departament | PR-SERV | MS | 3000 | [6 empty] | 0 |  |  |  |  | 4Q |  | 4Q | 2020 | 2020 |  |  |  |  | PROCUREMENT: Send technical specifications to PMO, PA, TO and official.mail@iaea.org using the corresponding format: Annex 2. Template for Consumables, reagents, etc. (requisition list form). Annex 3 Template for Equipment, Software, Services | bar: Q4
2061982 | GEO6011 | Activity | 3.3 RT: Dosimetry and radiation protection equipment is in place and operational | [24 empty] | (schedule should be moved to 2020 to coincide with budget year)
2061982 | GEO6011 | Input | 3.3.1 RT: Dosimetry and radiation protection equipment is purchased | PR-HW | MS | 70000 | [6 empty] | 0 |  |  |  |  | 3Q |  | 3Q | 2020 | 2020 |  | Realistic estimate 70K |  |  | PROCUREMENT: Send technical specifications to PMO, PA, TO and official.mail@iaea.org using the corresponding format: Annex 2. Template for Consumables, reagents, etc. (requisition list form). Annex 3 Template for Equipment, Software, Services | In PCMF you put this as a procurement covered by MoH. Is this a mistake? I changed it to 1 IEX | bar: Q3 to Q4
2061982 | GEO6011 | Input | 3.3.2 RT: Training for staff in dosimetry and radiation protection | EM | TCF | [6 empty] | 2100 | 2100 |  |  |  |  | 4Q |  | 4Q | 2020 | 2020 |  |  |  |  | EXPERT: Send Job Description proposing dates and duties to PMO, PA, TO, official.mail@iaea.org (Annex 1) | bar: Q4
| SUM |  |  |  |  | 1679750 | 1077000 | 0 | 0 | 0 | 0 | 817000 | 2094000 | 200000 | 0 | 93200 | 93200
[6 empty] | MS funds | EBT/ GCS f/a | EBT distribution of funds | EBT Reserved | EBT Under Impl | EBT Not Initiated (NOT Reserved) | TCF Approved Budget | TCF New Estimates | Reserved (Actual cost) | Under Impl (Funds Not Reserved) | Not Initiated (NOT Reserved) | Total Needed (Not Reserved)