Concept Number: GEO2016005

Title: Improving the Treatment of Oncologic Diseases

Original Language Title: ?????

Project Number: GEO6011

Project Type: National

Project For: Georgia

Submitted By: Member State and/or Observers With Rights

Priority: 2

Project duration (Total number of years): 3

Project duration (Start date): 2018-01-01

Field of Activity: 26 - Radiation oncology in cancer management

FOA Distribution: 
FoA Code: 26 = 95%           
FoA Code: 25 = 5%

Sustainable Development Goals: 
03 - Ensure healthy lives and promote well-being for all at all ages

Link to RB Programme: 2.2 Human Health - 2.2.3 Radiation Oncology and Cancer Treatment

Project Description/Abstract: To improve access of the population to oncology services, the Government of Georgia has implemented the following project: a multi-profile university hospital will be built in Rukhi, in the Zugdidi Municipality, which is planned to be completed in 2017 and equipped in the period 2018-2019. The village Rukhi is located in the border zone of the occupied territory of Abkhasia. Medical services will be provided by the hospital to the residents of the occupied territory of Abkhasia, the housholds of Zugdidi and the surrounding municipalities (Samegrelo/Upper Svaneti, with a population of 330 900, according to 2014 census data). Since hospitals in Abkhazia and the adjacent municipalities of Zugdidi do not provide radiation services, the population of Samegrelo/Upper Svaneti has to seek these service in Tbilisi, which is located 500 kilometers away. A high-technology, multi-profile hospital in Rukhi will be the only facility to offer radiation oncology services to the above mentioned population. Therefore, equipping the hospital with a radiation accelerator is of highest priority for the Ministry of Labor, Health and Social Affairs (MoLHSA) to guarantee access to radiation oncology services for the population of this vulnerable region.

Problem to be addressed: The World Health Organization (WHO) estimates the incidence of malignant tumors in Georgia to be lower than the rates in the Commonwealth of Independent States (CIS) and European countries. To improve cancer surveillance, the Ministry of Labor, Health and Social Affairs (MoLHSA) of Georgia has introduced a population-based cancer registry since 1 January 2015.  Analysis of the registry data has revealed a sharp difference with previous years. In 2014, the aggregate statistics showed 140 new cases of malignancies per 100 000, while according to the new cancer registry data, this figure was 270 per 100 000 in 2015. In Georgia, 47% of cancer patients are diagnosed at stage III or IV. Cancer mortality data are equally alarming. Reduction of cancer mortality and improving 5-year surveillance rates are important priorities of the MoLHSA. These can be achieved by improving early detection and treatment of oncological diseases, and particularly by increasing the availability of modern methods of radiation diagnostics and accessibility to radiation oncology services for patients. There are currently five radiotherapy departments in Georgia: one linear accelerator (LINAC) at the Oncology Centre of Adjara in Batumi, one cobalt-60 unit at the National Cancer Centre in Tbilisi; three LINACs capable of delivering 3D and intensity modulated radiotherapy (IMRT) treatment at the High Technology Medical Centre (Tbilisi); two LINACs that deliver 3D and stereotactic treatment at the Research Institute of Clinical Medicine (Tbilisi); and one LINAC at the Evex Hospital in Kutaisi. Two (and possibly) further radiotherapy departments are planned, one of them with two LINACs at the Hospital of Rukhi (Samegrelo/Upper Svaneti region). With regard to brachytherapy, there are two units in Georgia. Diagnostic nuclear medicine is present in two health care institutions only. There are currently two nuclear medicine departments in Georgia, namely at the High Technology Medical Centre (Tbilisi) and at Aversi Hospital (Tbilisi). Radiotherapy and nuclear medicine services are almost exclusively delivered through the private sector, with the exception of the National Cancer Center in Tbilisi which is unlikely to continue to function in the medium and long term. There are currently 20 radiation oncologists, two nuclear medicine doctors, 18 medical physicists and 40 radiation technologists employed in the radiotherapy and nuclear medicine services in the country. The majority of radiation oncologists are in Tbilisi and three are located outside of the capital (two in Batumi, one in Kutaisi). Both doctors of nuclear medicine are also employed in Tbilisi. Most of the medical physicists work in Tbilisi and only four of them work in other regions. Also, most of the radiation technologists work in the hospitals of the capital Tbilisi. Therefore, it is assumed that radiotherapy is an underused resource compared to international standards (especially in developed countries). A major problem is the lack of operational radiotherapy departments in some regions (such as the northwest of Georgia with about 1.5 million people) and the limited access, due to the geography. It is planned to develop public services in the future, e.g. a State hospital that is under construction close to the Abkhazia border (Rukhis Hospital in Rukhi Samegrelo). It will be completed in 2017 and equipped in the period 2018-2019. The new hospitals will improve the geographical availability of oncological systems (financial availability exists under the universal healthcare coverage) and early cancer diagnostic and treatment outcomes for the population in Western Georgia. This will lead to a reduction of cancer deaths and significant improvement of the health conditions of the population. As a result, mortality and morbidity related to oncological diseases will be decreased in the country.

Stakeholder: (1) In Georgia, the policy of the health care system is defined by the Ministry of Health which is also responsible for providing access to medical services for the Georgian population. Access to high quality oncological services is a high priority for the Ministry. To this end, a project is carried out to provide geographical availability of oncological services for the Samegrelo/Upper Svaneti population (financial availability exists since 2013 under the universal healthcare coverage). This project foresees building and equipping a multi-profile clinic in the village of Rukhi in the region of Samegrelo/Upper Svaneti. The implementation of the project was started in 2014. The building process will be accomplished in 2017 and during 2018-2019, the hospital will be equipped (it is planned to be equipped with machines for radiotherapy services, including brachytherapy) and human resources will be put in place. The main responsibility for the success of this project rests with the Ministry. (2) The Ministry of Environment and Natural Resources Protection of Georgia is the major local partner of the Ministry of Health in implementing the project. It also plays a major role in the preparation of the regulatory framework. (3) The Ministry of Finance of Georgia is in charge of mobilizing financial resources in the country. It is a major partner for the Ministry of Health and has an important impact on the success of the project. (4) Medical institutions, such as the Rukhis Hospital in Rukhi Samegrelo, are involved in the project and have an important impact on its implementation. Also, the further stability of the project depends on them. (5) Health care workers: for the success of the project, it is necessary to recognize the role and importance of health care workers, as the project cannot be implemented without their readiness to be members of the project.  (6) Patients: the aim of the project is to improve the health of the Georgian population. Therefore, potential patients are primarily interested in the implementation and success of the project. (7) The media and non-governmental organizations (NGOs) are important stakeholders, because their interests are to advocate patients, defend human rights, improve access to medical services, and detect the influence of nuclear and radiation instruments on the environment. The IAEA has a significant role and importance in the success of the project, as the accomplishment and stability of every step depend on IAEA support. The project needs technical support (assistance by experts, human resource development, and others) and investment. The Ministry of Labor, Health and Social Affairs of Georgia is the main stakeholder as the author and enforcer of the project.

Partnerships: Implementation, success and further stability of the project is fully dependent on the cooperation with the IAEA, which is also the main partner of the Ministry of Health in the project. Areas of collaboration with the IAEA include support in the phases of project preparation, planning, organization and implementation, which are expressed by means of expert support and financial investment. During the implementation of the project, we collaborate with the World Health Organization, which will provide us with additional support. Also, we will cooperate with sectoral health care worker associations, medical universities, equipment manufacturers, and experts.

Overall Objective: To decreased mortality and morbidity related to oncological diseases.

Role of nuclear technology and IAEA: Nuclear medicine has been developing in Georgia over the last ten years and nuclear technology plays a major role in cancer treatment. On that note, the Government's primary goal at this stage is an improved access to radiation medicine services for the population and assurance of the services’ security and quality. At present, there are five radiotherapy departments in Georgia: one LINAC at the Oncology Centre of Adjara in Batumi; one cobalt-60 unit at the National Cancer Centre in Tbilisi; three LINACs capable of delivering 3D and IMRT treatment at the High Technology Medical Centre (Tbilisi); two LINACs that deliver 3D and stereotactic treatment at the Research Institute of Clinical Medicine (Tbilisi); and one LINAC at the Evex Hospital in Kutaisi. Two (and possibly) further radiotherapy departments are planned, one of them with two LINACs at the Hospital of Rukhi (Samegrelo/Upper Svaneti region). With regard to brachytherapy, there are two units in Georgia. Radiotherapy medicine services are almost exclusively delivered through the private sector, with the exception of the National Cancer Center in Tbilisi which is unlikely to continue to function in the medium and long term. There are currently 20 radiation oncologists, 18 medical physicists and 40 radiation technologists employed in the radiotherapy services in the country. The majority of radiation oncologists are in Tbilisi and three are located outside of the capital (two in Batumi, one in Kutaisi). Most of the medical physicists work in Tbilisi and only four of them work in other regions. Also, most of the radiation technologists work in the hospitals of the capital Tbilisi. Within the project, the development of radiation oncology services in the Rukhi Hospital is planned. Rukhi Hospital will be under the ownership of State, so the Ministry of Health will have higher influence on it. The building process of the clinic was started in 2014 and will be accomplished in 2017. The department of radiation oncology will be equipped during the period 2018-2019. Human resources will be employed until the end of 2017 and trained during 2018-2019. This means that the project is planned for 2018-2019, when the Rukhi Hospital will be equipped with a radiation accelerator; appropriate human resources will be trained/retrained; and mechanisms for quality assurance and control will be established. For training of staff, resources of the project GEO6010 "Creating a Radiation Medicine Education and Training Strategy" (2016-2018) will be used and training will start in 2018. All activities will be carried out with the support and direct participation of the IAEA whose involvement in the project is the foundation for success and sustainability.

Participating Member State(s): 
Georgia

Physical infrastructure and human resources: 1. Multi-profile University Hospital in Rukhi, Zugdidi municipality; 2. Medical doctors (radiation oncologysts), radiation teqnologysts, medical phisisists, nurses. Within the project radiation therapy staff (Radiation Therapy Technologists, Radiation Oncologists, Medical Physicist, Oncology Nurses) will be trained.

Sustainability: Ministry of Labour, Health and Social Affairs of Georgia is interested to improve health  of georgian population by reduce mortality and morbidity of oncological deases in Georgia and  also to reduction health care expenditures.The project will be implemented by the Ministry of Labour, Health and Social Affairs of Georgia for state insitutions which  control for him is more easy. Within the project radiation oncology services in Rukhi’s hospital will be developed. Also, appropriate health care workers will be trained / retrained. The Ministry of Health will choose personnel for Rukhi hospital up to 2018 year. Taken into account the fact that project is implemented in the region, where geographic availability of radiation medicine services is limited for the population, state hospitals are involved in the program. Hospital will be equipped with modern technology and the services will be provided by project-trained staff. It will contribute sustainability of the project in the future.

Safety regulatory infrastructure: The legislative framework for radiation safety and the security of sources is provided primarily through the Law on Nuclear and Radiation Safety (Law 5912, March 2012) and the Law on Healthcare (Law 1139, 1997).   The general Law on Licensing and Permits is utilized for the purpose of issuing licences  relating to facilities and activities involving ionizing radiation.

Other considerations, e.g. environment, gender: In general, the beneficiaries will include the Georgian population, and some residents from Samegelo- Upper Svaneti region (the population is 330 900,  according to 2014 census data) and occupied territories of  Abkhasia for  radiotherapy services.  It is considered to have no environmental impacts regarding with this  Activity.

Implementation strategy: Uneven geographical distribution of medical services is familiar for Georgia. This firstly comprises high-tech services such as radial medical services. As mentioned above, there are currently 5 radiotherapy departments in Georgia: one linac at the Oncology Centre of Adjara in Batumi, one cobalt-60 unit at the National Cancer Centre in Tbilisi, three linacs capable of delivering 3D and IMRT treatment at the High Technology Medical Centre (Tbilisi), two linacs that deliver 3D and stereotactic treatment at the Research Institute of Clinical Medicine (Tbilisi) and one linac at the Evex Hospital in Kutaisi. The population of Samegrelo – Upper Svaneti who need to use services of radiation oncology have to go in Tbilisi in order to get one (on this stage Kutaisi’s services are being developed). Acording to this fact, in order to improve access on high-tech services for the regions’ population of Samegrelo – Upper Svaneti the Ministry of Health has started building a multi-profile hospital in Rukhi in 2014 year. Within which the provision of radiation oncology services (radiotherapy, brachytherapy) is provided. Implementation of the process is highly prioritized for Georgian side, because it will improve the availability of access on radiation oncology services in the region of Samegrelo – Upper Svanety. Also, it has political meaning, because it is located near the border of Abkhasia, so it will also provide services to the population of Abkhasia, who have no access on such treatment. The building of Rukhi hospital will be ended in 2017 year, after which it will be equipped. The hospital will be fully operational in 2019.  During 2014-2016 year  the Ministry of Health has spent about 11 000 000 euro on the building proves ( 26 180 400 GEL), in 2017 year 2 000 000 euro is thought to be spent on accomplishing the building process (5 000 000 GEL). A significant portion of this amount (about 20%) was used to construct a radiation oncology department. At this stage construction of the Radiation Oncology Department, in which the provision of radiation therapy and brachytherapy services is completed, also construction of two bunkers is completed (see attached document). The Ministry of Health will equip the hospital from its budget in 2018-2019 year. At this stage, it is difficult to talk about the budget allocations (the primary project will be ready in August 2017), but in assignments of 2018 year it will be provided for equipping the Radiation Department. Choosing / preparing human resources has a great importance for activation of the hospital. The selection of human resources for the Department of Radiation Oncology is especially important because the range of proper specialists, especially in regions, is very low. The ministry is planning to choose human resources for radiation oncology department of Rukhi hospital by the end of 2017 year, and to prepare them from 2018 year. For training will be used the resource of the project - GEO6010 "Creating a Radiation Medicine Education and Training Strategy" (2016-2018). The strategy is to tackle the cancer problem in Georgia by applying  early-diagnosis and treatment. Strategy of implementation is prepared by the Ministry (see attached document).

Monitoring and progress reporting: Project monitoring will be conducted on a regular basis as per the defined milestones in the  work plan. The reporting on the progress of the project will be conducted every six months. and reports on the Technical Officer and Project Management Officer supervision.

Risk management: The project will be implemented by the Ministry of Labour, Health and Social Affairs of Georgia. There are several assumptions which needs to be considered when evaluating risks.  They are as follows: Govermants commitment, including allocation of necessary resourses, prolong the installation of equipment, availability of adequate training course, availability of adequate exsperts, etc.

| CORE FINANCING |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Year | Human Resource Components (Euros) |  |  |  |  |  | Procurement Components (Euros) |  |  | Total (Euros) |
|  | Experts | Meetings/ Workshop | Fellow-ships | Scientific Visits | Training Courses | Sub-Total | Equipment | Sub-Contracts | Sub-Total |  |
| 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 350 000 | 0 | 350 000 | 350 000 |
| 2020 | 24 150 | 0 | 0 | 0 | 0 | 24 150 | 340 350 | 0 | 340 350 | 364 500 |
| FOOTNOTE-a/ FINANCING |  |  |  |  |  |  |  |  |  |  |
| Year | Human Resource Components (Euros) |  |  |  |  |  | Procurement Components (Euros) |  |  | Total (Euros) |
|  | Experts | Meetings/ Workshop | Fellow-ships | Scientific Visits | Training Courses | Sub-Total | Equipment | Sub-Contracts | Sub-Total |  |
| 2018 | 15 750 | 0 | 113 400 | 0 | 0 | 129 150 | 0 | 0 | 0 | 129 150 |
| 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 930 000 | 0 | 930 000 | 930 000 |
| 2020 | 17 850 | 0 | 0 | 0 | 0 | 17 850 | 0 | 0 | 0 | 17 850 |
| First Year Approved : 2018 |  |  |  |  |  |  |  |  |  |  |
| Non-Agency FINANCING |  |  |  |  |  |  |  |  |  |  |
| Year | Human Resource Components (Euros) |  |  |  |  |  | Procurement Components (Euros) |  |  | Total (Euros) |
|  | Experts | Meetings/ Workshop | Fellow-ships | Scientific Visits | Training Courses | Sub-Total | Equipment | Sub-Contracts | Sub-Total |  |
| 2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 500 | 1 500 | 1 500 |
| 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 800 000 | 0 | 800 000 | 800 000 |
| 2020 | 0 | 0 | 0 | 0 | 0 | 0 | 800 000 | 76 000 | 876 000 | 876 000 |
| First Year Approved : 2018 |  |  |  |  |  |  |  |  |  |  |

Logical Framework Matrix (LFM)

|  | Design Element | Indicator | Means of Verification | Assumptions |
| --- | --- | --- | --- | --- |
| Outcome | Accessibility to effective treatment of oncological diseases for population in Georgia improved. | new cases of malignancies per 100 000 in 2022 reduced by 10% | Medical statistic | Govermants commitment, including allocation of necessary resourses |
| Output | 1 Equipment installed and operational for providing radiotherapy services. | Radiation Oncology Department in Rukhis hospital enacted on octomber 1, 2020; | Mission report | Lack of financial resources |
|  | 2 Qualified staff available to deliver radiotherapy services. | Trained staff ratio in 2020 increased by 20% | Mission report | Shortage of adequate personnel |
|  | 3 QA/QC system established in radiotherapy services. | Since Jenuary 2021 in Rukhis hospital the routine radiological assessment is conducted. | Data of radiological assassment. | Lack of appropriate funding. |
| Activity | 1.1 RT: Procurement of equipment for radiotherapy services; | Contract with subcontractor is issued and implemented on April 15, 2020 | Counterpart report | Prolong the procurement and customs services |
|  | 1.2 RT: Physical infrastructure for radiotherapy in place and operational; | Contract with subcontractor is issued and implemented on Octomber 1, 2020 | Counterpart record | Prolong the procurement and customs services |
|  | 2.1 RT:Training of radiotherapy services staff (Radiation Oncologists, RTTs, Oncology Nurses) | Training of personnel is completed on December 15, 2018 | Counterpart report (project - GEO6010 "Creating a Radiation Medicine Education and Training Strategy" (2016-2018)) | Availability of correct schemes of training |
|  | 2.2 MP: Training of Medical Physicists for radiotherapy services. | Training of personnel is completed on jenuary 1, 2019 | Counterpart report (project - GEO6010 "Creating a Radiation Medicine Education and Training Strategy" (2016-2018)) | Availability of correct schemes of training |
|  | 3.1 RT: Develop QA/QC and clinical protocols; | QA/QC system is developed on december 31, 2020 | Counterpart report | Availability of correct schemes of training |
|  | 3.2 MP: Develop QA/QC and clinical protocols; | QA/QC system is developed on December 31, 2020 | Counterpart report | Availability of correct schemes of training |
|  | 3.3 RT: Dosimetry and radiation protection equipment is in place and operational | Equipment is tested on december 31, 2020 | Counterpart report. | Availability of appropriate subcontractor. |
| Input | 1.1.1 RT: EQ Procurement of CT-simulation, brachytherapy equipment. | Equipment has purchased on December 10, 2019 | Counterpart report. | Availability of adequate equipment, availability of appropriate subcontractor. |
|  | 1.1.2 RT: EQ Procurement of Imobilization equipment | Equipment has purchased on September 10, 2020 | Counterpart report. | Availability of adequate equipment, availability of appropriate subcontractor |
|  | 1.1.3 RT: EQ Procurement of Accelerator (with treatment planning system and spear parts) |  |  |  |
|  | 1.1.4 RT: EQ Procurement of Accelerator (with treatment planning system and spear parts) |  |  |  |
|  | 1.1.5 RT: EQ Procurement of Accelerator (with treatment planning system and spera parts) | Equipment has purchased on September 10, 2020 | Counterpart report. | Availability of adequate equipment, availability of appropriate subcontractor |
|  | 1.2.1 RT: Equipment installed | Equipmant instailled on December 1, 2020. | Counterpart report. | Availability of adequate equipment, availability of appropriate subcontractor |
|  | 1.2.2 RT: Radiation onkology department infrastructure (wards, mouldroom and etc) ready get to patients | Department is ready get to patients on Octomber 31, 2020 | Counterpart report. | Availability of adequate equipment, availability of appropriate subcontractor |
|  | 2.1.1 RT: Selecting of personal (radiation oncologysts, radiation tecnologysts, nurses) | Selection completed on March 1, 2018 | Counterpart report. | Availability of appropriate health care workers |
|  | 2.1.2 RT: IEX - Training of Radiation Therapy Technologists | Event held on Octomber 31, 2018 | Counterpart report (project - GEO6010 "Creating a Radiation Medicine Education and Training Strategy" (2016-2018)). | Availability of adequate exspert. |
|  | 2.1.3 RT: IEX - Training of Radiation Therapy Technologists | Event held on Octomber 31, 2018 | Counterpart report (project - GEO6010 "Creating a Radiation Medicine Education and Training Strategy" (2016-2018)). | Availability of adequate exspert. |
|  | 2.1.4 RT: Training of Radiation Therapy Technologist. | Event held on Octomber 31, 2018 | Counterpart report (project - GEO6010 "Creating a Radiation Medicine Education and Training Strategy" (2016-2018)). | Availability of adequate training course |
|  | 2.1.5 RT:Training of Radiation Oncologist. | Event held on November15, 2018 | Counterpart report (project - GEO6010 "Creating a Radiation Medicine Education and Training Strategy" (2016-2018)) | Availability of adequate training course |
|  | 2.1.6 RT:Training of Radiation Oncologist. | Event held on November 15, 2018 | Counterpart report (project - GEO6010 "Creating a Radiation Medicine Education and Training Strategy" (2016-2018)) | Availability of adequate training course |
|  | 2.1.7 RT:IEX - Training of a Oncology Nurses (in the place). | Event held on Octomber 15, 2018 | Counterpart report (project - GEO6010 "Creating a Radiation Medicine Education and Training Strategy" (2016-2018)) | Availability of adequate exspert. |
|  | 2.2.1 MP: Selecting of personal (Medical Physicist) | Selection completed on march 15, 2018 | Counterpart report (project - GEO6010 "Creating a Radiation Medicine Education and Training Strategy" (2016-2018)) | Availability of appropriate health care workers |
|  | 2.2.2 MP: Training of a Medical Physicist (for Radiation Therapy) | Event held on Jenuary 15, 2019 | Counterpart report (project - GEO6010 "Creating a Radiation Medicine Education and Training Strategy" (2016-2018)) | Availability of adequate training course |
|  | 3.1.1 RT: IEX - RTTs to establish treatment protocols and workflow for Radiatiom Medicine Department (2 IEX, 1 week) | Event held on December 1, 2020 | Counterpart report. | Availability of adequate exspert. |
|  | 3.1.2 RT: IEX -RTTs to establish treatment protocols and workflow for Radiatiom Medicine Department | Event held on December 15, 2020 | Counterpart report. | Availability of adequate exspert. |
|  | 3.1.3 RT: IEX -Radiation Oncologist to establish clinical protocols and workflow for Radiation Medicine Department (2 IEX, 1 week) | Event held on December 1, 2020 | Counterpart report. | Availability of adequate exspert. |
|  | 3.1.4 RT: IEX -Radiation Oncologist to establish clinical protocols and workflow for Radiation Medicine Departament | Event held on December 15, 2018 | Counterpart report. | Availability of adequate exspert. |
|  | 3.1.5 RT: Developing guidelines and protocols for Radiation Medicine Departament | Guidelines and protocols are developed on December 31, 2020 | Counterpart report. | Availability of appropriate local exsperts |
|  | 3.2.1 MP: IEX -Medical Physicist to establish QA and QC protocols and workflow for Radiation Medicine Department (2 IEX, 1 week) | Event held on December 15, 2020 | Counterpart report. | Availability of adequate exspert. |
|  | 3.2.2 MP: IEX -Medical Physicist to establish QA and QC protocols and workflow for Radiation Medicine Department (2 IEX, 1 week) | Event held on December 15, 2020 | Counterpart report. | Availability of adequate exspert. |
|  | 3.2.3 MP: Developing guidelines and protocols for Radiation Medicine Departament | Guidelines and protocols are developed on December 31, 2020 | Counterpart report. | Availability of appropriate local exsperts |
|  | 3.3.1 RT: Dosimetry and radiation protection equipment is purchased | Dosimetry and radiation protection equipment is delivered in the facility on December 15,2020 | Counterpart report. | Availability of adequate equipment, availability of appropriate subcontractor |
|  | 3.3.2 RT: IEX - Training for staff in dosimetry and radiation protection (1 IEX, 1 week) | Event held on December 31, 2020 | Counterpart report. | Availability of appropriate local exsperts |