Terms of Reference

for the work delivered by the National Center for Disease Control and Public Health of Georgia

in support of sustainable implementation/enforcement and further development of the

tobacco-control policy that is in line with the FCTC 2030

Terms of Reference

For the FCTC 2030 based work in Georgia that will be provided by the L. Sakvarelidze National Center for Disease Control and Public Health to contribute activities needed for the ensuring sustainability of enforcement of the new tobacco-control law in Georgia and implementation of FCTC.

Background information

Georgia adopted a “new generation” tobacco control legislation in May 2017. Main provisions of the law were enacted since May 2018. In the period of April 2018-March 2019 activities to implement the law were successfully conducted with support of second yearly plan of FCTC 2030 project. Following this, third year workplan for April 2019-March 2020 was developed based on FCTC 2030 country strategy. It aims to ensure sustainability of high compliance rates and further development of tobacco control policy. To provide this there is needed to strengthen multisectoral governance, develop and advocate for changes in the law and updating state policy according to the FCTC, provide sustainability of enforcement and implementation systems, conduct communication campaign. This plan was divided into two, due to end of BCA in December 2019 and first part was successfully implemented in period of June-December 2019. Recent plan is second part (continuations) of the yearly plan until March 2020.

Deliverables, timeline and costs

|  |  |  | Timeline |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | January | February | March |
| 1. Strengthening multisectoral governance and improvement of the policy |  |  |  |  |  |
| NCDC management costs and technical expertise |  |  |  |  |  |
| Updating Tobacco Control National Strategy and Action Plan | Draft new Tobacco Control National Strategy and Action Plan and agree with the stakeholders | Draft of the new Tobacco Control National Strategy and Action Plan |  |  |  |
| Epidemiological modeling to identify a timeline to achieve a smoke free Georgia | Carry out an epidemiological modelling for Georgia with the foreign technical assistance for identifying timeline for achieving smoke free Georgia | Timeline and report of achieving smoke free status of Georgia |  |  |  |
| Advocacy to incorporate WHO FCTC implementation in Georgia’s SDG plans and indicators | Consultative meetings with relevant ministries and international agencies to facilitate incorporation of WHO FCTC implementation in Georgia’s SDG plans and indicators | Plan of incorporation of FCTC implementation in Georgian NSDGs |  |  |  |
| Advocacy for mandatory brief interventions, NRT availability | develop policy briefs in support of increasing access and availability of the tobacco cessation services including medications and disseminate among relevant stakeholders | Policy briefs in support of increasing access and availability of the tobacco cessation services |  |  |  |
| 2. Ensure sustainable compliance and enforcement of acting regulations |  |  |  |  |  |
| Strengthening implementation and enforcement practice of the law by local governments | Meetings with local level governments/municipalities to improve smoke-free law compliance on municipal level and discuss opportunities of implementing WHO smoke-free city concept | Report on meetings with local government |  |  |  |
| Support approval and implementation of the Normative Act on art. 5.3 | Develop policy briefs/informational leaflets about obligations on ART.5.3 under the Tobacco Control Law of Georgia including obligation of approving relevant Normative Act and conduct targeted meetings with relevant stakeholders to catalyze the approval process. Training of the responsible state structures to implement the regulation | Endorsed Normative Act of article 5.3, Training of responsible agencies |  |  |  |
| Tobacco prevalence national survey | Development report of the study | Report of the study |  |  |  |
| 3. Communication campaign |  |  |  |  |  |
| Conduct communication campaign for quit smoking | Conduct campaign for quit smoking according to the plan prepared in previous FCTC 2030 plan | Communication plan and report of its implementation |  |  |  |
| Total |  |  |  |  |  |

Duration: period of January – 15 March 2020

Responsible officer

Kakha Gvinianidze

National Professional Officer of Tobacco Control

WHO Country Office Georgia

Office: Barnov Str. 81, 0179 Tbilisi

Tel.:    +995 32 2998073

+995599920760

E-mail: gvinianidzek@who.int