## Sheet1
P173911 | Georgia Emergency COVID-19 Response Project | Georgia | Health, Nutrition & Population | Volkan Cetinkaya, Maddalena Honorati | IPF | 2020-04-30 | 2022-04-30 | 80000000 | 0 | 80000000 | The project is co-financed with Asian Infrastructure Investment Bank (AIIB) - WB $80 million and AIIB $100 million. WB is providing HEIS. UN - The task team played a major role in organizing a procurement coordination meeting between the implementing agency and the UN agencies to help secure critical medical equipment and supplies. On May 8th, the project agency received the list of available items from the UN agencies. On May 25th, MoH has sent confirmed list of items to receive offers from UN as well as BFP. On June 4th, the ministry has received offer from UN on PPE, Hospital Equipment and Emergency cars. UNICEF has offered to supply Xpert (R) Xpress SARS-CoV-2 diagnostic test kits totalling USD 478,240.40 to NCDC. The contract will be financed under this project. PP - As of now, four contracts and one amendement are signed under Direct Contracting with local dealers: Procurement of Rapid COVID-19 Test kits (97,000 unit)- $504,000; Procurement of Critical Care Ventilators (30 units) for $405,000; and Mobile Emergency Ventilators - $313,476. Procurement of Standard COVID19 AG tests (50,000) - $612,200. The procurement of Real-Time PCR testing Machine is ongoing. NoB issued for Direct Contracting to Roche for IVD machine. The contract negotiation is planned on June 29. Overall value - EUR 440,000. No Objection was issued to procure PCR tests and extraction kits - overall value of the contracts - $ 6,851,810. The contracts will be finailized on June 29th. RFQ for Laboratory supplies is under preparation. BFP - The MoH has received ten offers under BFP, including offer on PPEs. ROI was registered from MoH on PPE items offered by Commander. On June 26, MoH has received final offer from Commander. This project has a provision for retroactive financing. MoH has proposed about 170 contracts (abut $6 million) for retroactive financing. The Bank team is conducting due diligence for acceptability and eligibility.