## Expertise days follow up 1year
[7 empty] | 2019 | [8 empty] | 2020 | [15 empty] | 2021 | [5 empty] | IDP/coordination | PWD | PWD | PWD | PWD | PWD | PWD | Health fin | Mental Health | Mental Health | Mental Health | Mental Health | Mental Health | Mental Health | IDP | IDP | IDP
|  | Total days - 1st year |  |  |  |  | April | May | June | July | Aug | Sep 19 | Oct | Nov | Dec | Jan | Fev | Mars | Total days - 2nd year |  |  |  | Avr | Mai | Juin | Juillet | Aout | Sept | Oct | Nov. | Déc. | Jan | Fevr | Mars |  |  | LAMBINON | POGORZELSKI | TRETYAK | DEIMAT | Bitinas | ??? | VILLAC | local experts | LAI | LEFEBVRE | KOVESS | ??? | Local experts | ??? | Local expert | ??? | Local expert | Local expert
Activities |  | TL | Int. | Local | Days used |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | TL | Int. | Local |  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Project coordination
C1 | Installation RTA
C.2 | Steering Committee |  |  |  | #REF! | 0 | [15 empty] | 0
C3 | Project Finalization
C4 | Administrative and financial project closure
Inception phase |  | TL | InE | LE | [14 empty] | TL | InE | LE | [14 empty] | 0
0.1 | Inception | 10 | 25 |  | #REF! | 25 | 1: 15; 4: 10 | [17 empty] | 25 | 10 | 10 |  |  | 5
0.2 | Launch event |  |  |  | #REF!
0
| Pillar I : Enhancing social support to vulnerable groups | [34 empty] | 0
| Improving the support to peoples with disabilities (PWD) by developing functional/social model of assessing and granting disability status in line with the UN Convention on the Rights of Persons with disabilities | [34 empty] | 0
1.1.1 | Development of methodology for piloting of disability assessment in Samtskhe Javakheti region |  | 27 |  | #REF! | 27 | 1: 17; 4: 10 | [17 empty] | 27 |  |  | 15 | 12
|  |  |  | 20 |  | 20 | 4: 20 | [17 empty] | 20 | [7 empty] | 20
1.1.2 | Piloting of assessment instruments in Samtskhe Javakheti region | 20 | 40 |  | #REF! | 40 | 4: 5; 6: 10; 8: 5; 10: 10; 12: 10 | 20 | 20 | [15 empty] | 40 |  |  | 10 | 20 | 10
|  |  |  | 60 |  | 60 | 4: 20; 5: 20; 6: 20 | [17 empty] | 60 | [7 empty] | 60
|  |  |  | Salaires | [16 empty] | 96 | 96 | 16 | 16 | 16 | 16 | 16 | 16 | [7 empty] | 0 | bar: 4 to 12
1.1.3 | Policy impact assessment based on the results of piloting in two Georgian regions and best international practices in implementing the functional/ social model for evaluation of disability | 5 | 5 |  |  | 5 | 10: 5 | 15 | 50 | [15 empty] | 5 | [6 empty] | 5
|  |  |  | 15 |  | 15 | 10: 15 | [17 empty] | 15 | [7 empty] | 15
1.1.4 | Proposal for minimum support package for people/children with disabilities | 5 | [16 empty] | 20 | 60 |  | 5 |  | 5 | [11 empty] | 5 |  |  |  | 5
[21 empty] | 100 | 10 |  | 10 | [11 empty] | 10 | [7 empty] | 10
1.1.5 | Support in drafting a realistic Action Plan for implementation of functional/social model in Georgia | [17 empty] | 25 | 30 | 60 | [14 empty] | 0
1.1.6 | Support in Implementation of awareness raising compaigns and consultations about implementation of functional/social model in Georgia | 10 | 10 |  | #REF! | 10 | 6: 10 | 5 | 20 |  | 10 |  |  |  |  | 10 | [8 empty] | 20 | [5 empty] | 20
|  |  |  | 20 |  | 20 | 6: 20 |  |  | 40 | 20 |  |  |  |  | 20 | [8 empty] | 40 | [7 empty] | 40
1.1.7 | Study Visit | 10 | 10 |  | #REF! | 10 | 11: 10 | [17 empty] | 10 |  | 5 | 5
Pillar 2 : Ensure affordable and quality healthcare and promote of a healthy lifestyle
Component 2.1 : Improve the effectiveness and efficiency of universal healthcare and other programs
2.1.1 | Define standard operating procedures for the implementation of performance-based contracting, especially to primary health care | 5 | 17 |  | #REF! | 17 | 1: 7; 6: 5; 8: 5 | 5 | 8 |  | 5 |  | 5 | [11 empty] | 7 | [8 empty] | 7
|  |  |  | 10 |  | 10 | 7: 5; 9: 5 |  |  | 10
2.1.2 | Analyse the functioning of IT in the health sector (E health) | 5 | 10 | 20 | #REF! | 10 | 1: 7; 12: 3 |  | 20 | 20 | [14 empty] | 7 | [6 empty] | 7
2.1.3 | Study visit |  |  |  | #REF! | [13 empty] | 10 | 10 | [15 empty] | 0
Component 2.2 : Strenghten Mental Health services
2.2.1 | Development of the roadmap for implementation of deinstitutionalization and the development of community based services in line with recomendations of WHO report | 39 | 65 |  | #REF! | 65 | 2: 5; 4: 10; 6: 15; 8: 10; 10: 10; 11: 10; 12: 5 | [17 empty] | 50 | [9 empty] | 5 | 35 | 10
|  |  |  | 20 |  | 20 | 6: 5; 8: 5; 11: 10 | [17 empty] | 90 | [12 empty] | 90
2.2.2 | Strenghtening monitoring mechanisms for the ministry | 15 | 25 |  | #REF! | 25 | 4: 5; 7: 5; 9: 5; 10: 5; 11: 5 | [17 empty] | 25 | [13 empty] | 25
2.2.3 | Improving the legal framework | 10 | 10 |  | #REF! | 10 | 11: 5; 12: 5 | [27 empty] | 5
|  |  |  | 20 |  | 20 | 11: 10; 12: 10 | [17 empty] | 15 | [14 empty] | 15
2.2.4 | Study visit |  |  |  | #REF! | [13 empty] | 10 | 10 | [15 empty] | 0
0
Pillar 3 : Optimizing resources allocated to IDP needs
3.1 | Impact analysis of the different reform scenarii of IDP allowance (from a status-based government benefit to a needs-based benefit) | 10 | 15 |  | #REF! | 15 | 6: 5; 8: 5; 9: 5 |  | 25 | [15 empty] | 0
|  |  |  | 10 |  | 10 | 8: 5; 9: 5 |  |  | 10
3.2 | Elaboration of a communication strategy for the reform | 10 | 10 |  | #REF! | 10 | 10: 5; 12: 5 |  | 25 | [15 empty] | 0
|  |  |  | 15 |  | 15 | 10: 10; 12: 5 |  |  | 10
3.1.3 | Organisation of workshop about best options for Georgia, including an benchmark of other countries' experiences in management of IDP issues |  |  |  | #REF! | [30 empty] | 0
0
TOTAL |  | 154 | 269 | 210 | #REF! | 459 | 46 | 5 | 0 | 80 | 20 | 90 | 10 | 35 | 20 | 60 | 50 | 43 | 110 | 278 | 346 | 146 | 16 | 36 | 16 | 16 | 46 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 1485 | 471 | 10 | 15 | 30 | 37 |  |  | 12 |  | 7 | 111

## Planning experts
WEEKS | DATES | Project coordination | NAME OF ACTIVITY | EXPERTS | TYPE OF CONTRACT (statut) | NUMBER OF DAYS | COMMENTS | SL | PURPOSE OF MISSION | PREALABLES | EXPECTED RESULTS
[7 empty] | 2019-04-01 |  |  |  |  | EXPERTS | Activities | Name of activity
[13 empty] | 0.1 | Inception
[13 empty] | 0.2 | Launch
16 | 14-20/04 |  |  | C.Lambinon | Autorisation cumul | 10 | [5 empty] | C.Lambinon | 1.1 | Development of methodology for piloting of disability assessment in Samtskhe Javakheti region
|  |  |  | A. Pogorzelski |  | 5 | [5 empty] | A. Pogorzelski | 1.2 | Piloting of assessment instruments in Samtskhe Javakheti region
|  | 1.1 | Development of methodology for piloting of disability assessment in Samtskhe Javakheti region | Y.Deimat | Autorisation cumul | 7 | [5 empty] | Y.Deimat | 1.3 | Policy impact assessment based on the results of piloting in two Georgian regions and best international practices in implementing the functional/ social model for evaluation of disability
|  | 1.1 | Development of methodology for piloting of disability assessment in Samtskhe Javakheti region | A. Tretyak |  | 10 | [5 empty] | A. Tretyak | 1.4 | Proposal for minimum support package for people/children with disabilities
|  | 2.1.2 | Analyse the functioning of IT in the health sector (E health) | M. Villac | CDDU | 7 | [5 empty] | M. Villac | 1.5 | Support in drafting a realistic Action Plan for implementation of functional/social model in Georgia
|  | 2.1.1 | Performance-based contracting in PHC | T. Lai | CPS | 7 | [5 empty] | T. Lai | 1.6 | Support in Implementation of awareness raising compaigns and consultations about implementation of functional/social model in Georgia
[12 empty] | V. Kovess | 1.7 | Study Visit
17 | 21-27/04 | [10 empty] | A. Lefebvre | 2.1.1 | Performance-based contracting in PHC
[7 empty] | 2019-05-01 |  |  |  |  | A. Bourdil | 2.1.2 | Analyse the functioning of IT in the health sector (E health)
18 | 28/04-04/05 | [10 empty] | Local expert | 2.2.1 | Deinstitutionalization and mental healthcare strategy
19 | 05-11/05 | [10 empty] | A. Bitinas | 2.2.2 | Elaboration of monitoring mechanisms in mental health institutions (public and private)
20 | 12-18/05 | [11 empty] | 2.2.3 | Formulation of recomendations for improving of legal framework for mental health care in line with best EU practices
[13 empty] | 2.2.4 | Study visit
| 19-25/05 | 2.2.1 | Deinstitutionalization and mental healthcare strategy | A. Lefebvre |  | 0 | confirmed |  |  |  |  | S. Megaladze | 3.1 | Impact analysis of the different reform scenarii of IDP allowance (from a status-based government benefit to a needs-based benefit)
| 19-25/05 | 2.2.1 | Deinstitutionalization and mental healthcare strategy | V. Kovess |  | 5 | confirmed |  | Methodology of epidemiological survey and review of MH activities |  | focal points and partners for epidemiological survey ; planing of A221 |  | 3.2 | Elaboration of a communication strategy for the reform
22 | 26/05-01/06
2019-06-01
23 | 02-08/06
24 | 09-15/06
25 | 16-22/06
26 | 23-29/06
2019-07-01
27 | 30/06-06/07
28 | 07-13/07 | 1.1 | Development of methodology for piloting of disability assessment in Samtskhe Javakheti region | A. Tretyak |  | 5 | confirmed
|  | 1.1 | Development of methodology for piloting of disability assessment in Samtskhe Javakheti region | Y.Deimat |  | 5 | confirmed
|  | 1.2 | Piloting of assessment instruments in Samtskhe Javakheti region |  |  |  | confirmed |  | local expert training, 112
29 | 14-20/07
30 | 21-27/07 | 1.2 | Piloting of assessment instruments in Samtskhe Javakheti region | A. Tretyak |  | 3 | 25-26/07
31 | 28/07-03/08 | 2.2.1 | Deinstitutionalization and mental healthcare strategy | A. Bourdil |  | 5 | OK
|  | 2.2.1 | Deinstitutionalization and mental healthcare strategy | A. Lefebvre |  | 5 | Ok
|  | 0.1 | Inception | A. Bitinas |  | 5 | 25/07-3/08
|  | 0.1 | Inception | A. Pogorzelski |  | 5 | Ok, departure on 29/07
2019-08-01
32 | 04-10/08
33 | 11-17/08 | 1.2 | Piloting of assessment instruments in Samtskhe Javakheti region |  |  | 20 | to be confirmed |  | local expert training
34 | 18-24/08
35 | 24-30/08
2019-09-01
36 | 01-07/09 |  | Piloting of assessment instruments in Samtskhe Javakheti region | Local expert |  | 20 |  |  | local expert training
37 | 08-14/09 |  |  | A. Tretyak |  | 5 | to be confirmed |  | 112
|  | 1.2 |  | Y.Deimat |  | 5 | to be confirmed |  | Y.Deimat, 112
|  | 1.6 | Support in Implementation of awareness raising compaigns and consultations about implementation of functional/social model in Georgia |  |  | 5 | to be confirmed |  | communication, 116
|  | 1.6 | Support in Implementation of awareness raising compaigns and consultations about implementation of functional/social model in Georgia | Local expert |  | 20 | to be confirmed |  | local expert communication, 116
|  |  | Support in Implementation of awareness raising compaigns and consultations about implementation of functional/social model in Georgia |  |  | 5 | to be confirmed |  | communication, 116
36 | 01-07/09 | 2.2.1 | Deinstitutionalization and mental healthcare strategy | V. Kovess |  | 5 | to be confirmed
|  |  | Deinstitutionalization and mental healthcare strategy | S. Megaladze |  | 5 | to be confirmed
|  |  | Deinstitutionalization and mental healthcare strategy | Local expert |  | 2 | to be confirmed |  | finance expert
|  | 2.1.1 | Performance-based contracting in PHC | T. Lai |  | 5 | to be confirmed
37 | 08-14/09 | 2.2.1 | Deinstitutionalization and mental healthcare strategy | V. Kovess |  | 2 | to be confirmed
|  | 2.2.2 | Elaboration of monitoring mechanisms in mental health institutions (public and private) | V. Kovess |  | 3 | to be confirmed |  | Assessment of monitoring tools and first recommendations
|  | 2.2.1 | Deinstitutionalization and mental healthcare strategy | S. Megaladze |  | 5 | to be confirmed
|  | 2.2.1 | Deinstitutionalization and mental healthcare strategy | Local expert |  | 3 | to be confirmed |  | finance expert
|  | 2.2.1 | Deinstitutionalization and mental healthcare strategy | A. Lefebvre |  | 2 | to be confirmed
|  | 2.2.1 | Deinstitutionalization and mental healthcare strategy | A. Bourdil |  | 3 | to be confirmed |  | finance
|  | 2.1.1 | Performance-based contracting in PHC | T. Lai |  | 5 | to be confirmed
|  | 3.1 | Impact analysis of the different reform scenarii of IDP allowance (from a status-based government benefit to a needs-based benefit) |  |  | 3 | to be confirmed
|  | 3.1 | Impact analysis of the different reform scenarii of IDP allowance (from a status-based government benefit to a needs-based benefit) | A. Pogorzelski |  | 2 | to be confirmed
2019-10-01
40 | 29/09- 05/10
29/09- 05/10
29/09- 05/10
06-12/10
41 | 13-19/10 | 2.1.1 | Performance-based contracting in PHC | Local expert |  | 5 | to be confirmed
42 | 20-26/10
43 | 27/10-02/11 | 2.2.1 | Deinstitutionalization and mental healthcare strategy | V. Kovess |  | 2 | to be confirmed
43 |  | 2.2.2 | Elaboration of monitoring mechanisms in mental health institutions (public and private) | V. Kovess |  | 5 | to be confirmed
2019-11-01
44 | 03-09/11 | 3.1 | Impact analysis of the different reform scenarii of IDP allowance (from a status-based government benefit to a needs-based benefit) |  |  | 5 | to be confirmed
44 | 03-09/11 | 3.1 | Impact analysis of the different reform scenarii of IDP allowance (from a status-based government benefit to a needs-based benefit) | Local expert |  | 5 | to be confirmed
44 | 03-09/11
45 | 10-16/11
46 | 17-23/11 | 1.2 | Piloting of assessment instruments in Samtskhe Javakheti region | Y.Deimat |  | 5 | to be confirmed |  | Y.Deimat, 112
|  | 2.2.1 | Deinstitutionalization and mental healthcare strategy | A. Lefebvre |  | 3 | to be confirmed
|  | 2.2.1 | Deinstitutionalization and mental healthcare strategy | Local expert |  | 5 | to be confirmed
47 | 24-30/11 | 2.2.2 | Elaboration of monitoring mechanisms in mental health institutions (public and private) | V. Kovess |  | 5 | to be confirmed
2019-12-01
49 | 08-14/12 | 3.1 | Impact analysis of the different reform scenarii of IDP allowance (from a status-based government benefit to a needs-based benefit) | Local expert |  | 5 | to be confirmed
|  | 3.1 | Impact analysis of the different reform scenarii of IDP allowance (from a status-based government benefit to a needs-based benefit) |  |  | 2 | to be confirmed
|  | 3.1 | Impact analysis of the different reform scenarii of IDP allowance (from a status-based government benefit to a needs-based benefit) | A. Pogorzelski |  | 3 | to be confirmed
|  | 2.1.1 | Performance-based contracting in PHC | Local expert |  |  | to be confirmed
|  | 2.2.2 | Elaboration of monitoring mechanisms in mental health institutions (public and private) | V. Kovess |  | 5 | to be confirmed
|  | 2.2.1 | Deinstitutionalization and mental healthcare strategy | A. Bourdil |  | 2 | to be confirmed |  | finance
2020-01-01
2 | 05-11/01
3 | 12-18/01 | 2.2.2 | Elaboration of monitoring mechanisms in mental health institutions (public and private) | V. Kovess |  | 5 | to be confirmed
|  | 2.2.1 | Elaboration of monitoring mechanisms in mental health institutions (public and private) | A. Bourdil |  | 5 | to be confirmed
|  | 2.2.1 | Elaboration of monitoring mechanisms in mental health institutions (public and private) | A. Lefebvre |  | 5 | to be confirmed
4 | 19-25/01 | 1.2 |  | A. Tretyak |  | 5 | to be confirmed |  | 112
|  | 1.2 |  |  |  | 5 | to be confirmed |  | Y.Deimat, 112
|  | 1.3 |  |  |  | 5 | to be confirmed |  | 1,1,3 Villac
|  | 1.3 |  | Local expert |  | 15 | to be confirmed |  | 1,1,3 local
|  | 1.4 |  |  |  | 5 | to be confirmed |  | 1,1,4 ???
|  | 1.4 |  | Local expert |  | 10 | to be confirmed |  | 1,1,4 local
|  | 1.6 |  |  |  | 5 | to be confirmed |  | communication, 116
|  | 1.6 |  | Local expert |  | 10 | to be confirmed |  | local expert communication, 116
|  | 2.2.1 | Deinstitutionalization and mental healthcare strategy | V. Kovess |  | 5 | to be confirmed
5 | 26/01-01/02 | 3.2 | Elaboration of a communication strategy for the reform |  |  | 5 | to be confirmed
|  | 3.2 | Elaboration of a communication strategy for the reform | Local expert |  | 5 | to be confirmed
2020-02-01
6 | 2-8/02 | 3.2 | Elaboration of a communication strategy for the reform | Local expert |  | 5 | to be confirmed |  | study visit
7 | 09-15/02 | 2.2.3 | Formulation of recomendations for improving of legal framework for mental health care in line with best EU practices | V. Kovess |  | 5 | to be confirmed
|  |  | Formulation of recomendations for improving of legal framework for mental health care in line with best EU practices | Local expert |  | 5 | to be confirmed
|  | 2.2.1 | Deinstitutionalization and mental healthcare strategy | Local expert |  | 5 | to be confirmed |  | finance
8 | 16-22/02 | 2.2.2 | Elaboration of monitoring mechanisms in mental health institutions (public and private) | V. Kovess |  | 5 | to be confirmed
|  | 2.2.1 | Deinstitutionalization and mental healthcare strategy | A. Lefebvre |  | 5 | to be confirmed
|  | 2.2.1 | Deinstitutionalization and mental healthcare strategy | A. Bourdil |  | 5 | to be confirmed
|  | 2.2.1 | Deinstitutionalization and mental healthcare strategy | Local expert |  | 5 | to be confirmed |  | finance
|  | 2.2.3 | Formulation of recomendations for improving of legal framework for mental health care in line with best EU practices | Local expert |  | 5 | to be confirmed
2020-03-01
11 | 08-14/03 | 2.2.3 | Formulation of recomendations for improving of legal framework for mental health care in line with best EU practices | Local expert |  | 5
12 | 15-21/03 | 1.2 |  | A. Tretyak |  | 5 | to be confirmed |  | 112
|  | 1.2 |  | Y.Deimat |  | 5 | to be confirmed |  | Y.Deimat, 112
|  | 2.2.3 | Formulation of recomendations for improving of legal framework for mental health care in line with best EU practices | V. Kovess |  | 5 | to be confirmed
|  |  | Formulation of recomendations for improving of legal framework for mental health care in line with best EU practices | Local expert |  | 5 | to be confirmed
13 | 22-28/03 | 2.2.1 | Deinstitutionalization and mental healthcare strategy | V. Kovess |  | 3 | to be confirmed
|  | 3.2 | Elaboration of a communication strategy for the reform | A. Pogorzelski |  | 2
|  | 3.2 | Elaboration of a communication strategy for the reform |  |  | 3 | to be confirmed
|  | 3.2 | Elaboration of a communication strategy for the reform | Local expert |  | 5 | to be confirmed
439