National Communication Strategy for Immunization

Georgia

2017 - 2021

Ministry of Health for Georgia,

National Centre for Disease Control and Public Health,

National Immunization Programme.

This strategy document has been developed with financial support from GAVI, the technical support of UNICEF Georgia and International Public Health Consultant, Jacqueline Moller Larsen.

Abbreviations	i

1. Introduction	2

2. Background and rationale for a national communication strategy	2

2.1 Current national immunization schedule	2

2.2 Vaccine coverage	3

2.3 Regional and district variations in coverage rates	3

2.4 Findings from the national Knowledge, Attitude and Practice (KAP) survey	4

Vaccine status and timeliness of survey respondents	5

Healthcare workers	5

Public perceptions and practice	6

Profiles of the caregivers of under-vaccinated children	7

Other relevant data	7

2.5 Strategic observations and discussion points	9

3. Aim, strategic goals and general approach	10

4. Communication objectives for each target group	10

Parents of children aged 5 and under	10

Teenagers (aged 12-14) and their parents	10

Primary Care Doctors	10

Primary Care Nurses	11

Policy makers	11

Adults born between 1989 and 2000 who have not been immunized with the MMR vaccine	11

5. Key challenges by each target group	11

6. Messages for each target group and associated channels of communication	13

7. Influencers of target groups	19

8. Action plan with broad costs	19

11. Crisis communication	30

12. New vaccine communication plans	30

13. Accountability, Monitoring and Evaluation Framework	31

Accountability	31

National Communication Strategy for Immunization Steering Group	31

National Communication Strategy for Immunization Working Group	31

Monitoring and evaluation framework	32

Annexes	36

Annex 1 Crisis Communication Plan	36

# Abbreviations

BCC	Behaviour Change Communication

BCG	Bacille Calmette-Guérin Tuberculosis vaccine

CCP	Crisis Communication Plan

DTP	Diphtheria, Tetanus and

EPI	Expanded Programme of Immunization

HCF	Health Care Facility

HCW	Health Care Worker

HepB	Hepatitus B vaccine

HEXA	Vaccine that protects from diphtheria, tetanus, pertussis, hepatitis B, poliomyelitis and 	Haemophilus influenza type b

HPV	Human Papilloma Virus

Hib	Haemophilus influenza type b

ICC  	Interagency Coordinating Committee

IPC	Inter Personal Communication

KAP	Knowledge, Attitude and Practice

MOH	Ministry of Health

MMR 	Mumps Measles and Rubella vaccine

NCDC 	National Centre for Disease Control and Public Health

NIP	National Immunization Programme

OPV	Poliomyelitis vaccine

PCV	Pneumococcal conjugate vaccine

ROTA	Rotavirus

SBCC 	Social and Behaviour Change Communication

SIP	Supplementary Immunization Programme

TIP	Tailoring Immunization programmes

Td	Tetanus, Diphtheria

VPD - 	Vaccine-preventable diseases

# 1. Introduction

This document sets out the National Communication Strategy for Immunization of the Ministry of Health in Georgia for the period, 2017 – 2021. The strategy’s development process has been led by the National Centre for Disease Control and Public Health (NCDC), and coordinated by the National Immunization Programme (NIP) with technical assistance from the Health Promotion Department (HPD). Funding for the strategy development process and the recently conducted knowledge, attitude and practice survey has been provided by GAVI as part of Georgia’s transition from GAVI support. UNICEF has provided technical support and contracted an independent public health consultant to support a participative process involving a wide range of stakeholders in the strategy development. This process has included: a one day stakeholder workshop held in Tbilisi, a series of smaller workshops with and a small team drawn from the NIP, HPD and the MoH, meetings held with the Deputy Minister for Health and key MoH staff, two focus group discussion with primary care nurses and specialist health media, site visits and discussions with a district office and three facilities in less urbanised areas of Tbilisi. Additionally, this strategy has been informed by the findings of the Knowledge, Attitude and Practice survey of public and health professionals conducted by the Health Promotion Division of the NCDC in 2016.

It is expected that the Government of Georgia will fund the bulk of the implementation of the strategy.

# 2. Background and rationale for a national communication strategy

The Ministry of Health and the NCDC have for some time been aware of the need to address strategically the issue of public and professional perceptions of immunization to increase coverage of the childhood immunization schedule. A WHO communications review conducted in 2015 also made this recommendation. GAVI are now funding its development as part of Georgia’s transition from GAVI funding.

Although at a national level coverage rates for many vaccines are relatively high, all antigens are below the WHO recommended 95%. Certain vaccines have better coverage than others while there are regional and district variations in coverage of the same vaccines. Negative perceptions, fear and hesitancy amongst the population are some of the known reasons for this low coverage and it is these that the communication strategy seeks to address.

## 2.1 Current national immunization schedule

Routine childhood immunization in Georgia is delivered according to the Public Health Law and the National immunization schedule (MoH Decree № 01-57/n, November 19, 2015). As of January 2016, the national immunization schedule provides vaccination against 12 infections:  tuberculosis, diphtheria, tetanus, pertussis, hepatitis B, Haemophilus influenzae type b (Hib), measles, mumps, rubella, poliomyelitis, rotavirus, and pneumococcal infection. In October 2017 HPV vaccine will be piloted in two major cities Tbilisi and Kutaisi, 6 districts in the Adjara region and all districts in the Abkhazia region. This approach will introduce the vaccine to approximately 70% of this vaccines target population girls aged nine years.

| Age | 0-12 h | 0-5 d | 2 m | 3 m | 4 m | 12 m | 18 m | 5 y | 14 y |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hepatitis B | HepB 0 |  |  |  |  |  |  |  |  |
| Tuberculosis |  | BCG |  |  |  |  |  |  |  |
| Diphtheria, tetanus, pertussis, IPV, Hib, hepatitis B* |  |  | Hexa 1 | Hexa 2 | Hexa 3 |  |  |  |  |
| Diphtheria, tetanus, pertussis |  |  |  |  |  |  | DTP 4 |  |  |
| Poliomyelitis (bivalent) |  |  |  |  |  |  | OPV 4 | OPV 5 |  |
| Rotavirus |  |  | Rota 1 | Rota 1 |  |  |  |  |  |
| Pneumococcal infection* |  |  | PCV1 | PCV 2 |  | PCV 3 |  |  |  |
| Measles, mumps, rubella |  |  |  |  |  | MMR 1 |  | MMR 2 |  |
| Diphtheria, tetanus |  |  |  |  |  |  |  | DT 5 |  |
| Tetanus, diphtheria |  |  |  |  |  |  |  |  | Td |

h: hours, d: days, m: months; y: years

## 2.2 Vaccine coverage

Immunization coverage in Georgia was high until 1990 but declined during the immediate period after the regaining of independence and subsequent armed conflicts and economic crisis of the 1990s.  Although immunization services have improved in the last decade, major challenges remain, as demonstrated by the occurrence of outbreaks of vaccine-preventable diseases (VPD) such as measles and rubella.  Reported coverage remains suboptimal for most antigens.

There are three broad issues to be aware of when looking at coverage. Firstly is measurement where there are difficulties determining target population for vaccination due to: long intervals between population census’s, extensive population migration within and outside the country and the lack of defined catchment populations for health care facilities (HCF) make accuracy of coverage data questionable.  To address the uncertainty with measuring immunization coverage in Georgia, a nationwide immunization coverage survey is being conducted among three birth cohorts throughout the country.

Secondly, health systems delivery changes in health care facility (HCF) management, operational and financing systems, “optimization” of health programs, lack of geographically defined catchment areas for HCFs and extensive turnover of medical staff has affected the quality of services and motivation of the personnel which has in turn affected coverage rates. The problems with planning target population and delivery of vaccinations are reported.  The lack of defined catchment areas creates greatest problems in big cities where large numbers of providers exist along with substantial populations unregistered with HCFs. The drop-out rate between planned BCG target and Hexavalent target populations is 7.3% (in 2015) and 2.5% (in 2016). Drop-out rate between provided BCG and Hexa1 is 6.3% in 2015 and 3.4% in 2016. Other health systems issues related to weak capacity, poor infrastructure and access to the services have been identified as barriers to high vaccination coverage in the country.

The third major contributors to low coverage and lack of timely vaccination is parent anxiety that creates a significant hesitancy to fully vaccinate children combined with a lack of motivation/confidence to promote in immunization amongst health care workers themselves.

Some vaccines do better than others in terms of coverage. Vaccines that require a second or third dose such as HEXA or MMR suffer from considerable drop off.  Rota at 3 months and Td for teenagers both have very poor coverage and are well below the recommended coverage rate with the highest and lowest regional coverage at around 57% and 38% respectively. Rota is relatively new and is considered to be on an upward coverage trajectory while Td at 14 years is at a stagnant low. There remains a substantial group of adults born between xx and xx that are under protected against measles to create a risk of outbreak in the wider population. Elimination of measles will not be achieved in Georgia unless this is addressed.

## 2.3 Regional and district variations in coverage rates

The majority of the population (29.8%) live in Tbilisi the rest of the population is split between 57, 3 % urbanised areas and 42.7 % in rural areas. The urbanised areas tend to have lower coverage rates than rural areas however variations in coverage rates do exist by region and within regions by districts. Occasionally, variations between districts can be explained due to the small numbers where a few non-vaccinated children can make a variation look substantive. Small numbers is not always the reason behind the variations at district level and more needs to be done to unpack the variations and the reasons behind them. This will include examining different population groups such as ethnic minorities, refugees, people displaced by conflict or war who are often cited as being less likely to have their children vaccinated. It also further justifies the need for district level communication plans where specific challenges can be better addressed.

## 2.4 Findings from the national Knowledge, Attitude and Practice (KAP) survey

The following summarizes the key KAP survey findings on the challenges for immunization that have informed this strategy. Using both qualitative and quantitative methods data was collected from family doctors, neurologists and caregivers in three major urban areas Batumi, Tbilisi and Kutaisi. Additionally, data on vaccination history for the same respondents was collected from health facilities and compared to that reported by caregivers.

### Vaccine status and timeliness of survey respondents

- Based on vaccine provider clinics data on vaccine status 45.3% of children surveyed were completely vaccinated (all vaccine shots recommended by the National Immunization Calendar), 51.0% of children had been partially vaccinated type #1 (provided with at least one vaccine shot after BCG/HepC vaccination at maternity hospital), 1.9% partially vaccinated type #2 (provided only BCG/HepC vaccination at maternity hospital) and 1.8% unvaccinated.

- Child immunization status and the timeliness with which vaccine were given are both greatly overestimated by caregivers based on a comparison between individual reported data and data held by the health facility where 79% of caregivers reported their child was completely vaccinated compared to an actual 45%.

- Health facility data by study site shows that the percentage of children completely vaccinated was 56% in Batumi, 38% in Kutaisi and 40.8% in Tbilisi. The highest percentage of unvaccinated children was identified in Kutaisi 4.0%, followed by Batumi 1.2% and Tbilisi 0.4%.

- Batumi had the highest proportion 43% who completed the first immunization by age of 4 months and 29 days compared to Kutaisi and Tbilisi at 20%. Batumi also had significantly better results on ‘timeliness’ where a child is provided with all vaccines according to their age defined by National Immunization Calendar.

- Only 8.8% of children were immunized with commercial vaccines.

- 20% of children were provided medication before immunization with recommendation from physicians and 2.5% without physician’s recommendation.

### Healthcare workers

Environmental and situational factors

- Changes in the primary health care system and paediatric services (including immunization) and high migration of population make it challenging for HCWs to outreach the patients particularly in large cities as Kutaisi and Tbilisi;

- Policy changes to mandatory vaccination was seen as an important step to improve vaccine coverage in the country;

- Inadequate collaboration with education system (including kindergarten and school HCWs) is a missed opportunity to immunization.

- Frequent disagreements with HCWs from other fields such as surgery and gynaecology as well as paediatricians from the hospitals regarding contraindications indicates a need for their training on immunization;

- Unsupportive work environment: more time and effort for communication and outreach of patients needed yet inadequate remuneration;

- Current EPI norms and standards e.g. eligibility around contraindications, residence requirements, screening and “approval” of vaccinations leaves HCW who immunize a child that goes on to develop serious side-effects vulnerable to aggression, assault, dis-crediting. This represents a barrier for implementation them in practice and discourage vaccination.

- Inadequate knowledge and belief in the current EPI norms and standards (i.e. medication before immunization, vaccines as trigger for complication for the given conditions, vaccination of a child who already contracted disease).

- ‘High’ quality of the vaccines introduced in the last 5 years was named as the leading factor for increased coverage. High quality vaccines increase HCWs confidence and decrease population resistance toward vaccines. Country of manufacture is considered as the main quality criteria. There are still questions regarding quality of commercial “paid” and government purchased “free” vaccines among population.

- Primary Health Care providers involved in EPI revealed high fear of complications after the vaccination. They still reported to prescribe medication against allergy and fever before immunization to prevent any complications among their paediatric patients. Also fear that in the event of an adverse reaction they will not get professional support and protection, or the time to officially determine the reaction was not vaccine related will be too long and as a result they will be personally blamed by the community.

- Though Primary Health Care providers involved in EPI were in general more informed about HPV vaccine those from regions were more interested and willing to recommend vaccine and give vaccine to their family members than Primary Health Care providers involved in EPI from Tbilisi.

- Neurologists feel their role and involvement in immunization has decreased and all FG participants insisted that they are pro vaccination and rarely give negative recommendation to vaccination.

Personal motivation factors

- In Tbilisi particularly there remains a high concern among both HCWs and patients regarding association of MMR and Autism (also paralysis and prolonged jaundice). In Kutaisi, higher concerns about safety profile of newly introduced vaccines.

- Physicians from Tbilisi and Batumi questioning efficacy of available vaccines (i.e. cases when no antibodies were developed) and immunization program particularly recently introduced vaccines (i.e. Rota virus and Pneumococcal) in general;

### Public perceptions and practice

- All stakeholders, reported quality of the vaccine as an important factor in caregiver decision-making. Caregivers reported the self-confidence of the physician while discussing vaccines influenced them.

- Quality of vaccine was defined as the vaccine manufacturer country; specifically, manufacturers from west European countries were given the highest credit and considered as the guaranty of the product quality.

- Decreasing cases of vaccine refusals during the last years is considered by HCW to be due to vaccines provided though immunization program are now manufactured in Europe. The problem “free” (government purchased) and “paid” (commercial vaccines) vaccines identified during the UNICEF and NCDC 2012 survey on immunization was no longer a problem to the extent it was as currently provided vaccines are considered of same quality as commercially imported vaccines. .

- Some groups of health care workers were still named as the source of concerns and resistance among caregivers including those specialists practicing in hospitals and “famous” paediatricians. Moreover, according to all stakeholders one of the immunization resistant groups of caregivers was the health care providers’ themselves. This trend was named by Primary Health Care providers involved in EPI as one of the important issues considering the fact that those groups usually have trust from the general population and their choice might influence on others. Verified by specialist media

- According to stakeholders Orthodox Christianity as a religion was not against immunization in general and there were few cases when priests would give negative recommendation on vaccination. However, there were a lot of cases when priests do not vaccinate their children again giving “bad’ examples to their parish even without actively discrediting the immunization in them preaches.

- Trust toward child’s paediatrician was not a significantly different amongst the two groups. However, younger caregivers are: more informed, active in child immunization compared to older caregivers; most difficult to communicate due to lower “respect” and “trust” during the consultations; most employed and busy group who often postpone the immunization.

- Resistant caregivers differed in their argumentation and general background. The most frequent reasons for refusals was named the potentially vaccine associated neurologic reactions in the child or their older siblings and neurological or allergic status of the child. The fear for neurologic complications after administration of vaccine was also named as the important barrier for other groups of caregivers. Caregivers from rich or so called celebrity families were also named as one of the resistant groups though with no specific argument against vaccination.

- Partially vaccinated child caregivers were more likely to be concerned about vaccine safety and quality and less likely to believe in vaccine benefits compared to fully vaccinated group.

- Health care providers are reported by 90% of caregivers to be their main source of information on immunization followed by websites 31%, other medical personnel 20%, TV 14% and friends, family and neighbours 12%

- Perceived risks and severity of vaccine preventable diseases amongst the general population is low.

- Discussions on HPV vaccination revealed low knowledge about vaccine and its importance for cancer prevention among caregivers.

### Profiles of the caregivers of under-vaccinated children

- Medical background

- Caregivers of children with some chronic or neurological disease; “Vaccination of children with neurological health issues (such as Cerebral palsy) is problematic though still much easier now than before since during old times people hided such kids and locked them at home. Now everyone talks about freely for instance about the story of our president’s child who has Down syndrome.”

- Very low social-economic status

- Employed caregivers

- Frequent migrants and those relocated due to conflict

- Orthodox Christian priests at the local level, despite that neither the Christian Orthodox official church or the related dogmas and catechisms are not against immunization, and some other religious minority group representatives (Jehovah witness)

### Other relevant data

Additional to the KAP survey and as part of the strategy development process two groups of other relevant professionals were brought together to discuss their experiences, perspectives and role in promoting immunization.  Ten nurses from several primary care clinics across Tbilisi met for a facilitated discussion with the independent consultant leading the strategy development and fifteen specialist health media professionals working in TV and radio as a separate group. In addition, visits were made to a district health office and to three different primary care facilities outside the centre of Tbilisi in smaller rural areas.

Specialist Health Media (15)

- The challenges: Misconceptions are not being adequately addressed; Autism is a fear but also other myths speak late pollutes the body reduces overall immunity

- Doctors themselves are the biggest a problem; they make negative statements in the media that is very damaging to parents confidence; these statements are counter to overwhelming scientific evidence, WHO recommendations and the Governments national policy but allowed as doctors are not professionally regulated; 10 great news stories negated by one individual statement from one doctor; parents get confused and anxious by the medical professions mixed messages; new vaccines introduced need better communication

- What else can be done to support the specialist health media: more medical champions; challenge the medics who propagate negativity; personal stories to create sense of fear of disease and increase perceived risk; more tailored and targeted campaign work; more systematic visibility; adress the myths head on; fear the disease not the vaccine…need to share the risks with new generations; proactively use media opportunities e.g. flu deaths of the elderly are an opportunity to promote flu vaccine, remind people of the 11,000 measles cases in 2008.

Primary Care Nurses (10)

- Feel their role is to: inform parents when to come for a vaccination and follow up non-attenders sometimes with home visits, administer vaccines following approval from physician, be trained in all new vaccines, provide information to parents and use decree 01-57 document as a resource for technical information on vaccines.

- All parents ask them questions: What is the origin of the vaccine? Is it safe? Will there be a bad reaction? What should we expect and how do we know it is a bad reaction or normal reaction? What is the difference between free and commercial? Do you vaccinate your children?

- Key challenges from their perspective: DPT is difficult because the origin is from Indonesia and has some side effects that parents know from others about; TD is difficult as teenagers refuse it themselves; Roma population say they do not need it as their families before never had it; some nurses have a bad attitude and performance but this is never addressed; there is no pre service training in inter personal skills; some nurses were very aware of their clinics coverage rates and others were not and did not know how to calculate, mothers are concerned to give their children vaccines when they are or have been unwell and are recovering from colds but in the winter time colds and sniffles are very common place in these cases they will postpone and then are difficult to get back or may miss the schedule of vaccines that are time sensitive

- Perspectives on what can help: incentives for children (UNICEF diaries helped); more media and advertisements and materials; IPC training pre-service and CPD for existing doctors and nurses; recognize the role nurses play and encourage it; formalize nurse home visits again; Nurse award scheme for high performers in immunization; gguidance on how to persuade more effectively particularly difficult groups e.g. Roma

- What motivates you: ‘I am a professional, it’s satisfying; Working with children gives me enormous satisfaction; We may not get respect in the system but parents and patients always thank us; We are respected by parents and this is gratifying; I love it when people say I was your patient and now I am bringing my child to you; I love my job, I feel like I am helping people.’

Primary Care Facilities (4)

- Visibly poor infrastructure in three facilities in terms of structure, access and heating, no computer access.

- HCW reported coverage was either the same or only slightly less than actual reported in the NCDC and between 85 and 97% for selected vaccines.

- Challenges included postponement and follow up of parents by nurses after postponement by busy working parents or where the child has been sick. In the winter months, the number of children sick is very high in the schools and the kindergartens and this is a problem when trying to convince caregivers over the phone to come for vaccines.

- Two facilities reported a close working relationship with the schools locally. One doctor indicated that they administered the vaccine s in the school premises for Td while another nurse said she walked a group of children from the school to the facility and administered the vaccine in the facility.

## 2.5 Strategic observations and discussion points

- Social mobilization is a key approach within a communication strategy however this is a potential weak area. Ideally the national strategy would be implemented at regional and district level with a small working group led by the NIP or HPD staff at those respective levels developing, in collaboration with key local stakeholders, a local communication action plan. In Georgia the EPI regional officers may not have this role or skill set. The district level public health officers are employed by the district public health centres and accountable to the local political management structures. In this instance although the NCDC generally have excellent relationships with these public health officers who provide the routine data on immunization to NCDC they are not accountable to them and have no budget necessarily for conducting and coordinating communication activities at the district level.

- Communication for Immunization is not in the State Programme and therefore has no identified budget. Within NCDC there is no separate budget line for communication, resources have been allocated in an ad hoc manner making an effective systematic approach difficult. Ideally a dedicated budget line and a budget allocation would be made to communication for immunization that is separate to the budget line for the procurement of vaccines. The HPD and EPI have a good working relationship and HPD have an important role in supporting the EPI team deliver communication for immunization. The Head of HPD has identified lead immunization staff however this may also need to be formalized given the HPD have other health areas they are responsible for supporting that do have budgets attached to them, unlike immunization. If this strategy is to be implemented then these are important issue to consider and address.

- Crisis communication is an area that seems to traditionally involve a good plan but without messages and preparedness of spokespersons. This is an area that the HPD and EPI team seek to address within the implementation of this strategy and the upcoming introduction of the HPV vaccine.

- The relationship between NCDC and Education experienced strain as a result of the MMR supplementary programme that was administered through schools and was curtailed due to an anxiety related adverse event that attracted negative media reporting. Individual schools teachers themselves are not, but the school itself does remain a key channel for information for parents and even though school vaccination programmes may not be appropriate, collaborations at the district level between health and schools are important and should be promoted. At a national level formalizing the role of the school doctor in endorsing and supporting vaccinations through the provision of information to parents and collaborating with the local public health officers and local health facilities could be useful.

- Public private partnerships seem to be an area that could be explored further. The Social Services Agency who manage the major health provider contracts with health care providers such as e.g. Curatio and Evex, are apparently introducing selective purchasing requiring health facilities to meet a number of criteria before they are eligible to be refunded for services through them. This may be an advocacy opportunity to include a minimum vaccination coverage rate as a criteria or some potential for quality standards concerning the provision and promotion of free vaccines as opposed to the promotion of ‘paid for’ vaccines. Additionally there may be some potential for support through public private partnerships with commercial organizations such as the telecommunication companies operating mobile networks where a mutually beneficial value proposition can be identified or other major commercial companies (meeting ethical standards of operation) who offer corporate social responsibility funding and support.

- Formative research has highlighted that those family doctors who are promoting the paid for vaccine over the free vaccine by informing parents that it has less side effects undermines the government immunization programme, confuse parents and generate uncertainty and doubt and make parents feel guilty if they are unable to pay. Regulation of this poor quality and potentially unethical practice may be possible through the SSA in the short term or a broader discussion on the need for professional regulatory bodies for health care workers in the longer term.

# 3. Aim, strategic goals and general approach

The national programme of vaccines for the population of Georgia includes a wider range of vaccines than addressed within this strategy.  This strategy focuses on childhood immunization and prioritizes those where the coverage rates are of greatest concern.

Overall Aim:

- Contribute to a sustained increase in immunization coverage for childhood immunizations to 95% nationally and 90% coverage in all districts.

Strategic Goals:

- Increase the confidence, demand and take up for childhood immunizations amongst parents of all children.

- Improve the quality of the health service delivery of childhood immunizations to all children.

- Reduce regional and district variations in immunization coverage rates

- Achieve elimination of measles.

General Approach:

- Targeted Communication through a wide range of channels that include the media, social media, printed materials, training programmes, mobile technology.

- Social mobilization to harness the support of local civil society organizations, religious groups, local opinion formers at regional and district level.

- Advocacy through influence and promotion of the profile of immunization amongst policy makers, decision makers and politicians.

# 4. Communication objectives for each target group

Informed by the formative research and the situational analysis the target groups prioritized within this strategy include:

## Parents of children aged 5 and under

- Raise awareness and knowledge of the importance of Childhood Immunization

- Increase the take up of the HEXA vaccine by parents for children under five which will lead to an increased coverage of HEXA 3 by 5% at national level and at least by 3% at the district level

- Raise awareness and knowledge of the importance of MMR 2

- Increase the take up of the MMR vaccine by parents of children under 5 which will lead to an increased national coverage of MMR 2 by 10% and 6% at the district level

## Teenagers (aged 14) and their parents

- Raise awareness,  knowledge and understanding of the importance of Td amongst teenagers

- Raise awareness, knowledge and understanding of the importance of Td amongst the parents of teenagers

- Increase the take up of Td vaccine amongst teenagers leading to an increased coverage of Td by 10% at the national level and 6% at the district level

## Primary Health Care Doctors

- Establish greater appreciation and adherence amongst primary health care doctors to the national policies that specify the critical and formal role of primary care doctors in raising immunization coverage rates and endorsing the safety and importance of vaccines

- Bring to the close attention of primary health care doctors the priority vaccines and target groups within this strategy and engage them as individuals in this effort in a practical and concrete way

- Increase primary health care doctors’ motivation to more effectively communicate with parents about the importance of immunization and increase the immunization rates in their facilities through the exploration and pilot testing of new approaches

- Increase the interpersonal communication skills of primary health care doctors in targeted geographical areas with low immunization coverage

## Primary Health Care Nurses

- Establish the formal recognition of the role of the primary health care nurse’ in raising immunization coverage rates and endorsing the safety and importance of vaccines

- Enable and motivate primary health care nurses through a formal recognition of their role to provide effective and accurate information to reassure parents on childhood immunizations

- Increase the IPC skills of primary health care nurses through the provision of training targeting low coverage area

## Policy makers

Advocate for:

- Standing Operating Procedures for primary health care doctors to specify the expected/required role of primary health care doctors in providing parents with sufficient evidence based and accurate information to support parent’s decision to vaccinate their child

- Standing Operating Procedures for doctors to specify the expected/required role of nurses in the provision of evidence based and accurate information to parents to support their decision to vaccinate their child

- Implementation of this national communication strategy to be included in the State Program with an associated dedicated budget line to enable its implementation

- A small pilot in a defined geographical area of the enforcement of the requirement for parents and guardians to present immunization certificates as part of the documentation needed for a child’s entry into to kindergarten and school to test the impact on immunization rates

- A review of incentives and disincentives used elsewhere for doctors and advocate for a small pilot to be conducted in a defined geographical area to evaluate for potential impact of these on immunization rates and inform future policy on this matter

- An examination of the professional support and protection offered to healthcare workers, whom have followed formal guidelines, in the rare event of a serious adverse reaction of a child to a vaccine

## Adults born between 1989 and 2000 who have not been immunized with the MMR vaccine

- Bring to the close attention and raise awareness of adults within this age group of the critical importance of being vaccinated to protect themselves and others from measles

- Reduce the number of under immunized adults born between 1989 and 2000 by 20 % at the national level

# 5. Key challenges by each target group

Parents of children under five

- Parents overestimate their child’s vaccine status and timeliness of when vaccines are given and may not be adequately aware of when they need to vaccinate their child and at what time

- Many misconceptions such as cause infertility, slow development, reduces immunity are in circulation about negative effects of vaccines that need to be dispelled

- Younger parents have more questions and want more information from HCW and may feel dissatisfied with responses or health professionals may feel challenged

- Postponement is common: busy employed parents often postpone, parents seem to be extra protective when a child is sick or recovering from a cough or cold as they feel reluctant to vaccinate when their child is vulnerable and feeling unwell believing it may make their child may feel worse or because their immunity is low

- Parents feel that giving more than one vaccine at a time is a lot for a small baby’s system to cope with and are concerned about managing immediate post vaccine symptoms like fever

- Parents feel more anxious about the potential negative effects of the vaccines than the disease. There is a generally low perception of risk of VPDs

- Confidence in the vaccine quality based on country of origin is of high importance and appears to no longer be a concern to the extent it was five years ago

- Fear of autism and disability resulting from the vaccine is the main concern of those parents who refuse vaccines

Family Doctors

- Lack inter personal skills to communicate effectively with parents and reassure them

- No IPC skills included in pre-service training

- Lack motivation to provide encouragement and accurate information to parents

- May feel challenged by younger parents who demand more information and answers to questions than they have traditionally been accustomed to

- May prioritize vaccinations low or perceive them to be unnecessary or some more critical than others

- May feel potentially vulnerable and unsupported by the health care system should a serious adverse reaction occur on one of their patients

- Inconsistent messages: Specialist doctors such as neurologists still give different messages about immunization than family doctors in primary care. Some family doctors may agree with postponement of vaccine to appease a parent if a child is feeling unwell  (without fever) and this makes it difficult to get the child back again particularly for vaccines that are time sensitive. Prescribing anti-allergy medicine prior to the vaccination is not uncommon yet is not in the guidelines. Parents may have two pediatricians, one preferred and paid for and one they are referred to from the hospital after their child is born for free vaccines and care. Messages these parents receive about vaccines have the potential to differ.

- A relationship and well-coordinated working between the health facility and the school health system is considered a positive way to increase coverage yet is variable across facilities.

Primary Care Nurses

Nurses present an opportunity to provide encouragement and accurate information to parents who seek advice, however currently nurses may:

- Go un-recognized for this role

- Lack accurate information/confidence to respond to parents question

- Informational materials to share or specially designed job aides to use with parents on the facts relating to each specific vaccination and managing side effects

- Hold same beliefs and myths and misconceptions as public

- Not perceive some vaccinations as less important

- Have weak inter personal communication skills and influencing skills

- Be unsure how to persuade specific hesitant populations e.g. ethnic minority groups such Roma

- Have low morale / poor attitude/lack motivation or incentive to fulfill this role

- Lack support and supervision

- Lack pre-service training in inter personal communication skills

In the same way nurses may also:

- Feel this is part of their professional role

- Feel satisfaction by being acknowledged and recognised both by parents and professionally as a source of advice

- Be motivated to fulfil the role of expert information provider

Under MMR immunized adults

Research has not been conducted with this group to identify the motivators and barriers however it is likely they may include a lack of awareness: of the potential risk of being under vaccinated and unprotected; that by remaining under vaccinated they put other vulnerable groups at risk; low understanding of the implications of contracting measles as an adult; of how to check your vaccine status of how to get vaccinated. A suggested action is to test these assumptions out with the target group.

Adolescents aged 14

This group has not been researched to identify the motivators and barriers it is assumed that they will include dislike and fear of vaccines, lack of concern now for their future health, low perception of risk of disease, reduced power of influence of parents for some teenagers, potential propensity to over react to temporary side effects. Research will be needed to test out these assumptions and identify the best motivators for this group and the channels of communication to be used.

# 6. Messages for each target group and associated channels of communication

To achieve the communication objectives for each target group the following messages are proposed. Messages that convey factual information are important to help caregivers make informed choices however this strategy recognises that factual information in isolation of other things is unlikely change a person’s behaviour. Emotional messages that have resonance to the target group can hook them in as well as appeal to the emotional drivers that influence decision-making.

Formative research shows parental concerns stem from their main drive to protect their children and do them no harm.  Messages used will reinforce that parents who vaccinate their child are doing the right thing. Health care workers can be motivated by different factors. One appears to be the acknowledgement and respect of their professional role in protecting the community or that being a doctor is often the result of hard work to fulfil a lifelong dream.  Commercial creative agencies can help to craft such emotional messages using findings from formative research (should the resources be available). Otherwise both informational and emotional messages can be developed internally and then pre-tested on the target audience to see if they are understandable and generate the desired response. Testing is seen as a critically important step as un-tested messages that create a negative response are extremely difficult to undo.

The informational messages below contain the key information the EPI want people to be aware of, accept and use to inform their behaviour. These messages will be packaged in a creative way to engage and generate a positive emotional response. Some initial suggestions are included as an annex.

Key messages cannot be finalized until they have been tested out with the target groups using qualitative focus groups. Final key messages and their supporting messages will be drawn from the messages below then tested for acceptability and impact with the target groups for which they are intended.

The strategy’s action plan details how these will be developed and tested before use.

| Messages for Parents of under 5’s | Channels |
| --- | --- |
| To help you protect your child from serious disease you will be offered a series of vaccines at different times in your child’s life up to the age of 14 years. This is the vaccine schedule for your child, these are the diseases they will protect your child from and this is how old your child should be when they have them. (detail to be added) Some vaccines need more than one dose if you miss the last one your child will not be protected. All doses are needed for your child to be fully protected. Vaccines must be given at the right time or your child may be unprotected. Hexa vaccines are needed at 1, 2 and 4 months of your baby’s life to keep your baby safe from serious disease. MMR at 1 and 5 years is a critical step to boosting your child’s protection against measles to keep them safe, strong and healthy. | Printed schedule of immunizations in easily accessible format and language. Laminated copies for HCW to use in consultations, printable copies from NCDC web site for distribution to parents, posters for display in clinics. Mobile SMS messages for specific vaccine reminders |
| Parents can feel reluctant to vaccinate their child if it is feeling unwell but it is safe, it protects your child and makes their immune system stronger. If your child is healthy and strong the vaccine will strengthen their immunity even further. A child with a specific long-term health condition is particularly in need of the added protection a vaccine can give. There is never a need to postpone a vaccine unless recommended by a family doctor. | HCW consultations, printed materials, NCDC web site, |
| Vaccine Preventable Diseases are serious and in cases can lead to death. The implications of not vaccinating are potentially dangerous to your child and the community as a whole. Thanks to science vaccine preventable deaths and suffering is part of Georgia’s past, let’s keep it that way, and vaccinate your child. | Printed material, posters, social media, NCDC/MoH web sites, specialist health media, schools and nursery |
| Every year around 89 % of Georgian parents vaccinate their children to prevent them from serious diseases. Doctors and nurses vaccinate their children to protect them from serious diseases. | Community mobilization of key opinion formers/national influencers |
| It is understandable that parents may feel unsure when there is so many misconceptions circulating, don’t be misled, know your facts, and make the right choice. Vaccines will strengthen your child’s immunity and protect your child from the harm of very serious illnesses in a way just being healthy cannot. Vaccinating your child is the best protection you as a parent can give them against serious diseases. Vaccines will not poison or weaken your child’s immunity, slow down their growth or speech development or make them infertile in later life or cause autism. These are misconceptions that have no scientific basis. Vaccines continue to save lives and protect 1000’s of children in Georgia and around the whole world. Vaccines may in a small number of children have some temporary side effect such as redness around the vaccine spot or a slight temperature/fever. Fever is easily manageable with ibuprofen/paracetamol and symptoms will disappear in a few hours. Do not worry some side effects are normal, temporary and easily managed. The short-term affect may in a small number of children be temporary symptoms and discomfort that can be managed with pain or fever relief. The long-term effect of a vaccine is safety and protection from serious disease. Vaccines are safe. They have been stringently tested and all of the vaccines used in Georgia are approved by the World Health Organization. 85 % of children worldwide and 110413 in Georgia have received the MMR vaccine in the last 12 months alone. 155925 in Georgia have received the HEXA vaccine | Printed material, NCDC /MoH web site, social media, specialist health media. |

| Messages for primary care doctors | Channels |
| --- | --- |
| Vaccines procured and used in Georgia are safe: Georgia uses WHO prequalified vaccines, a respected quality mark of safety and effectiveness. The vaccines used in Georgia are used in many other European countries including the UK, France, and Germany. The only difference between the commercial vaccine and the free vaccine is the commercial vaccine costs the caregiver money. The free vaccine is equally safe and is often from the same source as the commercial vaccine. The national immunization schedule of Georgia is based and supported by scientific evidence of the health benefits for the population and the expert guidance from the World Health Organisation that is used by every country globally. | Active advocacy with professional medical associations; Social media; Specialist health media NCDC – training Communication meeting – NCDC Include in printed booklets, flyers, |
| Ninety per cent of parents surveyed say that doctors are their greatest source of information on vaccinations. Parents say when doctors are confident about a vaccine they also feel confident about the vaccine. Parents also report that some doctors tell parents that the ‘paid for vaccines’ have less side effects than the free vaccines. This is inaccurate and therefore unethical as it undermines the free vaccine, confuses parents and makes people feel bad about themselves as a parent if they are unable to pay. Support parents make the right choice and feel good about their decision to vaccinate and protect their children. Parents say they rely on doctors to act in their interest and on the scientific evidence. Doctors have a central and critical role to play in protecting children and the community. Doctors who dissuade parents from vaccines put the health of the wider community they serve at risk. If in any doubt about a vaccine efficacy always access clinical information produced for doctors and available for doctors or call your regional NCDC officer. | Social media; Specialist health media NCDC – training Communication meeting – NCDC Specialized media, booklets, flyers, social media |
| The family doctor is one of the most highly respected members of the community. You are an important role model and have one of the greatest influencers on parent’s vaccination decisions. Use your influence well. Let your patients know that your own children have been immunized and are protected it will give them even more confidence in you and the vaccine. | Specialist health media Mobile messages Campaign IPC training |
| Only postpone vaccinations of children with the contraindications in the guidelines. If in doubt check your facts here (use the link to correct page on NCDC web site) Children with minor illnesses can be vaccinated safely, don’t postpone it may be difficult to get busy working parents back. Pre-medication with anti-allergy or anti-pyretic is not necessary in healthy children. Help parents manage the potential temporary side effects by normalising them with reassurance and advice on actions to take to reduce temporary fever or discomfort and swelling at the vaccination site. | IPC Immunization Training Job Aide (booklet) Provision of guidelines on contraindications in format to share with parents. NCDC web site Specialist Health media |
| In the event of a vaccine related adverse event as a doctor there are certain steps you should take. Follow the guidance produced by the NCDC for how to manage vaccine related adverse events (add technical detail) In the situation of a vaccine related adverse event in your practice you can expect the NCDC to support you and take the immediate investigative actions to quickly clarify the cause. | Active advocacy with professional medical associations for endorsement; NCDC – training Communication meeting – NCDC |
| The NCDC are concerned about the coverage rate of the following vaccines and seek your help to support them in efforts to increase these: HEXA vaccine at dose 2 and 3; MMR coverage at age 5; Td at age 14 and have introduced some targeted communication with parents to encourage them to vaccinate their children. In order to eliminate measles in Georgia NCDC are targeting under immunized adults born between 1989 and 2000 and directing them to their family doctors for two dose vaccination with the second dose at or within 6 months. Family doctors can be prepared to receive enquiries from adults born between this period and should offer the vaccination to those unsure of their vaccination status. | Formal communication channels with family doctors. Specialist health media. Professional Organizations endorsement and use of channels of communication with the membership. |

| Messages for Nurses | Channels |
| --- | --- |
| Nursing is a respected profession with a responsibility to care about children’s health. Your role in vaccinating and protecting children against serious diseases is valued. Parents respect and appreciate you. Children and parents feel safe with you when you vaccinate with care and comforting messages. Help parents vaccinate their child by instilling confidence and provide accurate information about the benefits and importance of the vaccine when you follow up by phone or before you vaccinate in in the clinic. Make sure you know the up to date facts about the vaccinations you administer to children. If you have doubts do not share these with your patients rather seek out information here (http://ncdc.ge/ka-GE/HealthIssues/%E1%83%98%E1%83%9B%E1%83%A3%E1%83%9C%E1%83%98%E1%83%96%E1%83%90%E1%83%AA%E1%83%98%E1%83%90) or contact the NCDC or speak to your family doctor or regional CDC officer. | Social media Specialist Health Media Motivational mobile text messages Professional associations endorsements IPC Training |
| The national immunization schedule of Georgia is based on scientific evidence of the health benefits for the population and the guidance from the World Health Organisation. You can be confident in the weight of the international body of scientific knowledge that you stand on when you promote immunization to your patients. By transferring your knowledge to parents you play your critical part in protecting Georgia’s future generation | Social media Professional associations endorsements IPC Training |
| All nurses know that being a nurse comes with responsibility in the community. Nurses are an important role model so use your influence well and let your patients know that your own children have been immunized and are protected. It will give them even more confidence in you and the vaccine. | Motivational mobile text messages Social media Specialist Health Media Professional associations endorsements |
| Messages for teenagers (14) | Channels |
| Td vaccine protects you from Diphtheria and Tetanus, which are both serious diseases that can be fatal. (Detail and examples) If you are between 14 and 16 years of age you need to get vaccinated against Td. You are at risk of serious illness without the Td vaccination. These diseases can be fatal. | Doctor, parent, social media, schoolteachers and school doctors, peer educators. |
| Messages for adults born between 1989 and 2000 | Channels |
| If you were born between 1989 and 2000 then you may be at risks of measles? Measles is a serious contagious disease that if contracted by adults, can be fatal. The majority of adults have been vaccinated from measles as children but people born between 1989 and 2000 may have lost out. Adults born in this period who are unsure whether they have been fully vaccinated are potentially vulnerable and unprotected against measles and should get vaccinated without delay. If you are not sure about your vaccination status do not take chances and check your status. If you cannot be sure about your vaccination status go to your family doctor and get MMR immunized. MMR vaccine is freely available for under immunized adults from the family doctor. Unprotected adults who are not properly vaccinated increase the risk of an outbreak. An outbreak of measles puts under vaccinated adults, newborn infants and children under five at risk of contracting measles, which is a serious and contagious disease. | TV, Radio, Social Media, Health professionals, urban public transport, large work places, community organizations. |

| Policy makers | Channels |
| --- | --- |
| Many Health Care Workers lack the inter-personal skills needed to convince parents of the need to vaccinate their children. HCW with better inter personal skills are needed if there is to be an increase in the take up of routine childhood vaccinations: IPC skills should not be left to chance or personality but should be included in formal pre service of both doctors and nurses. IPC skills are important skills required by HCWs to maximise their effectiveness. | Professional bodies, academic institutions, NCDC, NITAG, Health specialist media, ICC, National Voluntary Organizations representing children and health issues. |
| Georgia is not free from risk of outbreaks of serious vaccine preventable disease? Systematic and targeted communication to create a confidence and a demand for vaccines in the population and address myths and misconceptions is critically important to increase immunization coverage. Strategic communication for immunization should be an integral part of the State Programme for Health. This National Communication Strategy requires a dedicated budget line alongside vaccine procurement to enable its implementation. | Professional bodies, national children’s NGOs, NCDC, ICC |
| Urban Doctors with negative attitudes and poor performance in relation to immunization have a negative affect the overall coverage of the population and create risks for serious disease outbreaks. Incentives and disincentives for doctors may help increase immunization. Approaches used in other countries and the lessons learned and impact evaluations should be reviewed to inform the design of an approach that can be tested out in a small pilot study in Georgia to measure the impact and estimate the cost. | Professional bodies, Specialist health media, ICC |
| Regulation of doctors needs review. Doctors who propagate misinformation both publically and in doctor /patient consultations about immunization can contribute to irreparable damage to the integrity of the Government’s national immunization programme, jeopardize the populations health and therefore cost the Government money and lost opportunity. Messages that contradict to the scientific evidence available are misinformed and are counter to WHO recommendations and national policy. Negative misinformation is costly as one negative message from a doctor made publically, can negate the substantive and costly Government efforts to positively promote immunization. Professional regulation of doctors can help manage and limit damaging public statements from random individual medical professionals. | Professional bodies, Academic Medical Training Institutions, specialist health media, ICC, NITAG, Patient Associations, National Voluntary Organizations representing children and health issues. |
| The requirement for presenting immunization certification at the point of enrolment of children to kindergarten and school could potentially increase immunization coverage and reduce the risk of outbreaks. Its enforcement should be tested in a pilot for its potential impact in Georgia and costs and implications. |  |

# 7. Influencers of target groups

This group have an indirect influence on the target populations and should be provided with the same messages. They should be approached and mobilized to influence the target groups and where possible enabled to be effective influencers through the provision of information, materials and accurate information.

| Target Group | Influencers |
| --- | --- |
| Parents of children 5 years and under | Family, Friends, Media, Social Media, Doctors, Nurses, Inter-net, National Experts, Government policies, Orthodox Church, Community based organisations |
| Primary Care Doctors | MoLSA, Professional Organizations, specialist health media, general media, National and International Experts, policy makers and Social Services Agency and their contracted healthcare providers such as EVEX and Curatio. |
| Primary Care Nurses | Professional Organizations, Specialist Health Media, general media, parents, doctors, Orthodox Church |
| Teenagers aged 14 years | Peers, schools, parents, family, youth workers, health professionals, internet, social media |
| Parents of Teenagers aged 14 years | Peers, family, Health Professionals, Government policies, social media, internet, media, Orthodox Church |
| Adults born between 1989 and 2000 | Peers, family, Health Professionals, Government policies, social media, internet, Orthodox Church, community based organizations |
| Policy makers | Public opinion leaders, evidence, experts, international organizations, Government strategy, politicians, academics, Social Services Agency and their contracted healthcare providers such as EVEX and Curatio. |

# 8. Action plan with broad costs

| Actions Parents | Conducted by | Broad costs | Responsible lead | Source of funding |
| --- | --- | --- | --- | --- |
| Based on the results of the formative and KAP survey develop a two sided A4 Immunization Communication TOOL/ JOB AIDE MEMOIRE for HCWs that specifically addresses common misconception/myths and provides other key information including info graphics that can be shared with parents by health care workers. Framed in 3 sections Vaccinations are important because, vaccinations will not, Vaccinations may and vaccinations will… the content and layout will be tested with both parents and HCW before finalizing. Develop a brief guide for HCW on how to use this job aide with parents. Circulate electronically modified and tailored versions of this HCW job aide to different groups of people: politicians, spokespersons, MoH key policy makers, MoH communication staff, healthcare professional bodies, and specialist health media. | Year 1 | NCDC Staff time but no significant financial cost | EPI with some support from Health promotion.. | Not applicable |
| Desktop publish layout, print and laminate sufficient copies of the HCW Immunization Communication Aide to distribute at least 2 copies to all healthcare facilities (4500) and school doctors (300). Print sufficient copies of the brief guidance on how it can be used. Promote the job aide through specialist health media, HCW targeted social media, professional organisations, Ensure all HCW have their own copy a copy and understand how to use this tool in their consultations with parents. Use this tool as part of the IPC training (see actions for primary care nurses) | Year 1 | 5,500 GEL | EPI with some support on packaging from HPD | TBD |
| Procure the services of a creative agency to develop a communication platform that can be used to build three separate campaigns under-fives, teenagers and adults. Each targeted campaign should be based on an emotional concept drawn from the findings of the formative research and pre tested with the target audience. Develop a series of reinforcing communication campaign branded products that use the brand to communicate the informational messages and include: tv spots, national and regional radio spots, a series of very short videos for circulation on social media that address misconceptions and short personal stories told by real people of the implications of not being vaccinated as a way to increase perceptions of risk of the diseases; visual printed materials, posters for health facility display and sms messaging. Consider private sector collaboration with a telecommunication company/mobile network provider. Consider the concept of a ‘I vaccinated my child’ campaign which uses regular and real health care workers images and real names from around the country on campaign materials as well as well known and well respected personalities. And trusted public figures such as the Minister of Health, Paata Imnadze both of whom have been mentioned in the HPV formative by parents as trustworthy and respected. Their personal stories and those of other ordinary health care workers, parents can also be powerful if captured on video and used in social media. , tv and radio spots. Additionally identify advocates in national organizations representing children’s interests, consider other suggestions in the ‘ideas for campaign activity’ informal paper produced by the consultant. | Year 2 | 60,000 GEL | HPD with support from EPI | TBD |
| Finalize a broad set of messages and sub supporting messages for parents that can be used consistently throughout all communications and in all communications materials produced. Consider developing emotional messaging backed by directives or factual sub messages. Test these out using qualitative approaches with parents before finalising. Share these messages widely once developed including the health specialist media and the groups who have been identified as having an influence on parents. | Year 2 | 1,500 GEL (cover costs of message testing) | HPD | TBD |
| Consider the key influencers for this target group and identify a short and feasible set of 3 actions that can be carried out to utilize these influencers to positively promote the key messages for this target group. | End of Year 1 | Staff time | EPI with HPD support, | Not Applicable |
| Mobile Technology: Review the potential of the mobile app developed through UNICEF and test in a small number of facilities in an urban area to identify what training of facility staff or HCWs will be needed and how to best to launch it, market it and utilize this mobile application routinely within the health care system. Make recommendations on how to incorporate the use of mobile technology in the communication strategy. | End of year 1 | 2,500 GEL | EPI with HPD support | TBD |

| Actions primary care doctors | Conducted by | Broad costs | Responsible lead | Source of Funding |
| --- | --- | --- | --- | --- |
| Run a small number of supplementary focus groups with doctors using a purposeful sample drawn from Kutaisi where the coverage is low (to fill gap identified in KAP 1 and include some doctors who are potentially ambivalent, less motivated to promote vaccinations and unsupportive. Identify their sense of responsibility and commitment to implementing the immunization schedule, whether any vaccines considered more or less critical than others). Focus on identifying where doctors get information and specifically which web sites, radio, TV, social media, test out the idea of using mobile messaging to doctors as a channel. Test out the potential incentives and disincentives for this group. Explore their views on challenges and issues they face in trying to increase their immunization rates and how they feel they could be better supported. Identify any strategies of doctors to increase immunization or tackle hesitancy that appear to have worked elsewhere. | Year 1 | 1500 GEL | HPD | TBD |
| Based on the KAP survey findings, the findings from the above additional focus groups and the situational analysis identify three or four key messages with three sub messages to use consistently throughout the communication effort. One should be an emotional message. Test them with doctors before use. | Year 2 | 1500 GEL | HPD with support from EPI | TBD |
| Develop IPC training videos for both nurses and doctors that can be used as part of a training programme to improve IPC skills in immunization. Illustrate the difference between effective and poor IPC skills using a consultation about immunization as the context. Use HEXA 2, 3 and MMR 2 in the scenarios to create another opportunity to raise the profile of these vaccines to address drop off. Provide opportunity to discuss in this the changing relationship between doctor and patient in relation to greater information and what that means for the doctor patient relationship and potentially better patient outcomes generally. Share materials and training pack with institutions that train and accredit family doctors. | Year 1 | 50,000 GEL | UNICEF Georgia in collaboration with HPD/EPI | UNICEF Georgia |
| Develop a 2-day professional development training curriculum on Immunization to include: IPC skills using the UNICEF developed videos, updated evidence base for immunization, national immunization coverage and regional / district / population group variations, critical importance of the family doctor /school doctor role, how to respond to parent concerns, targeting hesitant groups to increase coverage and strategies generally to increase the facility coverage levels. Share materials and training pack with institutions that train and accredit family doctors. | Year 2 | 20,000 | EPI with support from HPD | TBD |
| Deliver the above IPC training to all family and school doctors using training the trainers approach. Carefully monitor the quality of this training. Include motivational mobile messaging post training to encourage doctors to practice new IPC skills. | Year 2 -3 | 20,000 | EPI | TBD |
| Review the current use of social media and identify and implement ways to better target doctors such as dedicated FB page, use of free/low cost pc to mobile messaging services to send special mobile alerts and motivational messages to promote the priority vaccines in this strategy. | Year 1-2 | 3,000 GEL | NCDC Communications Team with support from EPI | TBD |
| Work with specialist health media to influence their production of TV and radio programs on the role of the family doctor, IPC skills in immunization. Hold quarterly meetings with this group at NCDC to update them on issues, coverage rates, challenges and priority vaccines NCDC are targeting ensuring these media allies are well informed of the priority vaccines this communication strategy are targeting and ensure specialist health media are aware in advance of targeted communication work the NCDC are conducting. | Year 1-2 | 300 GEL | NCDC Communications staff with EPI and NITAG involvement. | NCDC |
| Identify doctors to be immunization champions and spokespersons on particular vaccines, offer media training and use them in media, written print materials, short videos. Work/contract with one specialist health media organization to conduct this training. Ensure all specialist health media are aware of champions and encourage media them to enable/incentivise the champions for their involvement in programmes. Include NITAG members where appropriate. | Year 1 - 2 | 2,000 GEL | HPD with support from MoH PR/EPI | TBD |
| Distribution of the information materials targeting doctors. Tips on parents’ concerns and how to manage them in consultations. | Year 2 | No cost | HPU/NIP | Not applicable |
| Produce a series of very short videos of doctors talking about why they feel immunization is important and how they promote it in their work. Include Paata Imnadze and other nationally known and respected ‘doctors’ such as the Minister of Health. Consider how to use support from international and national experts from other countries in these videos. Circulate these using social media networks frequented by health care professionals and share with specialist health media for their use. | Year 2 | 3,500 GEL | HPD with support from MoH PR/ EPI | TBD |
| Consider the key influencers for this target group and identify a short and feasible set of 3 to 6 actions that can be carried out to utilize these influencers to positively promote the key messages for this target group. | End of Year 1 | 3,000 GEL | HPD/EPI collectively | TBD |

| Actions primary care nurses | Conducted by | Broad costs | Responsible lead | Source of funding |
| --- | --- | --- | --- | --- |
| Conduct a series of supplementary focus groups with a purposeful sample of nurses from low coverage areas to identify their perceived role in immunization, levels of knowledge and information and gaps, perception of most or least critical vaccines, barriers for parents and challenges in their role, resources available to them, potential motivators for them, incentives and disincentives, support tools needed. Test the nurse award scheme concept as a potential motivator and explore other possible incentives. Test use of mobile messages as a channel for information. | Year 2 | 1,500 GEL | HPD | TBD |
| Develop a one-day stand-alone training curriculum on effective interpersonal communication skills for nurses using the IPC training videos produced by UNICEF Georgia. Include a short video of nurses from different parts of Georgia talking passionately about their role in supporting and caring for parents and children as they receive the vaccination. Use the priority vaccines of HEXA, MMR and Td within these video clips. | Year 2 | No cost | HPD/EPI in collaboration with UNICEF | Not applicable |
| Deliver the above IPC skills training to all primary care nurses. Targeting low coverage urban areas first. Monitor the quality of the training carefully. Collaborate with an academic or HCW training body. Evaluate the training and improve or modify based on findings. Consider sending a motivational mobile message to training participants at points post training to prompt nurses to adopt in their practice the IPC skills learned in the training. | Year 2 | 3,000 GEL | HPD staff | TBD |
| Advocate for nurse pre-service training to include IPC skills. Provide technical support for the development of a curriculum which should include the UNICEF Georgia supported IPC training videos.. | Year 3 | No financial cost | UNICEF NCDC EPI | Not applicable |
| Develop a series of motivational and informative messages based on the findings from the formative research to encourage and enable nurses to follow up, address parents’ concerns and provide accurate information. Consider an emotional message that directly appeals to their feelings of professionalism and desire for recognition of their role or being valued. Use these in all materials developed and targeted for the nurse. Test these messages with nurses’ and professional organisations with nurse membership before they are finalised and used. | Year 2 | 2500 GEL | HPD in collaboration with EPI | TBD |
| Ensure that nurses have access to a copy of the Immunization Communication Aide for HCW mentioned in actions for parents. | Year 1 | Costs included in actions for parents. | EPI | Not applicable |
| Collaborate with professional bodies that represent nurses to have their public endorsement and support. Identify national and regional champion nurses for use in visual materials and media programmes. Provide media training and support using the same specialist health media agency that provided the training for doctor champions. | Year 2 | 1000 GEL | HPD | TBD |
| Influence and encourage the specialist health media partners to develop programmes that promote the key messages to nurses and encourage the specialist health media to give nurses a voice and elevate how their role is presented. | Year 2 | No cost | EPD | Not applicable |
| Consider the key influencers for this target group and identify a short and feasible set of 3 to 6 actions that can be carried out to utilize these influencers to positively promote the key messages for this target group. | Year 2 | No cost | HPD in collaboration with EPI | Not applicable |

| Actions Teenagers | Conducted by | Broad costs | Responsible lead | Source of Funding |
| --- | --- | --- | --- | --- |
| Conduct a series of 8 focus groups in total. Four focus groups with a purposeful sample of young people, 2 female and 2 male of 14yrs respectively. Reflect different socio economic groups of rural/urban with greater emphasis on the urban. Additionally, 1 focus group of youth workers and schoolteachers of children aged 13 to 14, two focus groups with parents of children aged 13 to 14 year olds. One focus group with nurses and one with family doctors. Analyse and produce a report on the key findings identifying barriers and enablers, preferred channels of target groups. | Year 3 | 5,000 GEL | HPD | TBD |
| Procure the services of a creative agency to develop a campaign for Td vaccine for the teenage target group. Using the findings from the qualitative research develop a creative brief (terms of reference). Services should include the development of a campaign concept and brand, a set of emotional and informational messages, a social media strategy that includes three 1 – 2 minute videos for circulation via social media of young people / peers representing range of young people’s interest and backgrounds talking about why it’s cool to vaccinate and why they got vaccinated. Printed poster materials for schools and health facilities targeting this age group using celebrities and sportspeople and other people respected by this age group. Once developed use the same messages consistently throughout the communication efforts. Brand videos, materials with the campaign concept | Year 3 | 30,000 GEL | HPD in collaboration with EPI | TBD |
| Attempt to get the Td vaccination written into the script and story line of a popular teenager TV program. Consider setting up a Facebook page or social media site and enlisting young people as bloggers working closely with EPI to ensure the information is technically accurate. | Year 3 | 1000 GEL | HPD | TBD |
| Dissemination of branded informational and emotional messages about immunization through the schools. Establish support from the MoE for working collaborations between the two ministries at a national level that can be replicated at a regional and district level. | Year 3 | No cost | NCDC communications officer in collaboration with HPD | TBD |
| Consider the key influencers for this target group or advocates for young teenagers and identify a short and feasible set of 3 to 6 actions that can be carried out to utilize these influencers to positively promote the key messages for this target group. | Year 3 | 1000 GEL | EPI with support from HPD | TBD |

| Actions Teenagers’ parents | Conducted by | Broad costs | Responsible lead | Source of Funding |
| --- | --- | --- | --- | --- |
| Based on the findings from the above formative develop two or three key messages and two sub messages for each and use consistently throughout the communication effort for this groups. Test these messages with the target group before finalization and use. | Year 3 | 600 GEL | HPD | NCDC |
| Pilot in two urban facilities an SMS /mobile birthday message to parents of 14 year olds on their birthday to inform them their child is now 14 and therefore due the Td vaccine. Evaluate and make recommendations for the potential for scale of this intervention. | Year 3 | 1000 GEL | HPD in collaboration with a SSA healthcare provider such as EVEX or Curatio | TBD |
| Regional EPI officers / District Municipality Health Officers to develop collaboration with the regional / district education departments to enlist the schools to positively promote Td vaccine for this age group including the schools doctor should remind the vaccination time. Tight collaboration of school doctors with parent associations. | Year 3 | No financial costs | EPI | Not applicable |
| Consider the key influencers for this target group and identify a short and feasible set of 3 to 6 actions that can be carried out to utilize these influencers to positively promote the key messages for this target group. | Year 3 | No costs identified | HPD with support from EPI | Not applicable |

| Actions policy makers | Conducted by | Broad costs | Responsible lead | Source of Funding |
| --- | --- | --- | --- | --- |
| For each of the communication objectives for this target group map out the key people/organizations that need to be influenced to achieve each objective. Professionals bodies that represent doctors, nurses, teaching institutions, national parents associations, academics, large workforce organizations. | Year 1 | No costs identified | NCDC/EPI with support from HPD | Not applicable |
| Consider the key influencers for these individuals / organizations and identify a short and feasible set of 3 actions that can be carried out to utilize these influencers to positively progress the objectives and focus on the key themes. | Year 1 | No costs identified | NCDC/EPI with support from HPD | Not applicable |

| Cross Cutting Actions | Conducted by | Broad costs | Responsible lead | Source of Funding |
| --- | --- | --- | --- | --- |
| NCDC to establish a dedicated and rolling annual budget line for communications for immunization that is separate from the budget for the procurement of vaccines. | Year 1 | No cost | Director/ D. Dir. of NCDC/Head of EPI | NCDC |
| NCDC to identify a dedicated Health Promotion Officer within the HPD to provide dedicated support to the EPI team on communication for immunization. | Year 1 | No cost | Director/ D. Dir. of NCDC/Head of EPI | NCDC |
| District municipality health officers to be encouraged/supported to develop communication action plans targeting the known challenges specific to their areas. Plans should ideally be developed using participatory process involving a wide range of stakeholders including the municipality, orthodox church, health providers, schools, civil society organisations, relevant NGOs, and other key service providers or opinion formers in the communities. Community mobilization will be a strong feature of these local plans drawing on organised and respected groups and key opinion formers within communities to endorse immunizations and influence and shape opinions and practice of the local community. How district level plans will be financially supported should be agreed alongside and any proportion of the national communications budget allocated to support district level plans to be agreed. | Year 2 |  | Director/ D. Dir. of NCDC | NCDC TBD |
| The relationship and potential collaborations between educational institutions and the immunization programme to be considered at a national level. At a district level this will be part of the communication action plan. | Year 1-2 | No cost | Director/ D. Dir. of NCDC | NCDC TBD |
| CTo inform better targeting of activities and resources to where there is greatest need conduct further investigative work potentially through a WHO TIP approach (modified to the needs of Georgia) to help understand and therefore address, what lies behind some of the more notable regional and district differences for the priority vaccines. This should include looking at health care service delivery issues as well as the KAP of particular minority population groups such as displaced, ethnic minorities, highly educated/socio economic groups that may contribute to pockets of under immunization coverage. Identify ways to strengthen the current communications strategy, particularly identifying who and how to target population groups with very low and/or delayed immunisation coverage. Include an onsite deep dive into how vaccination services are provided in a facility with very low coverage to identify the bottlenecks and understand what lies behind those differences. Compare conducting the same in a high performing facility to identify the key contrasting characteristics. | Year 2 | 50,000 | EPI | WHO (potentially) |
| Consider the potential for an increased role of the health facility administrator/management in increasing immunization coverage potentially through: oversight and monitoring of the immunization coverage, strategies employed to increase or maintain coverage rates. Explore possibilities for performance based financing within health provider contracts with SSA. Consider the feasibility of and advocate for, a national or regional ‘Health Care Facility Award for Immunization’ for the facilities with the highest coverage and most active and effective strategies to maintain this. The award could have a financial performance related incentive attached and be managed by the SSA or their health provider contractors. | Year 3 | 20,000 | NCDC/EPI | TBD |
| Develop content with group of recognised national experts, design and desktop publish, print and circulate NCDC clinical guidelines for specialist doctors namely neurologists and gynaecologists on the contra indications for immunization. Guidance to be endorsed by the professional bodies in Georgia and potentially those professional bodies that represent these specialisms in other western European countries that may have the respect of Georgian specialists such as Royal Colleges of Neurologists and Gynaecologists. Share with the specialist health media. Upload onto the NCDC web site. Share with Specialist Training Institutions for Medical Specialities in Neurology and Gynaecology. | Year 2 | 2000 GEL | EPI with support from the HPD | TBD |
| Consider the possible uses of simple and relatively cheap computer based packages that facilitate mass mobile messaging to communicate with the public and the health professionals in a targeted way. Pilot the use in one geographical area or low coverage facilities and evaluate. Uses could include post training to consolidate learning, motivational messages to HCWs and prompts to action, use by large urban health facilities to provide mobile messages to remind parents of the need to vaccine targeting HEXA 2,3 and MMR 2 or messages to MMR under immunized adults within a facility. Explore public private partnerships with Telcos. | Year 3 | 2000 | HPD with support from EPI | TBD Consider seeking support /collaborations with a private sector mobile telecom company |
| Review and develop an action plan to improve the information available on the NCDC website on each of the vaccines in the national immunization programme. | Year 2 | 4,000 | EPI with support from HPD | TBD |

| Actions Influencers | Conducted by | Broad costs | Responsible lead | Source of Funding |
| --- | --- | --- | --- | --- |
| Civil society, local NGOs, professional and parent associations: Identify position of various NGOs and Civil Society Organizations on immunization. Support and enable allies to advocate for immunization by providing accurate information, materials and consistent messages. Identify Professional associations that can be potential supporters of immunization and support them to create or use existing fora for immunization issues to be discussed. Have them endorse guidelines and collaborate in developing and delivering trainings Work with Parents’ Associations to dispel misconceptions and enable them to serve as role models by providing materials and accurate information and messages include some of their personal stories in materials and video clips. | Year 2 | 1000 GEL | EPI with support from HPD | TBD |
| Religious Groups: At a national level the Orthodox Church is neutral however at a local level priests should be involved as stakeholders in district or at best the district plan should consider how to manage any potential negative influence. Include one or two supportive national / local priests in materials and video clips in campaign materials and videos. Support the involvement of local religious representatives in district level communication plans. | Year 2 | No cost | HPD/EPI | Not applicable |
| Mass Media: Analyze of the media landscape to identify the best ways to reach the identified audiences quickly and most sufficient. Explore the knowledge of the general media on immunization and vaccines. Develop a media reference pack to encourage accurate and responsible reporting of immunisation by the general media. Consider developing a one-day development day for general media to improve their understanding of the critical role immunization plays in maintaining the health of the population. Create a list of expert/champions/spokespersons for each vaccine. Train experts in personal presentation skills, media management. Create a champions spokesperson group and meet with them at regular intervals provide support and regular updates to them on issues and coverage. Provide media with a list of these expert/champions/spokespersons. Meet collectively with the specialist health media to discuss the strategy and the priorities and agree an annual plan for their support and specific programs. Agree support NCDC will provide to them. | Year 2 Year 2 | 1000 GEL 3000 GEL | NCDC communications lead officer with support from HPD and EPI. HPD, with support from EPI | TBD TBD |
| Social media: Review the way social media is used by NCDC to promote immunization. Identify key sites that the different target groups use. Develop a simple realistic social media plan with specific actions for each target group, use consistent messages and where appropriate circulate the materials being produced for the different target groups within the communication strategy on social media sites. | Year 1 to 2 | 18,000 | NCDC communications lead | TBD |

# 11. Crisis communication

A separate plan for crisis communication is included in this strategy as an appendix. This plan has been developed as a generic crisis communications plan for the National Immunization Programme and contains what actions need to be carried out in the event of a crisis and within what time frame. Specific messages regarding the safety of each of the vaccines within the national immunization programme are included.

The plan is finalized and approved by the NCDC and the ICC for Immunization then shared with the MoH Emergency and Crisis Management Department for approval. Once approved the plan is then adopted by the Ministry of Internal Affairs Emergency and Crisis Management.

| Actions Influencers | Conducted by | Broad costs | Responsible lead | Source of Funding |
| --- | --- | --- | --- | --- |
| Agree general holding messages that relate to the immediate investigative process for any crisis situation | Year 1 | No cost | EPI |  |
| Agree two or three key messages for each vaccine with supporting messages for each. | Year 1 | No cost | EPI |  |
| Re establish and identify key spokespersons for immunization generally and specific expert spokespersons and support persons for specific vaccines. Bring this group together to share, go through and understand the CCP agree roles and responsibilities and finalize the messages. | Year 1 | No cost | EPI |  |
| Develop FAQ sheet for each vaccine include the holding message and the specific messages for each vaccine. Produce laminated copies for all spokespersons and MoH / NCDC communication staff. Upload onto the NCDC website. | Year 2 | No cost | EPI |  |
| Bring the Crisis communication committee together at least once over each year to discuss progress with Immunization coverage and refresh on the messages. | Year 2 | No cost | EPI |  |

# 12. New vaccine communication plans

The introduction of a new vaccine always requires a specially tailored communication effort that targets the population groups concerned and the health care workers involved. Lessons have been learned in Georgia both from experiences of vaccine introduction in other countries within the region and from Georgia that are considered in designing communication approaches for the introduction of new vaccines.

Noteworthy here is that in the second half of 2017 the National Immunization Programme intend to conduct a pilot introduction of the HPV vaccine which in Georgia will target female children aged nine years. This pilot involves a small and defined geographical area.

An appropriately researched and targeted communication plan will be employed to prepare the target groups for the HPV pilot and manage any adverse incidents from a communication angle. Subject to some monitoring and review it will inform the final communication approach adopted should the HPV vaccine be scaled and introduced nationally at a later time.  It is not therefore included within this national strategy at this stage but will rather be developed and added as an appendix to this document nearer the time.

# 13. Accountability, Monitoring and Evaluation Framework

## Accountability

The planning and implementation of this strategy will be the responsibility of a small working group of staff drawn from the National Immunization Programme, the Health Promotion Department, the MoH Public Health Department and Communications Unit and the ICC. Members are named in the table below alongside their respective contact details. This working group will work together to ensure the strategy is implemented. They will meet regularly, draw on the expertise of others, engage with wider stakeholders, share information and update each other regularly via emails and face-to-face meetings. This group will report to the NCDC Director on progress and regularly present progress to the ICC.

## National Communication Strategy for Immunization Steering Group

| Name and Title | Contact details |
| --- | --- |
| Lika Jabidze, Head of EPI, Immunization Division, NCDC | l.jabidze@ncdc.ge |
| Nona Beradze, Deputy Head of EPI, Immunization Division, NCDC | n.beradze@ncdc.ge |
| Tamar Dolakidze , Chief Specialist NCDC | t.dolakidze@ncdc.ge |
| Nino Mamukashili, Head of PR Group, MoH | ninomamukashvili@gmail.com |
| Ekaterina Adamia, Head of Public Health Division, MoH | eadamia@moh.gov.ge |
| Maia Shishniashvili, Head of Health Promotion Division, NCDC | m.shishniashvili@ncdc.ge |
| Nino Sarashvili, Health Promotion Officer, NCDC | n.sarashvili@ncdc.ge |
| Teona Todua, Health Promotion Officer, NCDC | t.todua@ncdc.ge |
| Giorgi Kurtshikashvili, Health Officer, WHO Georgia | KURTSIKASHVILI, Giorgi <kurtsikashvilig@who.int> |
| Nitag members - Ivane Chkaidze, Maia Kherkheulidze | ivane_ch@internet.ge; mkherkheulidze@hotmail.com |
| Regional Officer, NCDC – Ramaz Urushadze | ramur47@gmail.com |
| District Health Officer, Municipal Government Office - Dali Kobuladze | dali kobuladze <d.kobuladze@mail.ru> |
| Nana Pruidze/Maya Kurtsikidze Tako Ugulava, UNICEF Georgia | tugulava@unicef.org/ npruidze@unicef.org/mkurtsikidze@unicef.org |

## National Communication Strategy for Immunization Working Group

| Name and Title | Contact details |
| --- | --- |
| Nona Beradze, Deputy Head of EPI, Immunization Division, NCDC | n.beradze@ncdc.ge |
| Tamar Dolakidze , Chief Specialist NCDC | t.dolakidze@ncdc.ge |
| Maia Shishniashvili, Head of Health Promotion Division, NCDC | m.shishniashvili@ncdc.ge |
| Nino Sarashvili, Health Promotion Officer, NCDC | n.sarashvili@ncdc.ge |
| Teona Todua, Health Promotion Officer, NCDC | t.todua@ncdc.ge |
| Nominated MOH communications/ PR representative- Sofiko Chumburidze | schumburidze@moh.gov.ge |
| Nino Mamukashvili, NCDC Communications / PR représentative | ninomamukashvili@gmail.com |

## Monitoring and evaluation framework

The action plan will be used to review and monitor progress of the strategy and quarterly written reports on progress against planned activities to be conducted will be produced by the Strategy Working Group and submitted to the Strategy Steering Group and the NCDC senior management team. Challenges and anticipated concerns will be included in the reports that will also be circulated for information to the NITAG and the ICC, chaired by the Minister of Health.

Targets have been set for selected activities drawn from the action plan and targets set to act as KPIs for Year One. The value of these will be evaluated after the first year and if useful another set of select KPIs will be developed for year two.

| Parents of children 5 and under |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Activity | Output | Outcome | Indicators | Targets | Verification data source |
| Develop a written misconception buster that can be shared with parents by health care workers | Written material produced | Increased awareness amongst parents of misconceptions in relation to immunization | Number of facilities aware of and using material and distributing to parents | 80% | Telephone survey of 25 facilities |
| Develop a series of very short videos for circulation on social media that address misconceptions | Videos produced | Increased awareness of parents of misconceptions in relation to immunization | Number of people who have seen the videos | 3,000 in first 6 months | Number of hits on the video |

| Doctors |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Activity | Output | Outcome | Indicators | Targets | Verification data source |
| Conduct Training the Trainers approach for doctors | Training materials Trainers Selected | 70 trainers are prepared by the end of 2017 | Number of doctors trained | 80 % of the doctors are trained by second year (2018) | Reports of the training sessions undertaken, registration of training participants; |
| Provision of guidelines to doctors on contra indications and how to assure hesitant parents to accept the vaccine | Development of the information materials | Improvement of the information on immunization provision to parents by the doctors | Percentage of doctors in receipt of printed information | 100 % of the doctors | Printed materials, booklets |

| Primary Care Nurses |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Activity | Output | Outcome | Indicators | Targets | Data source |
| Develop a one-day IPC skills training curriculum for nurses. | Training pack and programme | Increased opportunity for nurses to improve their IPC skills | Number of nurses involved in testing the training pack | 10 | Availability of Training pack in NIP |
| Encourage specialist health media to give nurses a voice and elevate how their role is presented and support the messages that target nurses | Programmes on radio and TV that promote the role of the nurse and use the campaign messages. | Nurses have raised awareness of their role and feel more motivated to reassure parents of the importance of immunization | Number of programmes produced and broadcast | 5 | TV and radio programmes guide |

| Teenagers |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Activity | Output | Outcome | Indicators | Targets | Data source |
| Identify the KAP of teenagers in relation to immunization | Report of Findings | The teenagers attitude, knowledge, information and barriers towards immunization informs communication messages | Number of FGs conducted | 32 teens participation in 5 FGs in 2017 | Report |
| Finalize communication messages | Report on testing | Messages developed have resonance for young people and address concerns build on motivators | Number of messages | At least three key messages and three sub messages for Teenagers | Messages |

| Teenage parents aged 12-14 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Activity | Output | Outcome | Indicators | Targets | Data source |
| Identify the KAP of teenager’s parents in relation to immunization | Report of Findings | The teenagers’ parents attitude, knowledge, information and barriers towards immunization informs communication messages | Number of FGs conducted | 25 parents of teens participate in 4 FGs in 2017 | Report |
| Finalize communication messages | Report on testing | Messages developed have resonance for parents of young people and address concerns build on motivators | Number of messages | At least three key messages and three sub messages for Teenagers are developed | Messages |

| Adults born between 1989 and 2000 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Activity | Output | Outcome | Indicators | Targets | Data source |
| Identify insights into the KAP of adults born in the specified period in relation to MMR and their perceived risk | Report of Findings | The adults attitude, knowledge, information and barriers towards immunization informs communication messages | Number of FGs conducted | 25 adult’s participation in 4 FGs in 2017 | Ad hoc NCDC/NIP Report |
| Finalize communication messages | Report on testing | Messages developed have resonance for adults and address concerns build on motivators | Number of messages | At least three key messages and three sub messages for adults | Messages |
| Reduce the number of under vaccinated adults with MMR | Increased number of adults protected from measles with MMR | Decreased risk of measles outbreak | Number of adults vaccinated with MMR in last 12 months | Around 400 adults receive vaccine | Monthly reports from District level’s PHC |

| Policy makers |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Activity | Output | Outcome | Indicators | Targets | Data source |
| Review of incentives and disincentives for doctors | Report on the review | Better understanding of what might work in Georgia to incentivise doctors to increase immunization | Number of country approaches reviewed | 4 | Final report with NCDC |
| Advocacy for the communication strategy funding | NCDC allocate budget line for communication for immunization separate to vaccine procurement | NCDC commit funds to a separate rolling annual budget line for Communication for Immunization | Funds allocated and received for 2017/18 | $50,000 | NCDC budget report |

Impact

To determine how impactful the strategy has been in achieving the overall goals and communication objectives the following objectives have been selected. Some negotiations will take place with UNICEF to determine whether questions can be included in the UNICEF Multiple Indicator Cluster Survey (MICS) to be conducted in 2018. Depending on when this is conducted and how frequently will be considered, as the 2022 may be more appropriate.

| Indicator and Target | Source |
| --- | --- |
| Coverage of HEXA 3 by 5% at national level and 3% at the district level by 2022 | National Immunization data |
| National coverage of MMR 2 by 10% and 6% at the district level by 2022 | National Immunization data |
| Coverage of Td amongst teenagers by 10% at the national level and 6% at the district level by 2022 | National Immunization data |
| Primary care doctors instill confidence in immunization amongst parents reported by 60% parents | MICS 2018 |
| Nurses provide useful information and support on immunization to parents reported by 40% of parents | MICS 2018 |
| Doctors’ motivated to effectively communicate with parents about the importance of immunization | MICS 2018 |
| Reduce the number of under immunized adults born between 1989 and 2000 by 2022 | National Immunization Data |

# Annexes

## Annex 1 Crisis Communication Plan

1. Situations in which this plan would be required to be followed

- Adverse affect of a vaccination

- Serious adverse reaction to a vaccine

- Misinterpretation of a case to be vaccine related

- Public spread of rumours and anxiety to a heightened degree

2. Objectives of this plan

- Fast response to media queries

- Address various rumours around the crises

- Keep the public, media and other key stakeholders informed of what the Government are doing and why

- To restore public trust in immunization

3. Key elements of this plan

- Anticipation and preparedness for an emergency

- An emergency

- An aftermath of an emergency

4. Anticipation and preparedness for an emergency

4.1 The purpose of the team is to:

• Build or restore public trust.

• Deliver key messages to the public.

• Deliver key messages to the internal organization structure.

• Respond to public requests for information.

• Respond to media requests for information.

4.2 Responsibilities of all members of a communication team:

• Identify whom to contact and when: internal management, the press, key partners and the public

• Identify of media outlets

• Define how to organize contacts and information files for access by the internal structure, the media and the public.

• Train the team members.

• Delegate the use of technical equipment.

4.2 The Team

| Members | Organization | Contact details | Responsibilities |
| --- | --- | --- | --- |
| Zaza Sopromadze | MoLHSA, Deputy Minister | 591907474 | Coordination of Crisis Management at the Governmental Level |
| Eka Adamia | MoLHSA | 577282825 | Coordination of Crisis Management |
| Paata Imnadze | NCDC | 599 90 68 53 | Crisis assessment and development and implementation of the final version of the messages |
| Lika Jabidze | NCDC | 599583790 |  |
| Nona Beradze | NCDC | 595956163 |  |
| Teona Kashibadze | NCDC | 591152535 | Provision of information and introduction of the Crisis Plan to the Regional field representatives |
| Sofo Chumburidze | MoLHSA | 599 120009 | Development of the key messages |
| Tako Ugulava | UNICEF | 599 929 009 | Support to the group in the implementation of the plan |
| Maya Kurtsikidze | UNICEF | 599 533 071 | Crisis assessment and development and implementation of the final version of the messages |
| Nana Pruidze | UNICEF | 599 555 779 |  |
| Giorgi Kurtsikashvili | WHO | 599 76 44 43 |  |
| Regional repress. Ramaz Urushadze | NCDC | 599 932272 | Coordinate on-site implementation of the plan |

4.3 Training

A workshop will be held to discuss and finalize the plan and that all members of the communication team have common understanding of their roles and responsibilities.  An emergency 24/7 plan should be finalized during the training. Similar workshops are to be held for the regional representatives of the communication team.

4.4 Development of an emergency 24/7 media plan

In the event of a crisis a comprehensive emergency plan must be readily available, formally approved and ready to be implemented. It must be available, understandable and familiar to the communication team. The press officer must devise staff cover 24 hours per day seven days a week (known as 24/7) with a roster in place. There can be no down time. Developing a 24/7 plan includes constant evaluation and relevant revision. It also includes new training based on any changes. Development of the plan includes liaison with other agencies so they understand the rollout of the plan.

5. Lead spokesperson / list of experts /potential supporters

A lead spokesperson is the public voice of the organization. It may not be the senior person but it will be the person who can best communicate key messages to all media. The person in this role must understand these messages in order to deliver information to the public through the media. He/she must be properly briefed and be able to take in vital points and deliver them-sometimes under great stress-so the greatest number of people understand them. The lead spokesperson must be perceived as honest, accurate, accessible and working with the public and media to disseminate information. Spokespersons selected will be those open to media training and constructive comments and be willing to make themselves very available during a time of crisis.

5.1 Spokespersons responsibilities

• Stay on message with agreed key points

• Never go off the record

• Not to use jargon or technical language

• Correct media errors immediately

• Admit mistakes and shoulder responsibility on behalf of the organization.

• Focus on known facts

• Avoid humour because it can be misinterpreted

• World Health Organization recommendation known as 27/9/3 will be followed: be prepared to give the facts in 27 words, 9 seconds or three bullet points.

| Spokesperson | Area | Contact |
| --- | --- | --- |
| David Sergeenko | MoLHSA | 2 51 00 11 info@moh.gov.ge |
| Amiran Gamkrelidze | Lead spokesperson | 599 501894 |
| Paata Imnadze | Spokesperson on technical issues | 599 90 68 53 |
| Ivane Chkhaidze Maia Kherkheulidze | Childhood vaccines | 577 10 08 01 577418839 |

5.2 Second level spokespersons

While it is ideal to have a single spokesperson throughout a crisis, there will also likely be a need to have subordinate spokespersons who can provide information in other locations and/or who, because of technical expertise, can assist the lead spokesperson in dealing with the media. No matter how many subordinate spokespersons, the information they give out must be consistent with that of the lead spokesperson. All spokespersons must communicate the same consistent messages.

| Supporting Expert Name | Field | Contact |
| --- | --- | --- |
| Dali Kobuladze | Imereti region NCDC | 595956132 |
| Nana Odisharia | Samegelo region PHC | 595956105 |
| Nino Nizharadze | Adjara region PHC | 577513636 |
| Shukia Giorgelashvili | Kakheti region PHC | 595956118 |
| Mari Ginuashvili | Shida Kartli region PHC | 599260427 |
| Giorgi Mumladze | Kvemo Kartli region PHC | 555476549 |
| Tsisnam Dilebashvili | Tbilisi region PHC | 599413986 |
| Naira Khabuliani | Samtskhe-Javakheti region PHC | 599193369 |
| Maia Kutidze | Guria region PHC | 599510260 |
| Badri Kukuladze | Mtskheta-Mtianeti region PHC | 599962108 |
| Zurab Nemsitsveridze | Racha-Lechkhumi region PHC | 599152055 |

5.3 Potential Supporters

Enlist the support of those who share your viewpoint. Informed supporters can have significant impact on the public. Supporters can be a first line of subtle response by initiating alternative viewpoints.

| Name | How to involve | Contact |
| --- | --- | --- |
| First Lady – Maka Chichua | Supporting statements | 599092854 |
| Marijan Ivanuša WHO Representative, Head of WHO Country Office Georgia | Evidence base | +995 599 305 207 |
| Nino Khetsuriani, CDC | Technical and Scientific | 595074576 |
| Laila Omar Gad, Representative, UNICEF | Children First | +995 591 225281 |

6. The Messages

6.1 Packaging the message

Key messages agreed in advance within the team must form the basis of any effective communication. They must be understandable to the media, the public and internal staff. Key messages can take the form of the overarching message, followed by supporting information such as safety tips, statements from an expert or vital facts about perceived dangers.

6.2 Delivering key messages

Key messages must be clear and simple. They must be devoid of jargon or technical language. It is important that each key message be supported by extra information to add context and background facts to the point being made. Once key messages are identified, they can form the basis of all types of communication whether it emanates from a press conference, a public meeting, a press release or a broadcast interview. Agreement of key messages means different spokespeople in different locations can deliver the same information. All member of the communication team must be aware of changes to key messages as the crisis changes. In delivery of the messages spokespersons and experts should always try to:

• Keep to a maximum of 3 key messages

• Know your audience and media outlets

• Pitch the messages to a 12 year old child to avoid misunderstanding

• Be able to limit key messages to the 27/9/3 principle (27 words, 9 seconds, 3 messages)

• Be able to expand with supporting information if time allows

• Create an evaluating process to gauge success of key message delivery.

6.3 Controlling message output

It is important to control key messages. Before an interview, ask what the questions are to see how they fit into a key message strategy. Also find out basic facts such as the journalist’s name, his/her employer and the knowledge the journalist possesses of the situation. If questions during an interview or press conference go ‘off message,’ become aggressive or are based on wrong facts, use a bridge statement to get back to your own message. Two sample bridges:

• ‘I think what is important here is …’

• ‘The public should understand that…’

Delivery success can depend on speed. By hesitating, a factual vacuum can be created which will allow bad information or opinion to fill a void. By publicizing key messages quickly, the template for vital messages will be created. This will help public understanding rather than add to a confusing combination of assumed fact, bias or rumour.

6.4 Key messages

Key messages will be developed in advance. These include:

- Holding messages

- General non vaccine specific messages

- Vaccine specific messages.

These can be found as an appendix to this plan for each vaccine within the Immunization Programme in Georgia.

7. Identifying the media outlets

- Press conference: MoH led press-conference immediately after the crises

- Television: Interviews to Rustavi 2, GPB, Imedi, Alania, Kavkasia

- Radio: GPB, Fortuna, Imedi

- Newspapers: 24 Saati, Rezonansi, Alia, Akhali Taoba, Kviris Palitra, Georgian Taimes, Georgian Messanger, Georgia Today.

- Internet: news agencies, internet media

- Local events: local press-conference if the crises in linked to the particular region.

7.1 Some elements to consider when determining which media outlets are appropriate in this crisis:

• Do the people you want to communicate with follow this media channel?

• Is the specific media channel relevant to your goals?

• Does it target the audience you are targeting?

8. Creating Material

Background material should be already prepared and ready for use.

| Type of material | Description | Responsible |
| --- | --- | --- |
| Updated media list | It is essential to have an updated list of all contact journalists | Nino Mamukashcvili, NCDC |
| Press-releases for each vaccine | Including key messages for every vaccine in the national schedule | Nino Mamukashvili, NCDC |
| Glossary of technical terminology | Some major technical terminology to ensure common understanding and interpretation | Lika Jabidze, NCDC |
| Instructions to staff in the event of an adverse event | What to do and how to respond to the media queries | Nona ¦Beradze, Maia Shishniashvili Nino Mamukashvili NCDC |
| Background material on vaccines | More information about the different vaccines | Lika Jabidze, NCDC |
| Q & A on vaccines and the process for managing the investigation into adverse event | Anticipated questions on the vaccine and the investigative process with the relevant and agreed answers for the key vaccines. | Maia Shishniashvili NCDC |

9. An Emergency: Crises Phase One

The first two weeks of a crisis is critical for external communication work.

This initial phase is when media attention is at its peak and needs to be both managed and maximised.

Day 1.

| Event | Objective | Who is responsible |
| --- | --- | --- |
| # Pre-establish a checklist of contacts | # When a crisis hits, it is essential that key personnel be notified as quickly as possible. Their names, telephone numbers, and where they could be reached 24 hours a day were circulated throughout the organization. All personnel, particularly regional personnel knew whom to call the instant a crisis was identified. | Working group |
| # Evaluate the nature of the crisis | # Why is it a crisis? Who says it is a crisis (the media, special interest groups)? When was it first identified as a crisis? | Working group |
| # Inform potential supporters | # Mobilize pre-identified supporter, e.g. first lady. Explore if she can be involved into the press-conference. | Working group |
| Preparation of the press-release | Respond to rumors about the case, provide accurate information, release key messages, include quotes from the leading spokesperson. | Working group |
| Press-conference | Invite media and key stakeholders to provide accurate information and spread key messages | MoLHSA, Working group |
| Dissemination of the press-release through news agencies | to spread accurate information and disseminate key messages | Working group |
| Responding to various media queries | to spread accurate information and disseminate key messages | Working group |
| Responding to various queries from International media | When crises emerge international media are on spot to highlight the situation. To spread accurate information and disseminate key messages | Working group |
| Monitoring media coverage | To be on the loop of the media coverage and to timely respond and correct potential errors and irregularities | Working group |

Day 2.

| Event | Objective | Who is responsible |
| --- | --- | --- |
| Monitoring media coverage | To be on the loop of the media coverage and to timely respond and correct potential errors and irregularities | Working group |
| Responding to various media queries | to correct potential errors and irregularities and spread accurate information, disseminate key messages | Working group |
| Producing newspaper articles and ads | To spread key messages through paper ads | Working group |
| Develop TV/radio spots with key messages and release them on air | This will ensure key messages are reaching wider audience and start converting the crises into the health communication | Working group |
| Organize press-conference into the crises hit region for local media | to correct potential errors and irregularities and spread accurate information, disseminate key messages | Working group |

Day 3.

| Event | Objective | Who is responsible |
| --- | --- | --- |
| Monitoring media coverage | To be on the loop of the media coverage and to timely respond and correct potential errors and irregularities | Working group |
| Responding to various media queries | to correct potential errors and irregularities and spread accurate information, disseminate key messages | Working group |
| Develop Inserts into the TV programme (Pulsi, Tkveni Ekimi) | This will ensure key messages are reaching wider audience and the crises is turning into the health communication campaign | Working group |
| Organize round-tables with key partners (professional associations, NGOs) with the invited experts | To discuss and analysis the situation, instilling key messages into the key partners | Working group |

Day 4.

| Event | Objective | Who is responsible |
| --- | --- | --- |
| Monitoring media coverage | To be on the loop of the media coverage and to timely respond and correct potential errors and irregularities | Working group |
| Responding to various media queries | The media queries may be getting to fade away but there night be still queries | Working group |
| Continue having TV/radio spots with key messages on air | This will ensure key messages are reaching wider audience and the crises is turning into the health communication campaign | Working group |
| Start preparation of a series of Talk shows about the issue, ideally should be phone-in | The talk shows will allow to discuss the key messages and information in more details, invited experts, audience participation | Working group |

Day 5.

| Event | Objective | Who is responsible |
| --- | --- | --- |
| Monitoring media coverage | To be on the loop of the media coverage and to timely respond and correct potential errors and irregularities | Working group |
| Responding to various media queries | The media queries may be getting to fade away but there night be still queries | Working group |
| Continue having TV/radio spots with key messages on air | This will ensure key messages are reaching wider audience and the crises is turning into the health communication campaign | Working group |
| Launching Talk shows about the issue, ideally should be phone-in | The talk shows will allow to discuss the key messages and information in more details, invited experts, audience participation | Working group |

Day 6.

| Event | Objective | Who is responsible |
| --- | --- | --- |
| Monitoring media coverage | To be on the loop of the media coverage and to timely respond and correct potential errors and irregularities | Working group |
| Responding to various media queries | The media queries may be getting to fade away but there night be still queries | Working group |
| Continue having TV/radio spots with key messages on air | This will ensure key messages are reaching wider audience and the crises is turning into the health communication campaign | Working group |
| Launching a series of Talk shows about the issue, ideally should be phone-in | The talk shows will allow to discuss the key messages and information in more details, invited experts, audience participation | Working group |

Day 7.

| Event | Objective | Who is responsible |
| --- | --- | --- |
| Monitoring media coverage | To be on the loop of the media coverage and to timely respond and correct potential errors and irregularities | Working group |
| Responding to various media queries | The media queries may be getting to fade away but there night be still queries | Working group |
| Continue having TV/radio spots with key messages on air | This will ensure key messages are reaching wider audience and the crises is turning into the health communication campaign | Working group |
| Launching a series of Talk shows about the issue, ideally should be phone-in . | The talk shows will allow to discuss the key messages and information in more details, invited experts, audience participation | Working group |

The following week will also include monitoring media coverage, responding to various media queries, having TV/radio spots and talk shows with key messages on air and monitoring regions.

10

10. An Emergency: Crises Phase Two

During week 2 to 6 there may still be a strong media presence, but the story is likely fading to inside pages of newspapers and later stages of newscasts. Continue to be available to feed the media where needed but support the slow adjournment of the issue.

11.  An Emergency: Crisis Phase Three

After six weeks it is likely the media interest is waning even if there are still substantial populations affected by emergency conditions.

12. Aftermath of an Emergency

Once an emergency has been identified as over, the aftermath programme begins. The communications team can stand down from 24/7 cover. But there should still be seven days per week cover. The lead spokesperson should still be on duty to articulate key post emergency messages.

All media should be given access to affected locations to report on conditions and the return to normalcy. Two-way communication channels, such as hotlines, should be kept opened and monitored. This allows the public to ask important questions and it gives an indication of problems experienced by the public.

As with the emergency plan, there should be a constant monitoring and review of the aftermath plan to ensure key messages are aired and that the public is given the opportunity to access the messages.

The Communication team may start developing the relevant immunization campaign to re-build trust in immunization and to promote desired behavioural objectives.

13. Evaluating and Reviewing the Emergency Plan

Once there is time to, an evaluation and review of the emergency plan can begin.

It can be split into three areas of review of the internal process, relations with partners and the public; the media: key messages offered and key messages delivered:

- Broadcast: Were key messages broadcast through news items: What were the audience figures? To what extent were messages heavily edited/reported accurately.

- Print: What percentage of newspapers covered the key messages and what were their circulations.

- Web: Were key messages taken up and how many ‘hits’ were on key sites.

- Traditional: How many people engaged with folk arts, open meetings, were they relevant to a specific community.

14. Timeline

|  | Preparation well in advance | 1st week | 2nd week | 3rd /4th week | 5th /6th week | 7th – 10th week |
| --- | --- | --- | --- | --- | --- | --- |
| Setting up the Communication Team | X |  |  |  |  |  |
| Identification of a lead spokesperson | X |  |  |  |  |  |
| Q&A sheet and key messages | X |  |  |  |  |  |
| Workshop for the communication team | X | X |  |  |  |  |
| Guidance to the regions | X | X |  |  |  |  |
| Workshop in the regions |  |  | X |  |  |  |
| Development and implementation of an emergency 24/7 media plan | X | X | X | X | X |  |
| Monitoring and review of media coverage |  | X | X | X | X |  |
| Evaluation and review |  |  |  |  |  | X |

15. Twelve Principles of Crisis Leadership

- Put people issues first.

- Timely, accurate information is the lifeblood for managing a crisis – and very difficult to obtain.

- Rapid response is essential, but media pressure must not skew decisions.

- Crisis management requires a team approach.

- People are usually very forgiving, but they will not tolerate arrogance, indifference, lying, or gross incompetence.

- To emerge from a crisis with its business base and reputation intact, an organization must respond in a manner that is 100% consistent with its image.

- The magnitude of the crisis dictates the level of the executive who responds.

- It is not enough to be legally or scientifically correct; the public insists on and is entitled to more.

- Government and media will expand their roles in a crisis if there is a public perception that the organization is not doing all it should do.

- All key audiences revise their image of an organization after it experiences a crisis.

- A major crisis will have a profound and long-term impact on an organization and its leaders.

- Remember the Chaos Theory: Unusual events tend to cluster.

16. General Goals of Crisis Communication

- Openness and accessibility – availability and willingness to respond.

- Truthfulness - unconditional honesty is the only policy.

- Responsiveness – recognition that any and all constituent concerns are legitimate and must be addressed.

- No secrets – Decisions and behaviours are unchangeable, unassailable, and positive.

17. Guidelines for Managing Crisis Communication

1.	Ascertain and accept the reality of the crisis.

2.	Activate the crisis management team and alert top management.

3.	Designate crisis media centre location and team.

4.	Conduct necessary fact-finding and investigations as quickly as possible and keep key people involved at all times.

5.	Ensure spokespersons are available and communicate consistent messages and regularly

6.	Quickly hold news conference and make disclosures to the media openly, honestly, and accurately. Appeal for support to manage the situation and minimise unnecessary anxiety.

7. 	Communicate directly with Government, employees, customers, stakeholders, and other key publics.

8.	Take appropriate remedial action.

9.	Keep a log.

18. Some Common Problems and Solutions

Problem:

Interviews go off message, become aggressive or are based on misinformation.

Solution:

Control the interview by knowing the questions you will be beforehand. Correct misassumptions and knowledge gaps. Bridge and return to key message territory.

Problem:

Key message contains too much jargon or too many statistics.

Solution:

Simplify messages so a 12 year old can understand them. One strategy is to imagine your child, your niece or your neighbour’s child. Would that young individual understand a key message? If not, simplify it and tell the media there is additional material available by email or on hard copy.

Problem:

A comment is recorded without your knowledge and then transmitted.

Solution:

Assume that all microphones are live. This is especially true of news conferences. Assume that as soon as you enter a studio- whether for television or radio- you are being recorded.

Problem:

A journalist asks for an off-the-record comment or briefing.

Solution:

It is best to have no off-the-record access. In an emergency, all information should be delivered to all media.

Problem:

A crisis develops and the media is about to print or broadcast before an official statement.

Solution:

It is of prime importance that a message is delivered first and fast. Only deal with known facts and say if certain information is unknown. By giving out some information and key messages as early as possible, even if this is not definitive but rather holding messages and information it prevents a void being created which can be filled with rumour, inaccuracies or badly informed editorial content.

Problem:

There is a continual demand for information - especially from the media and it feels difficult to keep up.

Solution:

It cannot be ignored. Be available: prepare in advance for a crisis and the consequent media rush for information. Have a 24/7 staffing plan and expect different approaches from foreign media who may want more direct and immediate forms of coverage such as live interviews at any time. NB. Deliver immediate media training for different forms of interviews for spokespersons if needed).

19. Messages

It is known that messages can be most effective when constructed as a key message with two or three supporting messages.

Holding messages in the event of a crisis

Investigation of the incidence will take place within x days of the incidence occurring and be completed within x days. In this case the investigation will commence on XX/XX/XXX.

Likelihood of vaccine related negligible

Expect findings within x days of completed investigation

Where to find information and updates

Be assured of action

General non vaccine specific messages

Safety

Country of origin

Avoidance of outbreaks and herd immunity

Severity of diseases vaccines protect against

Vaccine specific messages: MMR

Timely vaccination

MMR and autism. Reassurance through acknowledging concern example Understand difficult not to be concerned given misinformation such as examples but be assured these are misinformation and that vaccine safety and the health and well being of everyone is our priority.

Need of adult immunization

Vaccine specific messages: HEXA

Indication/importance of vaccine

Advantages of combined vaccines

Timely vaccination

Vaccine specific messages: Td

Necessity vaccination at this age

Concrete Messages

Holding messages in the event of a crisis

- In this situation I can tell you that the Working Group of Immunization experts has been created, their roles are defined, the main actions are planned to investigate the situation. In the near future you will be provided with the most accurate information through this media source. The information will be constantly updated at our website - ncdc.ge and through social media.

- The Working Group of immunisation experts is currently assessing the situation, identifying causes, and planning the further actions. Very soon we will provide you with updated information about current situation. The information will be updated at our web site ncdc.ge and through social media.

- The crisis has been confirmed. The incident occurred in the area x at x time. The local government and the group of immunization experts of MoH have been mobilized. Investigation is underway to study the incident. There is no reason for panic and we appeal to public to keep calm. In the nearest future you will be provided with the most accurate information through this media channel. The information will be regularly updated at our web site ncdc.ge and through social media.

- At the time being, the Ministry of Health continues working with immunization experts on this issue. We understand your concern, fear and questions emerged around this specific incident. However, I would like to assure you that safety and well-being of all members of our society is our top priority. We will provide you the most accurate information through media briefings very soon. The information will be also updated at our web site ncdc.ge and through social media.

General non vaccine specific messages

- Georgia uses vaccines approved by WHO, which is a guarantee of safety and effectiveness.

- Despite the country of origin, all government-procured vaccines intended for the planned immunisation are WHO- certified and are thus safe.

- Immunisation is a major tool to prevent outbreaks of infectious diseases in the country.

- Vaccine preventable diseases are dangerous and can be fatal in some cases.

Vaccine specific messages: MMR

- It is critical to conduct MMR vaccination at 12 months since protective immunity received from mother is no longer available. To strengthen protective immunity, the second boosting dose is needed at 5 years.

- We understand your concern about misinformation related to autism but we can assure that this vaccine is safe. The health and well-being of children is our priority.

- Non-vaccinated teenagers and adults increase the risk of spread of infection.

- MMR vaccine preventable diseases are characterised by severe complications in adults.

Vaccine Specific Messages: HEXA

- It is important to conduct the HEXA vaccination at 2, 3, 4 months when a child has a minimal exposure to infection

- Hexavalent vaccine is good since it protects a child from six contagious diseases through single shot.

- Timely vaccination averts post vaccination adverse events

Vaccine specific messages: Td

Td vaccine protects you from Diphtheria and Tetanus that are both serious diseases that can be fatal.

Direct comparison of pre 1990 coverage rates with the rates assesses since 1990 is not possible because of differences in methodologies