Ministry of the Internally Displaced People from the Occupied Territories, Labour, Health and Social Affairs of Georgia

Hepatitis C Elimination Program

Monthly Progress Report- June 2020

Contents

Introduction	2

1	Statistics	2

1.1	Georgia Hepatitis C Elimination Program Care Cascade, April 28, 2015  –  June 30, 2020	2

2	Update on programmatic activities	3

2.1	Information about screening activities	4

2.2	Information about drugs	5

2.3	Other Activities	5

# Introduction

In April 2016, The Government of Georgia and the company "Gilead" signed a long-term agreement on the continuous provision for zero price of the new generation of hepatitis C medicines by Gilead Science Inc., until the elimination of hepatitis C in Georgia.

In August 2016, a long-term strategy for elimination of hepatitis C (2016-2020) was developed to achieve the ultimate goal of eliminating the hepatitis C. Strategy sets forth the following targets, to be reached by 2020:

- 90% of HCV infected persons will be tested for their infection,

- 95% of people with chronic infection will receive treatment, and

- 95% of persons receiving treatment will be cured of HCV

This report reflects the Hep C elimination program progress in June 2020. The report was prepared by the Ministry of IDPs from the Occupied Territories, Labour, Health and Social Affairs of Georgia in collaboration with the National Center for Disease Control and Prevention.

# Statistics

## Georgia Hepatitis C Elimination Program Care Cascade, April 28, 2015 – June 30,  2020

# Update on programmatic activities

## Information about screening activities

 Total number of registered screening is 3 983 553

  Total number of positive screening among the registered ones is 181 135 (4.55%)

  Distribution by age and gender among the positive screenings (figures 1 and 2):

## 2.2. Figure 1. Number of Individuals screened on Hep C and confirmed with the disease per age categories, April 28, 2015 – June 30, 2020

## Figure 2: Number of individuals screened and found positive on Hep C per gender, April 28, 2015 – June 30, 2020

## Information about drugs (April 28, 2015 – June 30, 2020)

Total number of disbursed Sovaldi bottles: 39 478

Sovaldi bottles delivered to service Providers:  34 586

Sovaldi bottles donated to the Republic of Belarus: 1 500

Sovaldi bottles donated to the Republic of Armenia: 3 000

Sovaldi bottles remaining in central stock: 393 (validity period is expired, since sovaldi regimens are almost no longer used for treatment in practice)

Total number of disbursed Harvoni bottles: 173 440

Harvoni bottles delivered to service Providers:  166 300

Harvoni bottles remaining in central stock: 3 (+7137 expired as of April 30th , 2018)

Total number of disbursed Epclusa bottles: 10 976

Epclusa bottles delivered to service Providers:  10 976

Epclusa bottles remaining in central stock:  0

Total number of disbursed MyHepAll bottles: 24 003

MyHepAll bottles delivered to service Providers:  17 829

MyHepAll bottles remaining in central stock:  6174

## Information about Elimination Program Data Management System

- Technical support of screening “STOP C” and Hepatitis C treatment systems is ongoing.

## Other Activities

Blood safety program

The country has begun revision its national blood legislation and since January 2020 with support of EU has started implementation of EU Twinning Project: "Strengthening Blood Safety System in Georgia", which is dedicated to the comprehensive law approximation. There were a series of meetings including discussion of the option of establishing a National Comparative Audit and its functions in Georgia, along with roundtable discussions on transition to the mandatory non-profit organizational form for blood establishments.

The working group reviewed draft law on blood and blood components and concordance list, as well as normative acts of Lithuania and the Netherlands, which have been translated within component 1 of the project.

“Hepatos” meeting on HCC an avoidable fate: To Liver Cancer Prevention by Viral Hepatitis Elimination

On June 9 high-level meeting was organized by the Croatian Association for the Liver Diseases "Hepatos" led by the President of the organization Dr. Tatiana Reic. Meeting entitled “HCC an Avoidable Fate: To Liver Cancer Prevention by Viral Hepatitis Elimination (and beyond) through Universal Health Coverage with additional reference to COVID-19”. During the meeting Dr. Amiran Gamkrelidze, Director General of NCDC presented next phase of Georgian elimination plan HCV – attributable HCC.