## 2018-2019
Core areas | Actions | Responsible institution | Responsible person | Start date | End date | Transition phase | Status in February 26, 2018 | Status at the end of March 2018 | Comments | Comments 14-16 May mission | Comments 6-7 Dec 2018 mission | Comments 1 May, 2019 | Status at may, 2019
1.Adoption of DRG system | 1.1 Decide which DRG grouper will be implemented | MOH | N.Berdzuli; Z.Sopromadze | Dec 2017 | Dec 2017 | Phase 1 | Completed | Completed |  |  |  |  | Completed
1.Adoption of DRG system | 1.2 Contact the organization delivering the DRG system and start the negotiations | MOH | Z.Sopromadze/S.Belkania | Dec 2017 | March 2018 | Phase 1 | Due date depends on the negotiations with NCC (to be decided by end of mission). Unformal agreement is given by NCC. Nino will be taken and not replaced. | Completed | Letter sent to Nordic Casemix Centre in mid-December 2017. The definition tables should be developed by NCC and delivered to MOLSHA by the end of May 2018. The files with Georgian primary classifications have been sent to NCC in mid March 2018. |  |  |  | Completed
1.Adoption of DRG system | 1.3 Contact the organization delivering the grouper software | MOH | Z.Sopromadze/S.Belkania/K.Goginashvili | March 2018 | May 2018 | Phase 1 | Needs input by NCC (definition tables); email will be sent after call with Martti (Feb27). Add Keti here | Completed | Letter sent to Prodacapo and Norwegian Health Directorate on 12th of March 2018 by MOLSHA. The response from Prodacapo received on 21 of March with information about NordDRG grouper software. |  |  |  | Completed
2. Development of DRG implementation and transition strategy | 2.1 Define the phases of transition with concrete activities and time frames | MOH/SSA | Z.Sopromadze/S.Belkania | Jan 2018 | March 2018 | Phase 1 | Ok, after mission final version will be produced | Completed |  |  |  |  | Completed
| 2.2 Create the DRG core team with clear TORs within SSA and MOLHSA | MOH/SSA | T.gabunia | Jan 2018 | April 2019 | Phase 1 | Ok, after mission final version will be produced | Completed |  |  |  |  | Completed
3.Preparedness of IT systems | 3.1 Analyse (pros and cons of alternative business processes) adoption of the DRG grouper to the SSA’s IT system | SSA | I.Tabatadze | April 2018 | February 2019 | Phase 1 | Looks realistics timeline (depends mostly in 1.2). This might need additional analyis after the testing and pilote phase | MOLSHA/SSA needs to study the information sent by Prodacapo (see activity 1.3) and if the suggested solution is suitable, then Prodacapo can give a price quotation upon MOLSHA's request for proposal. |  |  | Documentation of the grouper is completed. Technical preparedness exists. | made disicion to integrate DRG grouper in case registration module | Completed
3.Preparedness of IT systems | 3.2.Adapt the SSA IT system to accommodate the grouper software (VisualDRG and batchgrouper) | SSA | I.Tabatadze | March 2019 | March 2019 | Phase 2 |  |  |  |  | Depends on when the grouper will be delivered | Instalation process completed | Completed
3.Preparedness of IT systems | 3.3 Analyse the need of change of business process according to DRG requirements | SSA/MOH | I.Tabatadze/M.Khomeriki/M.Darakhvelidze | April, 2019 | December 2019 | Phase 2 - Phase 3 | This might need additional analyis after the testing and pilote phase |  | This might need additional analyis after the testing and pilot phase |  | Pilot with 7 hospitals (Apr-Sept). 2020 shadow funding with all providers. |  | Started
3.Preparedness of IT systems | 3.4 Implement techinal changes in business process according to DRG requirements | SSA | I.Tabatadze/M.Khomeriki | April 2019 | March 2020 | Phase 2 - Phase 3 |  |  |  |  | The analysis and implementation of change of business process were split | Testing proccess of DRG grouper adaptation in case registration module | Started
3.Preparedness of IT systems | 3.5. Integration of pilot hospitals with DRG WEB API | SSA | I.Tabatadze | June 2019 | September 2019 | Phase 2 - Phase 3 |  |  |  |  | New activity added |  | Not started
3.Preparedness of IT systems | 3.6. Integration of all hospitals with DRG WEB API | SSA | I.Tabatadze | September 2019 | Dec 2019 | Phase 4 |  |  |  |  | New activity added |  | Not started
4.Improvement of data quality | 4.1.1 Prepare ICD-10 and NCSP to produce DRG definition tables by NCC | SSA/NCDC | M.Khomeriki/N.Tsetskhladze | Feb 2018 | March 2018 | Phase 1 |  | Completed | The final versions of ICD10 and NCSP files were sent to NCC 19th of March. |  |  |  | Completed
4.Improvement of data quality | 4.1.2 Translate and adjust DRG terminology into Georgian | NCDC/SSA | N. Tsetskhladze /M.Khomeriki | June 2018 | Sept 2018 | Phase 2 | [6 empty] | Completed
4.Improvement of data quality | 4.1.3 Develop standard procedure to revise and update ICD-10 and NCSP | SSA/NCDC | M.Khomeriki/M.Kereselidze | July 2018 | Dec 2019 | Phase 3 | Add one person from NCDC, add M.Kereselidze. 1st version ICD and NCSP have to be ready for producing 1st version of definition tables. |  |  |  | Postponed, getting back to the issue in 2019 |  | started
4.Improvement of data quality | 4.2.1. Prepare basic userfriendly guideline for ICD-10 and NCSP coding standards with basic overview about DRG grouping principles. Revise and improve the coding guidelines for ICD-10 and NCSP. | NCDC/SSA | M. Darakhvelidze/N. Tsetskhladze /M.Khomeriki | April 2019 | December 2019 | Phase 3 | DRG names translation into Georgian + some user guide for providers about DRG logic |  | The activity includes also a creation of a user guide for providers about DRG logic |  | First draft of the guidelines should be prepared in April 2019 |  | started
4.Improvement of data quality | 4.2.2 Conduct a training on ICD10 and NCSP for pilot hospitals during the pilot phase | NCDC/SSA | M. Darakhvelidze/N. Tsetskhladze /M.Khomeriki | June 2019 | July 2019 | Phase 2 - Phase 3 |  |  |  |  | New activity. To be added to the training plan. |  | Not started
4.Improvement of data quality | 4.3 Develop the external clinical coding audits | SSA/NCDC | M.Khomeriki/M.Kereselidze | July 2019 | Dec 2019 | Phase 4 | Might need postponing, changed to dec 2019 | [5 empty] | Not started
4.Improvement of data quality | 4.4 Revise and improve the SSA claims management process | SSA | M.Khomeriki/ I.Tabatadze | July 2019 | April 2020 | Phase 4 | Due dates will be decided afterwards when better understanding about coding guidelines etc |  | Due dates will be revised after the clinical coding audit system has been tested |  |  |  | Not started
5.Adaption of regulation needed for implementation of DRG system | 5.1 Analyze the legal framework to identify needed changes in legislation to implement the DRG system | MOH/SSA | T.Gabunia/ M.Darakhvelidze | June 2019 | June 2020 | Phase 3 | Will be done in parallel |  | In parallel with implementation of DRG system. However, approval by Director of SSA is needed for DRG piloting to involve providers in the first and second phase of the transition period. For actual implementation the dates should be revised. | Replace "Z.Sopromadze" "For actual implementation the dates should be revised." was added on the comments. "by Director of SSA" was added on the comments |  |  | Not started
5.Adaption of regulation needed for implementation of DRG system | 5.2 Prepare the legal documents needed for implementing the DRG system | MOH/SSA | T.Gabunia/ M.Darakhvelidze | August 2020 | Nov 2020 | Phase 4 |  |  |  | Replace "Z.Sopromadze" |  |  | Not started
6. DRG tariff setting methodology | 6.1.1 Develop cost weights and base rate estimation methodology for 2020 "shadow funding" and conduct simulation | MOH/SSA | l.Nikoladze/K.Goginashvili//M.Khomeriki | September 2019 | Dec 2019 | Phase 3 | Will be discussed next mission |  | I stage: the cost weights for 2018-2019, (when DRGs are not yet used for actual reimbursement) can be borrowed or developed based on GEO data. Discuss the topic once the GEO grouper is available. | Added to comments: Discuss the topic once the GEO grouper is available |  |  | Not started
6. DRG tariff setting methodology | 6.1.2 Develop cost weights and base rate estimation methodology for mid-2020 actual reimbursement "shadow funding" | MOH/SSA | l.Nikoladze/K.Goginashvili//M.Khomeriki | Jan 2020 | June 2020 | Phase 4 |  |  | II stage - cost weights for actual reimbursement. |  |  |  | Not started
6. DRG tariff setting methodology | 6.2 Analyze the vertical programs in the light of DRG implementation | MOH/SSA | l.Nikoladze/K.Goginashvili/M. Darakhvelidze /M.Khomeriki | September 2019 | Dec 2019 | Phase 4 | Will be discussed next mission |  | Vertical programs initial mapping could be done before next mission in May 2018 | Corrected: April 2018 -> March 2019 Sept 2018 -> May 2019 Phase 2 -> Phase 4 |  |  | Not started
7.Reimbursement policy | 7.1 Develop the DRG reimbursement policy and conduct simulations: a. Define exemptions (e.g. psychiatric care, rehab care, referred patients etc) and the payment method for financing them b. Define reimbursement rules for expensive drugs and devices, ICU, etc, and the payment method for financing them c. Define high-low cost/LOS outliers | MOH/SSA | T.Gabunia/M.Darakhvelidze/M.Khomeriki | September 2019 | June 2020 | Phase 3 | Vertical programs intial mapping could be done before next mission |  |  | Replace "Z.Sopromadze" |  |  | Not started
8.Monitoring and reporting system | 8.1.1 Group the data, analyze and provide feedback about grouping results to providers (testing and pilot period) | SSA | M.Khomeriki/ I.Tabatadze | June 2019 | Dec 2019 | Phase 3 | Key priority indictaors during the first phase, will be revised for the next phases |  | Key priority indicators will be developed during the first phase and will be revised for the next phases |  | Testing and pilot period merged |  | Not started
8.Monitoring and reporting system | 8.2 Implement performance indicators and principles for regular monitoring of providers and reporting by using DRGs | MOH/NCDC/SSA | M.Darakhvelidze/M.Kereselidze/M.Khomeriki/ | Jan 2020 | Dec 2020 | Phase 4 |  |  |  | Corrected: Develop -> Implement |  |  | Not started
9.Capacity building for all stakeholders | 9.1 Asses gaps in capacity and develop a training plan for capacity building among different stakeholders | SSA/NCDC | M.Khomeriki/ I.Tabatadze/M.Kereselidze | Feb 2018 | May 2018 | Phase 1 |  | Completed |  |  |  |  | Completed
9.Capacity building for all stakeholders | 9.2 Improve competence in DRG systems for all stakeholder organizations by offering training and educational opportunities according to need | SSA/NCDC | M.Khomeriki/ I.Tabatadze/M.Kereselidze | Feb 2018 | Dec 2020 | Phase 1 - Phase 4 | Activities according to the training plan | An overview about the timetable and main principles of the maintenance of NordDRG system (incl. the revision and update of the NCSP and the ICD10) was provided to DRG WG in Feb 2018. | Activities will be carried out according to the training plan throughout the transition period |  | Revision of deadlines and the content of training plan |  | Started
10.Communication | 10.1 Develop a DRG implementation communication plan | SSA | T.Gabunia/T.Bakradze | March 2018 | June 2018 | Phase 1 | Add additional names Revise and correct if needed the Start and End date according to the due dates in to the Communication plan | Work in progress |  | Replace "Z.Sopromadze" |  |  | Completed
10.Communication | 10.2 Implement the communication plan | SSA | T.Gabunia/T.Bakradze | July 2018 | Dec 2019 | Phase 2 - Phase 4 | Implementation start date depends on the developments with DRG grouper, probably should begin earlier |  | Implementation start date depends on the developments with DRG grouper, probably should begin earlier | Replace "Z.Sopromadze" | Revision of deadlines and content of communication plan |  | Started
Note on L12: lisasin selle ka siia - vt kas ok