## RFB
Request for Bids
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Prequalification (Y/N) | Procurement Process | Evaluation Options | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Draft Pre-qualification Documents |  | Specific Procurement Notice |  | Amendments to Pre-qualification Documents | Opening / Minutes of Pre-qualification |  | Pre-qualification Evaluation Report |  | Draft Bidding Documents |  | Specific Procurement Notice |  | Invitation to Providers |  | Amendments to Bidding Documents | Bid Submission / Opening / Minutes |  | Bid Evaluation Report and Recommendation for Award |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[15 empty] | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
COVID19/CW/RFB-01 / Repair works of public health facilities | No | IBRD-91130 | Emergency COVID-19 Response | Prior | Works | Open - National | N | Single Stage One Envelope |  | 2000000 |  |  | Pending Implementation | Cleared | [9 empty] | 2020/06/22 |  | 2020/06/27 |  |  |  |  | 2020/08/08 |  | 2020/09/07 |  | 2020/09/21 |  | 2020/10/12 |  |  | 2021/04/10

## RFQ
Request for Quotations
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Draft Request for Quotations |  | Specific Procurement Notice |  | Invitation to Supplier / Contractor |  | Amendments to Request for Quotations | Receive Quotations |  | Comparison of Quotations |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[12 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
COVID19/G/RFQ-01 / Procurement of fully equipped Ambulance car C type - Intensive Care Mobile Unit (30 Units) | No | IBRD-91130 | Emergency COVID-19 Response | Prior | Goods | Limited | 2500000 |  |  | Pending Implementation | Cleared | 2020/06/15 | [6 empty] | 2020/07/04 |  | 2020/07/11 |  | 2020/07/25 |  | 2020/08/15 |  |  | 2021/02/11
COVID19/G/RFQ-02 / Procurement of Equipment for Emergency Control Center | No | IBRD-91130 | Emergency COVID-19 Response | Prior | Goods | Open - National | 2800000 |  |  | Pending Implementation | Cleared | 2020/06/18 |  | 2020/06/23 |  | 2020/06/23 |  |  | 2020/07/07 |  | 2020/07/14 |  | 2020/07/28 |  | 2020/08/18 |  |  | 2021/02/14
COVID19/G/RFQ-07 / Procurement of ICT goods for public health facilities | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Open - National | 300000 |  |  | Pending Implementation | Cleared | 2020/06/15 |  | 2020/06/20 |  | 2020/06/20 |  |  | 2020/07/04 |  | 2020/07/11 |  | 2020/07/25 |  | 2020/08/15 |  |  | 2021/02/11
COVID19/G/RFQ-03 / Procurement of Motorcycle for ambulance first responders with helmets | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Limited | 1500000 |  |  | Pending Implementation | Cleared | 2020/06/15 | [6 empty] | 2020/07/04 |  | 2020/07/11 |  | 2020/07/25 |  | 2020/08/15 |  |  | 2021/02/11
COVID19/G/RFQ-04 / Procurement of motor vehicles for Infectious Control Monitoring Center | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Open - National | 300000 |  |  | Pending Implementation | Cleared | 2020/06/05 |  | 2020/06/10 |  | 2020/06/10 |  |  | 2020/06/24 |  | 2020/07/01 |  | 2020/07/15 |  | 2020/08/05 |  |  | 2021/02/01

## DIR
Direct Selection
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Procurement Category | Evaluation Options | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Justification for Direct Procurement |  | Invitation to Supplier / Contractor |  | Draft Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[12 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
COVID19/G/DC-06 / Procurement of Hospital Equipment for four dedicated COVID-19 clinics: Rukhi Hospital, Batumi Hospital, Lisi Hospital and Infectious Disease Hospital | No | IBRD-91130 | Emergency COVID-19 Response | Prior | Goods | Direct | 16950000 |  |  | Pending Implementation | Cleared | 2020/06/15 |  | 2020/06/20 |  | 2020/06/20 |  | 2020/07/04 |  | 2020/07/25 |  |  | 2021/01/21
COVID19/G/DC-07 / Procurement of Diagnostic Supplies | No | IBRD-91130 | Emergency COVID-19 Response | Prior | Goods | Direct | 5000000 |  |  | Pending Implementation | Cleared | 2020/06/15 |  | 2020/06/20 |  | 2020/06/20 |  | 2020/07/04 |  | 2020/07/25 |  |  | 2021/01/21
COVID19/G/DC-05 / Procurement of Personal Protective Equipment | No | IBRD-91130 | Emergency COVID-19 Response | Prior | Goods | Direct | 10000000 |  |  | Pending Implementation | Cleared | 2020/06/14 |  | 2020/06/19 |  | 2020/06/19 |  | 2020/07/03 |  | 2020/07/24 |  |  | 2021/01/20

## QBS
Quality Based Selection (QBS)
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Short List and Draft Request for Proposals |  | Request for Proposals as Issued |  | Amendments to Request for Proposals |  | Opening of Technical Proposals / Minutes |  | Evaluation of Technical Proposals |  | Combined Evaluation Report and Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[10 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
COVID19/CS/QBS-01 / Training and technical assistance to MoLSHA | No | IBRD-91130 | Emergency COVID-19 Response | Post | Consultant Services | Open - International | 300000 | Pending Implementation | Cleared | 2020/06/05 |  | 2020/06/26 |  | 2020/07/26 |  | 2020/08/09 |  |  |  | 2020/08/09 |  | 2020/09/06 |  | 2020/10/06 |  | 2020/11/05 |  | 2020/11/19 |  | 2020/12/10 |  |  | 2021/12/10

## INDV
Individual Consultant Selection
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Justification for Direct Selection |  | Invitation to Identified / Selected Consultant |  | Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[10 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
COVID19/CS/INDV-04 / Health Specialist | No | IBRD-91130 | Project Management | Post | Consultant Services | Open | 60000 | Pending Implementation | Cleared | 2020/05/25 |  | 2020/06/08 |  | 2020/07/08 |  |  |  | 2020/07/13 |  | 2020/08/03 |  | 2020/08/17 |  | 2020/09/07 |  |  | 2021/03/06
COVID19/CS/INDV-01 / Procurement Manager | No | IBRD-91130 | Project Management | Post | Consultant Services | Open | 72000 | Pending Implementation | Cleared | 2020/05/25 |  | 2020/06/08 |  | 2020/07/08 |  |  |  | 2020/07/13 |  | 2020/08/03 |  | 2020/08/17 |  | 2020/09/07 |  |  | 2021/03/06
COVID19/CS/INDV-06 / Environmental Standards Specialist | No | IBRD-91130 | Project Management | Post | Consultant Services | Open | 38400 | Pending Implementation | Cleared | 2020/05/25 |  | 2020/06/08 |  | 2020/07/08 |  |  |  | 2020/07/13 |  | 2020/08/03 |  | 2020/08/17 |  | 2020/09/07 |  |  | 2021/03/06
COVID19/CS/INDV-02 / Financial Manager | No | IBRD-91130 | Project Management | Post | Consultant Services | Open | 60000 | Pending Implementation | Cleared | 2020/05/25 |  | 2020/06/08 |  | 2020/07/08 |  |  |  | 2020/07/13 |  | 2020/08/03 |  | 2020/08/17 |  | 2020/09/07 |  |  | 2021/03/06
COVID19/CS/INDV-05 / Social Standards Specialist | No | IBRD-91130 | Project Management | Post | Consultant Services | Open | 38400 | Pending Implementation | Cleared | 2020/05/25 |  | 2020/06/08 |  | 2020/07/08 |  |  |  | 2020/07/13 |  | 2020/08/03 |  | 2020/08/17 |  | 2020/09/07 |  |  | 2021/03/06
COVID19/CS/INDV-03 / Procurement Specialist | No | IBRD-91130 | Project Management | Post | Consultant Services | Open | 52800 | Pending Implementation | Cleared | 2020/05/25 |  | 2020/06/08 |  | 2020/07/08 |  |  |  | 2020/07/13 |  | 2020/08/03 |  | 2020/08/17 |  | 2020/09/07 |  |  | 2021/03/06