[INITIAL DRAFT FOR COMMENTS
VERSION OF 29 APRIL 2020]

Memorandum of Understanding

between

Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia

and

European Bank for Reconstruction and Development

In respect of
Improving Nursing and Midwifery Occupations in Georgia 
through Professional Licencing, Related Skills Standards and Implementation Support

Dated [12 May 2020]

This Memorandum of Understanding (“the Memorandum”) is between:

- the Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia (“the Ministry”); and

- the European Bank for Reconstruction and Development (“EBRD”),

each referred to as a “Party” and together as “the Parties”.

WHEREAS

- EBRD is an international organization established under public international law pursuant to the Agreement Establishing the European Bank for Reconstruction and Development dated 29 May 1990.

- The Republic of Georgia acceded to the Agreement Establishing the European Bank for Reconstruction and Development and became a member of the EBRD on 4 September 1992.

- The Parties wish to collaborate together on strengthening the nursing and midwifery occupations in Georgia to boost training, skills and overall performance via three core initiatives:

  - Establishing core governance principles and standards for Georgia’s forthcoming professional licencing scheme for nurses (including midwives);

  - Defining related knowledge criteria, exam standards and a test-bank aligned to the new professional licencing curriculum; and

  - Creating and piloting a short-term continuous learning programme aligned to the new professional licencing requirements.

The Parties have come to the following understanding:

Section 1. Purpose

Insufficient education for nurses and midwives inhibits Georgia’s healthcare sector. Bachelor’s level programmes are not subject to clear teaching standards, giving rise to skills mismatches. Neither occupation is subject to professional licensing, which reduces accountability. An absence of local-language textbooks results in ad hoc learning outcomes. Demographic trends towards population ageing in Georgia place high demand on quality healthcare provision, making timely action a priority.

Nursing and midwifery occupations consequently underperform in Georgia, with many workers under-engaged and poorly remunerated despite their high demand. Georgia’s medical workforce, in turn, is distinguished by a significant shortage of nurses and midwives, achieving one of the lowest per-capita levels in EBRD’s geography and numbering only 0.7 nurses for every medical doctor (significantly below the 4:1 recommended by the World Bank to ensure cost-effective and quality care). Georgia equally encounters critical shortages among midwives.

Georgia’s Parliament has issued a Vision for Developing the Healthcare System in Georgia by 2030 (2017), highlighting a number of objectives and actions related to nurses and midwives’ education, training and overall performance (pp.11-13):

2.1.3.	[…] increase the number of nurses to achieve an adequate balance of medical staff.

2.2.	Support education for nurses, including the following:

2.2.1.	Subsidize/stimulate education for nurses from the side of the state.

2.2.2.	Due to the lack of nurses, support the system of re-training nurses at the transitional stage.

2.2.3.	Support the development of bachelor and master programmes in nursing […]

2.3.	Develop and implement tools for regulating nursing activities with active engagement of professional organizations in the field:

2.3.1.	Define competencies for nurses and develop the tools for assessing their professional knowledge and skills.

2.3.2.	Gradually introduce/implement the process of registration/certification for nurses.

2.3.3.	Ensure the functioning of a formalised system of continuing professional development for nurses and support the sustainability of the system.

The Vision includes a monitoring target to increase the ratio of nurses to medical doctors from its current 0.7:1 to at least 2:1 by 2030.

The Ministry issued a more targeted Strategy for the Development of Nursing in July 2019. The Strategy’s primary objective (Goal 1) on “Promoting the improvement of the quality and availability of healthcare services” targets full take-up of professional licencing among nurses by 2025 (Outcome Indicator 1.2.2) alongside a range of quantitative sub-objectives to achieve:

| Indicators |  | Baseline (and year) | Mid-term target by 2022 | Eventual target by 2025 |
| --- | --- | --- | --- | --- |
| Goal 1. Promoting the improvement of the quality and availability of healthcare services through generation of qualified human resources in nursing and creation of a sustainable professional regulation system |  |  |  |  |
| Impact Indicator 1.1. | In-patient mortality rate | 2.6% (2017) | 2.4% | 2.2% |
| Impact Indicator 1.2. | Ratio of nurses to medical doctors | 0.7:1 (2017) | 1:1 | 1.3:1 |
| Impact Indicator 1.3. | Patients’ satisfaction with nursing services | n/a | 40% of respondents | 65% of respondents |
| Objective 1.1. Developing a healthcare system focused on generating qualified human resources in nursing |  |  |  |  |
| 1.1.1. New nursing graduates per year |  | 916 (2018) | +15% | +30% |
| 1.1.2. Number of nurses per 100,000 people |  | 509 (2017) | 550 | 610 |
| Objective 1.2. Developing a sustainable system of continuous professional development and regulation |  |  |  |  |
| 1.2.1. Share of employed nurses participating in formal system of continuous professional development |  | 0% (2019) | 10%* | 50% |
| 1.2.2. Share of employed nurses who have gone through licencing / registration / certification processes |  | 0% (2019) | 10%* | 100% |
| Objective 1.3. Promotion and awareness-raising of nursing |  |  |  |  |
| 1.3.1. Students enrolled for nursing and midwifery |  | 958 (2018) | +15%* | +30% |
| 1.3.2. Awareness of the significance of nursing |  | n/a | 50% positive response* | 70% positive response |

Note: * Mid-term target to be met by 2023.
Source: Ministry of Health, Labour and Social Affairs (2019) Strategy for the Development of Nursing.

Adequately tackling Georgia’s labour shortages and skills-related deficits in nursing and midwifery will improve employment outcomes for young women and men while boosting healthcare standards nation-wide. This Memorandum establishes the scope and provisions for EBRD’s engagement with the Ministry’s towards fulfilling these imperative policy goals.

Section 2. Scope

EBRD’s technical support programmes promote young people’s access to employment and skills within a range of vocational areas aligned to its client enterprises’ needs. Within Georgia’s healthcare sector, EBRD recognises the clear and pressing needs for reforming nursing and midwifery education and licencing to boost entry-level numbers and improve professional standards. These goals align with EBRD’s mandate to promote transition towards inclusive market-led economies and, in particular, the embedded focus on improving economic opportunities and career pathways for young women and men.

In this spirit, the Parties agree to collaborate in fulfilling three joint objectives aligned with fulfilling Georgia’s national priorities for reforming the nursing and midwifery professions:

- Establishing core governance principles and institutional standards for the planned professional licencing scheme for nurses (including midwives) with learning gathered from other countries’ successful models and best practices around successful implementation and sustainably.

- Establishing detailed knowledge criteria, exam standards and a test-bank aligned to the new professional licencing curriculum alongside core principles for its governance and maintenance in line with international best practices, drawing closely on EBRD local partners’ experience and successful role in developing nursing and midwifery skills standards through the National Centre for Education Quality Enhancement.

- Creating and piloting a short-term continuous learning programme designed to refresh incumbent nurses’ knowledge and skills in fulfilment of the new licencing requirements.

In fulfilment of these three core objectives, EBRD commits to:

- Design, procure and manage the delivery of technical support in developing the necessary background knowledge, best-practice standards and capacity to realise the above-stated joint actions.

- Select and engage external experts (“Implementation Partners”) to fulfil the necessary deliverables in this work, working in close partnership and consensus with the Ministry.

- Finance such engagement through its technical cooperation funds generously provided, in this instance, through the Japan-EBRD Cooperation Fund.

- Ensure necessary coordination among various stakeholders including (but not limited to): private and public healthcare services providers; nurse and midwife training institutions (at both the vocational and Bachelor’s levels); relevant employers’ and workers’ organisations; and the National Centre for Education Quality Enhancement in securing holistic and sustainable outcomes under the joint objectives.

- Holistically integrate the fulfilment of these goals with EBRD’s existing and ongoing initiatives around promoting more effective and sustainable nursing in Georgia through: a) establishing skills standards for degree-level nursing and midwifery programmes; b) developing Georgian-language nursing textbooks; and c) improving outreach to male nurses.

In fulfilment of the three core objectives, the Ministry commits to:

- Engage closely with EBRD in the design and delivery of technical support in developing the necessary knowledge, standards and capacity to realise the joint objectives.

- Share relevant reporting, statistics and contacts with EBRD and the Implementation Partners relevant to the fulfilment of the joint objectives and the monitoring of their success including (but not limited to) performance on the formal targets established under the Vision for Developing the Healthcare System and the Strategy for the Development of Nursing.

- Select and maintain a dedicated contact person, reporting directly to the First Deputy Minister, to ensure regular and continuous engagement and exchange with EBRD and the Implementation Partners and participate in future meetings and events.

- Provide formal response on the core deliverables to emerge from the technical support, detailing the Ministry’s planned steps in utilising them.

- Support EBRD to ensure fulfilment of visibility requirements of our Japanese donors in this work.

The Parties recognise that fulfilment of these activities aligns closely with Georgia’s stated policy goals under the Vision for Developing the Healthcare System and Strategy for the Development of Nursing, namely: upgrading professional competency standards and necessary appraisal tools (Objective 2.3.1 in the Vision and Objectives 1.1 and 1.3 in the Strategy); implementing the new professional licencing scheme (2.3.2 and 1.2, respectively); and establishing a formal system of continuous learning (2.3.3 and 1.2, respectively).

Section 3. Communications

Any notice or other communication to be given or made under this Memorandum will be addressed and sent to the following contact points or at such other address as either Party designates by notice to the other Party:

For the Ministry:

144, Ak. Tsereteli Ave., Tbilisi 0119

Attention: Ms Tamar Gabunia

Fax: [fax number]

For the EBRD:

Tbilisi Resident Office, Merani Business Center, 31a Griboedov Street, 6th Floor, 0108 Tbilisi

Attention: Ms Catarina Bjorlin Hansen

Fax: [fax number]

Section 4. Final Provisions

- This Memorandum reflects the views and intentions of the Parties to co-operate on a non-exclusive basis, expressed in good faith but without the creation of any legal or financial obligations or the incurrence of any liability on the part of either of them. No third party shall obtain any legal benefit from this Memorandum.

- It is understood and agreed that nothing in this Memorandum will constitute, or be construed as, an offer, promise or undertaking by either Party to finance all or part of any activity or project identified in or pursuant to this Memorandum.

- In the event that opportunities are identified, specific arrangements for any such activity or project would need to be agreed upon between the Parties. Each of the Parties will incur its own expenditures arising as the result of the implementation of this Memorandum, unless otherwise specified in relevant separate agreements.

- Nothing in this Memorandum will limit the right of, or prevent either Party from entering into memoranda or arrangements with other parties with respect to any activity, project or area of co-operation covered by this Memorandum.

- The Parties will meet periodically, but not less frequently than once every three months, to review and discuss the implementation of this Memorandum, assess the achievement of the objectives as set out herein above, and consider necessary adjustments, if any.

- Nothing in this Memorandum will constitute nor be construed as a waiver, renunciation or other modification, either express or implied, of any of the privileges, immunities and exemptions granted to EBRD under the Agreement Establishing the European Bank for Reconstruction and Development, international convention or any applicable law.

- Any dispute arising out of, or in connection with, the interpretation or application of any provision of this Memorandum will be settled amicably through consultations.

- This Memorandum will come into effect on the date when the last of the two Parties sign and will remain in effect for [two years]. Either Party may terminate this Memorandum before the expiry date upon submitting to the other Party of a prior written notice of its intention to terminate this Memorandum. In such case, this Memorandum will terminate 28 days after receipt of such notice by the corresponding Party.

- This Memorandum may be amended by mutual written consent of the Parties.

IN WITNESS WHEREOF, the Ministry and EBRD, each acting through its duly authorized representative, have signed this Memorandum in [number of originals] originals, in the English language.

| For the Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia: | For the European Bank for Reconstruction and Development: |
| --- | --- |
| ___________________________ Name: [TBC, please advise from Ministry side] Title: […] Date: [12 May 2020] | ___________________________ Name: [TBC from EBRD side] Title: […] Date: [12 May 2020] |