## Slide 1
Technical Assistance to Social Welfare in Georgia
Update of the project
First year: 1 April 2019-31 March 2020
Second year: 1 April 2020-31 March 2021 (approved)

## Slide 2
IMPLEMENTED ACTIVITIES AND PROGRESS

## Slide 3: Pillar I – Enhance the social support to PWD
Situational analysis (done)
Development of methodology (done)
Contracting, questionnaires, staff, IT support (done)
Trainings and international practise (done)
Collection of data on-site and piloting (on-going. Impacted by Covid-19. Will be extended by 8 months)
Creation of data analysis tools (on-going)
Proposals for minimum support package, based on results of piloting (not started)
Policy impact assessment, based on results of piloting in S-J region and in Adjara region (started. Analysis of data of Adjara under evaluation.)
Drafting of the Action plan (not started)
Awareness raising (started with dissemination tools, to be continued)
Study visit (depends on the epidemiological situation)

## Slide 4: Pillar II – Ensure affordable and quality healthcare: effectiveness, efficiency of healthcare
Define standard operating procedures for the implementation of performance-based contracting, especially to primary health care (done).
Collection of necessary data, field visits (done).
Analysis of e-health sector (done).
Selective contracting in PHC (in progress, work plan adjusted with Ministry).
Study visit (depends on the epidemiological situation).

## Slide 5: Pillar II – Ensure affordable and quality healthcare: strengthening of the Mental health
Collection of necessary data, field visits, situational analysis (done).
The analysis of the implementation for the deinstitutionalization and the development of community-based services in line with recommendations of WHO report (done)
Recommendations for the legislation in the mental health (done. Fine-tuning)
Epidemiological survey for adults/validation (impacted by Covid-19. Restarted).
Epidemiological survey for children (financing approved. Methodology elaborated. Postponed to the end of 2020. Report in 2021).
Mental health strategy, monitoring tools, action plan (in progress. Work with the legislation).
Study visit (not decided).

## Slide 6
Policy, legislation, financing, International organisation reports analysis (done)
Collection of necessary data for reform modelling and actuarial analysis (done)
Meetings with government stakeholders and with international partners (done)
Preparation of TA report, including the reform sub-scenarios (done)
Gap and SWOT analysis of the reform sub-scenarios (done)
International comparison of IDPs social support (done)
Focus groups in three different regions (done)
Legislation analysis on the actual situation and reform scenarios (done)
Actuarial-forecast tools and simulations (done)
Memorandum of understanding with the Agency of IDPs and Eco-migrants (done)
The workshop (12-14 December 2019) (done)
Support for the communication of the reform (in progress, after decision on reform)
Drafting the recommendations and report (done)
Pillar III – Support to IDP allowance reform

## Slide 7
SECOND YEAR ACTIVITIES

## Slide 8
I PILLAR
modelling the disability data and analysis using different tools and approaches in both Adjara and Samtshe-Javakheti region
cooperation with Adjara pilot in the field of data analysis tools
elaboration of proposals based both in Adjara and Samtshe-Javakheti pilots databases
extension of the pilot for 8 additional months (25 January 2021).

## Slide 9
II PILLAR
epidemiological survey for children with recommendations
adjustment of the TA proposed Mental health strategy according to the results of the epidemiological survey for children
continuation of activities in the selective contracting
e-health approaches

## Slide 10
III PILLAR
further improvement of actuarial-forecast tools of the IDPs database and relevant trainings;
modelling and actuarial analysis and forecasts for the new housing system for IDPs;
communication of the reform

## Slide 11
IV (New) PILLAR
Work plan discussed with Ministry.
Team of experts selected (France, Lithuania, Finland).
Presentations (via zoom) for Ministry performed.
3 core objects, related to the activation of the employment: emergency basic income guarantees, short-term work guarantees, employment activation tools.
The first draft report will be prepared by the end of September.
A mission planned in the beginning of October.

## Slide 12
Visibility events
Internal workshop on 6th October.
Bigger visibility event-in November (tbc).