## 3Q2018_report
| Goals | Initiatives | Q3 18 | Q4 18 | Q1 19 | Q2 19 | Q3 19 | Q4 19 | Q1 20 | Q2 20 | Q3 20 | Q4 20 | Date | Owner | Comments: Nov 13 | Comments: January 2019
1 | Improve payment and contracting mechanisms | Developing and introducing DRG system | Contact the organization delivering the grouper software and license | DRG grouper integrated to the SSA system; DRG terminology in Georgian; feedback to providers; Adaption of regulation needed for implementation of DRG system; Preparation for DRG cost weights and reimbursement principles |  | DRG cost weights and reimbursement principles for the "virtual implementation" | Simualtions and analytics to develop DRG cost weights and reimbursement rules | DRG cost weigts and reimbursement policy for 2020; overall preparedness for DRG implementation |  |  |  |  | 3.2020 | SSA/MoLHSA | Status by end of 3Q2018 no DRG licence yet, government needs to approve (after elections, Dec 2018) Recommendations to change activities and/or due dates no need to revise | Status by end of 4Q2018
|  | Critical assessment of basic financing PHC (considering the need for integration of rural and UHC, state vertical programs) including RBF principles | Assessment of current financing mechanisms of PHC considering possibility of integration of rural and UHC |  | Revision/redisign of financial mechanisms of PHC including RBF indicators; Piloting RBF using redesigned financing of PHC |  |  |  | Final revision/preparation for redesigned PHC financing |  |  |  | 3.2020 | MoLHSA/SSA | Status by end of 3Q2018 activity has been started: pilot project in 10 municipalities, pilot starts 2018 (duration 6-12 month) Recommendations to change activities and/or due dates needs revision: 2019 milestones with clear deliverables for the pilot need to be added; final due date 1Q2020 stays same | Status by end of 4Q2018
|  | Developing principles of contracting for purchasing services, including selective contracting and monitoring and evaluation system of contracts performance |  | Assessment of current contracting arrangements, including selective contracting practice of MCH care. analysing the current distribution of Highly specialised hospital services; Analyzing proper epidemiological data for selective contracting services, existing services allocation comparing to international experience | Design of the concept for new contracting service system; Elaborate highly specialised hospital services allocation according to data analysis | Design of Major Diagnostic Categories and case based planning system | Analyses of provider performance, forecast of MDC and case based planning, drafting SOP, SSA internal capacity building | Piloting volume based contracting, without financial obligations | Develop monitoring procedures and SOP |  | Develop legal regulation. Linking with payment mechanisms. | Final preparation for going live. | 12.2020 | MoLHSA/SSA | activities not started | Status by end of 4Q2018
|  | Needs assessment in health care services | Assessment of what kind of services are priorities for needs assesement (ex. onco surgery, critical care, NICU..) | Analyze epidemiological data, service utilization, existing resources, international experience |  |  | elaborate the requirements for each directions based on statistical data taking into consideration the geografical accsessibility and utilization | [5 empty] | 6.2020 | MoLHSA/SSA | Status by end of 3Q2018 cardiosurgery and ICU have been analysed, ICU is not completed as document. Other areas discussed: neurosurgery, cancer care. Recommendations to change activities and/or due dates 2019 activity plan needs revision to establish clear deliverables and milestones by quarters | Status by end of 4Q2018
2 | HBP in line with population health needs | Designing the system and process of HBP revision and renewal | elaborate of the methodology for assesment of health needs and HBP design | analyze the health service utilization of existing HBP and detect weak an strong sides |  | assesment of health (among them essential) needs, service alocation and finansial resoirses |  | Redesighn HBP |  |  |  |  | 3.2020 | MoLHSA | Status by end of 3Q2018 no classic methodology to assess needs for HBP revision, epi data is indirect measure for need assessment Recommendations to change activities and/or due dates review 2019 activity plan and revise deliverables and milestones if needed | Status by end of 4Q2018
3 | Consolidate highly specialised and hospital care | Analysing the need for hospital care services including highly specialised services and current distribution of service providers and Developing a plan for sustainable purchasing of hospital and highly specialised medical services. |  |  | Analysing the need for hospital care services including highly specialised services and current distribution of service providers |  | Developing a plan for sustainable purchasing of hospital and highly specialised medical services. |  | implementation of the plan |  |  |  | 3.2020 | MoLHSA/SSA | activities not started | Status by end of 4Q2018
4 | Ensure equitable access to essential specialist care and strengthen PHC | Revision of referral system and developing GP functions. | Elaboration of PHC strategy; Elaborate requirements (technical , specialisation …) for service providers taking into consideration mapping results; elaborate the data-collecting system to receive the data from PHC centers about pacients with ambulatory care-sensitive conditions, their outpatient visits and referrals |  |  | Analyze received data, hospitalization rate with ambulatory care sensitive conditions according to PHC centers |  |  | revise/redign the referral system |  |  |  | 3.2020 | MoLHSA/SSA | Status by end of 3Q2018 Concept written paper available, consultations with PHC providers and SSA have been conducted. Document is agreed but not formalised but will be used as an input for the pilot. starting in January 2019. Recommendations to change activities and/or due dates 2019 activity plan needs revision to establish clear deliverables and milestones by quarters | Status by end of 4Q2018
|  | Strengthening the capacity of GP ( certification, recertification and continious medical education) |  | Elaborate the training and qualifications system of GP taking into consideration the data received by analysis of work of PHC centers with patients ambulatory care-sensitive conditions |  | Consider draft of training sistem with primary health care professionals and international partners and analyze their remarks and comments; Elaboration of GP qualification monitoring syste |  |  | revise/finalise the wonk on training and re-qualification system of GP. |  |  |  | 3.2020 | MoLHSA/SSA | activities not started | Status by end of 4Q2018
5 | Improvement efficiency and quality of health services | Developing the concept to upgrade quality assurance and improvement system | Analysis of current situation |  | Elaboration of quality improvement strategy and instruments |  |  | start of implementation of quality strategy |  |  |  |  | 3.2020 | MoLHSA | Status by end of 3Q2018 Current system is analysed, internal document available (ministry level), will be used as a basis for the new quality assurance system. Concept paper (when finalised) will be used as input for new structure and for training. Recommendations to change activities and/or due dates Concept paper ready by end of 2018 and based on that 2019 quarterly milestones will be added | Status by end of 4Q2018
|  | Defining set of indicators to assess the quality of medical services, mechanism to monitor and control quality, and coordinate the quality functions with Regulatory Authority |  |  | Define the set of quality indicators |  | Elaborate the mechanism to monitor and control quality | start of implementation of set of indicator ssystem |  |  |  |  | 3.2020 | MoLHSA/SSA | activities not started | Status by end of 4Q2018
|  | Develop concept of medical audits (in cooperation with Regulatory Authority). |  |  | Identify the standards and audit criteria |  | selecting and developing appropriate performance levels; identify inclusion/exclusion criteria abd exceptions |  | Elaborate measuring performance methodology: data collection, data analysis, drawing conclusions, presentation of results; Identify principal steps of quality improvement plans and sustaining improvements according the elaborated mechanism to monitor and control quality |  | Final revision of concept of medical audits, analysing feedback from professionals and international partners |  | 12.2020 | MoLHSA/SSA | activities not started | Status by end of 4Q2018
|  | Develop principles and functions of health economics within SSA, the structural alignment of functions. | Analysis of current structural alignment of functions of SSA |  | Revision/redign of structural alignment of functions according to principles and functions of health economics within SSA | [7 empty] | 6.2019 | SSA | Status by end of 3Q2018 SSA has been discussing the needs but not finalised yet. Plan is to finalise by end of 2018 (statement by end of 2018 about new structure and traning needs) Recommendations to change activities and/or due dates no need to make changes | Status by end of 4Q2018
6 | Enhance electronic data exchange and improve quality of data | Mapping of key processes related with health service provision and SP and defining the needs for developing solutions for electronis exchange of data with stakeholders. | Defining SP key areas in need of IT development, new tech applications and solutions. |  | System analyses and TOR for SP and IT development |  | Final preparation for going live. | [5 empty] | 12.2019 | SSA | Status by end of 3Q2018 Will be available by end 2018. 5 additional people approved for IT development (SSA) by GOV. Recommendations to change activities and/or due dates no need to make changes | Status by end of 4Q2018
|  | Introduce the use of electronic signature. | Implement the relevant software with legislative changes on electronic signature |  | estimate the software characteristics | Final preparation for going live. | [6 empty] | 6.2019 | SSA | Status by end of 3Q2018 Implemented and used in internal communication between SSA and Ministry (90% of overall gov documetation is done by usin electronic signature). In claims management its also possible but not mandatory now but enforcement starts Jan 2019. EMR will be implemented in big cities. From May 2019 all providers will be included Sept 2019 PHC providers (under UHC program). By end of 2019 all claims will be electrionically signed. Recommendations to change activities and/or due dates 2019 activity plan needs revision to establish clear deliverables and milestones by quarters | Status by end of 4Q2018
|  | Mapping of claims management process and design of electronic claims management solution. | Mapping of claims manage ment process AS-IS | Designing SHOULD BE SOP (incl TOR for tech application...) |  | SSA wide training to introduce new practice |  | New claims management process introduced |  |  |  |  | 12.2019 | SSA | Status by end of 3Q2018 AS-IS is described in draft format, needs some revision based on feedback recieved by WHO consultants. DRG implementation triggers also changes in claims management and shoul dbe taken into account. Recommendations to change activities and/or due dates no need to make changes | Status by end of 4Q2018
7 | Improve population awareness | Development of Citizen Portal and applications to increase transparency for patients. | Ensure to provide precise information for beneficiaries about covered services by State and other (municipal and etc.) programs |  | Elaborate the questionary for visitors of web site |  | Analyze the feedback for improvement of site data/information/characteristics/appearance | Final work on Citizen Portal and applications to present a transparent clear information/data for beneficiaries |  |  |  |  | 12.2019 | SSA | Status by end of 3Q2018 Accomplised. Plan is to develop social and employmnet related services as bigger demand for that. 800 users by so far. Recommendations to change activities and/or due dates Revised activites that would supprot to achieve bigger take up of the system | Status by end of 4Q2018
|  | Develop concept of citizen communication and communication plan for 2019. | elaboration of communication plan; elaboration of key messages | Finaising communication plan | [8 empty] | 12.2018 | MoLHSA | Status by end of 3Q2018 Not started yet; some new directions and therefore communication plan needs to take these into account. Elections may change directions. Recommendations to change activities and/or due dates Revise due date to 1Q2019 (due to upcoming elections more time is needed to understand if there are changes in priorities) | Status by end of 4Q2018
8 | Increase transparency and accountability | Development and introducing of quarterly reporting on SP performance | Designing Q/A reporting system, defining data needs |  | Piloting reporting based on Q 3 & 4 | [7 empty] | 3.2019 | SSA | Status by end of 3Q2018 Quater 3 reporting is done, template is revised based on the experiences by end of 2018. Recommendations to change activities and/or due dates no need to revise | Status by end of 4Q2018
Initiative under develepoment with milestone definition
Initiiative due date with final approval
fulfilled
Partially fulfilled
Not fulfilled
Started work
Note on Q1: Please report about status of each activity by describing key achievements and challenges