## Tbilisi Service Centers (hidden)
Tbilisi Service Center
Vake Saburtalo Service Center
Isani Samgori Service Center
Gldani Nadzaladevi Service Center
Dzveli Tbilisi Service Center
Didube Chugureti Service Center
Head of Tbilisi Service Center

## Regional& Distric Centers (hidden)
Regional Coordination Centers of the Agency
Kakheti
აბაშა
ვლადიმერ ქორჩილავა
Racha Lechkhumi Kvemo Svaneti
Guria
ონი
ზაზა ისაკაძე მ/შ
ლანჩხუთი
ეკატერინე წილოსანი მ/შ
Zestafoni
Imereti
Kharagauli
Tkibuli
Shida Kartli
ხაშური
გოჩა ბარბაქაძე
Chiatura
ცაგერი ჯონი ხალიანი
ახალქალაქი ირადიონ გოგოლაძე მ/შ
Samtskhe Javakheti
ახმეტა
თამარ ონიაშვილი
Samegrelo Zemo Svaneti
თიანეთი
ირმა იარაჯული
Mtskheta Mtianeti
თერჯოლა ალექსანდრე ზანკალიანი
ბაღდათი
ემილიანე ლომიძე
ვანი დავით ხარძეიშვილი
სამტრედია
ბესიკ მიქაძე მ/შ
ხონი ლევან ქუთათელაძე მ/შ
წყალტუბო
მარიამ ნადარეიშვილი მ/შ
საჩხერე
დავით გელბახიანი მ/შ
ლენტეხი
ლალი ბენდელიანი
ჩოხატაური
ზურაბ კალანდაძე
წალენჯიხა
ინგა სარია მ/შ
ჩხოროწყუ
პაატა სორდია
მესტია
ნატო რატიანი
ფოთი
ინგა ღვინჯილია
ყვარელი
ვალერიან ბურდიაშვილი მ/შ
გურჯაანი
თეიმურაზ ზავრაშვილი
სიღნაღი
ზურაბ ზურაბაშვილი
ლაგოდეხი
თამაზ კაკიაშვილი
საგარეჯო
თამარ ბერიძე
დედოფლისწყარო
თეა ბენაშვილი მ/შ
ასპინძა ირაკლი ჯვარიძე მ/შ
ადიგენი
პეტრე აფრიამაშვილი
ბორჯომი მანანა ჩხეიძე
ნინოწმინდა
ჯემალ ხმალაძე
დუშეთი შორენა ადეიშვილი
ახალგორი
მარინე ღამბაშიძე
ყაზბეგი
დოდო გელაშვილი მ/შ
ქარელი
უჩა ელბაქიძე
კასპი
მარინე მეტრეველი
თიღვის თემი
ქურთის თემი
ნელი ქრისტესიაშვილი
Kvemo Kartli
Adjara
ხობი
ბადრი ჭითაშვილი
სენაკი
ირმა მურღულია- მზარელუა
მარტვილი
თემურ კაკულია მ/შ
დმანისი
დავით დაუთაშვილი
თეთრიწყარო
ნანი დალაქიშვილი-ჯორჯიაშვილი მ/შ
წალკა
რომან სუბელიანი
ბოლნისი
ციცინო ჯოხაძე მ/შ
გარდაბანი
ლეილა ზურაბიანი
მარნეული
მამუკა შუბითიძე მ/შ
ბათუმი
ნოდარ ფუტკარაძე
ქობულეთი
თეიმურაზ ჭანტურიშვილი მ/შ
ქედა
ზურაბ ყადიძე მ/შ
შუახევი
პაატა ქათამაძე მ/შ
ხულო ნინო ქონიაძე
ხელვაჩაური
ნანი კახაძე
აფხაზეთის ა/რ ფილიალი
ომარ ნარსავიძე

## Management
Activities | Deputy Director of SSA | Head of Department | Assistant | Deputy Director of SSA | Head of Department | Assistant | Total FTE
Management support | 0 | 0 | 1 | 0 | 0 | 3 | 3
General management | 1 | 1 | 0 | 1 | 2 | 0 | 3
| 1 | 1 | 1 |  |  |  | 0
FTE | 1 | 2 | 3 |  |  |  | 6

## Contracting_unit
Feasibility
Activities | Head of Unit | Deputy Head of Unit | Team Leader | Senior Specialist | Specialist | Head of Unit | Deputy Head of Unit | Team Leader | Senior Specialist | Specialist | Total FTE | Timeline | Number of staff currently fullfilling this responsibility | Financial | Legal | Current Functions
Elaborate contracting principles, process and format (general part and special part for concrete components/services) | 0.1 | 0.1 | 0.05 | 0.05 | 0.05 | 0.1 | 0.1 | 0.15 | 0.35 | 0.35 | 1.05 |  | 0 |  | Introducing these functioins will require amendments in the SSA staff function Regulatory act
Contracting (including selection) according to the approved principles of contracting for purchasing services, including selective contracting | 0.1 | 0.2 | 0.25 | 0.25 | 0.25 | 0.1 | 0.2 | 0.75 | 1.75 | 1.75 | 4.55 |  | 15 |  |  | Currently the same functions are assigned to the Unit of Technical Support of the Universal Healthcare Program and Unit of Healthcare Programs
Monitoring of contract execution (volume, money, agreed service standards) | 0.05 | 0.1 | 0.25 | 0.15 | 0.15 | 0.05 | 0.1 | 0.75 | 1.05 | 1.05 | 3 |  | 0
Develop Q & P measurement indicators | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.15 | 0.35 | 0.35 | 0.95 |  | 0
Monitor developed Q & P measurement indicators and provide feedback to providers | 0 | 0.1 | 0.15 | 0.1 | 0.1 | 0 | 0.1 | 0.45 | 0.7 | 0.7 | 1.95 |  | 0
Planning contracts, including need assessment and analysis of health care services utilisation | 0.05 | 0.05 | 0.1 | 0.35 | 0.35 | 0.05 | 0.05 | 0.3 | 2.45 | 2.45 | 5.3 |  | 0
Provider relations | 0.15 | 0.15 | 0.15 | 0.05 | 0.05 | 0.15 | 0.15 | 0.45 | 0.35 | 0.35 | 1.45 |  | 0
General management | 0.5 | 0.25 | 0 | 0 | 0 | 0.5 | 0.25 | 0 | 0 | 0 | 0.75 |  | 0
| 1 | 1 | 1 | 1 | 1
FTE | 1 | 1 | 3 | 7 | 7 | [5 empty] | 19 |  | 15

## Claims_management
Feasibility
Activities | Head of Unit | Cheif Specialist | Head of Unit | Cheif Specialist | Total FTE | Timeline | HR: Number of staff currently fulfilling this responsibility | Financial | Legal | Current Function
Development of claims management procedures (including providing input to develop claims management IT system) | 0.1 | 0.05 | 0.1 | 0.2 | 0.3 |  |  |  | Amendments in the SSA staff function Regulatory act | the same functions in the Unit of Healthcare Programs, Unit of Management of Fulfilled Work, Unit of Organization Support of the Universal Healthcare Program
Support and training to BOs (including consulting BOs with complicated cases how to finance) | 0.2 | 0.5 | 0.2 | 2 | 2.2
Monitoring claims management at BO level (incl planning BO level workload) | 0.2 | 0.45 | 0.2 | 1.8 | 2
General Management | 0.5 | 0 | 0.5 | 0 | 0.5
| 1 | 1
FTE | 1 | 4 |  |  | 5 |  | 6
Note:
192 of staff os repsonsible for these functions in branch offices, In addition there are 17 service centers
The staffing level within the new structure is estimated at 167

## Monitoring
Feasibility
Activities | Head of Unit | Cheif Specialist | Head of Unit | Cheif Specialist | Total FTE | Timeline | HR: Number of staff currently fulfilling this responsibility | Financial | Legal | Current Function
Development the on site monitoring methodology and procedures | 0.1 | 0.05 | 0.1 | 0.15 | 0.25 |  |  |  | Amendments in the SSA staff function Regulatory act | the same function in the Unit of Monitoring of Universal Healthcare Program
Support and training to BO (incl consulting complex cases) | 0.2 | 0.5 | 0.2 | 1.5 | 1.7
Monitoring of BO level on site monitoring (incl planning BO level workload) | 0.2 | 0.45 | 0.2 | 1.35 | 1.55
General management | 0.5 | 0 | 0.5 | 0 | 0.5
| 1 | 1
FTE | 1 | 3 |  |  | 4 |  | 4
76 of staff os repsonsible for these functions in branch offices
The staffing level within the new structure is estimated at 65

## Pharma
Feasibility
Activities | Head of Unit | Senior Specialist | Specialist | Logistic | Head of Unit | Senior Specialist | Specialist | Logistic | Total FTE | Timeline | HR: Number of staff currently fulfilling this responsibility | Financial | Legal | Current Function
Preparing proposals for amending the regulation of pharmaceuticals reimbursement | 0.2 | 0.1 | 0 | 0 | 0.2 | 0.5 | 0 | 0 | 0.7 |  |  |  | Amendments in the SSA staff function Regulatory act | The same functions of the Unit of Provision of Population with the Specific Medicines and Unit of Management of Program Hepatitis C
Monitoring and analysis of medicines utilization according to the existing HBP and financial resources | 0.1 | 0.2 | 0.25 | 0 | 0.1 | 1 | 2.5 | 0 | 3.6
Preparing input for the procurement process of medicines | 0.05 | 0.2 | 0.25 | 0 | 0.05 | 1 | 2.5 | 0 | 3.55
Coordination and supervision of logistics of procured pharmaceuticals | 0.05 | 0.2 | 0.15 | 0 | 0.05 | 1 | 1.5 | 0 | 2.55
Hep C logistics | 0.1 | 0.1 | 0.1 | 1 | 0.1 | 0.5 | 1 | 15 | 16.6
Develop prices and copayment rules of pharmaceuticals covered by HBP | 0.1 | 0.2 | 0.25 | 0 | 0.1 | 1 | 2.5 | 0 | 3.6 |  | 0 |  |  | not currently available-should be introduced
General management | 0.4 | 0 | 0 | 0 | 0.4 | 0 | 0 | 0 | 0.4
| 1 | 1 | 1 | 1
FTE | 1 | 5 | 10 | 15 |  |  |  |  | 31 |  | 25

## Pricing_payment
Feasibility
Activities | Head of Unit | Senior Specialist | Specialist | Head of Unit | Senior Specialist | Specialist | Total FTE | Timeline | HR: Number of staff currently fulfilling this responsibility | Financial | Legal | Current Function
Prepare proposal to amend pricing, payment methods and HBP related regulation | 0.2 | 0.1 | 0.1 | 0.2 | 0.3 | 0.4 | 0.9 |  |  |  | Amendments in the SSA staff funqction Regulatory act | New functions
Pricing health services (DRG covered and uncovered services), incl cost analyis and budget impact | 0.1 | 0.4 | 0.4 | 0.1 | 1.2 | 1.6 | 2.9
Develop payment methods for health services (DRG covered and uncovered services), incl DRG logic | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0.4 | 0.8
Anaysis and assessment of HBP (services, copayment rules), incl health technology assessment | 0.1 | 0.4 | 0.4 | 0.1 | 1.2 | 1.6 | 2.9
General management | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0.5
| 1 | 1 | 1
FTE | 1 | 3 | 4 |  |  |  | 8 |  | 0
It's necessary to add DRG working group functions in this functional unit
HR - 5

## Evaluation_planning
Feasibility
Activities | Head of Unit | Senior Specialist | Head of Unit | Senior Specialist | Total FTE | Timeline | HR: Number of staff currently fulfilling this responsibility | Financial | Legal | Current Function
Developing methodology and procedures for strategic planning, monitoring and reporting | 0.1 | 0.1 | 0.1 | 0.2 | 0.3 |  |  |  | Amendments in the SSA staff function Regulatory act | New functions
Coordination of SP startegy renewal | 0.2 | 0.2 | 0.2 | 0.4 | 0.6
SSA strategic purchasing monthly/quarterly/annual reporting | 0.3 | 0.7 | 0.3 | 1.4 | 1.7
General management | 0.4 | 0 | 0.4 | 0 | 0.4
| 1 | 1
FTE | 1 | 2 |  |  | 3 |  | 0
M&E Officer is responsible for the preparation of the TOR to secure external consultant who will be supporting – Developing methodology and procedures for planning, monitoring and reporting, also needs assessment and analysis of health care services and other arised issues.
Prepare the guidelines and share with the CEO for approval
Organise a workshop and share with staff the guidelines

## Beneficiaries _relations
Feasibility
Activities | Head of Unit | Senior Specialist | Head of Unit | Senior Specialist | Total FTE | Timeline | Number of staff currently fullfilling this responsibility | Financial | Legal | Current Functions
Ensure to provide precise information for beneficiaries about covered services by State and other (municipal and etc.) programs | 0.05 | 0.2 | 0.05 | 0.6 | 0.65 |  | 0 |  | Introducing these functioins will require amendments in the SSA staff function Regulatory act
Elaborate/update the questionnaire for beneficiaries (e.g. Satisfaction with the use of Citizen Portal) | 0.1 | 0.15 | 0.1 | 0.45 | 0.55 |  | 15 |  |  | Currently the same functions are assigned to the Unit of Technical Support of the Universal Healthcare Program and Unit of Healthcare Programs
Support and training to BOs | 0.05 | 0.2 | 0.05 | 0.6 | 0.65
Elaborate/update the key messages | 0.15 | 0.1 | 0.15 | 0.3 | 0.45 |  | 0
Analyze the feedback for improvement of site data/information/characteristics/appearance | 0.15 | 0.35 | 0.15 | 1.05 | 1.2 |  | 0
General management | 0.5 |  | 0.5 | 0 | 0.5
| 1 | 1
FTE | 1 | 3 |  |  | 4 |  | 15

## SSA_CURRENTstructure
Structural unit | Key functions of the structural unit | Position | Number of full time equivalent staff (headquarter) | Number of full time equivalent staff (regional offices)
Department of Healthcare Programs
|  | Head of Department of Healthcare Programs | 1 | 49 employees
Unit of Provision of Population with the Specific Medicines |  | Deputy Head of Healthcare Programs | 1
head of unit of Provision of Population with the Specific Medicines
| *supervision of utilization of specific medicines | Chief specialist | 1
| * informing SSA management about utilization of medicines | Senior specialist | 2
| *prepare recommendations and proposals for revision of program | expert-consultant | 2
| *informing and consulting providers and beneficiaries about program specifics | employed by contract | 2
Unit of Healthcare Programs |  | Head of unit of healthcare programs
| * Administration of the claims in scope of State Health Programs | Chief specialist | 4
| * Decision making on financing of the medical cases | Senior specialist | 14
| * Decision making on financing of program cases according to monitoring results | employed by contract | 1
| * On site visit of authorized person and check transferred information by providers | specialist | 1
*with collaboration of IT department clarification of business logics in connection with State Healthcare Program service financing
*prepare recommendations and proposals for revision of program
Unit of Management of Program Hepatitis C |  | Head of Unit of Management of Program Hepatitis C
| *coordination and supervision of registration and inclusion process of beneficiaries in the program | chief specialist | 2
| *supervision of ensuring by specific medicines for hepatitis C of beneficiaries | employed by contract | 16
*regulation of referral system of beneficiaries
*coordination of distribution of medicines among providers
*preparing guarantee letters
*preparing concrete finance documents
Department of Administration of Universal Healthcare
|  | Head of Department Administration of Universal Healthcare | 1
|  | Deputy Head of Department of Administration of Universal Healthcare | 1
Unit of Monitoring of Universal Healthcare Program | * On site visit of authorized person and check transferred information by providers | head of Unit of Monitoring of Universal Healthcare Program | 1
|  | Chief specialist or employed by contract | 21 | 54
* verification of documents of program cases with transferred information by providers
* Decision making on financing of program cases according to monitoring results
Unit of Management of Primary Documentation | * Entering the information in the service center according to the medical recordings/document presented by the beneficiary | head of Unit of Management of Primary Documentation | 1
|  | persons employed by contract | 13 | 8
* Issuing/printing Guarantee Letter and Receipt in the service center
* consulting the beneficiaries
* Decision making on financing of delivery /c/section and preparing guarantee letters
Unit of Management of Fulfilled Work |  | head of Unit of Management of Fulfilled Work | 1
| * Administration of the claims in scope of UHC | Chief specialist or employed by contract | 46 | 35
* Decision making on financing of the medical cases
* Prepare appropriate documentation for the transfer of funds to providers according to made decision on financing the medical cases
*prepare recommendations and proposals for revision of program
Unit of Organization Support of the Universal Healthcare Program | * Decision making on financing of the elective surgery and preparing guarantee letters | head of Unit of Organization Support of the Universal Healthcare Program | 1
|  | Chief specialist or employed by contract | 23 | 23
* Decision making on financing of the chemotherapy, radio therapy and preparing guarantee letters
*supervision of the state tariffs on planned services
*prepare recommendations and proposals for revision of program
Unit of Technical Support of the Universal Healthcare Program | *registration of the service providers | Head of Unit of Technical Support of the Universal Healthcare Program | 1
|  | employed by contract | 7
*with collaboration of IT department clarification of business logics in connection with Universal Healthcare Program service financing
*prepare of statistical reports
* technical support of providers and other units of department on various stages of program administration

## TransitionPlan
Goals | Initiatives | Q1 19 | Q2 19 | Q3 19 | Q4 19 | Q1 20 | Q2 20 | Q3 20 | Q4 20 | Q1 21 | Q2 21 | Q3 21 | Q4 21 | Owner | Cooperation
3.3. Improvement efficiency and quality of health services | 3.3.1. Developing the concept to upgrade quality assurance and improvement system | ToR for the consultant to support development of quality improvement startegy and instruments prepared | Situation analysis and advocacy among stakeholders (state agencies, providers, clinicians) regarding quality improvement needs done | Elaboration of quality improvement strategy and instruments |  | Quality improvement strategy and instruments ready for implementation | [7 empty] | Head of Health Care Department MOH | Head of Department of UHC SSA, Head of Department of Health Programs SSA, State Regulatory Agency of Medical Activities
| 3.3.2. Defining set of indicators to assess the quality of medical services, mechanism to monitor and control quality, and coordinate the quality functions with Regulatory Authority |  | Elaboration concept of quality control for medical services | Establishment of structural unit and human resources | Elaborate indicators and mechanism to monitor and control quality | Pilot elaborated indicators and monitoring tools |  | Pilot elaborated indicators and monitoring tools |  | Start implementation set of indicator system |  |  |  | Head of Health Care Department MOH | Head of Department of UHC SSA, Head of Department of Health Programs SSA, State Regulatory Agency of Medical Activities
| 3.3.3. Develop concept of medical audits (in cooperation with Regulatory Authority) |  |  |  |  | Identify the standards and audit criteria |  | Selecting and developing appropriate performance levels; identify inclusion/exclusion criteria and exceptions |  | Elaborate measuring performance methodology: data collection, data analysis, drawing conclusions, presentation of results; Identify principal steps of quality improvement plans and sustaining improvements according the elaborated mechanism to monitor and control quality |  |  | Final revision of concept of medical audits, analysing feedback from professionals and international partners | Head of Health Care Department MOH | Head of Department of UHC SSA, Head of Department of Health Programs SSA, State Regulatory Agency of Medical Activities
3.4. Improve payment and contracting mechanisms | 3.4.1. Developing and introducing DRG system | DRG grouper integrated to the SSA system | Preparations for the pilot in piloting hospitals. Analytical work to prepare for the development of DRG pricing and reimbursement policy | DRG pilot in piloting hospitals. DRG cost weights and reimbursement principles for the "virtual implementation" | Simulations and analytics to develop DRG cost weights and reimbursement rules for 2020 "virtual implementation" period | DRG "virtual implementation" in all hospitals |  | DRG cost weights and reimbursement policy for 2020; overall preparedness for DRG implementation, |  | DRG implementation as reimbursement system |  |  |  | Head of Department of UHC SSA | Head of Department of IT SSA; Head of Health Care Department MOH; Head of Department of Health Programs SSA
| 3.4.2. Critical assessment of basic financing PHC (considering the need for integration of rural and UHC, state vertical programs) including RBF principles |  | Revision/redesign of financial mechanisms of PHC including RBF indicators | Piloting RBF using redesigned financing of PHC |  | Final revision/preparation for redesigned PHC financing | [7 empty] | Head of Department of UHC SSA | Head of Health Care Department MOH; Head of Department of Health Programs SSA; Head of Department of IT SSA;
| 3.4.3. Developing principles of contracting for purchasing services, including selective contracting and monitoring and evaluation system of contracts performance |  |  | Design of the concept for new contracting system | Design of planning system for hospital care based on Main Diagnostic Categories (MDC) | Analyse provider performance and develop principles for MDC based planning; SSA internal capacity building | Prepare piloting MDC based "virtual" contracting | Develop standards of procedure for contracting (planning, execution, monitoring) | Develop legal regulation. | Final preparation for going live |  |  |  | Head of Health Care Department MOH | Head of Department of UHC SSA; Head of Department of Health Programs SSA; Head of Department of IT SSA;
| 3.4.4. Needs assessment of health care services |  |  |  |  | Analyze epidemiological data, service utilization, existing resources, international experience |  | Elaborate the requirements for each directions based on statistical data taking into consideration the geographical accessibility and utilization |  | Implementation of requirements for each directions |  |  |  | Head of Health Care Department MOH | Head of Department of UHC SSA; Head of Department of Health Programs SSA; Head of Department of IT SSA;
3.5. HBP in line with population health needs | 3.5.1. Designing the system and process of HBP revision and renewal |  |  |  |  | Analyze the health service utilization of existing HBP and detect weak an strong sides |  | Assessment of health (among them essential) needs, service allocation and financial resources |  | Redesign HBP |  |  |  | Head of Health Care Department MOH | Head of Department of UHC SSA; Head of Department of Health Programs SSA; Head of Department of IT SSA;
3.6. Ensure equitable access to essential specialist care and strengthen PHC | 3.6.1. Revision of referral system and developing GP functions | Elaborate requirements (technical , specialisation …) for PHC service providers Develop new contracts and payment system for the PHC centers Elaborate the data-collecting system to receive the data from PHC centers about patients, their clinical condition, outpatient visits and referrals | Piloting data collection and new contracts among piloting PHC centres in Tbilisi |  | Piloting data collection and new contracts among 14 piloting PHC centres in each region |  | Analyze received data, hospitalization rate with ambulatory care sensitive conditions according to PHC centers | Revise/redesign the PHC system | [5 empty] | Head of Health Care Department MOH | Head of Department of UHC SSA, Head of Department of Health Programs SSA, Head of Department of IT SSA
| 3.6.2. Strengthening the capacity of GPs (certification and continuous medical education) |  |  | Elaborate the continuous medical education system and curricula of GPs |  | Elaboration of GP qualification monitoring system. Implementation plan for certification and continuous medical education for GPs | Revise/finalise the work on training and re-qualification system of GP | [6 empty] | Head of Health Care Department MOH | State Regulatory Agency of Medical Activities
3.7. Consolidate highly specialised and hospital care | 3.7.1. Analysing the need for hospital care services including highly specialised services and current distribution of service providers and Developing a plan for sustainable purchasing of hospital and highly specialised medical services |  |  |  |  | Analysing the need for hospital care services including highly specialised services and current distribution of service providers |  | Developing a plan for sustainable purchasing of hospital and highly specialised medical services. | Develop legal regulation. | Implementation of the plan |  |  |  | Head of Health Care Department MOH | Head of Department of UHC SSA, Head of Department of Health Programs SSA, Head of Department of IT SSA
3.8. Increase transparency and accountability | 3.8.1. Development and introducing of quarterly reporting on SP performance | Piloting reporting based on 2018 Q3 & Q4 | [11 empty] | Head of Health Care Department MOH | Head of Department of UHC SSA, Head of Department of Health Programs SSA
3.9. Improve population awareness | 3.9.1. Development of Citizen Portal and applications to increase transparency for patients | Elaborate the questioner for visitors of web site | Conduct of survey | Analyze the feedback for improvement of site data/information/characteristics/appearance | Final work on Citizen Portal and applications to present a transparent clear information/data for beneficiaries | [8 empty] | Head of Department of UHC SSA | Head of Department of Health Programs SSA, Head of Department of IT SSA, Head of Health Care Department MOH
| 3.9.2. Develop concept for citizen communication and communication plan | Prepare ToR for outsourcing the concept of citizen communication | Development of the concept of citizen communication | [10 empty] | Head of the Department of PR, MOH | Head of Health Care Department MOH
3.10. Enhance electronic data exchange and improve quality of data | 3.10.1. Mapping of key processes related with health service provision and SP and defining the needs for developing solutions for electronic exchange of data with stakeholders | System analyses and IT development plan to support SP Strategy implementation | [11 empty] | Head of Department of IT SSA | Head of Department of UHC SSA, Head of Department of Health Programs SSA
| 3.10.2. Introduce the use of electronic signature | Estimate the software characteristics (activity depends on the implementation of Electronic Medical Records) | Final preparation for going live | [10 empty] | Head of Department of IT SSA | Head of Department of IT MOH
| 3.10.3. Mapping of claims management process and design of electronic claims management solution | Designing SHOULD BE SOP for UHC program and implementation plan (incl TOR for tech application...) | Implementation and SSA wide training to introduce new practice |  | New claims management process introduced | [8 empty] | Head of Department of UHC SSA | Head of Department of IT SSA, Head of Department of Health Programs SSA
3.11. Align SSA management and structure around the strategy | 3.11.1. Design the new SSA health care related structure to reflect strategic needs and implement the new structure (regulation, appointment of key staff and managers, etc.). Develop principles and functions of health economics within SSA, the structural alignment of functions | Design of the new SSA health related structure approved Human recourses needs assessed Plan to implement the new structure prepared | Job descriptions and necessary legislative amendments approved Key positions of the new SSA structure (headquarter level) are filled New structure launched headquarter level 01.07.2019 | Regional structure of the SSA assessed and plan to align the regional structure to the headquarter new structure is papered | New SSA health care related structure fully implemented
3.12. Improve motivation and competencies of SSA staff | 3.12.1. Define key competencies to support implementation of strategic purchasing strategy and develop a system for prospective competency development and compile a competency development plan for SSA health care related key staff, (linked to the strategic initiatives 3.11. |  |  | Functions and competences of the new SSA health care related structure defined | Competency development plan for SSA health care related key staff developed | Competency development plan for SSA health care related key staff finalised and ready for implementation
3.13. Develop IT systems | 3.13.1. Define and prioritize SSA health care related IT system development needs (related to the strategic initiative 3.10.1) | System analyses and IT development plan to support SP Strategy implementation
3.14. Improve monitoring, reporting and analysis | 3.14.1. Develop comprehensive SSA health care organizational planning and reporting system, covering the cascade of management tools – translation of strategic planning into operational execution and reporting of performance and outcomes (SSA regional offices performance, strategic purchasing strategy), annual performance report (related to the strategic initiative 3.8.1) | 4Q2018 strategy execution report prepared and quarterly SPS WG reporting meeting conducted SOP for the planning and reporting system for the SP Strategy prepared | 1Q2019 strategy execution report prepared and quarterly SPS WG reporting meeting conducted | 2Q2019 strategy execution report prepared and quarterly SPS WG reporting meeting conducted SP Strategy 2020-2022 review process plan prepared | 2Q2019 strategy execution report prepared and quarterly SPS WG reporting meeting conducted Template for the annual report (yearbook) 2019 developed based on first year experiences SP Strategy revision for the period 2020-2022 completed | SP Strategy yearbook 2019 prepared
Initiative under development with milestone definition
Initiative due date with final approval

## PlantoimplementnewSSA Sturcture
Plan to implement new SSA structure
| Activities | Description of Work | April 2019 | May 2019 | June 2019 | July 2019 | Aug 2019 | Sep 2019 | Oct 2019 | Nov 2019 | Dec 2019
1 | Establishing the claims management unit by merging/reorganizing the extisting 2 departments and 4 divisions (such as the units of State Programs management, Organizational support, management of primary documentation and management of fullfilled work) | Revise the SSA statute to reflect intended structural changes
2 | Staff optimization/recruitment for the claims management office at HQ and BOs | Develop/finalize job descriptions and a recruitment plan
3 | Staff optimization/recruitment for the SSA monitoring office at HQ and BOs | Develop/finalize job descriptions and a recruitment plan
4 | Staff optimization/recruitment for the SSA pharm office at HQ and BOs | Develop/finalize job descriptions and a recruitment plan
5 | Recruit staff from the current personnel for the SSA contracting unit | Develop/finalize job descriptions and a recruitment plan
6 | Launch a new contracting unit | Train newly recruited staff
7 | Recruit additional staff for the contracting unit | Develop/finalize job descriptions and a recruitment plan
8 | Establish planning and monitoring unit | Train newly recruited staff
9 | Recruit staff for the planning and monitoring unit | Develop/finalize job descriptions and a recruitment plan
10 | Establish unit responsible for developing [pricing, reimbursement and payment methodologies (pricing and payment unit) | Train newly recruited staff
11 | Staff recruitment for pricing unit | Develop/finalize job descriptions and a recruitment plan
12 | Redesign IT system to support DRG implementation
13 | Redesign IT system to optimize the claims management process | Revisit the role of service centers and elaborfate adequate mechanism for provision of drugs for cancer patients
14 | Establishment of the SSA new structure finalized | New SSA structure legally endorsed, staff recruited and trained, IT system in place to support revised bussiness processes