Funding Request Form Global Fund COVID-19 Response Mechanism.

Summary Information

| Country | Georgia |
| --- | --- |
| Funding for COVID-19 response already accessed with Global Fund grant flexibilities | 484,500 |
| Priority 1 funding request | 570,585.80 USD |
| Priority 2 funding request: contingent on additional sources of funding | 625,000 USD |

# Section 1: Funding Request

## Context

a) Briefly describe the country context that informed the development of this funding request. If there is a national COVID-19 response plan you are invited to attach it and refer to this document.

On January 30, 2020 WHO declared public health emergency of international concern and recommended early detection, isolating and treating cases, contact tracing and social distancing measures in line with the level of risk. The Government of Georgia has immediately initiated an effective multi-sectoral response to COVID-19. Namely, in January 2020, the government adopted Decree #164 on “Approval of Measures to Prevent the Possible Spread of the New Coronavirus in Georgia. On February 23 the Country COVID-19 Emergency Coordination Board was created with NCDC having two members. The Emergency Response Plan for Cases Caused by COVID-19” (amended on April 1, 2020, with the GoG Decree #625) was developed. A state of emergency was declared on March 21, 2020. The first cases of the COVID-19 in Georgia were confirmed on February 26, 2020. As of May 15, 2020, the total number of infected people had risen to 671 with 393 recoveries and 12 deaths. Under the Operational Response Plan, approved by the GoG, each line ministry and government entity has clearly defined roles and responsibilities at every stage of COVID-19 response. On March 2, 2020, the Government Reserve Fund has allocated 1 million GEL (US$ 358,358 equivalent) to the Ministry of IDPs from the Occupied Territories, Labour, Health and Social Affairs (MoIDPLHSA) to respond to the challenge of the new coronavirus in Georgia. Risk-communication was initiated by developing clear messages related to symptom recognition, first contact, appropriate use of health services, financial access and social protection measures related to COVID-19. The government has also scaled up its communication efforts by establishing a unified hotline and an informational platform (StopCov.ge is a web site available in five languages with all necessary governmental links and related information) and disseminated a special sms to all phones in Georgia informing population about measures and recommendations. The Government has started mobilizing resources and building or identified the systems to be utilized for an effective national response. For scale up of COVD-19 diagnostics the existing systems of HIV, TB and hepatitis C testing were utilized including the Lugar Laboratory in Tbilisi that covers about 80% of tests and regional public health laboratories that have testing capacities to diagnose the novel coronavirus infection. Special consideration was given to development and institutionalization of COVID-19 related infection control guidelines for health and non-health facilities, healthcare safety and quality standards. The NCDCPH and district health authorities track down people who may have been exposed to the virus through a process of contact tracing. Health services use contact tracing to find people who may have been exposed to an infectious disease. By customizing the WHO COVID-19 Essential Supplies Forecasting Tool, MoIDPLHSA, in collaboration with partner organizations and WHO expert support, have conducted a detailed gap and needs analysis pointing at the significant need for test systems, PPE and other means for infection control. The success of the national response to COVID-19 in Georgia was well recognized by WHO and NIH (USA) leadership. The country was able to contain COVID-19 cases at the safe level to guarantee adequate diagnostic and treatment services. On April 24, the Georgian government presented a plan to gradually open the economy step-by-step over the next three months. There will be six stages of reopening the economy and moving to the next stage will go through only after an analysis of the epidemiological situation in the country. Ease of lockdown and renewal of economic activities in Georgia will require high level of preparedness from the side of medical facilities and public health institutions in Georgia. In the absence of further mitigation measures, the COVID-19 health crisis is likely to be most severe for vulnerable households, influencing their ability to abide by actions (such as social distancing) to contain the spread of the disease. Among the key interventions to be implemented to sustain the reached control over the COVID-19 epidemic the CCM has identified the following interventions for the Global Fund Priority 1 funding request: Section1. Mitigating COVID-19 impact on HIV, TB, Malaria programs: - Improving Access to General Health Services for KPs, PLHIV and TB patients KPs and PLHIV and TB patients generally experience stigma and discrimination while seeking health services, leading to disparities in access, quality and availability of healthcare. The discrimination can elevate the COVID-19 infection risk among KPs, PLHIV and TB patients. Many members of KPs who lost income and housing reported being deprived from access to reliable information on COVID-19 epidemic due to having limited access to general information sources such as television and internet. They couldn’t cover the mobile communication basic package fees. PLHIV and TB patients had particular concerns due to compromised immune status and needed additional information/clarification on potential impact of COVID-19 on their health and regarding the access to treatment in case of experiencing symptoms. - Addressing Barriers and De-prioritization of required HIV/STI/Drug use related health services Given overloaded health systems, treatment of KPs may be interrupted or deprioritized, including HIV and STI treatment and testing, harm reduction services, hormonal treatment for trans people, etc. Due to stay-at-home restrictions, many LGBTI, sex workers and female drug users were confined in hostile environments with unsupportive family members or co-habitants. This increased their anxiety and depression. OST service provision was adapted to the restrictions posed by the lockdown. OST patients were provided with 5-7 day supply of take home methadone that considerably reduced patients’ potential exposure to COVID-19infection. On the other hand PWIDs outside of OST program have faced serious difficulties due to limited illegal supply of injectable drugs. The increased demand on detoxification and OST services were reported but the financial barriers (pre-enrollment medical evaluation fee for OST program and high cost of detoxification program) were protecting PWIDs from utilization of addiction treatment and HR services. The needle and syringe programs were adapted to COVID-19 epidemic imposed restrictions by intensifying mobile and peer outreach based service delivery. - Living support for Key Population Members, PLHIV and TB Patients and migrant KPs; Many in the KP communities work in the informal sector and lack regular income or unemployment compensation and social protection. Due to lockdown of the cities KPs were deprived of income, food, medicine and in many cases housing. PLHIV and TB patients have faced economic hardships as well as the most of them were self-employed or working in small business that were the most affected by the lockdown. Migrant KPs were also severely affected by the COVID-19 epidemic and related restrictions. Many of them lost income due to COVID-19, and do not have any savings. - Sample collection for COVID-19, contact tracing and referral capacity development at CBOs/NGOs working with KAPS As KPs are particularly vulnerable to COVID-19 and the same time, due to high stigma and fear for discrimination, are reluctant to seek health assistance at the general health care facilities relying greatly on the support from CBOs/NGOs working with them. The community organizations have a big potential for early identification of COVID-19 infection cases among KPs and providing prompt referral to diagnostic and treatment facilities if equipped with relevant knowledge and skills through capacity development and professional supervision from the part of NCDC COVID-19 response team. Section 2: Reinforcing national COVID-19 response - Strengthen COVID-19 testing capacity Georgia started use of PCR technology for COVID-19 testing from January 30 and all cases were confirmed with this “Gold Standard”. Until March 1 the testing was provided by the Lugar Research Center and afterwards several regional public health and several private laboratories were engaged. At this stage, the number of COVID-19 PCR tests performed in the country is about 1,500 tests per day, from which about 43% of COVID-19 tests are performed at the Lugar Research Center and due to the National Protocol update, the number of tests should increase to 3,000 tests / day, and with the increase in testing the ability to increase the productivity of other laboratories is less possible, so the workload of Lugar Research Center will increase significantly. Currently, the Lugar Research Center uses the BIO-RAD CFX system and the Applied Biosystems Quantstudio 5 RT-PCR systems to diagnose COVID-19, as the workload is huge the staff has to work in shifts, for 16-18 hours per day, and the systems are loaded as much as it possible can be. In addition to a large number of routine tests, the Georgian government has commissioned the Lugar Center to implement a diagnostic decentralization project, thus improving Lugar's laboratory capabilities and acquiring new modern technologies became more significant. Quality control, mentoring and monitoring of laboratory diagnostics throughout Georgia requires quite high standards from the center. Therefore, it is necessary to have technologies in the country for the multiple and random quality control of the laboratories presented by a wide range of equipment. - Ensure Protection of health care workers and personnel of NGO/CBOs providing HIV and TB services Despite the global shortage the Government of Georgia made every effort for provision of personal protective equipment and staff training in line with the latest recommendations first of all to facilities taking care of COVID-19 cases and also to other large hospitals, primary healthcare providers, public health epidemiologists and lab technicians. Still the health professionals represent about 12% of all confirmed cases. This figure is in line with the international average and points at the need to further strengthen safety measures. Section 3. Urgent improvements in health and community systems - Support Primary Health Care based response on COVID-19 epidemic The national response to COVID-19 implied the potential for home-based care for patients with mild symptoms (such are 80 % of all cases), which means bigger role for primary care system. Through reallocation of grant savings TB program supported the introduction of outpatient model of care for presumptive and confirmed COVID-19 patients through development of care protocol, capacity building and supportive supervision. Both patients and service providers expressed satisfaction with such arrangement. The evaluation based on a specially designed quality assessment tool proved the model effectiveness and identified specific areas for additional capacity building and service provision improvement that will be addressed during the subsequent training. Activities selected for the priority 2 funding request Section1. Mitigating COVID-19 impact on HIV, TB, Malaria programs - IT Capacity strengthening of NGOs/CBOs for outreach data management during COVID-19 epidemic During the COVID-19 epidemic imposed restrictions NGOs/CBOs work was largely moved to the outreach service delivery modes. Outreach workers were providing HIV prevention commodities and brief counseling to KPs at homes. They had to do increased paperwork to document provided services which on the other hand increased potential for COVID-19 infection spread through paper forms. Equipping outreach workers with planshets will enable them to document services provided directly during the outreach sessions. The model will improve the HIV prevention service data collection in general as the HIV Prevention Data base will be updated to have online real time data collection option. Section 2: Reinforcing national COVID-19 response - Conduct COVID-19 sero-prevalence survey to inform policy decisions NCDC plans to conduct a COVID-19 seroprevalence survey to provide a more complete estimate of the infection incidence, determine the types and amount of education, counseling, and testing services offered, and identify access points for infected persons for medical follow-up and care. The findings will inform the control measures. Section 3. Urgent improvements in health and community systems - Strengthening COVID-19 Surveillance and Public Health Network of Georgia for Effective COVID-19 Response There are 65 municipal Public Health Centers located in each district of Georgia that are responsible for awareness raising of local population on COVID-19, case identification, contact tracing, sample collection and transportation, organization of quarantine or providing referrals to designated quarantine and treatment facilities, monitoring of quarantine observation for suspected and confirmed COVID-19 patients in their respective districts. Additional resources in terms of personnel and equipment are needed to cope with significantly increase workload and added responsibilities. - Improve capacity for oxygen therapy The National Center for TB and Lung Diseases serves as a referral hospital for the most severe TB patients in the country and also has been designated as for care of presumptive COVID-19 cases and potentially confirmed COVID-19 cases (as needed). These patients often require oxygen supply. There are 251 patient beds at the NCTLD hospital within the hospital wards and the ICU that are equipped with the medical oxygen panels installed 12 years ago. On 227 out of the 251 panels, no oxygen humidifiers are operational. For both TB and COVIF-19 patients it is essential to ensure the supply of the humidified oxygen to those beds.

All CCM members are required to endorse this funding request. Note that CCM Eligibility Requirement 1 applies to this funding request submission.

b) Summarize how a range of stakeholders, including civil society and key populations, have been engaged in the development and decision-making on the priorities in this funding request.

[Applicant response] CCM

## Priority 1: Primary Funding Request

- Indicate your allocation in the table below, and calculate funds available for COVID-19 Response Mechanism support.

| 2020-2022 total allocation | 17,556,486.00 USD |
| --- | --- |
| Funds available for COVID-19 Response Mechanism support | 570,585.80 USD |

The designated funds available for financial support can be used for any of the following areas:

- Mitigating COVID-19 impact on HIV, TB, malaria programs

- Reinforcing the national COVID-19 response

- Urgent improvements in health and community systems

- Briefly describe your Priority 1 funding request. Note that Global Fund investments must be in line with Global Fund technical guidance and WHO recommendations, and should support a national strategic preparedness and response plan.

|  | Funding Requested | Activities proposed and rationale |
| --- | --- | --- |
| Mitigating COVID-19 impact on HIV, TB, Malaria programs | 106,500 USD | COVID-19 impact mitigation measures on KPs, PLHIV and TB Patients Key population (Lesbian, gay, bisexual, trans and intersex (LGBTI) people, sex workers and people who inject drugs (PWIDs) are particularly vulnerable during the COVID-19 pandemic. People living with compromised immune systems, including some persons living with HIV/AIDS and TB, face a greater risk from COVID-19 also. Homeless and/or unemployed persons, a population that includes many members of key populations, are less able to protect themselves through physical distancing and safe hygiene practices, increasing their exposure to infection. - Improving Access to General Health Services for KPs, PLHIV and TB patients CBOs can play critical role in ensuring quick and effective linkage of KPs and PLHIV to COVID-19 and general health related primary health care and specialized services during the epidemic as well as awareness raising and reinforcing COVID-19 preventive measures among KPs and PLHIV and TB patients. Although online primary care clinics were established for general population during the COVID-19 epidemic to assess their health care needs and direct to specialized services as needed, KPs, PLHIV and TB patients couldn’t benefit from the service due to lack of information about the clinics as well as of fear of discrimination and unfriendly attitude that they generally experience when seeking health care. As online clinics and some of PHC facilities were identified by the Government as gatekeepers for COVID-19 health care response a joint Online Clinics/PHC facilities and HIV and TB service providers’ communication plan, response protocol and service delivery model has to be developed and implemented to address general health needs of KPs and PLHIV and TB patients in Georgia. Online clinics’ personnel needs capacity building to get understanding of special needs of KPs, PLHIV and TB patients and to reduce risks for discrimination or break of confidentiality. Tailored to KP and PLHIV needs informational campaigns, online informational webinars, online patients’ schools are clearly needed to fill the gaps and raise awareness on COVID-19 infection and related potential health consequences. Proposed mitigating interventions: - Needs assessment, development and implementation of COVID-19 communication plan and informational campaign. A small scale qualitative survey will be conducted among all KPs (PWIDs, LGBTI, SW), PLHIV and TB patients to identify the main channels and critical barriers to COVID-19 related health information and health related needs, health care seeking behavior and access to services during the epidemic. Depending on the COVID-19 epidemic trends either focus group discussions or online/telephone individual interviews will be conducted to collect the information. The report of the need’s assessment will greatly inform the COVID-19 epidemic response planning of the PR and prepare service providers for the next wave of the epidemic. The Communication Plan will support establishment of effective communication lines and coordination of all available resources at different HIV and TB service providers. The plan will ensure well established linkage to COVID-19 and general health services for KPs, PLHIV and TB patients. It will contain the mapping of all COVID-19 related services and supports available for KPs, PLHIV and TB patients. The information campaign will be designed based on the evidence based information on COVID-19 and on the outcomes of the needs’ assessment survey (activity 1.1) that will inform the campaign designers about the most needed information for KPs, PLHIV and TB patients regarding the COVID-19 infection and the best communication vectors for the campaign. The campaign will be largely relying on social media and other online communication means. Total for the activity 1.1: 6,800 USD. - Establishing Online Primary Care Clinics A pilot program of Online Primary Care Clinics will be supported as a primary health care gateway for KPs. PLHIV and TB patients during the COVID-19 epidemic and beyond. Primary health care physicians of Online Clinics who will undergo training on special needs of KPs, PLHIV and TB patients will be providing online and telephone consultations to patients seeking medical assistance and ensure proper referral to treatment facility, including mental online and telephone mental health assistance intervention for KPs, PLHIV and TB patients. Qualified phycologists with experience of working with KPs, PLHIV and TB patients will be providing 24/7 mental health support during the epidemic. There will be four Online Clinics supporting KPs, PLHIV and TB patients operating at designated PHC facilities in Tbilisi, Batumi, Kutaisi and Zugdidi. Their work will be guided by joint CBO/Online Clinic/Primary Health Care facility protocol for management of KPs, PLHIV and TB patients who experience COVID-19 symptoms or have any other health needs. Relevant training sessions, including online training and webinars will be organized to train Online Clinics physicians and to inform service providers at NGO/CBOs and PHC facilities how urgently reinforce new service delivery model. Number of training session to be organized would be 4. The Online Clinics’ services will be promoted by the COVID-19 communication platform and campaign (activity 1.1). Estimated total for the intervention including training, monitoring and quality assurance would be 30,000 USD. Total estimated for the activity 1: 36,800 USD - Addressing Barriers and De-prioritization of required HIV/STI/Drug use related health services Importance of access to mental health services as well as prevention of and management of GBV were identified by HIV prevention service providers among the priority needs during the lockdown period to ease a complex mental pressure on KPs. During the isolation period a greater demand on HIV prevention supplies such as condoms and syringes was observed and documented by outreach service providers to be addressed during COVID-19 epidemic impact mitigation planning. In addition KPs were requesting PPE support, mainly face masks/face shields and hand sanitizers due to shortage of these supplies in pharmacies countrywide (the needed supplies of PPE are considered in COVID-19 Response Section of the funding request). The most of PLHIV were provided with 3 months refills of ARV medicines and AIDS centers have organized mobile teams to deliver the medicines as well to collect blood samples for ART monitoring laboratory testing, however limited number of mobile units and staff restricted them from reaching all PLHIV in need of ARV refills. Provision of clients support services required development of different service delivery model relying on improved/assured communication systems (phone/internet), online consultations of case managers and different health specialists, but full-scale implementation of the model was restricted by the budgetary constraints. 2.1 Strengthening of Case Management Services Within HIV and TB Programs additional case management support will be provided to clients to ensure that KPs, PLHIV and TB and OST patients can easily navigate across the health care continuum during COVID-19 epidemic and can benefit from available HIV, TB and drug addiction treatment services. Case managers and social workers will identify individual needs of beneficiaries, that will be documented and relevant support will be approved by program coordinators. Social workers and peer supporters will help beneficiaries in need to actually get needed service and fully benefit from eligible support. Eligible case support will include payments for pre-enrollment fees in OST programs, support for GBV victims, payment for basic health services for uninsured KPs, etc. (10,000 USD) 2.2 Improved delivery of ART services New models of ARV distribution for PLHIV will be established to address the transportation restrictions during the lockdown such as postal distribution of ARVs and distribution through mobile delivery companies. New models of ARV medication distribution will support PLHIV to refill their critical stocks of ARV medications countrywide. (3,500 USD) 2.3 Procurement of additional HIV prevention commodities In order to refill the stock of HIV prevention supplies for HIV prevention program and address the increased demand on such commodities during COVID-19 epidemic, such as syringes and needles and condoms additional q-ties of these products will be procured. 17,300 USD is requested. TOTAL for activity 2: 30,800 USD 3. Living support for Key Population Members, PLHIV and TB Patients and migrant KPs: KPs are more likely to be unemployed and to live in poverty than the general population. Through limited support of some donor organizations CBO working with LGBTI was able to raise some funds to support TGs and SWs by paying house rents. Some food packages were provided by the Government also, but due to limited funds CBO wasn’t able to sustain this critical support. Need of food, hygiene products and basic medications support for some PWIDs was documented by the NSP service provider organizations also, especially in the regions of the country. Community based organizations working with PLHIV and TB patients have reported the sever need of food or monetary support to ensure their wellbeing and continued adherence to HIV and TB treatment regimens. Another group that was severely affected by the COVID-19 epidemic and related restrictions are migrant KPs. Many of them lost income due to COVID-19, and do not have any savings. Housing needs (quality and affordability) and residence/ visa related legal needs were frequently reported issues by the migrant KPs. Language barrier and lack of information on free access to COVID-19 related testing and treatment in case of experiencing symptoms were keeping the migrant KPs from seeking health care during the epidemic. Proposed Interventions 3.1 Living support for procurement of Food/Hygiene Products/Basic Medications. With proposed living support intervention KPs, PLHIV and TB patients will be assisted based on the individual needs assessed by social and outreach workers of CBOs. The assistance that will be aligned with national living support allowance policy will cover food and hygiene products support and provision of basic medication. (Average 4 month minimum living allowance in 2020), total 28,100 USD for 6 months. 3.2 Shelters for KPs, including migrant KPs left without housing. Several apartment will be rented for homeless KP members including migrants to ensure that they have adequate temporary housing and sanitation conditions and can follow the isolation and quarantine regulations. Those who will be provided with housing will have access to other living support services based on the individual needs’ assessment. Budget allocated for 6 month intervention is 8,600 USD. Total budget of activity 3: 36,700 USD 4 Sample collection for COVID-19, contact tracing and referral capacity development at CBOs/NGOs working with KAPS In case of large COVID-19 epidemic CBOs/NGOs may play critical role in identification of COVID-19 infection cases, contact tracing and providing effective referrals for treatment of key population members affected by disease. Such capacity development among social workers/outreach workers of CBOs/NGOs will greatly support early identification of COVID-19 cases among KAPs through assessment of symptoms, samples’ collection, giving testing results and providing prompt referral to treatment facilities. Five groups of 10 staff members of different CBOs/NGOs working with KAPs will be trained by NCDC epidemiologists on COVID-19 infection symptoms, samples collection for testing, epidemiological assessment for contacts tracing, providing effective referral to appropriate treatment of quarantine facilities as needed and on infection control measures. Selected and trained 10 members of NGO/CBOs staff will be able to provide necessary instructions/training to other personnel as needed and they will have financial support during the COVID-19 infection outbreak and lockdown periods if engaged in the COVID-19 response under NCDC direct supervision. Total support envisaged for training and fees of staff members working on COVID-19 is 2,200 USD. Grand TOTAL: 106,500 USD |
| Reinforcing national COVID-19 response | 446,540 USD | The key to successful control of COVID-19 epidemic and quick recovery with minimal health impact will be expanded testing capacity and strengthened case surveillance system through procurement of additional testing platforms, diagnostic tests and training of public health professionals on COVID-19 case identification and management of new cases and contacts, assessment of epidemic trends and determine if return to response mode is warranted. 5. Strengthen COVID-19 testing capacity In line with WHO guidance, timely identification of cases using the PCR technology and screening with rapid tests have become the cornerstone of the successful national efforts in Georgia. The protocol specifying the target groups was developed and regularly updated in line the epidemic trend and diagnostic capacity. With the ongoing gradual reopening of the economy the need for testing even increased. About 250, 000 COVID19 PCR test reagents and consumables are required for Georgia by WHO estimation. Decentralization and diversification of testing using various available platforms is highly recommended. The country already uses RealTime Sars-CoV-2 Assay - ABBOTT MOLECULAR INC and Xpert® Xpress SARS-CoV-2 cartridges for Cepheid’s GeneXpert® Systems. Global shortage of reagents and consumables as well as low throughput of these platforms hinder the ability to scale-up the process. Using grant savings and FX gains of Global Fund HIV and TB grants NCDC has procured 1,500 Xpert® Xpress SARS-CoV-2 cartridges and has placed an order for 11,500 more cartridges. In addition 8000 Abbott RealTime Sars-CoV-2 Assays procurement was approved by the Global Fund Country Team. Additional funding requested within priority 1 funding will support procurement of - Thermo Fisher Scientific QuantStudio 12K 384 W TWR - TaqPath™ COVID-19 CE-IVD RT-PCR Kits - MagMAX™ Viral/Pathogen II (MVP II) Nucleic Acid Isolation Kits And also - Sample Collection vials for Cepheid’s GeneXpert® Systems. The QuantStudio system was selected due to the ability to easily install additional TaqMan and Open Array blocks. Through these blocks it is possible to multiply the productivity of the system and test a larger number of samples simultaneously on multiple target genes. Also this feature gives QuantStudio 12K advantage over any other system, as the array blocks will allow the system, therefore the Lugar Research Center to set up a country-adapted, multi-infection diagnostic combined panel for the development and validation of new tests, and there are ongoing negotiations with CDC and DETRA on co-financing and procuring this additional array blocks for Lugar research center. It should also be noted that according to the official representative of Applied Biosystems in Georgia (ABM), the device QuantStudio 12K Flex is ready to be sent from the European warehouse to Georgia and it is possible to receive and install the device within 2 weeks after order is placed (usually it takes at least 2-3 months to receive goods). Total budget of activity 5: 349,940 USD - Ensure Protection of health care workers and personnel of NGO/CBOs providing HIV and TB services To ensure the preparedness of the health system to address the pandemic, the government has identified a list of designated public and private facilities to provide treatment to COVID-19 patients. Both leading facilities for COVID-19 treatment providing TB and HIV services - Infectious Diseases, AIDS and Clinical Immunology Research Center and the National Center for TB and Lung Diseases have been listed. It is essential that all WHO-recommended infection prevention and control measures are observed and followed when health professionals are in close contact with patients and/or handling any infectious specimens, including use of the N95 respirator, handwashing, use of gloves, goggles or protection shield, waterproof aprons, regular decontamination of surfaces. Therefore the need for PPE increased in both facilities, besides, front-line workers of NGOs providing preventive services within the GF funded programs also require additional PPE. Less than half of the country need has been committed this far through government funding and other donor support. Total budget of activity 5: 96,600 USD |
| Urgent improvements in health and community systems | 17,500 USD | - Support Primary Health Care based response on COVID-19 epidemic PHC engagement became essential for promotion of service’ efficiency and gatekeeping the hospital sector. So called “online clinics” have been established with the function to be the first medical contact of presumptive COVID-19 patients who are directed to the clinic by the Georgia Emergency and Operative Response Center (112). The online clinic ensures presumptive patients home triage through telephone consultations or onsite visits, counselling on COVID-19 as well as other health conditions, infection control, and referral to a hospital. The model has proved its benefits for COVID-19 and may also be rapidly deployed in case of other outbreaks. It is planned to obtain the formal program accreditation. Further efforts are needed to sustain the process, including the updates in line with emerging evidence and scale it up especially in light of the anticipated second wave of COVID-19. The activity implies revision of protocol, training, supportive supervision, monitoring and evaluation during 10 months period. Total budget of activity 6: 17,500 USD |

- If you are requesting COVID-19 diagnostic tests and will be using machines currently used for TB testing and HIV viral load testing, indicate your plan to mitigate the impact on these activities.

N/A

## Priority 2: Additional Funding Request

Briefly describe the additional prioritized investments you would request the Global Fund support, in case additional funding becomes available.

|  | Funding Requested | Activities proposed and rationale |
| --- | --- | --- |
| Mitigating COVID-19 impact on HIV, TB, Malaria programs | 55,000 USD | 1 KAPs HIV Self-testing capacity strengthening in preparation of the next wave of COVID-19 infection Procurement of additional HIV saliva self-tests is planned to ensure that for the next wave of COVID-19 infection NGOs/CBOs working with KAPs have sufficient stocks to sustain the testing during the lock-down periods. Procurement of additional 10,000 HIV saliva self-tests is planned through WAMBO online procurement platform of the GF that will be sufficient for 3 month testing of KAPs (PWIDs, MSM and SWs). Some funding will be required for packaging of self-tests and payments for mobile delivery. The existing self-testing platform developed for MSM population will be adapted to accommodate the needs of other KAPs and relevant promo internet campaign will be implemented. Total estimated budget for activity: 30,000 USD 2 IT Capacity strengthening of NGOs/CBOs for outreach data management during COVID-19 epidemic 40 plashets will be procured for outreach workers of NGOs/CBOs working with KPs. Outreach workers will be able to document all services they provide during outreach sessions immediately in real time regimen. The HIV Prevention Database will be updated to have a real time data collection options activated. Total estimated budget for activity: 25,000 USD |
| Reinforcing national COVID-19 response | 445,000 USD | 3 Conduct COVID-19 seroprevalence survey to inform policy decisions According to WHO recommendations in addition to active case finding and testing, it is critical to enhance surveillance activities to detect and monitor if there is COVID-19 transmission in the community. The seroprevalence studies to date conducted in other countries show that a significant fraction of the populations examined have antibodies against SARS-CoV-2 in their bloodstream that allowed the countries’ leadership to ease the restriction measures and get adequately prepared for COVID-19 epidemic second wave. The studies showed also that exact prevalence levels are highly country and region specific. To ensure obtaining of good antibody prevalence estimates for Georgia and inform the country’s response plan to the epidemic, randomly selected adult individuals from the list of universal insurance database will be enrolled in the seroprevalence survey for SAPS-CoV-2 antibodies at their respective households. The selection will cover individuals living in the most and list affected by COVID-19 regions of Georgia. Quality IgM and IgG ELISA tests will be used for testing of obtained blood samples. The survey will include structured individual interviews to collect information on history of COVID-19 confirmed or suspected cases prior the enrollment period as well as health seeking behavior and experience of getting medical support during the manifestation of symptoms, if any. Total time period of the study will be 8 months including 5 months of field work. The state budget will cover procurement of test-kits, while technical assistance, travel, sample processing, data collection and analysis will be co-funded from the GF grant. Total budget of activity 1: 60,000 USD 4 Supporting effective treatment of COVID-19 patients 4.1 procurement of Plasmapheresis and extracorporeal "blood purification" in patients with COVID-19 As clinical trials continue in various countries to determine effective new treatments for COVID-19, one of the treatment approaches is to reduce the amount of cytokines and other inflammatory mediators in a patient's blood, which can be achieved by using plasmapheresis and/or extracorporeal "blood purification" using various filters and sorbents. The cytokines and inflammatory mediators play an important role in the pathogenesis of COVID-19, often leading to the severity of the disease and sometimes to lethal outcome. Consequently, reducing their number in the blood is considered to be one of the promising approaches in the treatment of COVID-19. On April 10, 2020 the U.S. FDA issued an emergency use authorization for a blood purification system to treat patients 18 years of age or older with confirmed COVID-19 admitted to the intensive care unit with confirmed or imminent respiratory failure. Blood purification device Spectra Optia Apheresis System (Terumo BCT Inc) - is an industry-leading therapeutic apheresis, cell processing and cell collection platform that allows operators to spend more time focusing on patient care. This advanced system uses continuous-flow centrifugation and optical detection technology, providing operators the ability to perform a wide variety of apheresis procedures on a single platform. Terumo BCT, a U.S. based leader in blood component, therapeutic apheresis and cellular technologies. Procurement of this system will considerably reduce potential lethal outcomes of COVID-19 infection and will reduce the numbers of patients’ hospital treatment days. (Budget 75,000 USD) 4.2 Improve capacity for oxygen therapy The first-line therapy for those with respiratory distress and/or hypoxemia is supplemental oxygen, with a goal of improving oxygen to > 88-90% and reducing their work of breathing. To enable supply of the humidified oxygen to hospital beds at the National Center for TB and Lung Diseases there is need to purchase 227 oxygen humidifiers, 10 medical gas quick-release valves, and 400 disposable single-mode oxygen breathing tubes for panels located within ICU. (Budget 60,000 USD) Total budget of activity 4: 135,000 USD 5 Strengthen COVID-19 testing capacity The activity implies procurement of COVID-19 test-kits and supplies. Total budget for activity 5: 200,000 USD 6 Ensure Protection of health care workers and personnel of NGO/CBOs providing HIV and TB services Taking into consideration the unmet need for PPE and the utmost importance of protecting health professionals, the activity will cover procurement of PPE and other means for infection control. Total budget for activity 6: 50,000 USD |
| Urgent improvements in health and community systems | 125,000 USD | 7 Strengthening COVID-19 Surveillance and Public Health Network of Georgia for Effective COVID-19 Response ## 7.1 Capacity building of NCDC and regional public health centers staff on COVID-19 surveillance, contact tracing, samples collection and infection control measures Additional 10 staff members of NCDC and regional public health centers will be trained as a reserve for COVID-19 national surveillance/contacts tracing/ samples collection and infection control forming additional five groups of two specialists who will be assisting/substituting the existing teams of public health workers tasked to perform such activities during the current epidemic stage. They will be incentivized/ paid from the grant in case of actual enrollment in the COVID-19 response and performing the above indicated tasks. Budget for the intervention is estimated for 6 months support but will be utilized as needed. Total budget of activity 7.1: 5,000 USD ## 7.2 Improve Public Health Centers Distance Working Capacity during the COVID-19 outbreaks and lockdowns Due to shortage of office IT equipment, specifically laptop computers, the employees of the Centers don’t have possibility of distance work and by going to the offices daily were exposed to COVID-19 infection risk both individually and as groups. Procurement of three laptops per center, total of 200 pieces is planned to address this limitation and enable public health center’s personnel to coordinate their work from homes. Total budget of activity 7.2: 120,000 USD |

Note: this prioritized request, in addition to funding for the COVID-19 response already accessed with Global Fund grant flexibilities and the Priority 1 funding request above, should not go beyond 10% of the total 2020-2022 allocation. Although there is no guarantee that additional funds will become available, the Global Fund requests that countries complete this section to ensure the Global Fund can fully assess demand. Countries are encouraged to exhaust all flexibilities under grant savings and reprogramming in the interim, following guidance available on the Global Fund website https://www.theglobalfund.org/en/covid-19/grants/.

## Implementation

Describe planned implementation arrangements for each activity, including Principal Recipient(s) and Sub-recipient(s). These must be existing Global Fund implementers. Indicate the grant(s) into which the funding will be integrated and the planned year of implementation.

| Ac Activity | Principal Recipient | Sub-recipient(s) | Grant into which funding will be integrated | Year where a Year of implementation (2020 or 2021) |
| --- | --- | --- | --- | --- |
| Priority 1 |  |  |  |  |
| ProcurePromPro Improve access to PHC services for KPs | ProcurePromPro Procurement of Thermo fisher National Center for Disease Control and Public Health | TBD | GEO-H-NCDC | 2020-2021 |
| ProcurePromPro Addressing Barriers and De-prioritization of required HIV/STI/Drug use related health services | ProcurePromPro Procurement of Thermo fisher National Center for Disease Control and Public Health | TBD | GEO-H-NCDC | 2020 |
| ProcurePromPro Living support for Key Population Members, PLHIV and TB Patients and migrant KPs | National Center for Disease Control and Public Health | TBD | GEO-H-NCDC | 2020 |
| Sample collection for COVID-19, contact tracing and referral capacity development at CBOs/NGOs working with KAPS | National Center for Disease Control and Public Health | TBD | GEO-H-NCDC | 2020-2021 2020-2021 |
| Procurement of Thermo Fisher Scientific QuantStudio 12K 384 W TWR | ProcurePromPro Procurement of Thermo fisher National Center for Disease Control and Public Health |  | GEO-H-NCDC | 2020 |
| ProcurePromPro Procurement of Thermo Fisher Scientific QuantStudio 12K 384 W TWR | ProcurePromPro Procurement of Thermo fisher National Center for Disease Control and Public Health |  | GEO-H-NCDC | 2020 |
| ProcurePromPro Procurement of TaqPath™ COVID-19 CE-IVD RT-PCR Kits and MagMAX™ Viral/Pathogen II (MVP II) Nucleic Acid Isolation Kits | National Center for Disease Control and Public Health |  | GEO-H-NCDC | 2020 |
| Procurement of PPE | National Center for Disease control and Public Health | National Center for TB and Lung Diseases | GEO-H-NCDC | 2020 |
| Procurement of PPE | National Center for Disease control and Public Health | Infectious Diseases, AIDS and Clinical Immunology Research Center | GEO-H-NCDC | 2020 |
| Procurement of PPE | National Center for Disease control and Public Health | NGO Tanadgoma | GEO-H-NCDC | 2020 |
| ProcurePromPro Procurement of PPE | National Center for Disease control and Public Health | NGO GHRN | GEO-H-NCDC | 2020 |
| ProcurePromPro Procurement of PPE | National Center for Disease control and Public Health | NGO Equality Movement | GEO-H-NCDC | 2020 |
| ProcurePromPro Procurement of PPE | National Center for Disease control and Public Health | NGO HAPS | GEO-H-NCDC | 2020 |
| ProcurePromPro Support Primary Health Care based response on COVID-19 epidemic | National Center for Disease control and Public Health | TBD | GEO-H-NCDC | 2020-2021 |
| Priority 2 |  |  |  |  |
| KAPs HIV Self-testing capacity strengthening in preparation of the next wave of COVID-19 infection | National Center for Disease control and Public Health | NGO/CBOs |  |  |
| IT Capacity strengthening of NGOs/CBOs for outreach data management during COVID-19 epidemic | National Center for Disease control and Public Health | NGO/CBOs | GEO-H-NCDC | 2020 |
| Conduct COVID-19 seroprevalence survey | National Center for Disease control and Public Health |  | GEO-H-NCDC | 2020 |
| Supporting effective treatment of COVID-19 | National Center for Disease control and Public Health | Infectious Diseases, AIDS and Clinical Immunology Research Center; National Center for TB and Lung Diseases | GEO-H-NCDC | 2020 |
| Strengthen COVID-19 testing capacity | National Center for Disease control and Public Health | TBD | GEO-H-NCDC | 2020-2021 |
| Ensure Protection of health care workers and personnel of NGO/CBOs providing HIV and TB services | National Center for Disease control and Public Health | TBD | GEO-H-NCDC | 2020-2021 |
| Strengthening COVID-19 Surveillance and Public Health Network of Georgia for Effective COVID-19 Response | National Center for Disease control and Public Health | TBD | GEO-H-NCDC | 2020-2021 |

# Section 2: Coordination

The Global Fund must ensure that all COVID-19 Response Mechanism funding awarded is complementary to funding from other partners.

List any applications for funding for the COVID-19 response you have made, or intend to make, to international donors. If the funding requests are completed, please attach the applications. Indicate if any of these applications have already been approved.

As in other countries across the world international partners support was mobilized quickly in Georgia. Since the breakout of the disease, the United Nations AFPs, WB, USAID and EU in Georgia have been taking robust steps to ensure preparedness and to enhance their response capabilities coordinated by the Government of Georgia and Office of the UN Resident Coordinator (RCO). RCO supported establishment of the ‘health procurement group’ with participation of UN Agencies, WB and Georgia’s health authorities to ensure harmonization of the respective assistance based on the commodity lists elaborated through WHO’s technical expertise.

WHO has been providing technical lead to the joint strategic planning on supporting the Government with its response efforts. The health parts of the Country Strategic Preparedness and Response Plan (CSPR) have been finalized, costed and are entered into the COVID-19 online Partners Platform (https://covid19-response.org/).

Multisectoral efforts to mitigate social and economic consequences of the outbreak were finalized by the respective UN agencies and national counterparts being coordinated by the RCO in support of the government, for some activities funding is approved and utilization has started, for other the approval is pending.

| Indicate name of international donor and focus of funding request | Indicate status of application: [completed or in-progress] | Has this funding request been approved? [Yes/No] If Yes, indicate how much was approved and for what activities |
| --- | --- | --- |
| UNICEF has identified 449,000 USD funding for Georgia COVID-19 response to be spent on education, child protection, health and nutrition, including procurement of COVID-19 test kits and PPE spending. | In-progress | 449,000 USD approved (10% of estimated need) |
| USAID – COVID19 response grant to IFRC | Completed | Yes. $1 million for risk communication, community engagement and assistance to vulnerable populations |
| USAID – COVID19 response grant to WHO | Completed | Yes. $700,000 for lab support, infection prevention and control, epidemiological surveillance, clinical case management and risk communication |
| USAID – COVID19 response grant to UNICEF | In-progress | Yes. $1 million |
| UNFPA supports health authorities with information on continuity of sexual and reproductive health services and interventions as a part of planning procedures and algorithms for respective service provision which results in pregnant women with suspected or confirmed COVID-19, or in isolation, having access to woman-centred, skilled care | In-progress | 60,000USD from core resources and additional 175000USD from MDTF |
| UNDP supports COVID-19 readiness for conflict-affected populations, Namely, to provide medical commodities and train front-line medical personnel in Abkhazia, and to help meet the needs of vulnerable members of Georgia’s IDP communities. To address vulnerabilities in healthcare provision in Abkhazia, UNDP is organizing deliveries of medical commodities to hospitals. | In-progress | USD 250,000 in internal rapid response funding and repurposed an additional USD 250,000 were secured from ongoing programs |
| EU support will reach medical workers and other workers on the first line of response, patients, and vulnerable people – all those most in need in East European region, including Georgia | In-progress | Support to Georgia Phase I of procurement country plan is budgeted at 1,6M EUR, including 1,4M for PPE and 146,440 EUR for medical equipment. |
| EU funded TA “ Support to Public Administration Reform in Georgia”. | In-progress | 664,560 EUR on health related expertise, including ad hoc analyses and advice on other aspects of COVID-19 response in Georgia |

# Annex 1: Documents Checklist

Use the list below to verify the completeness of your application package:

| ☐ | Funding Request Form |
| --- | --- |
| ☐ | CCM Endorsement of Funding Request |
| ☐ | National COVID-19 Response Plan (if available) |
| ☐ | Funding applications to international donors (as relevant) |

# Annex 2: Only Required if Requesting COVID-19 Diagnostic Tests

Context: There is a currently a global shortfall in supply of COVID-19 diagnostics. Please submit your request for number of tests and sample collection kits for the full amount needed over the next 16 weeks, noting that due to supply constraints the actual amount provided may be less than that or be distributed in tranches over the period rather than as a single batch. We will be transparently communicating updated diagnostic volumes on a frequent basis as and when more supply becomes available. More granular guidance on the exact operational model will be issued shortly. In addition, we are cognizant that there is an evolving landscape of manual and rapid diagnostic tests, and we will be revising our approach and guidance as the WHO guidance evolves on those products. Currently, the Global Fund will focus primarily on funding automated rather than manual tests. The following information is required if requesting COVID-19 diagnostic tests:

| A. Manufact-urer / Type | B. Name of COVID-19 test kit | C. Required Instrument Model | D. Number of instruments available for COVID-19 testing in Country | E. Indicative Cost per Test (USD)* | F. Number of Tests Requested | G. Implied Cost of Requested Tests (column E x column F) | H. Indicative Cost per Sample Collection Kits (USD)** | I. Number of Tests Requested | J. Implied Cost of Requested Sample Collection Kits (column H x column I) | K. Implied Total Cost of Requested Sample Collection Kits (column G + column J) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Abbott Molecular Diagnostics | Abbott RealTime SARS-CoV-2 Amplification Reagent Kit | Abbott m2000rt | 1 | $21.85 |  |  | $2.00 |  |  |  |
|  |  | Abbott m2000sp | 1 | $21.85 |  |  | $2.00 |  |  |  |
| Cepheid HBDC | Xpert Xpress SARS-CoV-2 kit | GeneXpert Laptop Instruments | 4 |  |  |  |  |  |  |  |
|  |  | GeneXpert II, 2 sites analyser with Laptop |  | $22.80 |  |  | $2.00 |  |  |  |
|  |  | GeneXpert IV, 2 sites analyser with Laptop |  | $22.80 |  |  | $2.00 |  |  |  |
|  |  | GeneXpert IV, 4 sites analyser with Laptop | 2 | $22.80 |  |  | $2.00 |  |  |  |
|  |  | GeneXpert XVI, 4 sites analyser with Laptop |  | $22.80 |  |  | $2.00 |  |  |  |
|  |  | GeneXpert XVI, 8 sites analyser with Laptop |  | $22.80 |  |  | $2.00 |  |  |  |
|  |  | GeneXpert XVI, 12 sites analyser with Laptop |  | $22.80 |  |  | $2.00 |  |  |  |
|  |  | GeneXpert XVI, 16 sites analyser with Laptop | 2 | $22.80 |  |  | $2.00 | 10,000 |  |  |
|  |  | GeneXpert Desktop Instruments | 38 |  |  |  |  |  |  |  |
|  |  | GeneXpert II, 2 sites analyser with Desktop |  | $22.80 |  |  | $2.00 |  |  |  |
|  |  | GeneXpert IV, 2 sites analyser with Desktop | 12 | $22.80 |  |  | $2.00 |  |  |  |
|  |  | GeneXpert IV, 4 sites analyser with Desktop | 24 | $22.80 |  |  | $2.00 |  |  |  |
|  |  | GeneXpert XVI, 4 sites analyser with Desktop |  | $22.80 |  |  | $2.00 |  |  |  |
|  |  | GeneXpert XVI, 8 sites analyser with Desktop |  | $22.80 |  |  | $2.00 |  |  |  |
|  |  | GeneXpert XVI, 12 sites analyser with Desktop |  | $22.80 |  |  | $2.00 |  |  |  |
|  |  | GeneXpert XVI, 16 sites analyser with Desktop | 2 | $22.80 |  |  | $2.00 |  |  |  |
| ROCHE | cobas® SARS-CoV-2 Test | Cobas® 6800 System |  | $18.40 |  |  | $2.00 |  |  |  |
|  |  | Cobas® 8800 System |  |  |  |  |  |  |  |  |
| ThermoFisher SCIENTIFIC | Applied Biosystems TaqPath COVID - 19 CE-IVD RT-PCR Kit | Applied Biosystems 7500 Fast Dx Real-Time PCR System Applied Biosystems 7500 Fast Real-Time PCR System (RUO version) and |  | $17.25 |  |  | $2.00 |  |  |  |
|  |  | Other manual and automated systems such as BGI, Da An, Thermo, Perkin Elmer and PrimerDesign |  |  | 10000 | 172500 |  | 10000 | 20000 | 192500 |
| *Conservative estimates based on cost of test in USD, EXW ($19.80 for Cepheid, $19 for Abbott, $16 for Roche and $15 for Thermo Fisher) with additional 15% cost for freight, insurance and quality assurance; these will be updated on a rolling basis to update budgets as more information is known |  |  |  |  |  |  |  |  |  |  |
| **Conservative estimates with additional 15% cost for freight, insurance and quality assurance; these will be updated on a rolling basis to update budgets as more information is known |  |  |  |  |  |  |  |  |  |  |

Optional: Please detail out below any needs for additional platforms beyond what is existing in your country that may be required to deliver your COVID-19 testing strategy.

ThermoFisher SCIENTIFIC QuantStudio™12K Flex - the price is 123,440 USD Thermo Fisher Scientific QuantStudio 12K 384 W TWR was selected as high throughput machine

| Optional: Please provide a description of any other diagnostic-specific health products that may be required to deliver your COVID-19 testing strategy. [Applicant response]. Optional: Please provide a description and indicative budget for any technical assistance needed to implement your COVID-19 diagnostics strategy. [Applicant response]. Notes and references: Note: COVID-19 diagnostics will be procured and utilized in full compliance with the requirements for health products in the relevant grant agreement. Reference: For a Diagnostics procurement framework reference, see Global Fund HIV Viral Load and Early Infant Diagnosis Selection and Procurement Information Tool; whilst developed for viral load, many of the concepts are applicable to COVID-19 diagnostics. |
| --- |
| https://www.theglobalfund.org/media/5765/psm_viralloadearlyinfantdiagnosis_content_en.pdf?u=637166002690000000 |  |  |

xcvxcv

https://www.who.int/emergencies/diseases/novel-coronavirus-2019/technical-guidance/covid-19-critical-items

Interventions to mitigate the impact of COVID-19 on HIV, TB and malaria programs should  be informed by the COVID-19 Technical Guidance Pages published and regularly updated on the Global Fund website www.theglobalfund.org/en/covid-19/technical-guidance/

Early response investments must be in line with WHO recommendations and could include, but are not limited to: COVID-19 response planning, preparation and surveillance (Technical Assistance, in-country planning missions, meetings, M&E investments); Protection of front-line health workers including those working for Global Fund programs (PPE, hospital infection control products, set up of isolation and quarantine wards); Diagnosis of infection (lab equipment and lab consumables, lab staff, specimen transportation); Treatment (ancillary treatment, equipment, hospital beds, systems for home-based care).

Initiatives to make urgent improvements in health and community systems should focus on interventions required to adapt to COVID-19, enabling the maintenance and impact of existing HIV, TB and malaria programs, and supporting the country’s COVID-19 response (including with respect to laboratory

networks, supply chains and engagement with vulnerable communities). These interventions should draw on the appropriate COVID-19 Technical Guidance Pages.

https://www.theglobalfund.org/en/funding-model/applying/materials/