Annex 2 – DRG Implementation Plan in Georgia 2016-2018

| DRG IMPLEMENTATION IN GEORGIA |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PHASE | PACKAGE | ACTIVITY | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| 1. PILOT PHASE - YEAR 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1. ORGANIZE THE PROJECT |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Project kick-off meeting |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Organize project team (local and international) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Identify Steering Committee |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 | Identify with stakeholders technical working groups |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5 | Hospital site visits |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6 | Assessment of the current situation of each hospital |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2. AR-DRG CLASSIFICATION SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Sign Deed of Confidentiality for evaluation licence of AR-DRG system (for 18 months) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Decide and procure the long term licence for AR-DRG system |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Procure the classification package (manuals and electronic lists) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 | Translate the tabular list of procedures from English to Georgian |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5 | Get a mapping of the Georgian list of procedures to ACHI |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6 | Deploy the classification materials (primarily the list of procedures) to all hospitals |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 7 | Adapt the patient paper documentation to accommodate the new coding system for diagnosis and procedures |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 8 | Training of local trainers in Coding and AR-DRG classification, done by international trainers |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 9 | Training of all hospitals representatives by the local trainers (2-3 persons for each hospital) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 10 | Training of all doctors by the hospital trainers |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 11 | Monitor and support for hospitals to improve the coding performance |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3. DRG DATA COLLECTION |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Adapt all hospitals' software to collect the new codes for diagnosis and procedures for each discharged patient |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Adapt SSA's software to receive the new patient data set |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Design a new schedule for data collection at central level (e.g. monthly reporting of discharged patitents) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 | Collect administrative and clinical patient data set for each discharged patient in each hospital |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5 | Monitoring, technical assistance for hospitals, improving data collection performance |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4. DRG GROUPING & GROUPING SOFTWARE |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Buy a grouper licence for evaluation / pilot period |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Buy a grouper licence for long term use |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Integrate the grouper with SSA data collection software |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 | Group all patients |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5 | Analise grouping results and send feedback to hospitals |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5. DRG TRAINING |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Training of local trainers in DRG principles by international trainers |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Training of hospital representatives by local trainers |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Participation of stakeholders / decision makers in study tours in other countries having a DRG system in place |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 | Participation of beneficiaries in international DRG conferencies |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5 | Participation of beneficiaries in international DRG courses |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6 | Capacity building for local stakeholders and beneficiaries |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6. DRG TOP-DOWN COSTING |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Design top-down costing methodology adapted to Georgian data availability |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Train hospitals for cost data collection |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Collect cost data |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 7. CALCULATION OF RELATIVE VALUES AND PRICING |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Calculation of DRG relative values - case-mix cost modelling |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Design pricing policies |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 8. DRG FUNDING POLICIES AND LEGISLATION |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Design hospital funding policies for case-based payment |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Develop transition strategy (management and budgeting) for succesful transition to case-based payment |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Design specific hospital contrats for DRG reimbursement |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 | Adapt health legislation to allow and support sistem changes required by DRG implementation |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 9. COMMUNICATION CAMPAIGN |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Communication campaign to obtain hospital support and participation to DRG implementation |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | DRG dissemination conference and consensus building |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Public dissemination of results (web based, printed, electronic media etc) |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. IMPLEMENTATION PHASE - YEAR 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Start using "basic" DRG hospital financing principles - January 1st, 2017 ("budget neutral like") |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1. SUPPORT FOR DRG REPORTING AND REIMBURSEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Technical assistenace for SSA in the ongoing process of DRG payment |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2. PATIENT LEVEL COSTING |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Design top-down costing methodology adapted to Georgian data availability |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Buy a software licence for patient level costing |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Train hospitals for cost data collection |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 | Collect patient level cost data |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5 | Calculate patient level costs |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3. REFINE THE DRG RELATIVE VALUES |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Refine the DRG relative values based on the patient level cost study |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Refine pricing policies |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4. REFINE FUNDING POLICIES |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Adjust and refine funding policies |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5. CAPACITY BUILDING FOR A DRG UNIT |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Capacity building for a DRG Unit |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. FINE TUNNING AND SUSTAINABILITY PHASE - YEAR 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Start using "advanced" DRG hospital financing principles - January 1st, 2018 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1. FINE TUNE THE FUNDING POLICIES |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Study and implement DRG funding adjustments (outliers, inclusion/exclusion of services etc.) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2. PRACTICAL MEASURES FOR A SUSTAINABLE DRG SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Study related to aligning incentives across other types of care settings (in terms of deliery and payment) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Linking the output based payment system to performance indicators |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Creating an auditing and monitoring system to monitor fraud and abuse |  |  |  |  |  |  |  |  |  |  |  |  |