TERMS OF REFERENCE

Monitoring progress towards universal health coverage:

generating new evidence on financial protection in health systems in Europe

Short description: FP data analysis GEO

Background

The WHO Barcelona Office for Health Systems Strengthening has embarked on a multi-year project to monitor financial protection in health systems across WHO’s European Region. The broad aims of the project are to strengthen the evidence base on universal health coverage and to support policy development at national and regional levels.

National experts in Greece are preparing an assessment of financial protection in Greece using a new approach developed by the WHO Barcelona Office. New household budget survey data for 2017 became available at the end of 2018.

Objectives and expected outputs

- To gain access to the 2016 and 2017 household budget survey data for Georgia

- To analyse the 2016 and 2017 survey data using do files supplied by WHO

- To use the statistical results obtained from this analysis to update appendix tables

- To review the draft report on financial protection in Georgia once it has been updated by WHO

Timetable

| Deliverables | Delivered within |
| --- | --- |
| - Acquire the new survey data | 1 month of start of project |
| - Analyse the 2016 and 2017 household budget survey data using STATA and the do files supplied by WHO and submit the relevant log files to WHO | 1 month of start of project |
| - Add 2016 and 2017 results to the appendix tables | 1 month of start of project |
| - Review the draft report on financial protection in Georgia which will be revised by WHO and respond to any queries | 3 weeks of receipt of draft report and any queries |

The contract begins on 10 June 2019 and ends on 15 December 2019.

Skills required

The national expert(s) are expected to have a very good understanding of health financing policy in their country, experience of using statistical packages to analyse quantitative data (preferably Stata) and experience of analysing household survey data. Familiarity with national household budget survey data is essential.

Payment

The rate of payment is USD 2,000 per national expert.

Payment will be made in two instalments:

- upon submission to and acceptance by WHO of the log files and updated appendix tables (USD 1,000)

- upon submission to and acceptance by WHO of a review of the revised country report and responses to any queries from WHO and a financial statement (USD 1,000)

Person responsible for the WHO contract

Sarah Thomson, Senior Health Financing Specialist, WHO Barcelona Office for Health Systems Strengthening, thomsons@who.int