| Sector PRIORITY: Introducing and institutionalizing GRB in the planning and budgeting system in Georgia as a key contribution to operationalize the state guarantees for supporting and ensuring gender equality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GOAL 1: Introduce and institutionalize GRB systematically in the planning and budgeting system in Georgia as a key contribution to operationalize the state guarantees for supporting and ensuring gender equality. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Impact Indicator 1.1: System to focus on planning and public allocations for gender equality and women’s empowerment is effectively implemented by all institutions and agencies |  |  |  |  |  |  |  | Baseline | Target |  |  |  |  | Verification Sources: - Budget Programs - SAO external audit reports |  |  |  |
|  |  |  |  |  |  |  |  |  | Midterm |  |  | Final |  |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2019 | 2021 |  |  | 2025 |  |  |  |  |  |
|  |  |  |  |  |  |  | Value | In 5 min. | In all ministries in least one budget program |  |  | In all ministries and agencies fully implemented |  |  |  |  |  |
| Impact Indicator 1.2: Well identified gender equality and women’s empowerment goals is visible throughout the planning and budgeting documents |  |  |  |  |  |  |  | Baseline | Target |  |  |  |  | Verification Sources: - Budget Program annex |  |  |  |
|  |  |  |  |  |  |  |  |  | Midterm |  |  | Final |  |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2019 | 2021 |  |  | 2025 |  |  |  |  |  |
|  |  |  |  |  |  |  | Value | ? | In 1 budget program per ministry |  |  | In all relevant budget programs |  |  |  |  |  |
| Impact Indicator 1.3: Data on allocations for gender equality and women’s empowerment is made public in Gender Budget Summary statement |  |  |  |  |  |  |  | Baseline | Target |  |  |  |  | Verification Sources: - Budget Program annex |  |  |  |
|  |  |  |  |  |  |  |  |  | Midterm |  |  | Final |  |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2019 | 2021 |  |  | 2025 |  |  |  |  |  |
|  |  |  |  |  |  |  | Value | 0 | Including 1 budget program per ministry |  |  | Including all relevant budget programs |  |  |  |  |  |
| OBJECTIVE 1.1: Effective coordination of GRB work between all involved institutions and agencies in place |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Relevance to SDGs: SDG 5 |  |  |  |
| Outcome Indicator(s) 1.1.1: GRB Coordination Group in frame of inter-agency Commission for Gender Equality is operational and staffed |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  |  | Verification Sources: - Report of the Inter-Agency Commission on Gender Equality |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Final |  |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2019 |  | 2021 |  | 2025 |  |  |  |  |  |
|  |  |  |  |  |  |  | Value | By mid 2019: yes |  | yes |  | yes |  |  |  |  |  |
| Risk: No or too few resources for staff or lack of commitment for effective coordination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  |  | Other | Deficit |
| 1.1.1 (I level) | Secretariat at IA Commission for Gender Equality for GRB coordination is operational | 1.1.1.1 | Secretariat staff is hired |  |  |  |  |  |  | Mid 2019 | Staff cost (3 full-time) |  |  |  |  |  |  |
|  |  | 1.1.1.2 | Mandate is adopted |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | GRB Coordination Group at political level is established and mandate is adopted | 1.1.2.1. | Regular meetings of GRB Coordination group (at political level (bi-monthly in first year, every 3-4 months in subsequent years) | Minutes | IA Commission |  |  |  |  | Mid 2019 | Administrative budget |  |  |  |  |  |  |
| 1.1.3 | GRB Coordination Group at technical level is established and mandate is adopted | 1.1.3.1. | Regular meetings of GRB Coordination group (at a technical level take place (monthly meetings) | Minutes | IA Commission |  |  |  |  | Mid 2019 | Administrative budget |  |  |  |  |  |  |
| 1.1.4 | Overall guidance document on practical implementation of GRB methodology is elaborated | 1.1.4.1. | Overall guidance document on practical implementation of GRB methodology is adopted | Guidance document | IA Commission |  |  |  |  | Mid 2019 | Administrative budget |  |  |  |  |  |  |
| OBJECTIVE 1.2: Effective coordination of GRB work within ministries and agencies in place |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Relevance to SDGs: SDG 5 |  |  |  |
| Outcome Indicator(s) 1.2.1: Effective coordination of GRB work within ministries and agencies in place |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  |  | Verification Sources: |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Final |  |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2018 |  | 2021 |  | 2025 |  |  |  |  |  |
|  |  |  |  |  |  |  | Value | 3 ministries |  | All min |  | All min |  |  |  |  |  |
| Risk: no or too few resources for staff or lack of commitment for effective coordination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  |  | Other | Deficit |
| 1.2.1 (I level) | GRB Coordinator at ministry level established | 1.2.1.1 | GRB coordinator is working Option 1: Existing staff to be retrained Option 2: New staff hired | Staff plan of Ministries | Each ministry |  |  |  |  | Mid 2019 | Staff cost (1 staff) |  |  |  |  |  |  |
| 1.2.2 | ToR of Program Budget WG is extended to include GRB coordination function | 1.2.1.2 | ToR if Program Budget WG includes clear mandate for GRB coordination function | ToR of WG | Each ministry |  |  |  |  | Mid 2019 | Administrative budget |  |  |  |  |  |  |
| 1.2.3. | Strategic programs and budget programs of highest and high gender equality relevance are selected | 1.2.1.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OBJECTIVE 1.3: GRB Work is fully implemented within ministries and agencies to advance gender equality |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Relevance to SDGs: SDG 5 |  |  |  |
| Outcome Indicator(s) 1.3.1: GRB approach is applied in budget program preparations |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  |  | Verification Sources: |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Final |  |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2019 |  | 2021 |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Value | 3 |  |  |  |  |  |  |  |  |  |
| Risk: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  |  | Other | Deficit |
| 1.3.1 (I level) | Strategic programs and budget programs of highest and high gender equality relevance are selected | 1.3.1.1 | List of budget programs with highest and high gender equality is available |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.3.1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | GRB methodology is applied to selected budget programs | 1.3.2.1. | Budget programs include well defined gender equality objectives, indicators, activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.3.2.2. | Adequate financing of activities to promote gender equality is secured |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome Indicator(s) 1.3.2: Progress is regularly monitored within ministries |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  |  | Verification Sources: |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Midterm |  |  |  |  |  |
|  |  |  |  |  |  |  | Year |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Value |  |  |  |  |  |  |  |  |  |  |
| Risk: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  |  | Other | Deficit |
| 2.3.1 (I level) |  | 2.3.1.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2.3.1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OBJECTIVE 1.4: A focus on gender equality and women’s empowerment is well integrated in the planning process |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Relevance to SDGs: |  |  |  |
| Outcome Indicator(s) 1.4.1: Share of ministries and agencies with a focus on gender equality and women’s empowerment in the strategies and action plans within their responsibilities |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  |  | Verification Sources: |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Midterm |  |  |  |  |  |
|  |  |  |  |  |  |  | Year |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Value |  |  |  |  |  |  |  |  |  |  |
| Risk: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  |  | Other | Deficit |
| 1.4.1 (I level) | Develop guidelines to fully include a focus on gender equality and women’s empowerment in strategies and action plans | 1.3.1.1 | GRB guidelines part of general guidelines on planning |  | Administration of the Government |  |  | IA Commission for Gender Equality |  |  |  |  |  |  |  |  |  |
|  |  | 1.3.1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.2 | Develop guidelines to fully include a focus on gender equality and women’s empowerment in BDD | 1.4.2.1. | BDD guidelines include focus on gender equality and women’s empowerment |  | MoF Administration of the Government |  |  | IA Commission for Gender Equality |  |  |  |  |  |  |  |  |  |
| 1.4.3 | Adequate training on implementing guidelines is provided | 1.4.2.2. | Capacity available in responsive units within ministries and agencies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OBJECTIVE 1.5: A focus on gender equality and women’s empowerment is well integrated in the budgeting process: The GRB implementation is specified in a clear and concrete way so that all institutions involved can effectively work and contribute towards full integration of GRB in their planning and budgeting activities. |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Relevance to SDGs: |  |  |
| Outcome Indicator(s) 1.5.1: Gender equality and women’s empowerment is a visible focus in budget programs |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  | Verification Sources: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Midterm |  |  |  |  |  |
|  |  |  |  |  |  |  | Year |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Value |  |  |  |  |  |  |  |  |  |  |
| Risk: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  |  | Other | Deficit |
| 1.5.1 (I level) | Strategic programs and budget programs of highest and high gender equality relevance are selected | 1.5.1.1 | List of budget programs with highest and high gender equality is available |  | IA Commission for Gender Equality |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 2.5.1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.2 | GRB methodology (budget programs to include well defined gender equality objectives, indicators, activities and adequate financing) is provided to ministries and agencies | 1.5.2.1 | GRB methodology available |  | IA Commission for Gender Equality |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.3 | Ministries and agencies have adequate resources to apply GRB approach | 1.5.3.1. | Budget programs of highest and high gender equality relevance have fully integrated GRB approach |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OBJECTIVE 1.6: The results of GRB work are visible and information is made public in a timely and accessible manner |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Relevance to SDGs: |  |  |
| Outcome Indicator(s) 1.6.1: Gender Budget Summary Statement is developed and added to the Budget Program Annex of the annual draft budget |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  | Verification Sources: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Midterm |  |  |  |  |  |
|  |  |  |  |  |  |  | Year |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Value |  |  |  |  |  |  |  |  |  |  |
| Risk: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  |  | Other | Deficit |
| 1.6.1 (I level) | Guidance on template for GRB summary statement is prepared | 1.6.1.1 | Guidance on template for GRB summary statement is available to ministries |  | IA Commission on Gender Equality |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.2 | Ministries and agencies elaborate GRB part of budget programs and submit GRB summary statement table to coordinating body | 1.6.2.1. | For each program of highest and high relevance for gender equality a Gender Budget Summary table is available |  | All ministries and agencies |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.3 | IA Commission on GE compiles GRB Summary Statement and submits it to MoF | 1.6.3.1. | GRB Summary Statement is part of budget program annex |  | IA Commission on Gender Equality and MoF |  |  |  |  |  |  |  |  |  |  |  |  |
| OBJECTIVE 1.7: An effective monitoring and evaluation mechanism is in place and carried out regularly |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Relevance to SDGs: |  |  |
| Outcome Indicator(s) 1.7.1: Regular internal monitoring and evaluation results are available to show progress and detect gaps and problems with regard to gender equality |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  | Verification Sources: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Midterm |  |  |  |  |  |
|  |  |  |  |  |  |  | Year |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Value |  |  |  |  |  |  |  |  |  |  |
| Risk: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  |  | Other | Deficit |
| 1.7.1.1 (I level) | Guidelines for internal audit are adapted to include GRB auditing | 1.7.1.1 | Guidelines including GRB auditing are adopted |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.7.1.2 | Guidelines including GRB auditing are used in all ministries |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.1.2 | Internal audit procedures at ministry level include GRB focus | 1.7.2.1. | Audit reports include section on GRB and gender equality |  | Ministries and agencies |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome Indicator(s) 1.7.2: Regular government level monitoring and evaluation results are available to show progress and detect gaps and problems with regard to GRB implementation |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  | Verification Sources: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Midterm |  |  |  |  |  |
|  |  |  |  |  |  |  | Year |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Value |  |  |  |  |  |  |  |  |  |  |
| Risk: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  |  | Other | Deficit |
| 1.7.2.1 (I level) | Develop a methodology for GRB monitoring | 1.7.2.1 | Methodology for GRB monitoring is adopted |  | IA Commission on Gender Equality |  |  | Administration of the Government and MoF |  |  |  |  |  |  |  |  |  |
|  |  | 1.7.2.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.2.2 | Carry out regular government level GRB monitoring |  | Results of government level GRB monitoring provide information on progress and room for improvement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome Indicator(s) 1.7.3: Regular external audit results are available to show progress and detect gaps and problems with regard to GRB AP implementation |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  | Verification Sources: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Final |  |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2019 |  | 2021 |  | 2025 |  |  |  |  |  |
|  |  |  |  |  |  |  | Value | 0 |  | Audit report available |  | Audit report available |  |  |  |  |  |
| Risk: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  |  | Other | Deficit |
| 1.7.3.1 (I level) | Develop a methodology for GRB auditing based on AP indicators | 1.7.3.1 | Methodology for GRB auditing is adopted |  | SAO |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.3.2 | Carry out regular external GRB audits | 1.7.3.2 | Results of external audit provide information on progress and room for improvement |  | SAO |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Share of recommendations of external audit which are implemented |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7.3.3 | Option: Process of involvement of CSOs and international organisations in external auditing is set up | 1.7.3.3. | Report with recommendations by CSOs / intl. org. is in place |  | IA Commission on Gender Equality (SAO) |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Recommendations are implemented |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OBJECTIVE 1.8: Officials involved in GRB work have adequate capacities |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Relevance to SDGs: |  |  |
| Outcome Indicator(s) 1.8.1: Officials carry out GRB work professionally in their regular work and deliver high quality results |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  | Verification Sources: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Midterm |  |  |  |  |  |
|  |  |  |  |  |  |  | Year |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Value |  |  |  |  |  |  |  |  |  |  |
| Risk: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  |  | Other | Deficit |
| 1.8.1. (I level) | GRB Training of trainers | 1.8.1.1. | Group of trainers is capacitated |  | IA Commission on Gender Equality |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1.8.1.2 | Core group of GRB experts is established |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.8.2. | GRB training and support program is established | 1.8.2.1. | Training program in place |  | Civil Service Bureau |  |  | Training Centers of the Ministries |  |  |  |  |  |  |  |  |  |
| 1.8.3. | Training program is implemented | 1.8.3.1. | Share of training program implemented |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Number of officials trained |  |  |  |  |  |  |  |  |  |  |  |  |  |  |