| Sector PRIORITY: Introducing and institutionalizing GRB in the planning and budgeting system in Georgia as a key contribution to operationalize the state guarantees for supporting and ensuring gender equality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GOAL 1: Introduce and institutionalize GRB systematically in the planning and budgeting system in Georgia as a key contribution to operationalize the state guarantees for supporting and ensuring gender equality and thus contribute to effective resource allocation and high quality service delivery. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Impact Indicator 1.1: Share of Ministries/Agencies having system to focus on planning and public allocations for gender equality and women’s empowerment which is effectively implemented |  |  |  |  |  |  |  | Baseline | Target |  |  |  |  | Verification Sources: - Budget Programs - SAO external audit reports |  |  |
|  |  |  |  |  |  |  |  |  | Midterm |  |  | Final |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2019 | 2020 |  |  | 2022 |  |  |  |  |
|  |  |  |  |  |  |  | Value | 30% | 50% |  |  | 100% |  |  |  |  |
| Impact Indicator 1.2: Progress on state gender equality and women’s empowerment goals is visible by improvements in relevant indicators |  |  |  |  |  |  |  | Baseline | Target |  |  |  |  | Verification Sources: - SDG reports |  |  |
|  |  |  |  |  |  |  |  |  | Midterm |  |  | Final |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2019 | 2020 |  |  | 2022 |  |  |  |  |
|  |  |  |  |  |  |  | Value |  |  |  |  |  |  |  |  |  |
| OBJECTIVE 1.1: Ensure effective coordination of GRB work between and within all involved institutions and agencies in place |  |  |  |  |  |  |  |  |  |  |  |  |  | Relevance to SDGs: SDG 5 |  |  |  |
| Outcome Indicator(s) 1.1.1: GRB Coordination Group in frame of inter-agency Commission for Gender Equality is adequately staffed |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  | Verification Sources: - Report of the Inter-Agency Commission on Gender Equality |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Final |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2019 |  | 2020 |  | 2022 |  |  |  |  |
|  |  |  |  |  |  |  | Value | None (0 staff) |  | Yes: 2 full time staff |  | Yes: 3 full time staff |  |  |  |  |
| Outcome Indicator(s) 1.1.2: GRB Coordination Group in frame of inter-agency Commission for Gender Equality is working effectively so that all involved institutions have clear guidelines and knowledge on what to do |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  | Verification Sources: - Report of the Inter-Agency Commission on Gender Equality - Feedback from ministries and agencies |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Final |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2019 |  | 2020 |  | 2022 |  |  |  |  |
|  |  |  |  |  |  |  | Value | By mid 2019: yes |  | yes |  | yes |  |  |  |  |
| Outcome Indicator(s) 1.1.3: Share of Ministries/Agencies having GRB coordinators officially assigned and effective coordination of GRB work within ministries and agencies in place |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  | Verification Sources: |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Final |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2018 |  | 2020 |  | 2022 |  |  |  |  |
|  |  |  |  |  |  |  | Value | 0% |  | 50% |  | 100% |  |  |  |  |
| Risk: no or too few resources for staff or lack of commitment for effective coordination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  | Other | Deficit |
| 1.1.1 (I level) | To establish and make operational Secretariat at IA Commission for Gender Equality for GRB coordination | 1.1.1.1 | Secretariat staff is hired | Mandate; staff contracts |  |  |  |  |  | 2nd quarter, 2019 | Staff cost (3 full-time) |  |  |  |  |  |
|  |  | 1.1.1.2 | Mandate is adopted |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.2 | To establish GRB Coordination Group at level of deputy ministers and adopt mandate | 1.1.2.1. | Regular meetings of GRB Coordination group (at political level (bi-monthly in first year, every 3-4 months in subsequent years) | Minutes | IA Commission |  |  |  |  | 2nd quarter, 2019 | Administrative budget |  |  |  |  |  |
|  |  | 1.1.2.2. | Regular review of progress, updated work plans, and recommendations issued are available |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1.3 | To establish GRB technical coordination Group and adopt mandate | 1.1.3.1. | Regular meetings of technical GRB Coordination group take place (monthly meetings) | Minutes | IA Commission |  |  |  |  | 2nd quarter, 2019 | Administrative budget |  |  |  |  |  |
| 1.1.4 | To elaborate overall guidance document on practical implementation of GRB methodology | 1.1.4.1. | Overall guidance document on practical implementation of GRB methodology is adopted | Guidance document | IA Commission |  |  |  |  | 2nd quarter, 2019 | Administrative budget |  |  |  |  |  |
| 1.1.5 | To establish GRB Coordinator at ministry level to be officially part of the Program Budget WG | 1.1.5.1 | GRB coordinator is working Option 1: Existing staff to be retrained Option 2: New staff hired | Staff plan of Ministries | Each ministry |  |  |  |  | Mid 2019 | Administrative budget |  |  |  |  |  |
| 1.1.6 | To officially include GRB Coordinator in Program Budget WG | 1.1.6.1 | ToR of Program Budget WG includes GRB coordination in its mandate | ToR of WG | Each ministry |  |  |  |  | Mid 2019 | Administrative budget |  |  |  |  |  |
| OBJECTIVE 1.2: A focus on gender equality and women’s empowerment is well integrated in the planning process |  |  |  |  |  |  |  |  |  |  |  |  |  | Relevance to SDGs: SDG 5 |  |  |  |
| Outcome Indicator(s) 1.2.1: Share of policy documents (strategies and Action Plans) proved by GOV with gender issues addressed and at least one goal/objective and outcome level indicators in gender equality and women’s empowerment related issues |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  | Verification Sources: - Policy documents - Report by IA Commission for Gender Equality |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Midterm |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2018 |  | 2020 |  | 2022 |  |  |  |  |
|  |  |  |  |  |  |  | Value | ? |  | 50% |  | 80% |  |  |  |  |
| Risk: Lack of attention on gender equality and women’s empowerment issues |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  | Other | Deficit |
| 1.2.1 (I level) | Develop guidelines to fully include a focus on gender equality and women’s empowerment in strategies and action plans | 1.3.1.1 | GRB guidelines part of general guidelines on planning | Guidelines | Administration of the Government |  |  | IA Commission for Gender Equality |  |  |  |  |  |  |  |  |
|  |  | 1.3.1.2 | Share of ministries which apply guidelines |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 | Develop guidelines to fully include a focus on gender equality and women’s empowerment in BDD | 1.4.2.1. | BDD guidelines include focus on gender equality and women’s empowerment | BDD | MoF Administration of the Government |  |  | IA Commission for Gender Equality |  |  |  |  |  |  |  |  |
|  |  | 1.4.2.2. | Gender equality and women’s empowerment well visible in BDD in terms of indicators and priorities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3 | Adequate training on implementing BDD guidelines is provided | 1.4.2.2. | Capacity available in responsive units within ministries and agencies | Reports | Administration of the Government |  |  | IA Commission for Gender Equality |  |  |  |  |  |  |  |  |
| OBJECTIVE 1.3: GRB implementation is specified in a clear and concrete way so that all institutions involved work and contribute effectively towards full integration of GRB with a focus on gender equality and women’s empowerment in their activities |  |  |  |  |  |  |  |  |  |  |  |  |  | Relevance to SDGs: SDG 5 |  |  |
| Outcome Indicator(s) 1.3.1: Share of Ministries/Agencies having GRB guidelines applied in budget program preparations and a visible focus on gender equality objectives and indicators in budget programs |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  | Verification Sources: |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Final |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2018 |  | 2020 |  | 2022 |  |  |  |  |
|  |  |  |  |  |  |  | Value | 3 (=%?) |  | 50% |  | 100% |  |  |  |  |
| Risk: Lack of priority on and attention to GRB implementation. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  | Other | Deficit |
| 1.3.1 (I level) | Strategic programs and budget programs of highest and high gender equality relevance are selected | 1.3.1.1 | List of budget programs with highest and high gender equality is available | List of budget programs selected | IA Commission for Gender Equality |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | To provide ministries and agencies with GRB practical guidance and adequate support | 1.3.2.1 | GRB practical guidance available in all ministries and agencies | Report | IA Commission for Gender Equality |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.3 | Ministries and agencies have adequate resources to apply GRB approach | 1.3.3.1. |  |  | Ministries/Agencies |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.5 | To apply GRB guidelines to selected budget programs | 1.3.2.1. | Budget programs of highest and high gender equality relevance include well defined gender equality objectives, indicators, activities | Budget program annex | Ministries/Agencies |  |  |  |  |  | Administrative budget |  |  |  |  |  |
|  |  | 1.3.2.2. | Adequate financing of activities to promote gender equality is secured |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OBJECTIVE 1.4: Increase accessibility of information on the results of GRB |  |  |  |  |  |  |  |  |  |  |  |  |  | Relevance to SDGs: SDG 5 |  |  |
| Outcome Indicator(s) 1.4.1: Gender Budget Summary Statement is developed and added to the Budget Program Annex of the annual draft budget |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  | Verification Sources: - Budget Program Annex |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Midterm |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2018 |  | 2020 |  | 2022 |  |  |  |  |
|  |  |  |  |  |  |  | Value | no |  | yes |  | yes |  |  |  |  |
| Risk: Lack of cooperation from Ministry of Finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  | Other | Deficit |
| 1.4.1 (I level) | Prepare guidance on template for GRB summary statement | 1.4.1.1 | Guidance on template for GRB summary statement is available to ministries | Guidance document | IA Commission on Gender Equality |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.2 | Elaborate GRB part of budget programs and submit GRB summary statement table to coordinating body by ministries and agencies | 1.4.2.1. | For each program of highest and high relevance for gender equality a Gender Budget Summary table is available | Submissions of ministries | All ministries and agencies |  |  | IA Commission on Gender Equality |  |  |  |  |  |  |  |  |
| 1.4.3 | IA Commission on GE compiles GRB Summary Statement and submits it to MoF | 1.4.3.1. | GRB Summary Statement is available and submitted to MoF | GRB Summary Statement | IA Commission on Gender Equality and MoF |  |  | MoF |  |  |  |  |  |  |  |  |
| 1.4.4 | MoF adds GRB Summary Statement to budget program annex for submission to Parliament | 1.4.4.1. | GRB Summary Statement is part of budget program annex | Budget Program Annex | MoF |  |  |  |  |  |  |  |  |  |  |  |
| OBJECTIVE 1.5: An effective monitoring and evaluation mechanism is in place and carried out regularly |  |  |  |  |  |  |  |  |  |  |  |  |  | Relevance to SDGs: SDG 5 |  |  |
| Outcome Indicator(s) 1.5.1: Share of Ministry/Agencies in which progress on GRB is regularly monitored within ministries by internal monitoring |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  | Verification Sources: - Internal reports |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Midterm |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2018 |  | 2020 |  | 2022 |  |  |  |  |
|  |  |  |  |  |  |  | Value | 0 |  | 50% |  | 100% |  |  |  |  |
| Risk: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  | Other | Deficit |
| 1.5.1. (I level) | Adapt internal audit guidelines to integrate GRB | 1.5.1.1 | Guidelines including GRB auditing are adopted | Internal Audit Guidelines Internal audit reports | ? |  |  | Ministries/Agencies |  |  |  |  |  |  |  |  |
|  |  | 1.5.1.2 | Share of ministries/agencies using guidelines including GRB auditing |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.2. | Carry out internal audit procedures at ministry level with GRB focus | 1.5.2.1. | Audit reports include section on GRB and gender equality with specific recommendations | Internal audit reports | Ministries and agencies |  |  |  |  |  |  |  |  |  |  |  |
| Outcome Indicator(s) 1.5.2: Regular government level monitoring and evaluation results are available to show progress and detect gaps and problems with regard to GRB implementation |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  | Verification Sources: |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Midterm |  |  |  |  |
|  |  |  |  |  |  |  | Year |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Value |  |  |  |  |  |  |  |  |  |
| Risk: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  | Other | Deficit |
| 1.5.2.1 | To develop a methodology for GRB monitoring | 1.5.2.1 | Methodology for GRB monitoring is adopted |  | IA Commission on Gender Equality |  |  | Administration of the Government and MoF |  |  |  |  |  |  |  |  |
|  |  | 1.5.2.1 | Process of government level GRB monitoring is defined |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.2.2 | To carry out regular government level GRB monitoring | 1.5.2. | Results of government level GRB monitoring provide information on progress and room for improvement |  | IA Commission on Gender Equality |  |  | Administration of the Government and MoF |  |  |  |  |  |  |  |  |
| Outcome Indicator(s) 1.5.3: Regular external audit results are available to show progress and detect gaps and problems with regard to GRB AP implementation |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  | Verification Sources: - SAO Audit |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Final |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2019 |  | 2020 |  | 2022 |  |  |  |  |
|  |  |  |  |  |  |  | Value | 0 |  | SAO Audit report available |  | SAO Follow-up audit report available |  |  |  |  |
| Risk: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  | Other | Deficit |
| 1.5.3.1 (I level) | Include GRB AP in regular auditing schedule | 1.5.3.1 | GRB AP auditing in SAO work plans for 2020 and 2022 |  | SAO |  |  |  |  | First GRB AP auditing: 2020 Follow-up auditing 2022 | Administrative budget |  |  |  |  |  |
| 1.5.3.2 | Carry out regular external GRB audits | 1.5.3.2 | Results of external audit provide information on progress and recommendations to involved institutions for improvement | Audit report | SAO |  |  |  |  |  |  |  |  |  |  |  |
| 1.5.3.3 | Implement recommendations issued by SAO | 1.5.3.3. | Share of recommendations of external audit which are implemented | Report on implementation Follow-up audit report | Ministries and agencies |  |  | IA Commission on Gender Equality |  |  |  |  |  |  |  |  |
| 1.5.3.4 | Option: Set up process of external review of GRB work involving PDO, CSOs and international organisations | 1.5.3.4. | Report with recommendations by CSOs / PDO / intl. org. is in place | External review report | IA Commission on Gender Equality |  |  | PDO |  |  |  |  |  |  |  |  |
|  |  |  | Share of recommendations implemented |  | Ministries and agencies |  |  |  |  |  |  |  |  |  |  |  |
| OBJECTIVE 1.6: Public Servants involved in GRB work have adequate capacities to carry out high quality GRB work in planning and budgeting |  |  |  |  |  |  |  |  |  |  |  |  |  | Relevance to SDGs: SDG 5 |  |  |
| Outcome Indicator(s) 1.6.1: Officials carry out GRB work professionally in their regular work and deliver high quality GRB results in planning and budgeting (share of ministries) |  |  |  |  |  |  |  | Baseline |  | Target |  |  |  | Verification Sources: - Budget Program Annex - Assessment by GRB coordination body |  |  |
|  |  |  |  |  |  |  |  |  |  | Midterm |  | Midterm |  |  |  |  |
|  |  |  |  |  |  |  | Year | 2018 |  | 2020 |  | 2022 |  |  |  |  |
|  |  |  |  |  |  |  | Value | 0 |  | 50% |  | 100% |  |  |  |  |
| Risk: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity |  | Output Indicator(s) |  | Verification Source |  | Responsible Agency |  | Partner Agencies |  | Completion Deadline | Projected Budget (GEL) |  | Funding Source |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | State Budget |  | Other | Deficit |
| 1.6.1. (I level) | Organize at least 2 GRB Trainings of trainers | 1.6.1.1. | Group of trainers is capacitated |  | IA Commission on Gender Equality |  |  |  |  | 2019 |  |  |  |  |  |  |
|  |  | 1.6.1.2 | Core group of GRB experts is established |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.2. | Establish GRB training and support program | 1.6.2.1. | GRB training and support program over whole AP period is in place | Training program | IA Commission on Gender Equality & Civil Service Bureau |  |  | Training Centers of the Ministries |  | By end of 2019 |  |  |  |  |  |  |
| 1.6.3. | Implement training program | 1.6.3.1. | Share of training program implemented | Training reports Assessment questionnaires |  |  |  |  |  | 2019/2020 and continued |  |  |  |  |  |  |
|  |  | 1.6.3.2. | Number/Share of officials with adequate GRB capacities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6.4. | Provide support activities (on a call-in basis) for GRB work by GRB group of experts | 1.8.4.1. | Number of support consultancies requested by ministries/agencies per year | Activity Report | IA Commission on Gender Equality |  |  |  |  | ongoing |  |  |  |  |  |  |