1

good afternoon ladies and gentlemen, dear guests. i am honored to be here today and  present some achievements that we reached since launching the most important program in Georgia elimination hepc

My presentation is devoted to the current and planned activities of the main phase of the program - DECENTRALIZATION AND INTEGRATION OF HCV SERVICES IN PRIMARY CARE, HOSPITALS AND HARM REDUCTION SETTINGS IN GEORGIA.

2

to reach the elimination targets is the main goal of the Hepatitis C State Program. As most of the attendees are aware here, the target indicators are 90-95-95 by 2020, which means that 90% of people are diagnosed with Hepatitis C, 95% among them are treated and 95% among them are cured.

3

The program was launched on April 20, 2015 and has began for the patients suffering from severe liver damage. then in several months has been expanded and  now is available for all Georgian citizens. there have been made many changes within the program since launching. such as simplifing inclusion criteria in the program, simplifing diagnostic algorithm, developing electronic database of hepatitis management etc.

From the beginning of the program implementation more then 54 000 HCV patients were registered, more then 53 000 out of registered patients have already started treatment and more than 49 000 completed treatment. cure was achieved in 98,2% of cases.

4

these are impressive figures, but at this stage the program faces such serious problem as Declined enrollment in the treatment program (In last period, we have been observing gradual decrease of patient’s inflow (about 1000 patients per month) and Limited provider capacity and a scarcity of treatment centers in some geographic and especially in rural areas

The program has began with the provision of services in 4 service providers in 2015, the number of which increased to 31 by 2017. It should be noted that the majority of suppliers (15) were located in Tbilisi, 4 in Kutaisi, 2-2 in Batumi, Zugdidi, Guria and Shida Kartli, 1 Kvemo Kartli, 1 in Kakheti. Obviously, there was no fair distribution of services, and in some regions there was no service provider at all.

5

In response to these challenges, there has been developed objectives, such as, increase the geographical availability through decentralization of screening, care and treatment services and enhancing financial access through simplification of diagnostic algorithms and minimize cost of diagnostic test.

6

for developing and implementing decentralization concept several working groups were established under the ministry. in particular, primary health care/hospital group, harm reduction group and oversight and coordination group. within the groups were developed action plans for decentralization. we launched the project in June 2018 and presented first progress report to tag in November 2018.

7

Decentralization means establishing minimum one HCV service provider, especially in primary health care and harm reduction centers, in each municipality and cities of local governance, to provide geographical access as much as possible.  All centers, will ensure comprehensive service delivery within diagnostics and treatment components.

8-9

The stages of decentralization can be seen in the following way:

- Selection of providers

- Evaluating of providers

- Equipping of providers

- Staff training

- Registration of providers

- Launch of the program

10

in order to choose service providers, we have developed some selection criteria. the first condition is, that the service provider should be operated as an Outpatient service provider within UHC Program. among them we choose centers with maximum numbers of active patients.

it should be taken into consideration hcv prevalence in region/municipality (with priority on maximum figures) and current situation for hcv care access (is there any provider or not in this region/municipality). another criteria are equipping of providers (some of them are fully equipped, and some needs to be given a hand).

at selection stage priority should be given also to mental health providers, to clinics with their own requests and to the concept of micro elimination, which means to cover all municipality in region.

11

The next step after the selection is supplier evaluation by the group of monitoring, which include checkup regulatory requirements (such as license of clinics or doctors etc.), programs requirements (special room, security guard etc.) and equipment’s (computer, fireproof safe, camera etc.)

12

after all these checkups coming the steps of equipping the clinics, if it is needed (it might be realized by themselves, by donors or by the government), then registration providers at social service agency, staff training (technical and clinical part) and launch the program.

13-14

as I mentioned, decentralization launched in June 2018 and we started it with a pilot project. within pilot four primary health care providers started Integrating HCV screening and simplified treatment services (SENAKI, TBILISI, KHASHURI, TELAVI).

15-16

next was first phase of decentralization. within first phase there were 8 new clinics included as service providers, 4 of them are Primary Health Care facilities ( Akhalkalaki, Akhaltsikhe, Kobuleti, Poti), and 4 of them are Harm Reduction sites (2 in Tbilisi, Zugdidi, Batumi).

17

on this slide you can see expansion process of service providers, total number of service providers by regions including newly opened primary health care and harm reduction centers.

18-19

now let me show you some examples for progress reporting. senaki and telavi are municipalities with almost the same numbers of population, one in samegrelo zemo svaneti region and another in kakheti region. hcv prevalence in this regions are different. we have high burden of hepc in samegrelo zemo svaneti, about 7,2% of population and about 3.2% in Kakheti

20

here is care cascade from senaki and telavi primary health care centers. Maybe these are not high figures but it is very important that these beneficiaries will get the full services near their homes.

21-22

Another example is for harm reduction sites. ksenoni is a harm reduction center in zugdidi, samegrelo zemo svaneti region. as I already mentioned hcv prevalence here is very high, the number of registered beneficiaries at this site is about 370.

imedi is harm reduction center in batumi, adjara region. hcv prevalence is about 5,4% in this region. and the number of registered persons at this site is about 500.

23

here are care cascade from these harm reduction centers. maybe these are not high figures, but it is very important that these beneficiares will get the full services in trusted areas

24

Another important point of decentralization is to reduce the financial barrier. on the next two slides you can see how cost of diagnostic tests for patients was change through years. should be noted that cost significantly decreased in 2018, when we started decentralization project and simplified diagnostic algorithms for this reason.

25

In order to ensure successful linkage to care we planned some activities Within the decentralization project.

- Decentralization of confirmatory testing – like Lugar center, service providers are allowed to conduct confirmatory tests of patients with screening-positive results;

- The relevant units of the NCDC are obliged to ensure surveillance of HCV positive patients revealed by screening testing;

- The relevant units of the SSA are obliged to ensure patient navigator services after confirmatory testing;

- The right to seek and attract HCV positive patients (approved by confirmatory testing) are given to service providers.

27

in conclusion let me  briefly summarize progress towards decentralization :

- HCV screening widely accessible at all levels

- Point of care –

- RNA confirmatory testing is available and free of charge

- HCV genotype testing is available and free of charge

- Expansion of the area of beneficiaries - Cost of the diagnostic tests for war and military veterans is covered by 70% within the state program.

- introduction of the new generation hepatitis C treatment medicine Epclusa (Sofosbuvir/velpatasvir) is already done and Vosevi (Sofosbuvir/velpatasvir/voxilaprevir) – in the nearest future

- Simplified diagnostic and treatment protocols adopted for general health settings and harm reduction centers

- training program for PHC physicians developed and approved

- Training for PHC and Hospital staff has been launched

- ECHO platform is utilized for training and care decentralization support

- HCV elimination program database is modified in response to HCV care decentralization needs

28

Thank you for your attention.