ROLLING WORK-PLAN No 3. TO TWINNING GRANT CONTRACT Twinning Project “Improving the standards of employment conditions/relations as well as health and safety at work in Georgia“ Twinning number: GE 17 ENI OT 02 19 WORK-PLAN AND BUDGET FOR THE PERIOD: 7th July – 6th January, 2021

Contracting Authority

Jurate Juodsnukyte

Delegation of the European Union to Georgia

64b Chavchavadze Avenue

0179 Tbilisi, Georgia

General remark:

This 3rd Rolling Work Plan issues from the Twinning Proposal “Improving the standards of employment conditions/relations as well as health and safety at work in Georgia”, which is an Annex 02b of the Twinning Grant Contract No. ENI/2019/409 - 668, taking into consideration rules of the Twinning Manual (revision 2017 - update 2018) and its Annex C15: Template for rolling work-plan.

According to the Twinning Manual (revision 2017 - update 2018), Section 5.2, the key initial task of the Project is elaboration of the initial work-plan, which is considered the first rolling work-plan covering at least the first six months. This initial rolling work-plan is the basis for the effective and timely implementation of the whole project. It stipulates detailed description of particular project activities, methods of their implementation, indicators, human resources and timing saturation.

ARTICLE 1: Objective

The Member State Project Leader Mr. Branislav Ondruš and the Beneficiary Project Leader Mrs. Tamila Barkalaia hereby notify the Contracting Authority of the detailed work-plan and budget of the above-mentioned Twinning Grant Contract for the 6 -month period from 7th July 2020 to 6th January, 2021.

ARTICLE 2: Tasks (Inputs)

Budget Heading - RTA and related expenses

Indicators and benchmarks agreed:

-  timely and correct implementation of project activities in accordance to initial work plan

ensured

-  administrative management and mission backstopping, as well as translation and

interpretation services ensured by RTA assistants

Budget Heading – Horizontal costs

Sub-heading Steering Committee Meetings

Indicators and benchmarks agreed:

- 3rd Rolling WP is prepared and signed

- SCM is conducted to TW regulations

Activity 0.2. Steering Committee meeting

Method:

The MS Project Leader and Junior MS Project Leaders will dedicate at least 2 days per quarter for the management of the project during 24 months of the implementation period. This will include the SC meetings on a quarterly basis. This approach will guarantee the implementation is overseen and any difficulties are resolved immediately without any delay in timing.

During the period covered by the 3rd  Rolling work-plan the fourth  Steering Committee meeting will be organised in October/November, 2020, promote effective management and monitoring of the project activities. Progress in the areas of the project’s interventions will be discussed with the beneficiary and the members of the SC.

Apart from these meetings, it is planned that the Project Leaders, RTA and RTA counterpart, on both sides, will carry out the necessary preparatory activities essential for the proper functioning of the SC.

Resources

- Member State human resources needed: 3 MS experts, 6 WDs / 1 mission

Mr Branislav Ondrus HB, Mr Jose Ignacio Martin Fernandez HB, Ms Ulla Saar HB

- Beneficiary administration human resources: SC members: EUD, PAO, BC PL, RTA Counterpart, invited staff of the Labour and Employment Policy and Collective Labour Disputes Division of MoIDPHLSA, Labour Conditions Inspecting Department,

- Other resources: 0

Communication and Information

Public awareness campaign was prepared and designed for implementation of the World OSH Day. Details can be find in act.2.2.2.

Indicator(s) and benchmark(s) agreed: Work plan plus Communication and Visibility plan preparation

Budget Heading - Mandatory Results / Components

Component 1/Mandatory result 1: Approximation of primary and secondary legislation related to Labour Law, Gender Equality, and Occupational Safety and Health in accordance with the Union acquis

Indicators of achievement:

Status of the legal basis allowing for a labour inspection system covering standard labour rights and working conditions

Baseline: Legal basis is incomplete, in need of further elaboration

Target: The legal basis allowing for a labour inspection system covering standard labour rights and working conditions elaborated to the end of the project implementation.

In progress. Target partially achieved. The amendments of the Labour Code submitted to the Parliament and went through the first reading. Law on Labour Inspection submitted to the Parliament and went through the first reading.

Status of amendments in the field of Labour Law, Gender Equality, and Occupational Safety and Health as per Union acquis, with an inclusive and evidence-based approach.

Baseline: Delay in harmonisation of the legal framework  covering standard labour rights and working conditions reflected in amendments of the relevant laws

Target: Legal amendments prepared in the field of Labour Law, Gender Equality, and Occupational Safety and Health as per Union acquis, with an inclusive and evidence-based approach until the end of the project.

In progress. Target partially achieved. The amendments of the Labour Code submitted to the Parliament and went through the first reading. Law on Labour Inspection submitted to the Parliament and went through the first reading.

Sub-result 1.1:

Legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis

Number of the Tables of Concordance prepared for the Labour Law acquis, including aspects of labour inspection system

Baseline: 7   ToC

Target   : 8 Toc prepared until June 2020

Target achieved. 1 Table of Concordance of the Council Directive 91/383/EEC of 25 June 1991 supplementing the measures to encourage improvements in the safety and health at work of workers with a fixed- duration employment relationship or a temporary employment relationship was developed and completed.

List of amendments to be made in the Georgian primary and secondary labour legislation specified with explanatory notes

Baseline: 3

Target   : 8 Directives until the end of 2020

Target achieved. 4th version of the Compliance Report of Amendments to the draft Organic Law of Georgia the Labour Code with 8 Directives in the field of the Labour Law was prepared during the reporting period. All versions were submitted to the BA as well as to the representatives of the Parliament, the initiators of the amendments. All reports have included main findings, recommendations for the amendments, good practise and the recent CJEU law. Reports were submitted to the DG Employment and the ETF which provided additional comments

Sub-result 1.2:

Legal framework on non-discrimination and gender equality, including aspects of labour inspection system, amended in compliance with the Union acquis

List of amendments to be made in the  Georgian primary and secondary legislation on Gender Equality acquis specified with explanatory notes

Baseline: 2

Target   : 4 Directives  until July 2020

Target achieved. 2 table of Concordance of  Council Directive 2004/113/EC implementing the principle of equal treatment between men and women in the access to and supply of goods and services and Council Directive 79/7/EEC on the progressive implementation of the principle of equal treatment for men and women in matters of social security were elaborated and a level of harmonisation was assessed.

Share of staff from relevant public institutions who are fully informed on regulatory and fiscal impact of changes in labour law and gender equality acquis

Baseline: 0

Target   : 90% of staff in LCID and LEPD until the end of 2020

In progress. Activities to contribute to fulfilment of the Indicator were not planned during the reporting period.

Sub-result 1.3:

Legal framework on OSH, including aspects of labour inspection system, amended in compliance with the  Union acquis

Availability of quality checked translation of the OSH acquis with clear technical terminology (if necessary)

Baseline:  9

Target   : Quality check of 13 Directives until the end of the project

In progress. Target partially achieved. In total quality of 4 EU Directives improved.

- Quality of Directive 89/656/EEC on minimum safety and health requirements for the use of personal protective equipment was checked and improved

- Quality of Directive 92/58/EEC on minimum requirements for the provision of safety and health and/or health sign at work was checked and improved

- Quality of Directive 2009/104/EEC on minimum requirements for the use of work equipment by workers at  work was checked and improved

- Quality of Directive 89/654/EEC on minimum requirements for the use of workplace was checked and improved

Availability of the Tables of Concordance prepared for the OSH acquis, including aspects of labour inspection system

Baseline:  5

Target   :  13 ToC  prepared until the end of the project

No significant progress. Activities to contribute to fulfilment of the indicator were planned during this reporting period but finally not conducted.

Availability of the list of amendments to be made in the Georgian primary and secondary OSH legislation specified with explanatory notes

Baseline:  2

Target   : amendments related to 13 Directives prepared until the end of the project implementation

No significant progress. Activities to contribute to fulfilment of the indicator were planned during this reporting period but finally not conducted.

Share of staff from relevant public institutions who are fully informed on regulatory and fiscal impact of changes in OSH acquis

Baseline:   0

Target   : 90% of staff in LCID and LEPD until the end of the project implementation

No significant progress. Activities to contribute to fulfilment of the indicator were planned during this reporting period but finally not conducted.

Activity 1.1.1: Aligning Georgian legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis

Method

The objective of this activity is providing support of the BC staff and relevant stakeholders to the transposition of the provisions of the relevant EU Directives in the field of labour legislation into a national legislation.

During a previous period, harmonisation of the labour code with “labour directives” was finalised. Proposals for amendments of the primary and secondary legislation were  submitted, explained and discussed with the representatives of the MoIDPLHSA (Ms Irma Geliashvili and advisors of the Ministry) as well as with the team of ILO and Mr Tskitishvili. Taking into consideration the current state of play, the amendments of the Labour Code were prepared and submitted to start the legislation process.  4 versions of the Assessment of the amendments were prepared based on the package of 10 EU Directives (to be adopted in 2018 – 2020 as per AA/DCFTA) which has not been transposed yet.

In the EU-Georgia “Sub-Committee Cluster -6” meeting on 13 February 2020 in Tbilisi, where the DG EMPL gave an update of new EU Directives in the field of employment. Some of these new developments at the EU level would replace directive from the Annex XXX in the EU-Georgia association Agreement, and creates a need for approximation for Georgia as well.

This activity in this reporting period will be focused on assessment of the 2 table of Concordances with Labour Code to be approved in September:

- EC Directive 2019/1152 on Transparent and Predictable Working Conditions (June 2019), which repeals the directive 91/533 and effects the way online platforms operate in the EU

- EC Directive 2019/1158 on Work-life balance for Parents and Carers (April 2019), which repeals the directive 2010/18/EU and others on parental leave

Due to an outbreak of COVID - 19 and restriction measures applied this activity will be implemented exclusively remotely.

Outputs:

2 ToC

Resources

- Member State human resources allocated: 4 MS experts, 20 WDs / 4 missions:

Jozef Toman 5 WD/1 mission HB, Maros Palik 5 WD/1 mission HB; Seili Suder 5WD/1mission HB, Marillis Proos 5WD/1 mission HB;

- Beneficiary administration human resources: all together around 20; staff of the Labour and Employment Policy and Collective Labour Disputes Division of MoIDPHLSA, Labour Conditions Inspecting Department, Technical working group members; social partners and other relevant stakeholders; specialists/ experts from the relevant institutions on the topic

- Other resources: 0

Provisional timeschedule of the missions:

Last 2 weeks of October: Jozef Toman 5 WD HB, Maros Palik 5WD HB;

Last 2 weeks of November : Seili Suder 5WD/1mission, Marillis Proos 5WD/1 mission

Activity 1.2.1: Analysis / Assessment of current legal framework on non-discrimination and gender equality including aspects of Labour Inspection System, in order to amend it in compliance with the EU aquis

Method

The objective of this activity is providing support of the BC staff and relevant stakeholders to the transposition of the provisions of the relevant EU Directives in the field of labour legislation into a national legislation.

Taking into consideration the current state of play, the amendments of the Labour Code were submitted to start the legislation process.  Assessment of the amendments were prepared based on the package of 8 EU Directives (to be adopted in 2018 – 2020 as per AA/DCFTA) which has not been transposed yet.

This activity will be focused on finalisation of the 2 ToC in close cooperation with the beneficiary.

Activities to be delivered will cover the following EU Directives to be adopted in 2018, 2019 and 2020 as per AA/DCFTA:

- 2004/113/EC implementing the principle of equal treatment between men and women in the access to and supply of goods and services

- 79/7/EEC on the progressive implementation of the principle of equal treatment for men and women in matters of social security

Outputs:

- Final version of the Table of Concordance 2004/113/EC implementing the principle of equal treatment between men and women in the access to and supply of goods and services completed

- Final version of the able of Concordance on Directive 79/7/EEC on the progressive implementation of the principle of equal treatment for men and women in matters of social security completed

Resources

- Member State human resources allocated: 1 MS Experts, 5WD/1 mission

Jose Ignacio Martin Fernandez 5 WD/1 mission HB;

- Due to an outbreak of COVID - 19 and restriction measures applied this activity will be implemented exclusively remotely.

- Beneficiary administration human resources: all together around 20; staff of the Labour and Employment Policy and Collective Labour Disputes Division of MoIDPHLSA, Labour Conditions Inspecting Department, Technical working group members; social partners and other relevant stakeholders; specialists/ experts from the relevant institutions on the topic

- Other resources: 0

Provisional time schedule of the missions:

Last  week of August: Jose Ignacio Martin Fernandez 5 WD HB

Activity 1.3.1: Aligning Georgian legal framework on Occupational Health and Safety, including aspects of Labour Inspection System, amended in compliance with the Union acquis:

Method

The objective of this activity is providing support of the BC staff and relevant stakeholders to the transposition of the provisions of the relevant EU Directives in the field of non-discrimination and gender equality legislation into a national legislation.

Based on the original planning 4 missions were planned to be conducted in the 2nd reporting period but were postponed to March and April, 2020. Due to a restriction measures of pandemic the missions weren’t implemented during a previous reporting periods, but were re planned into this period.

Taking into consideration the current state of play, there are 4 EU Directives from the package of 15 EU Directives (to be adopted in 2019 – 2020 as per AA/DCFTA) which have been identified as a priority to be transposed, were postponed  and will be dealt with during the implementation of the 3rd  work plan:

- 89/656/EEC on minimum safety and health requirements for the use of personal protective equipment – postponed from a previous work plan

- 92/58/EEC on minimum requirements for the provision of safety and health and/or health sign at work – postponed from a previous workplan

- 2009/104/EC on minimum safety and health requirements for the use of work equipment by workers at work

- 92/57/EEC on minimum safety and health requirements at temporary or mobile construction sites – based on request of the beneficiary

Moreover, during a previous reporting period the additional task was requested by the Beneficiary’s Project Partner the Makhviladze  Scientific - Research Institute of Occupational Medicine and Ecology with the consent of the BI-  to provide an expertise on the functioning the System of the Occupational Medicine in a selected  member states, focused on medical examinations (prior and periodic) in relation to work; diagnosis and treatment of occupational diseases, work-related illnesses and the consequences of accidents at work as well as identifying factors of work and working environment, performing their measurement, qualification and evaluation. Review on the functioning the System of the Occupational Medicine was submitted and translated. There is a possibility to conduct I week mission for presentation and discussion of the Review.

This activity will be focused on applying the general concept of transposition process, in accordance with the following pattern:

Shortened methodology for harmonisation

The specific procedure of implementation of this activity is based on the methodology described in the Project proposal, as well as the Rolling Work Plan No 2 – Activity 1.3.1. The Activity links to the Technical Assistance Project to VET and Employment Reforms in Georgia implemented during 2015-2017. In the frame of that project the initial steps of transposition of mentioned Directives were done. Elaborated documents from 2016-2017 can be revised and used for this activity in order to simplify current procedure.

Procedure

- Initially it is essential to ensure an important thing, called “ownership”. It means that the beneficiary is conscious of their task and accepting their responsibility in transposition of mentioned Directives and leading legislation process of new harmonised Regulations. It requires the beneficiary will nominate (appoint) one Coordinator, fully responsible for whole process, being active in organising all steps of transposition; being a contact person with Project experts providing support to BC; leading a Technical Working Group.

- The process of transposition shall be implemented in cooperation and consensus with social partners and other stakeholders. Working method – work in the Technical Working Group (TWG), appointed by beneficiary. The composition of the TWG is attached in annex. The nominated persons shall be conscious of their task of active participation at the process, be available and follow the deadlines. The Coordinator of Activity is a chair of the WG.

- The procedure of transposition and preparation of harmonised draft Regulation is described in project documents (Project Proposal, Rolling Work Plan), as well as the Guideline elaborated in frame of previous project – “Concept of harmonisation of OSH legislation in Georgia 2017” (attached in GEO). The detail description can be simplified and summarized as follows:

- Elaboration of a Comparative table (comparing the text of Directive and eventual related provisions of current national legislation

- Introduction meeting for WG members (familiarizing with principles of the Directive and concept of approximation

- Elaboration first draft of Regulation

- WG meeting – mutual detail revision of the text of draft Regulation – article by article

- Elaboration a final version of Regulation

- Verification and confirmation of final version by Beneficiary

- Elaboration Table of Concordance (ToC)

- Submission the final version of Regulation and ToC for further legislation process (public comments, reasoning, fiscal impact assessments, etc.)

Mutual cooperation with Project experts will require translation of documents of particular steps and interpretation of meetings. The fine-tuning of Regulation wording shall be carried out in Georgian language. The final output is determining in Georgian language.

- Taking into account the special situation and restriction measures relating with COVID-19, as well as already developed materials of previous Project of the Technical Assistance, as well as above mentioned structure we will proceed as follows,

- we already have the final draft regulation elaborated in December 2015. We will work with this version (Draft 15) as an initial one. We just need to verify it from point of view of new GEO legislation, adopted since 2016.

- a) WG members should initially read the relevant Directive, to refresh the content of this basic document

- b) STE will prepare the Comparative Table - not with EU Directive, but with our Draft 15 on left side, and right side of the Table will be empty.

- c) WG members are required to go through the Table – particular provisions and if they recognise any paragraph, which is in similar sense – used in other current law of regulations, they should find the document and write its wording into the Table in the relevant cell. We expect, it will be not very much similarities – nevertheless estimation of the load is about 4 hours.

- d) Based on this input of the working group members the working draft Regulation will be updated – on the base of Draft 15 and the findings of adequate wording in other legislation,

- e) Working group meeting – verifying the text of working draft Regulation. Members will meet and the work will be coordinated and led by the Coordinator. The text will be displayed from PC on the wall (screen), coordinator will read the text Article by Article and WG members can discuss and confirm the text. All comments shall be solved by consensus – if any problem, TWG members  can vote. (Note, that final comments will be done in public comments procedure,  if this procedure is applied). Due to already discussed version of draft Regulation (in 2015), we expect, it will go much faster than in 2015 (it lasted 3 days). Now we estimate 6-7 hours. During the TWG meeting STEs will be available (on line) if it would be necessary to explain what is needed. The result of TWG meeting will be the final draft of the Regulation.

- f) Afterwards STEs will prepare the Table of Concordance of the EU Directive – new Regulation), which is necessary for legislative process. On the other hand, probably the ToC will be done after the public consultation. This will be an output of our activity. Next steps are on lawyers of the Legislation department, according procedures of national legislation.

- g) STE will be available to consult any issue raised during this process online (due to Covid-19)

- Detailed time schedule of each directive will be attached to each mission plan

During the whole transposition process the participation of the following departments, institutions and partners are considered essential in the implementation of this activity: MoIDPLHSA - Labour and Employment Policy and Collective Labour Disputes Division; Labour Conditions Inspecting Department; Technical and Construction Supervision Agency (TCSA), MoESD; The Tripartite Social Partnership Commission (TSPC); Representatives of social partners;

Outputs:

- 4 Tables of Concordance prepared for the OSH acquis, including aspects of labour inspection system;

- 4 regulations prepared for further legislation specified with explanatory notes;

- 4 Quality checked translation of the OSH acquis with clear technical terminology (if necessary) completed;

- Table of Concordance to the Government Decree No.477 on safety requirements for working at height 92/57/EEC on minimum safety and health requirements at temporary or mobile construction sites

Resources

- Member State human resources needed: 7 MS experts, 43 WDs /9 missions

Ivan Majer  13 WD/3 missions HB, Laurencija Jancurova 5 WD/ 1 mission HB, Tomas Criado Navamuniel 5WD /1 mission HB, Eva Poldis 5WD /1mission (home based), Ulla Saar 5 WD/1 mission, HB,  Michal Nemec 5 WD/1 missions in the BA Slavomir Stastny 5 WD/1 missions in the BA,

- Due to an outbreak of COVID - 19 and restriction measures applied this activity will be implemented remotely, with exemption of the mission for Makhviladze Scientific - Research Institute of Occupational Medicine and Ecology, it is advisable to be implemented face to face. If not possible, remotely.

- Beneficiary administration human resources: around 30; Staff of the Labour Conditions Inspecting Department of MoIDPHLSA, Technical working group members; social partners and other relevant stakeholders

- Other resources: Translation of Regulations and relevant texts, 40 pages, Interpretation 5 WD /200,-EUR

Provisional timeschedule of the missions:

Last two weeks of September:  Ivan Majer  5 WD HB, Ulla Saar 5 WD HB,Tomas Criado Navamuniel 5WD /1 mission HB,  Michal Nemec 5 WD in the BA country, Slavomir Stastny 5 WD in the BA country

last 2 weeks of October: Ivan Majer 5 WD home based, Eva Poldis 5 WD home based, Laura Jancurova 5 WD HB

First 2 weeks of November: Ivan Majer 8 WD/2 missions HB, Ulla Saar 5WD/1 mission, HB

Budget Heading - Mandatory Results / Component

Component 2: Capacity building, inter-institutional cooperation, and awareness raising of relevant state authorities and private sector for full implementation of amended legislation in labour law, gender equality and OSH

Indicators of achievement:

Status of operational plans and administrative procedures of the MoIDPLHSA and other relevant stakeholders to be amended in accordance with the new requirements

In progress. Started. Activities to contribute to fulfilment of the Indicator were not planned during the reporting period.

Baseline: Operational guidelines, manuals and procedures outdated and in need of amendments based on further harmonisation

Target: Operational plans and administrative procedures of the MoIDPLHSA and other relevant stakeholders amended in accordance with the new requirements until the end of the project implementation

Share of participants in capacity building activities

In progress. Started. Activities to contribute to fulfilment of the Indicator were not planned during the reporting period.

Baseline: Staff development needs partially analysed.

Target: The relevant staff of the MoIDPLHSA and other stakeholder representatives trained for the implementation of new legal framework until the end of the project implementation.

Sub-result 2.1:

Analysis for strengthening state authorities’ capacity for implementation of the EU best practices performed and required strategies developed

Functional review of the relevant state authorities to implement changes, including human and financial resources, administrative structures and equipment needed

Baseline: 0

Target   : 1 Functional review completed until June 2020

Target achieved. During the reporting period 2 missions focused on the development of the functional review were conducted, detailed mapping and assessment of the interinstitutional relationships between the various state and non-governmental actors dealing with the occupational health and labour relations were conducted. Functional review will be completed in the next reporting period.

Training needs analysis and plan of the whole staff of beneficiary department and representatives from other relevant institutions listed

Baseline: 0

Target   : 1 Training needs analysis completed until June 2020

Target achieved. Evaluation of the TNA analysis was completed including the design of the training.

Sub-result 2.2:

Implementation of the EU best practices regarding the amended legislation piloted and awareness of the citizens and private sector on the topic increased

Share of BA staff who received training to implement necessary changes and the representatives from other relevant institutions listed

Baseline: 10%

Target   : 90% of staff in BA and others  stakeholders until the end of the project implementation

In progress. Started. Delivery of targeted training for newly hired inspectors have been postponed due to a delay in the recruitment process. Starting in the 4th Reporting period (September 2020).

Number of labour inspectors who are trained more to become ‘trainers’ with full knowledge and competency in implementing new laws

Baseline: 0

Target   : 5 Trainers trained till the end of the project implementation

In progress. Activities to contribute to fulfilment of the Indicator were not planned during the reporting period.

Plan for improving institutional operations and procedures of the relevant state authorities to support their pilot implementation, each with clear competences and coordination roles

Baseline: 0

Target   : 1

Completed. Functional review submitted with recommendations and training plan.

Number of written operational guidelines, manuals and procedures required to implement all changes, explaining all steps of implementation to the relevant staff

Baseline: 0

Target    : At least 15 documents until the end of the project implementation

In progress. Started. The state of achievement is in line with the implementation of the Initial Work Plan – activities just have started during the reporting period without significant results to be compared.

Number of OSH online Glossary and Risk Assessment checklists and their dissemination to relevant parties

Baseline: 0

Target   : At least 20 related documents until the end of the project implementation

In progress. Started. Activities to contribute to fulfilment of the Indicator were not planned during the reporting period. However, first approaches have been discussed during this reporting period.

Number of elaborated promotional materials and public information campaigns in printed and online media, TV and other tools

Baseline:  5

Target   : 30 short written materials + 2 public campaigns until the end of the project implementation

In progress. Target partially achieved. 1st information campaign elaborated. 1 promotional video elaborated and transmitted via facebook of the MoIDLPHSA.

2nd Public awareness campaign including other communication tools foreseen to be prepared for October OSH week is going to be postponed due to elections.

Share of private companies (i.e. both employers and workers) which are informed and number of citizens reached out on the new rules and changes made in labour legislation

Baseline: 50

Target: 90% of registered companies informed until the end of the project implementation

In progress. Started. Activities due to COVID -19 pandemic were cancelled.

Proposal for a structure of inter-institutional cooperation and working procedures, with a review of existing options

Baseline: 0

Target   : 1

Completed. Functional review submitted

Sub-result 2.3:

Organisation of working group(s) on labour law, gender equality and OSH comprising line ministries and social partners completed and functional

Working groups operational with team members from relevant institutions with a clear mandate and their continuous involvement in the ‘Technical Working Group’ and ‘Coordination Group’

Baseline: 0

Target   : 2 working groups operational until the end of 2020

No progress: not started yet. Activities to contribute to fulfilment of the Indicator were postponed  during the previous reporting period.

Number of meetings facilitated for effective functioning of working groups through team building, training and expert inputs

Baseline: 0

Target   : at least 4 meetings a year

No progress: not started yet. Activities to contribute to fulfilment of the indicator was postponed  during the 2nd reporting period

Activity 2.1.1. Assessment of the administrative structures and institutional capacities of the beneficiary and relevant stakeholders and improvement of their inter-institutional operation

Activity was completed in 2nd reporting period and the days not spent will be reallocated to another activity.

Activity 2.1.2. Training needs analysis and strengthening the institutional capacity of the beneficiary and relevant stakeholders

Activity was completed in 3rd reporting period, in June, 2020.

Activity 2.1.3

Delivery of Training of Trainers of the labour inspectors

Activity was postponed.

Activity 2.1.4. Delivery of comprehensive training programmes to improve the institutional capacities of the beneficiary and relevant

Method

- New harmonised OSH legislation, new methodologies and guidelines, as well as new challenges for acting of beneficiaries’ staff involved in the approximation process as well as for labour inspectors require to provide specific broadly designed training with the aim of equal implementation, performance and enforcement.

- The activity should have been originally conducted in the period of February – May 2020 but the recruitment process of new inspectors was delayed and the initial training for at least 60 new inspectors and advanced training for 15 inspectors already working as inspectors was postponed as well. If the original assumption will be fulfilled and new labour inspectors hired both types of trainings is foreseen to be implemented since September. On request of the beneficiary, the methodology of the training will be based on face to face training, not for alternative e-learning methods.

Based on the training needs analysis and the request of the beneficiary the TW team propose two key training programmes:

- An intensive induction training for newly hired inspectors

- A refresher and advanced training for existing inspectors

Structure of the training modules to be delivered:

| TRAINING PLAN |  |  |  |
| --- | --- | --- | --- |
| Module | Unit | Hours | Target group |
| The role of labour inspection | UNIT 1.1 Functions of labour inspection | 8 | J / S |
|  | UNIT 1.2 Labour inspectors’ rights and obligations UNIT 1.3 Ethical code and safety considerations | 8 | J / S |
| Key areas and topics on EU Directives | UNIT 2.1: Key areas and topics in EU Directives on safety and health at work |  | J / S |
|  | Subunit 2.1.1 Health and safety requirements for the Workplace and Provision of safety and/or health signs at work | 16 | J / S |
|  | Subunit 2.1.2 Health and safety requirements for the use of work equipment by workers at work and for work with display screen equipment | 16 | J / S |
|  | Subunit 2.1.3 Health and safety requirements for use of personal protective equipment and manual handling of loads | 16 | J / S |
|  | UNIT 2.2: Key areas and topics on EU Directives on labour issues and gender equality |  | J / S |
|  | Subunit 2.2.1 Standards on working time | 16 | J / S |
|  | Subunit 2.2.2 National legislation on the information of employees | 8 | J / S |
|  | Subunit 2.2.3 Gender aspects in employment relationship | 8 | J / S |
| Identification of occupational hazards and preventive measures | UNIT 3.1 Physical agents | 16 | J / S |
|  | UNIT 3.2 Biological and chemical agents | 16 | J / S |
|  | UNIT 3.3 Mechanical and electrical hazards | 16 | J / S |
|  | UNIT 3.4 Ergonomic hazards | 16 | J / S |
|  | UNIT 3.5 Psychosocial hazards | 8 | J / S |
| Identification of risks and preventive measures in specific sectors | UNIT4.1 Mining | 8 | J / S |
|  | UNIT 4.2 Metallurgic sector | 8 | J / S |
|  | UNIT 4.3 Care sector | 8 | J / S |
|  | UNIT 4.4 Construction | 16 | J / S |
|  | UNIT 4.5 Retail | 8 | J / S |
|  | UNIT 4.6 Tourism | 8 | J / S |
| Performance of the tasks of labour inspection | UNIT 5.1: Labour inspection visit on OSH | 16 | J |
|  | UNIT 5.2: Labour inspection visit on labour and gender issues | 8 | J |
|  | UNIT 5.3: Integrated labour inspection visit | 8 | J |
| Creating professional documents | Module 6: Creating professional documents | 16 | J |
| Investigation of occupational accidents and diseases | UNIT 7.1 Investigation of occupational accidents: the procedure | 8 | J |
|  | UNIT 7.2 Investigation methodologies | 16 | J |
| Personal and social skills in inspection: emotional intelligence | Module 8: Personal and social skills in inspection: emotional intelligence | 24 | j/S |

Due to an outbreak of COVID - 19 and restriction measures applied we are willing and experts are ready to deliver face to face training.  All preparatory work will be done remotely. Face to face will depend on actual epidemiologic situation in the countries concerned. If further restriction measures will be applied, we continue in a remote mode. Potential changes in the budget will submitted through a side letter.

Outputs:

- 4 training modules for newly hired Labour inspectors fully trained:

- Module 1 The role of labour inspection: Unit 1.1., 1.2. 1.3.

- Module 2 Key areas and topics on EU Directives:  2.1.1.; 2.1.2.; 2.1.3.

- Module 3 : Identification of occupational hazards and preventive measures: 3.1.;3.2.; 3.3.

- Module 4: Identification of risks and preventive measures in specific sectors:4.3., 4.4., 4.5

- Module 5: Performance of the tasks of labour inspection: 5.1.

- Delivery of training for newly hired inspectors: 32 days of training delivered for 40 newly hired inspectors

- 3 training modules for senior inspectors developed:

- Modul 1 LI functions with a view to OSH enforcement

- Modul 2 The role of the LI

- Modul 3 Identify occupational hazards and preventive measures LI

- Delivery of training for senior inspectors: 4 days of training delivered for 16  inspectors

Resources

- Member State human resources needed: 9 MS experts, 197 WD / 20 missions

Consuelo Manchón García 40 WD / 3 missions, 19 WD of them HB;  José Ignacio Martín Fernández 40 WD / 3 missions,  19 of them HB, Gabriela Beltran Fernández  15 WD/3 missions,  Ms. Laurencia Jancurova 21 WD / 1 mission, 6 WD of them HB, Ivan Majer 21/1 mission, 6 WD of them HB; Tomas Criado Navamuniel 7 WD/1 mission, 2 WD of them HB; Silja Soon 23 WD/3 missions, 8 WD of them HB; Eneken Hiire 21WD /3 missions, 6 WD of them HB; Maria Mercedes Tejedor Aibar 9 WD/1 mission, 4 WD of them HB.

- Beneficiary administration human resources: Staff of the Labour Conditions Inspecting Department of MoIDPHLSA,

- Other resources: 0

Provisional timeschedule of the missions:

Last 2 weeks of September: Ms Consuelo Manchon Garcia   - 19 WD home based,  Jose Ignacio Martin Fernandez – 19 WD/1 mission home based,

First 3 weeks of October: Ivan Majer -  15 WD/1 mission,  Laurencia Jancurova – 15 WD

Last week of October and first week of November: Silja Soon – 15 WD, Eneke Hiire – 15 WD, Ms Maria Mercedes Tejedor Aibar – 9 WD/1 mission

Last 2 weeks of  November: Ms Consuelo Manchon Garcia   - 10 WD home based,  Jose Ignacio Martin Fernandez – 10 WD/1 mission home based, Mr Tomans Criado – 7 WD

First 2 weeks of September: : Ms Consuelo Manchon Garcia   - 5 WD/1 mission,  Jose Ignacio Martin Fernandez – 5 WD/1 mission, Silja Soon - 5 WD, 5 WD/1 mission

Last  week of December: Ms Silja Soon - 5 WD/1 mission,

2 weeks in December -  Jose Ignacio Martin Fernandez – 10 WD/1 mission, Consuelo Manchon Garcia - 10 WD/1 mission

Activity 2.2.1. Development of the relevant guidelines, labour inspection manuals, checklists and other tools to improve the institutional operations and procedures focused on precise implementation of newly adopted legislation

Method

The success of labour inspection performance depends on a good management, clear instructions, strict rules and standardised procedures. All processes shall be described and available for all inspectors and other relevant staff involved in the implementation of the newly adopted legislation. Therefore, suitable manuals and guidelines are essential.

Implementation of this activity is related to act. 1.3.1. Due to the harmonisation hasn’t started yet, this activity was postponed into a current period.

During these implementation period we will focus on development of operational guidelines and the check lists of the prioritised OSH Directives to be implemented and adapted to Georgian legal framework:

- 89/656/EEC on minimum safety and health requirements for the use of personal protective equipment

- 92/58/EEC on minimum requirements for the provision of safety and health and/or health sign at work

- 2009/104/EC on minimum safety and health requirements for the use of work equipment by workers at work

- During the implementation of the workplan 3 operational guidelines, 3 risks assessment checklists and the structure of OSH online glossary will be developed.

Outputs:

- Operational guidelines for personal protective equipment and relevant checklists developed

- Operational guidelines for safety and health and/or health sign at work and relevant checklists developed

- Additional guidelines on the request of the beneficiary

Resources

- Member State human resources allocated: 5 MS experts, 40 WD / 8 missions

Ivan Majer 5 WD/1 mission, Eva Poldis 10WD /2missions, Ulla Saar 10 WD/2 missions, Laurencia Jancurova 5 WD/1 missions, Jose Ignacio Martin Fernandez 10 WD/2 missions

- Due to an outbreak of COVID - 19 and restriction measures applied this activity will be implemented remotely.

Beneficiary administration human resources: Staff of the Labour Conditions Inspecting Department of MoIDPHLSA, social partners and other relevant stakeholders

- Other resources: Interpretation 5 WD ; Translation 12 x 50 pages = 600,- Eur

Provisional time schedule of the missions:

First 2 weeks of October:  Ulla Saar -  5 WD/1 mission home based,  Ms Eva Poldis  5 WD  home based, Laurencia Jancurova – 5 WD/1 mission home based

Last 2 weeks of October  - Jose Ignacio Martin Fernandez 10 WD/2 missions

Last 2 weeks of November : Ivan Majer 5 WD/1 mission, Eva Poldis 5WD /1mission, ,Ulla Saar -  5 WD/1 mission home based,

Activity 2.2.2. Preparing and implementing public information campaign aiming to raise awareness among the project among key stakeholders, public, private sector and civil society

Method

- Public awareness raising campaigns are an effective tool for increasing awareness of the private sector and citizens (companies, employers and workers) about legal changes, new requirements and practices, promoting occupational safety and health at the workplaces, increasing of awareness and motivation of employers and employees, as well as building a positive attitude of public. The project team attaches significance to this activity due to its comprehensive coverage and possibility of effective influence.

- During the previous 2 quarters a campaign on World OSH Day was prepared with the assistance of STE experts but due to a State of Emergency in Georgia printing of leaflets, posters and Opening Conference was postponed. An alternative short video was produced.

- Evaluation of the questionnaires were completed in the previous quarter and provide us a good knowledge what themes should be communicated in the campaigns.

- Second campaign for the OSH week will be postponed after elections.

- Mission of expert will be focused on the development of leaflets and brochures on promotion OSH.

Outputs:

- 2 leaflets prepared

Resources

- Member State human resources needed: 1 MS Experts, 10WD/ 2 missions face to face, in case of applied pandemic restrictions – remote.

- Branislav Ondrus 10 WD/2 missions

- Beneficiary administration human resources: Staff of the Labour Conditions Inspecting Department of MoIDPHLSA, social partners and other relevant stakeholders

- Other resources: 0

Provisional time schedule of the missions:

- Last 2 weeks of October:  Branislav Ondrus -  5 WD/1

- Last 2 weeks of November:  Branislav Ondrus -  5 WD/1

Activity 2.3.1.

Supporting inter-institutional cooperation in the process of approximation and implementation of the relevant EU acquis

Method

The inter-institutional cooperation is in the process of approximation and implementation of the relevant EU acquis one of the key elements which should ensure that developed policies and legislation (law making process) are implementable and meet government objectives.  Although the government regulations define the role and policy responsibilities of individual ministries (including their respective departments) they do not define the process or requirements for consultation, involvement of the different stakeholders in the policy development and level of cooperation.

During the initial phase of the project implementation the current institutional cooperation settings were reviewed, shortcomings were analysed and discussed with some members of the Technical Work Group (technical expertise staff including representatives of relevant stakeholders) who were involved regularly in the process of Directive´s transposition. A similar process will be done for the current members of the Coordination Group as well with the aim to ensure that inclusive, evidence-based policy and legislative development enables the achievement of intended policy objectives.

It seems the Technical working group members lacks of coordination and ownership in harmonising secondary legislation. We need to assist them in the inter-institutional cooperation through organising introductory sessions for both groups – TWG and CG as well. The proposal of the inter-institutional cooperation will be organised by a common residential meetings focused on attractive topics: 1) Economic aspects of occupational health and safety costs and losses of the economy due to accidents at work and occupational diseases, 2) financing of prevention, examples of good practice. 3) Employer liability insurance. Meaning and possible examples. Meetings will be used for discussion which kind of documents could meet their needs : description of the structure, clear mandate of the working group member, nomination of the working group member, description of the responsibilities, functions, professional requirements, guideline establishing clear relations and forms of cooperation.

Capacity building programme designed and implemented in the previous activities will be applied for these members as well, supported through the team building and other forms of participatory training.

Resources

- Member State human resources needed: 2 MS experts, 20 working days/4 missions will be allocated, face to face. In case of applied pandemic measures, homebased.

- Mr Branislav Ondrus 10/2 missions, Michal Nemec 10 WD/2 missions

- Beneficiary administration human resources: Staff of the Labour Conditions Inspecting Department of MoIDPHLSA, social partners and other relevant stakeholders

- Provisional time schedule of the missions:

- First 2 weeks of October: Mr Branislav Ondrus 5WD/1 mission, Michal Nemec 5 WD/1 mission

- First 2 weeks of November: Mr Branislav Ondrus 5WD/1 mission, Michal Nemec 5 WD/1 mission

ARTICLE 3: Risks

Specify/update the internal conditions related to the project that must be fulfilled to guarantee efficient and timely implementation and achievement of results.

| Risk | Corrective measures/ Mitigation |
| --- | --- |
| Unexpected national and international policy or jurisdiction changes affecting the objectives of the project, e.g. slowdown of structural reforms | Continuous policy monitoring in order to react early in project governance. Close and regular exchange between project partners. |
| Unexpected outbreak of COVID – 19 and restrictive measures applied causing the delay in implementation of project activities | New working methods (remote work, teleworking, videoconferencing and other innovative methods) agreed with the beneficiary to keep the project activities implemented |
| Inadequate commitment and support from decision making level in particular with regard to adoption of amended legislation, draft acts, guidelines and procedures | Close and regular exchange between project partners, in particular PL, JPL and RTA. Involvement of (MoIDPHLSA) decision-makers in workshops, consultations and presentations of output. |
| Unsuccessful beneficiary administration´s reorganization | Close and regular cooperation and communication between project partners. Regular Project Steering Committee meetings to inform on upcoming changes and if needed agree on actions to be taken. |
| Delay in implementation of project activities | Sufficient human and technical resources allocated in BC and MS administrations. Sound and joint planning of initial work plan. |

ARTICLE 4: Schedule

| Project Month 2020 | July | August | September | October | November | December |
| --- | --- | --- | --- | --- | --- | --- |
| Horizontal costs |  |  |  |  |  |  |
| Steering Committee |  |  |  |  |  |  |
| Component 0 |  |  |  |  |  |  |
| Activity 0.1 Kick-off |  |  |  |  |  |  |
| Activity 1.1.1 |  |  |  |  |  |  |
| Activity 1.1.2 |  |  |  |  |  |  |
| Activity 1.1.3 |  |  |  |  |  |  |
| Component 2 |  |  |  |  |  |  |
| Activity 2.1.1. | completed |  |  |  |  |  |
| Activity 2.1.2. | completed |  |  |  |  |  |
| Activity 2.1.3. |  |  |  |  |  |  |
| Activity 2.1.4. |  |  |  |  |  |  |
| Activity 2.2.1. |  |  |  |  |  |  |
| Activity 2.2.2. |  |  |  |  |  |  |
| Activity 2.2.3. |  |  |  |  |  |  |
| Activity 2.3.1. |  |  |  |  |  |  |

ARTICLE 5: Human Resources

| Member State or Beneficiary | Name | Present position | Employer | Years of experience | Education | Specialist knowledge | BC experience | Languages |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Slovakia 1 | JOSEF TOMAN | Director of the Legal department of the MoLSAF | Ministry of Labour, Social Affairs and Family, Slovakia | 17 | Comenius University of Bratislava | - Expert in industrial relations policy and practice; - Labour law and employment legislation, social dialog and collective bargaining; - Long-lasting experience with the transposition and implementation of the EU and the EP regulations and directives in the field of employment and social policy, social dialog and collective bargaining into the Slovak legislation | Slovak, English German | Serbia, Croatia, Romania, |
| Slovakia 2 | MAROS PALIK | Chief lawyer for labour relations | Regional Development Agency Senec-Pezinok, Slovakia | 16 | Faculty of Law, Comenius University, Bratislava, Slovak Republic | - Legal assistance in the field of labour law, labour law relations, individual and collective, anti-discrimination law - Legal analysis of labour legislation, anti-discrimination legislation and its alignment with the EC Directives related to labour relations acquis - Analysis of the labour code, occupational health and safety, employment, antidiscrimination, wage regulations and commitments arising from collective agreements, undeclared work - Member of the working group for amendment of the labour legislation in terms of undeclared work ( employment contract, fixed term part-time contract, atypical form of contracts, and development of the deterrence measures) | Slovak, English German | Georgia, Serbia |
| Slovakia 3 | IVAN MAJER | Advisor and Trainer | National Labour Inspectorate | 40 | Technical University, Faculty of Mechanical Engineering Kocise | - Profound knowledge, skills and experiences on occupational safety and health, prevention principles, risk assessment, - safety management, organisation of safety and health services, implementation of OSH legislation, OSH policies and OSH expertise | Slovak, English, Russian | Serbia, Croatia, Albania, Romania, Albania, Croatia, Kosovo, Turkish Cypriot Community, Turkey, Ukraine, Tunisia |
| Slovakia 4 | LAURENCIA JANCUROVA | Senior Inspector and the representative of Focal Point for European Agency for Health and Safety at Work | National Labour Inspectorate | 25 | Technical University, Faculty of Mining Engineering, Slovakia | - Profound experience in safety and health at work, prevention protection, risk management - unifying and rationalising of working methods of the labour inspectorates, - preparation of conceptual materials, programme materials and draft measures for improving the situation in the area of labour protection - development inspection manuals and instructions - implementation of OSHA activities at the national level | Slovak, English, Russian | Croatia, Albania, Romania, Albania, Croatia, Turkish Cypriot Community, Turkey, Ukraine, Tunisia |
| Slovakia 5 | Luba Pavlovova | Director/trainer | Regional Development Agency, Slovakia | 29 | Master in Engineering | - Highly experienced in implementing activities related to raising public awareness, management of several public campaigns - public awareness campaigns – preparation and implementation - development of the radio and TV spots, short documentary films, professional debate, round tables - training of trainers | English French Bulgarian Russian Serbian Croatian Czech Macedonian | Jordan, Croatia, Serbia, North Macedonia, BiH Romania Bulgaria Azerbaijan Albania Turkey Georgia |
| Slovakia 6 | Lubica turner | Trainer/methodologist | Regional Development Agency, Slovakia | 25 | Academic diploma MA in Education and Linguistics | - Extraordinary knowledge and professional skills in elaboration of training methodologies and evidence-based learning - Excellent trainer recognised at EU-level - Proven twinning experience in ToT in Serbia | English Serbian Croatian/Bosnian Russian French Macedonian | North Macedonia Croatia Monte Negro Jordan Serbia, Georgia |
| Croatia 7 | KRISTINA BALENOVIC | Legal Counsellor Specialist | Ministry of Labour and Pension System, Zagreb | 10 | Faculty of Law, Zagreb | - Knowledge and experience in necessary administrative structures and institutional capacities for the implementation of the relevant acquis | Croatian (native), English, Bosnian, Serbian, Slovene ,Spanish | Serbia, Montenegro Ukraine Portugal Slovenia |
| Croatia 8 | TOMISLAV MARKOTA | Legal Counsellor | National Labour Inspectorate, Zagreb | 10 | Faculty of Law, Zagreb | - Knowledge and practical experience in working in the EU approximation field | Croatian (native), English, Italian | Serbia, Montenegro |
| Hungary 9 | TAMAS BERKY | Management Counsellor | Regional Development Agency Senec-Pezinok, Slovakia | 19 | Corvinus University, School of Management, | - Extensive experience in training needs analysis (TNA), development of competency systems and competency based training and education programmes, as well as development of curricula, training methodology support, training delivery and evaluation | English Spain | Georgia Serbia Croatia Romania |
| Croatia 10 | ZDRAVKO MURATTI | Dep. Director of OSH Department | Ministry of Labour and Pension System, Zagreb | 32 | Faculty of Mechanical Engineering and Naval Architecture, Zagreb | - Proven working experience in alignment of the Croatian OSH legislation with EU acquis, - Knowledge and experience of drafting OSH legislation, including regulatory impact assessment, costing and inter-institutional coordination, - preparation of conceptual materials, programme materials and draft measures for improving the situation in the area of labour protection, developing good practice solutions for strengthening capacities to protect workers’ health, reducing of work relate accidents, - Member of the Focal Point EU-OSHA, - drafting opinion on legal OSH provisions; provide explanations to workers, employers, trade unions and employers association; monitoring judicial practice in OSH issue; providing opinion on drafts and proposed regulations form other government bodies. | English | Croatia |
| SPAIN 11 | concepción pascual lizana | Team Leader Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency.(Ministry of Labour, Migrations and Social Security) | 34 | Law degree | - Transposition of EU Directives on OSH. - Occupational Safety and Health. - Labour relations. - Social Partners. - 2008 – 2012 Director National Institute Safety and Health at Work (INSST) of Spain. - EU OSHA governing board member. - ACSH member. | English French | Ecuador |
| SPAIN 12 | consuelo manchón garcía | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. (Ministry of Labour, Migrations and Social Security) | 20 | Political Science and Sociology | - Occupational Safety and Health. - Labour relations. - Social Partners. - 2007 – 2019, Chief OSH Unit Labour and Social Security Inspectorate, Albacete. - 2005 – 2007, Associate professor, Law Universidad Castilla – La Mancha. Teacher LSSI School. - 2009, external consultor ILO, “enhancing LI effectiveness”, FYR Macedonia. - 2010, SLIC exchange, OSH, Romania. - 2011, Speaker “OSH inspection visit”, ITC ILO, Turin Italy. - 2014-2015, project coordinator, ILO “increasing workplace compliance through LI”, Vietnam. - 2015, Speaker “risks assessment OSH”. - 2016, OSH and LI, Panama | English | Sweden. Cape Verde Mexico |
| SPAIN 13 | JUAN MARTÍN GARCÍA ALLOZA | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. (Ministry of Labour, Migrations and Social Security) | 34 | - Law degree - Postgraduate courses. - Superior Technician on OSH. | - Occupational Safety and Health. - Labour relations. - Social Partners. - 1990 -1996, 2015 – 2016, Associate professor, Law Valencia University - Teacher LSSI School - 1987, training LI. Bolivia - 1996, Training OSH LI, Bolivia. - 1997, training OSH LI, Bolivia. - 2000, TU worker’s, Guatemala. - 2005, Labour mediation and conciliation, ILO, Bolivia | English | Colombia El Salvador Bolivia |
| SPAIN 14 | MARÍA MERCEDES TEJEDOR AIBAR | Head International Relations Department | National Institute Safety and Health at Work (INSST) of Spain. Ministry of Labour, Migrations and Social Security. | 23 | Industrial engineer. Ecomonics degree. Master in OSH. Auditor in OSH. | - Transposition of EU Directives on OSH. - Occupational Safety and Health. - Labour relations. - Social Partners. - EU OSHA governing board alternate member. - ACSH alternate member. - PEROSH. | English French | EU OSHA governing board alternate member |
| SPAIN 15 | marta zimmermann verdejo | Head Research and Information Department. | National Institute Safety and Health at Work (INSST) of Spain. Ministry of Labour, Migrations and Social Security. | 33 | Degree in Medicine and Surgery Postgraduate specialization Epidemiology and Public Health. Master degree in Public health Degree in design and statistics methodology for health sciences. Master degree in field of Epidemiology Training programs | - Transposition of EU Directives on OSH. - Occupational Safety and Health. - Labour relations. - Social Partners. - Spanish strategy for safety and health at work. - Surveys on working conditions. - Work relates accidents, occupational diseases. - Epidemiological reports. - Scientific steering group PEROSH. - External expert EUROFOUND. | English | EUROFOUND. |
| SPAIN 16 | RAQUEL CALVERAS AUGÉ | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. Generalitat Cataluña. | 31 | Law degree | - Occupational Safety and Health. - Labour relations. - Social Partners. | English French | STE TW Romania, |
| SPAIN 17 | JAIME ADMETLLA RIBALTA | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. Generalitat Cataluña | 34 | Law degree | - Occupational Safety and Health. - Labour relations. - Social Partners. | English | Czech Republic, Romania, |
| SPAIN 18 | Gabriela Beltran Fernandez | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. (Ministry of Labour, Migrations and Social Security) | 37 | Degree in Law | - In accordance to European acquis and Spanish Legal framework, on site Labour and Social Security Subinspector activities, task of control at the working sites in all areas with relevant competences - Occupational Health and Safety OHS (Factories, Entreprises,Building construction sector, on-site inspectionvisits, campaigns sector ),talks with representatives of social agents, workers, workers’ representatives, Trade Unions, employers’ associations, within the occasion of labour conflicts, strikes, layoffs, etc. - Antidiscrimination, gender equality, Gender Pay Gap | English French Italian Arab | EU ILO |
| SPAIN 19 | Tomas Criado Navamuniel | Labour and Social Security Inspector | Labour and Social Security Inspectorate of Spain State Agency. (Ministry of Labour, Migrations and Social Security) | 10 | Law degree Universidad Complutense de Madrid, Madrid (Spain) | - Compliance with social legislation, advising, reporting, assessment, mediation or interaction with workers and entrepreneurs’ representatives, - Good command and deep knowledge of the European Acquis in the fields of OSH, Labour Law, Social Security, Labour Migration, Equality, Undeclared Work and Labour Relations. | English French Romanian | Romania Albania Panama |
| SPAIN 20 | JOSÉ IGNACIO MARTÍN FERNÁNDEZ | Labour and Social Security Inspector. International Relations Unit. | Labour and Social Security Inspectorate of Spain State Agency. (Ministry of Labour, Migrations and Social Security) | 20 | Law degree Jean Monnet Course on European legal Culture | - Transposition of EU Directives on OSH. - ILO Conventions and Regulations. - Technical counsellor ILC 2018 ILO “ending violence and harassment in the world of work”. - ILO legal officer, CEACR 2016. - Occupational Safety and Health. - Labour relations, Social Partners, EU Strategy on OSH. - Spanish strategy for safety and health at work. - SLIC European Campaigns. - SLIC working groups. - SLIC LI exchange programs. - Psychosocial risks. - IMI system. Posting of workers. - ECPW, EPAUW, working groups. - EUROFOUND governing board alternate member. - Teacher LSSI School. - Teacher National Institute Public Administration. - Teacher master access to legal practice. | English French Portuguese Italian Russian | see CV. |
| Estonia 21 | Eva Põldis | Adviser in Working Life Development Department, Work Environment Unit | Ministry of Social Affairs of Estonia | 4 years in the field of OSH | Master´s degree in economics | - Knowledge and experience of drafting labour legislation (with focus on OSH), including regulatory impact assessment and inter-institutional coordination. - Experience in developing strategy documents and implementation guidelines. - Knowledge and experience working on legal approximation issues, particularly Union acquis. - Knowledge and experience of developing public consultations, information campaigns and awareness raising. - Good command of written and spoken English. - Good computer literacy (word, excel, power point). | English | Member of the Advisory Committee on Safety and Health, Member of Baltic Sea Network of Occupational Health and Safety |
| Estonia 22 | Silja soon | Head of Supervisory Department | Labour Inspectorate of Estonia | Since 1995 | Medical doctor | - Occupational health and safety - Occupational hazards and their effect to the health | English | Member of SLIC working groups (Chemex, Long Latency, Enforcement) |
| Estonia 23 | Seili Suder | Working Life Development Department, Head of Work Environment | Ministry of Social Affairs of Estonia | Since 2005 | Magister Juris degree in law at the University of Tartu, where she is currently also pursuing a doctorate degree. | - 14 years of professional experience in the field of labour legislation (both individual and collective labour law and OSH), 2 years of it in the Labour Inspectorate of Estonia - knowledge and experience of drafting labour legislation (labour law, OSH) - knowledge of relevant EU legislation and other international instruments (European Social Charter and ILO conventions, labour law, OSH) - working experience on EU legislation and practical law enforcement issues in Member States - experience in developing strategy documents, implementation guidelines, operational/ procedural manuals and instruction handbooks - Knowledge and experience of developing public consultations, information campaigns and awareness raising. - Good command of written and spoken English. - Good computer literacy (word, excel, power point). - Member of the working party on Occupational Safety and Health Signs Directive 92/58/EEC (special working party in the Advisory Committee on Safety and Health at Work). | English | Finland, Ireland |
| Estonia 24 | Mariliis Proos | Working Life Development Department, Head of Employment Relations | Ministry of Social Affairs of Estonia | Since 2002 | Degree equal to bachelor’s degree in law | - 17 years of professional experience in the field of labour legislation (both individual and collective labour law and labour dispute resolution), 4,5 years of it in the Labour Inspectorate of Estonia and 4,5 years in trade union - knowledge and experience of drafting labour legislation - knowledge of relevant EU legislation and other international instruments (European Social Charter and ILO conventions) - working experience on EU legislation, ILO instruments and practical law enforcement issues in Member States - experience in developing strategy documents, implementation guidelines, operational/ procedural manuals and instruction handbooks - experience in industrial relations (industrial actions, collective bargaining) - knowledge and experience of developing public consultations, information campaigns and awareness raising. - Member of the Advisory group for the European Labour Authority - Member of the European Commission Committee of Experts on Posting of workers and subgroup on the transposition of directive 2018/957/EU. | English | Participation experience in the working group meetings of the Council of European Union. Presidency of EU. |
| Austria 25 | Manuela HARGASSNER-DELPOS | Senior Specialist | Austrian Federal Ministry of Labour, Social Affairs, Health and Consumer Protection | 25 | University of Vienna/Social Sciences Faculty (Vienna, Austria) | Training methodologist, Training of trainers Soft skills Gender Mainstreaming implementation | English German | Czech Republic Azerbaijan |
| Greece 26 | Marios Charalambous | Senior advisor | Regional Development Agency, Professional Adult Trainer | 27 | Higher Technical Institute, Nicosia, Cyprus | Development of working tools for labour inspectors Training of Trainers of State Labour Inspectorate on Effective Labour Inspection Performance Safety and Health on construction sites | English | Kosovo, Saudi Arabia Serbia |
| 27 Estonia | Eneken Hiire | Lawyer, Labour Inspector | Ministry of Social Affaires | 6 | University of Tallin | 6 years experience in the field of labour law and occupational health and safety - knowledge and experience of drafting labour legislation - knowledge and experience of labour inspector work in the field of labour relations and occupational health and safety - experience on EU legislation and practical law enforcement issues in Member States | English | International, not specified |
| 28 Slovakia | Michal Nemec | Senior Manager | RDA Senec Pezinok | 22 | Pedagogic University of Military, specialization andragogy and sociology, Bratislava | - 22 years of professional experience in social dialogue, OSH issues, Liability of employers in case of accident at work - 15 years of experience in occupational health service - Professional trainer on different topics of OSH issues | English | Serbia, Croatia, Georgia |
| 29 Slovakia | Slavomir Stastny | Head of Department | Ministry of Labour and Social Affairs and Family, Slovakia | 28 | Technical University in Prague | - Experienced in a work injury and occupational diseases insurance schemes - Support of Occupational health service - Professional trainer on different OSH issues | English | Serbia, Croatia, |

ARTICLE 6: Budget

We hereby provide you with Budget including details of the activities according to the Initial Work-plan.

I. BUDGET HEADING: Resident Twinning Advisor and related costs

II. BUDGET HEADING: Horizontal activities related Costs” are kept as in original budget included in the Twinning contract because these costs are foreseen and known for the entire implementation of the Twinning project (24months).

III. BUDGET HEADING: Components Mandatory Results” is further updated with the Activities foreseen in the period covered by the Initial Work-plan.

The Member State PL

Signature________________________________

date 6th May, 2020

The Beneficiary Country PL

Signature________________________________

date 6th May, 2020