## QR3
| FINANCIAL REPORT Q3 - Twinning project: GE 17 ENI OT 02 19 (GE) “Improving the standards of employment conditions/relations as well as health and safety at work in Georgia” | 3rd quarterly report: 07.04.2020-06.07.2020
Section No./Activity | Name of services/ goods purchased or direct costs | Date(s) of service | Invoice No. | Date of invoice | Breakdown and clarification | Amount paid in local currency (if applicable) | Info EURO exch. Rate | Amount paid in EUR | Amount foreseen in original budget | Amount introduced by side letter/amendment | Amount charged to contingencies
I. | I. BUDGET HEADING: Resident Twinning Advisor and related cost
| Compensation wage and non wage | 07.04.2020-30.04.2020 01.05.2020-31.05.2020 01.06.2020-30.06.2020 01.07.2020-06.07.2020 | RfP Nr. 7, 8, 9, 10 | 02.05.2020, 29.06.2020, 31.07.2020, 31.07.2020, | April 2020 (5500Eur/30days)* 24days = 4400,00Eur May 2020: 5500Eur June 2020: 5500Eur July 2020 (5500Eur/31days)* 6days = 1064,52 Eur |  |  | 16464.52 | 132000 | 132000
| Compensation Daily Subsistence | 07.04.2020-30.04.2020 01.05.2020-31.05.2020 01.06.2020-30.06.2020 01.07.2020-06.07.2020 | RfP Nr. 7, 8, 9, 10 | 02.05.2020, 29.06.2020, 31.07.2020, 31.07.2020, | April: 148,50Eur x 24days = 3564,00Eur May: 148,50Eur x 31days = 4603,50Eur June: 148,50Eur x 30days = 4455,00Eur July: 148,50Eur x 6days = 891,00Eur |  |  | 13513.5 | 108553.5 | 108553.5
| Removal | [7 empty] | 0 | 0
Travel
| Taking up duty | [7 empty] | 914 | 914
| Accompanying Family | [7 empty] | 0 | 0
| Annual Return Trip | [7 empty] | 0 | 0
| Annual Return Trip spouse and family | [7 empty] | 0 | 0
| Monthly Travel | 07.04.2020-30.04.2020 01.05.2020-31.05.2020 01.06.2020-30.06.2020 01.07.2020-06.07.2020 | RfP Nr. 7, 8, 9, 10 | 02.05.2020, 29.06.2020, 31.07.2020, 31.07.2020, | April 2020: 0Eur May 2020: 0Eur June 2020: 0Eur July 2020: 0Eur |  |  | 0 | 10511 | 10511
| School Fees | [7 empty] | 0 | 0
RTA Training Brussels
| Travel Costs | [7 empty] | 550 | 550
| Daily Subsistence Allowance | [7 empty] | 464 | 464
RTA Assistants contracts
| Assistant(s) | 07.04.2020-30.04.2020 01.05.2020-31.05.2020 01.06.2020-30.06.2020 01.07.2020-06.07.2020 | Inv. Nr. 06 Machkhaneli Inv. Nr. 07 Machkhaneli Inv. Nr. 08 Machkhaneli Inv. Nr. 09 Machkhaneli | 30.04.2020, 31.05.2020, 30.06.2020, 31.07.2020, | April 2020: (1600/30) x 24days = 1280,00Eur May 2020: 1600Eur June 2020: 1600Eur July 2020: (1600/31) x 6days = 309,68Eur |  |  | 4789.68 | 38400 | 38400
| Interpreter/translator salary | 07.04.2020-30.04.2020 01.05.2020-31.05.2020 01.06.2020-30.06.2020 01.07.2020-06.07.2020 | Inv. Nr. 06 Goisashvili Inv. Nr. 07 Goisashvili Inv. Nr. 08 Goisashvili Inv. Nr. 09 Goisashvili | 30.04.2020, 31.05.2020, 30.06.2020, 31.07.2020, | April 2020: (1600/30) x 24days = 1280,00Eur May 2020: 1600Eur June 2020: 1600Eur July 2020: (1600/31) x 6days = 309,68Eur |  |  | 4789.68 | 38400 | 38400
| Total: Resident Twinning Advisor and related cost | [6 empty] | 39557.38 | 329792.5 | 329792.5 | 0
II. | II. BUDGET HEADING: Horizontal activities related Costs
Short term staff: MS PL and other Support staff / Component Leaders
| Work Plan preparation* | [7 empty] | 4550 | 4550
| Steering Committees* | [7 empty] | 14700 | 14700
| Communication/Visibility programme* | [7 empty] | 0 | 0
| Twinning Project Support Cost | [7 empty] | 26180 | 26180
| Compensation for Daily Subsistence | [7 empty] | 15642 | 15642
| Travel Costs Bratislava (PL 7xSCM) | [7 empty] | 3199 | 3199
| Travel Costs Madrid (JPL 1xWP, 7xSCM) | [7 empty] | 4520 | 4520
| Travel Costs Albacete (CL2 1xWP, will be based on real costs) | [7 empty] | 616 | 616
| Travel Costs Tallinn (JPL 1xWP, 7xSCM) | [7 empty] | 3192 | 3192
PC PL and/or RTA Counterpart Training Brussels
| Travel Costs | [7 empty] | 550 | 550
| Compensation for Daily Subsistence | [7 empty] | 464 | 464
Communication/Visibility programme
| Maximum amount for all components | [7 empty] | 15000 | 15000
| Purchase of Goods | [7 empty] | 0 | 0
| Expenditure Verification / Audit costs | [7 empty] | 5000 | 5000
| Steering Committee 2: Flat Daily Allowance Ondrus | 05.05.2020-06.05.2020 | MC | 2020-06-17 | 350Eur x 2days |  |  | 700
| Twinning Project Support Cost (Ondrus) | 05.05.2020-06.05.2020 |  |  | 700*136% |  |  | 952
| Compensation for Daily Subsistence Ondrus | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Travel Costs (Ondrus) | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Steering Committee 2: Flat Daily Allowance Fernandez | 05.05.2020-06.05.2020 | MC | 2020-06-17 | 350Eur x 2days |  |  | 700
| Twinning Project Support Cost (Fernandez) | 05.05.2020-06.05.2020 |  |  | 700*136% |  |  | 952
| Compensation for Daily Subsistence Fernandez | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Travel Costs (Fernandez) | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Steering Committee 2: Flat Daily Allowance Saar | 05.05.2020-06.05.2020 | MC | 2020-06-16 | 350Eur x 2days |  |  | 700
| Twinning Project Support Cost (Saar) | 05.05.2020-06.05.2020 |  |  | 700*136% |  |  | 952
| Compensation for Daily Subsistence Saar | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Travel Costs (Saar) | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Total: Horizontal activities related Costs | [6 empty] | 4956 | 93613 | 93613 | 0
III. | III. BUDGET HEADING: Components Mandatory Results
COMPONENT 0: Kick-off meeting and Closing event
0.1. | Activity 0.1 Kick-off meeting
| Total cost ACT 0.1. | [6 empty] | 0 | 0 | 0 | 0
0.2. | Activity 0.2 Closing event
| Total cost ACT 0.2. | [6 empty] | 0 | 0 | 0 | 0
COMPONENT 1
1.1. | Sub-Result 1.1: Legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis
1.1.1. | Activity 1.1.1 Aligning Georgian legal framework on labour law, including aspects of labour inspection system, amended in compliance with the Union acquis
8 MS experts, 85WDs / 17 missions - Zagreb: Kristina Balenovic 11 WD/3 missions, - Bratislava: Jozef Toman 17 WD/3 missions, Maros Palik 12WDs/2 missions, Branislav Ondrus 10WD/2 missions - Tallin: Saili Suder 10WD/2 missions, Marilis Proos 10WD/2 missions, - Madrid: Jose Ignacio Martin Fernandez 10 WD/2 missions, - Donostia / San Sebastian: Gabriela Beltran Fernández 5WD/1 missions, - Valencia: Juan Martin Garcia Alloza 5WD/1 missions,
| Flat Daily Allowance | [7 empty] | 29750 | 29750
| Twinning Project Support Cost | [7 empty] | 40460 | 40460
| Compensation for Daily Subsistence | [7 empty] | 20196 | 20196
| Travel Costs Bratislava | [7 empty] | 3199 | 3199
| Travel Costs Madrid | [7 empty] | 1130 | 1130
| Travel Costs Valencia** | [7 empty] | 0 | 0
| Travel Costs Donostia / San Sebastian (will be based on real costs) | [7 empty] | 616 | 616
| Travel Costs Tallin*** | [7 empty] | 1596 | 1596
| Travel Costs Zagreb (will be based on real costs) | [7 empty] | 1500 | 1500
| Translation | [7 empty] | 1200 | 1200
| Flat Daily Allowance Toman | 20.05.2020-29.05.2020 | MC | 2020-05-30 | 350Eur x 7days |  |  | 2450
| Twinning Project Support Cost (Toman) | 20.05.2020-29.05.2020 |  |  | 2450*136% |  |  | 3332
| Compensation for Daily Subsistence Toman | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Travel Costs (Toman) | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Flat Daily Allowance Palik | 20.05.2020-29.05.2020 | MC | 2020-07-12 | 350Eur x 7days |  |  | 2450
| Twinning Project Support Cost (Palik) | 20.05.2020-29.05.2020 |  |  | 2450*136% |  |  | 3332
| Compensation for Daily Subsistence Palik | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Travel Costs (Palik) | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Total cost ACT 1.1.1. | [6 empty] | 11564 | 99647 | 99647 | 0
1.2. | Sub-Result 1.2: Legal framework on non-discrimination and gender equality, including aspects of labour inspection system, amended in compliance with the Union acquis.
1.2.1. | Activity 1.2.1 Aligning Georgian legal framework on Occupational Health and Safety, including aspects of Labour Inspection System, amended in compliance with the Union acquis
3 MS experts, 25WDs / 5missions - Valencia: Mr. Juan Martín GARCÍA ALLOZA 5WD/1 missions, - Madrid: Jose Ignacio Martin Fernandez 15 WD/3 missions, Gabriela Beltran Fernández 5WD/1 mission,
| Flat Daily Allowance | [7 empty] | 8750 | 8750
| Twinning Project Support Cost | [7 empty] | 11900 | 11900
| Compensation for Daily Subsistence | [7 empty] | 6138 | 6138
| Travel Costs Madrid | [7 empty] | 2260 | 2260
| Travel Costs Valencia** | [7 empty] | 616 | 616
| Translation | [7 empty] | 0 | 0
| Flat Daily Allowance Fernandez | 05.06.2020, 12.06.2020, 19.06.2020, 25.06.2020-26.06.2020 | MC | 2020-07-29 | 350Eur x 5days |  |  | 1750
| Twinning Project Support Cost (Fernandez) | 05.06.2020, 12.06.2020, 19.06.2020, 25.06.2020-26.06.2020 |  |  | 1750*136% |  |  | 2380
| Compensation for Daily Subsistence Fernandez | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Travel Costs (Fernandez) | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Total cost ACT 1.2.1. | [6 empty] | 4130 | 29664 | 29664 | 0
1.3. | Sub-Result 1.3: Legal framework on Occupational Safety and Health, including aspects of labour inspection system, amended in compliance with the Union acquis.
1.3.1. | Activity 1.3.1 Aligning Georgian legal framework on Occupational Health and Safety, including aspects of Labour Inspection System, amended in compliance with the Union acquis
7 MS experts, 70WDs / 14 missions - Bratislava: Michal Nemec 10WD/2 missions, Slavomir Stastny 10WD/2 missions, - Kosice: Ivan Majer 20WD/4 missions, Laurencia Jancurova 5WD/1 mission - Zagreb: Zdravko Muratti 15WD/3 missions, - Tallin: Seili Sudder 5WD/1 mission, Eva Poldis 5WD/1 mission, Ulla Saar 10WD/2 missions - Madrid: Tomas Criado Navamuniel 5WD/1 mission,
| Flat Daily Allowance | [7 empty] | 24500 | 24500
| Twinning Project Support Cost | [7 empty] | 33320 | 33320
| Compensation for Daily Subsistence | [7 empty] | 16632 | 16632
| Travel Costs Bratislava | [7 empty] | 1828 | 1828
| Travel Costs Kosice (will be based on real costs) | [7 empty] | 2500 | 2500
| Travel Costs Madrid | [7 empty] | 565 | 565
| Travel Costs Tallin*** | [7 empty] | 1596 | 1596
| Travel Costs Zagreb (will be based on real costs) | [7 empty] | 0 | 0
| Translation | [7 empty] | 480 | 480
| Flat Daily Allowance Nemec | 08.06.2020-12.06.2020 | MC | 2020-06-29 | 350Eur x 5days |  |  | 1750
| Twinning Project Support Cost (Nemec) | 08.06.2020-12.06.2020 |  |  | 1750*136% |  |  | 2380
| Compensation for Daily Subsistence Nemec | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Travel Costs (Nemec) | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Flat Daily Allowance Stastny | 08.06.2020-12.06.2020 | MC | 2020-06-29 | 350Eur x 5days |  |  | 1750
| Twinning Project Support Cost (Stastny) | 08.06.2020-12.06.2020 |  |  | 1750*136% |  |  | 2380
| Compensation for Daily Subsistence Stastny | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Travel Costs (Stastny) | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Flat Daily Allowance Majer | 22.06.2020-30.06.2020 | MC | 2020-07-13 | 350Eur x 7days |  |  | 2450
| Twinning Project Support Cost (Majer) | 22.06.2020-30.06.2020 |  |  | 2450*136% |  |  | 3332
| Compensation for Daily Subsistence Majer | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Travel Costs (Majer) | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Total cost ACT 1.3.1. | [6 empty] | 14042 | 81421 | 81421 | 0
COMPONENT 2
2.1. | Sub-Result 2.1: Analysis for strengthening state authorities’ capacity for implementation of the EU best practices performed, and required strategies developed.
2.1.1. | Activity 2.1.1 Assessment of the administrative structures and institutional capacities of the beneficiary and relevant stakeholders and improvement of their inter-institutional operation
| Total cost ACT 2.1.1. | [6 empty] | 0 | 0 | 0 | 0
2.1.2. | Activity 2.1.2 Training needs analysis and strengthening the institutional capacity of the beneficiary and relevant stakeholders
5 MS experts, 35 WD / 7 missions - Tallin: Ms. Silia Soon 10WD/2 mission, - Albacete: Ms. Consuelo Manchón García 15WD/3 missions, - Valencia: Mr. Juan Martín GARCIA ALLOZA 0WD/0 mission, - Budapest: Mr Tamas Berky 10WD/2 missions, - Barcelona: Raquel CALVERAS AUGÉ 0WD/0 mission,
| Flat Daily Allowance | [7 empty] | 12250 | 12250
| Twinning Project Support Cost | [7 empty] | 16660 | 16660
| Compensation for Daily Subsistence | [7 empty] | 8316 | 8316
| Travel Costs Valencia** | [7 empty] | 0 | 0
| Travel Costs Barcelona** | [7 empty] | 0 | 0
| Travel Costs Albacete (will be based on real costs) | [7 empty] | 1848 | 1848
| Travel Costs Tallin*** | [7 empty] | 798 | 798
| Travel Costs Budapest (will be based on real costs) | [7 empty] | 1000 | 1000
| Translation | [7 empty] | 0 | 0
| Flat Daily Allowance García | 27.05.2020-29.05.2020 | MC | 2020-05-29 | 350Eur x 3days |  |  | 1050
| Twinning Project Support Cost (García) | 27.05.2020-29.05.2020 |  |  | 1050*136% |  |  | 1428
| Compensation for Daily Subsistence García | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Travel Costs (García) | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Flat Daily Allowance Berky | 27.05.2020-29.05.2020 | MC | 2020-05-29 | 350Eur x 3days |  |  | 1050
| Twinning Project Support Cost (Berky) | 27.05.2020-29.05.2020 |  |  | 1050*136% |  |  | 1428
| Compensation for Daily Subsistence Berky | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Travel Costs (Berky) | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Flat Daily Allowance Soon | 2020-05-29 | MC | 2020-05-29 | 350Eur x 1day |  |  | 350
| Twinning Project Support Cost (Soon) | 2020-05-29 |  |  | 350*136% |  |  | 476
| Compensation for Daily Subsistence Soon | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Travel Costs (Soon) | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Flat Daily Allowance García | 03.06.2020-05.06.2020, 17.06.2020-19.06.2020, 26.06.2020 | MC | 2020-06-26 | 350Eur x 7days |  |  | 2450
| Twinning Project Support Cost (García) | 03.06.2020-05.06.2020, 17.06.2020-19.06.2020, 26.06.2020 |  |  | 2450*136% |  |  | 3332
| Compensation for Daily Subsistence García | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Travel Costs (García) | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Flat Daily Allowance Soon | 05.06.2020, 19.06.2020 | MC | 2020-07-27 | 350Eur x 2days |  |  | 700
| Twinning Project Support Cost (Soon) | 05.06.2020, 19.06.2020 |  |  | 700*136% |  |  | 952
| Compensation for Daily Subsistence Soon | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Travel Costs (Soon) | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Flat Daily Allowance Berky | 18.06.2020-19.06.2020 | MC | 2020-06-22 | 350Eur x 2days |  |  | 700
| Twinning Project Support Cost (Berky) | 18.06.2020-19.06.2020 |  |  | 700*136% |  |  | 952
| Compensation for Daily Subsistence Berky | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Travel Costs (Berky) | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Total cost ACT 2.1.2. | [6 empty] | 14868 | 40872 | 40872 | 0
2.1.3. | Activity 2.1.3 ……………………..
| Total cost ACT 2.1.3. | [6 empty] | 0 | 0 | 0 | 0
2.1.4. | Activity 2.1.4 Delivery of comprehensive training programmes to improve the institutional capacities of the beneficiary and relevant
| Total cost ACT 2.1.4. | [6 empty] | 0 | 0 | 0 | 0
2.2. | Sub-Result 2.2: Implementation of the EU best practices regarding the amended legislation piloted and awareness of the citizens and private sector on the topic increased.
2.2.1. | Activity 2.2.1 Development of the relevant guidelines, labour inspection manuals, checklists and other tools to improve the institutional operations and procedures focused on precise implementation of newly adopted legislation
| Total cost ACT 2.2.1. | [6 empty] | 0 | 0 | 0 | 0
2.2.2. | Activity 2.2.2 Preparing and implementing public information campaign aiming to raise awareness among the project among key stakeholders, public, private sector and civil society
5 MS experts, 75 WD/15 missions - Bratislava: Ms. Luba Pavlovova 20 WD/4 missions, Mr. Ivan Majercak 5 WD/1 mission, Mr Branislav Ondrus 10 WD/2 missions - Madrid: Ms. Maria Mercedes Tejedor Aibar 20 WD/4 missions, Ms. Marta Zimmerman Verdejo 20 WD/4 missions,
| Flat Daily Allowance | [7 empty] | 26250 | 26250
| Twinning Project Support Cost | [7 empty] | 35700 | 35700
| Compensation for Daily Subsistence | [7 empty] | 17820 | 17820
| Travel Costs Bratislava | [7 empty] | 3199 | 3199
| Travel Costs Madrid | [7 empty] | 4520 | 4520
| TV, radio broadcasting Public awareness campaign | [7 empty] | 5000 | 5000
| Translation | [7 empty] | 0 | 0
| Flat Daily Allowance Majercak | 18.05.2020-22.05.2020 | MC | 2020-05-27 | 350Eur x 5days |  |  | 1750
| Twinning Project Support Cost (Majercak) | 18.05.2020-22.05.2020 |  |  | 1750*136% |  |  | 2380
| Compensation for Daily Subsistence Majercak | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Travel Costs (Majercak) | N/A | N/A | N/A | Home based mission: Coronavirus Pandemic |  |  | 0
| Total cost ACT 2.2.2. | [6 empty] | 4130 | 92489 | 92489 | 0
2.2.3. | Activity 2.2.3 ……………………..
| Total cost ACT 2.2.3. | [6 empty] | 0 | 0 | 0 | 0
2.3. | Sub-Result 2.3: Organisation of working groups(s) on labour law as well as OSH comprising line ministries and social partners completed and functional.
2.3.1. | Activity 2.3.1 ……………………..
| Total cost ACT 2.3.1. | [6 empty] | 0 | 0 | 0 | 0
| SUB-TOTAL | [6 empty] | 93247.38 | 767498.5 | 767498.5 | 0
IV. | IV. Direct Costs Overall Amount Reserve Funds | [6 empty] | 93247.38
V. | V. Reserves | [6 empty] | 0
VI. | VI. Provision for Indirect Costs | [6 empty] | 5594.8428
| TOTAL COSTS | [6 empty] | 98842.2228
| Mr. Branislav Ondruš |  |  |  | Ms. Tamila Barkalaia
| Member State Project Leader |  |  |  | Beneficiary Country Project Leader
| Date: |  |  |  | Date: