## RFB
Request for Bids
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Prequalification (Y/N) | Procurement Process | Evaluation Options | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Draft Pre-qualification Documents |  | Specific Procurement Notice |  | Amendments to Pre-qualification Documents | Opening / Minutes of Pre-qualification |  | Pre-qualification Evaluation Report |  | Draft Bidding Documents |  | Specific Procurement Notice |  | Invitation to Providers |  | Amendments to Bidding Documents | Bid Submission / Opening / Minutes |  | Bid Evaluation Report and Recommendation for Award |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[15 empty] | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
COVID19/G/RFB-01 / Procurement of 33 units of Minibus-B-type Ambulances and 5 units of Minibus-C-type Ambulances | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Open - International | N | Single Stage One Envelope |  | 2250000 |  |  | Submitted | Under Review | [9 empty] | 2020/09/09 |  | 2020/09/14 |  |  |  |  | 2020/10/26 |  | 2020/11/25 |  | 2020/12/09 |  | 2020/12/30 |  |  | 2021/06/28
COVID19/CW/RFB-01 / Repair works of public health facilities | No | IBRD-91130 | Emergency COVID-19 Response | Post | Works | Open - National | N | Single Stage One Envelope |  | 2000000 |  |  | Pending Implementation | Cleared | [9 empty] | 2020/06/22 |  | 2020/06/27 |  |  |  |  | 2020/08/08 |  | 2020/09/07 |  | 2020/09/21 |  | 2020/10/12 |  |  | 2021/04/10

## RFQ
Request for Quotations
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Draft Request for Quotations |  | Specific Procurement Notice |  | Invitation to Supplier / Contractor |  | Amendments to Request for Quotations | Receive Quotations |  | Comparison of Quotations |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[12 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
COVID19/G/RFQ-01 / Procurement of the 33 Units of Minibus-B-type Ambulances and 5 Units of Minibus-C-type Ambulances | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Limited | 2500000 |  |  | Submitted | Under Review | 2020/06/15 | [6 empty] | 2020/07/04 |  | 2020/07/11 |  | 2020/07/25 |  | 2020/08/15 |  |  | 2021/02/11
COVID19/G/RFQ-04 / Procurement of motor vehicles for Infectious Control Monitoring Center | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Open - National | 300000 |  |  | Under Implementation | Cleared | 2020/06/05 | 2020/08/06 | 2020/06/10 |  | 2020/06/10 |  |  | 2020/06/24 |  | 2020/07/01 |  | 2020/07/15 |  | 2020/08/05 |  |  | 2021/02/01
COVID19/G/RFQ-05 / Procurement of the 200,000 Sample collection tubes with VTM 2-3 ml and two plastic swab applicators. | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Open - National | 320000 |  |  | Under Implementation | Cleared | 2020/08/05 | 2020/08/12 | 2020/08/08 |  | 2020/08/08 |  |  | 2020/08/28 |  | 2020/09/02 |  | 2020/09/07 |  | 2020/09/12 |  |  | 2020/11/11
COVID19/G/RFQ-02 / Procurement of Equipment for Emergency Control Center | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Open - National | 2800000 |  |  | Pending Implementation | Cleared | 2020/06/18 |  | 2020/06/23 |  | 2020/06/23 |  |  | 2020/07/07 |  | 2020/07/14 |  | 2020/07/28 |  | 2020/08/18 |  |  | 2021/02/14
COVID19/G/RFQ-07 / Procurement of ICT goods for public health facilities | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Open - National | 300000 |  |  | Pending Implementation | Cleared | 2020/06/15 |  | 2020/06/20 |  | 2020/06/20 |  |  | 2020/07/04 |  | 2020/07/11 |  | 2020/07/25 |  | 2020/08/15 |  |  | 2021/02/11
COVID19/G/RFQ-03 / Procurement of Motorcycle for ambulance first responders with helmets | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Limited | 1500000 |  |  | Pending Implementation | Cleared | 2020/06/15 | [6 empty] | 2020/07/04 |  | 2020/07/11 |  | 2020/07/25 |  | 2020/08/15 |  |  | 2021/02/11

## DIR
Direct Selection
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Procurement Category | Evaluation Options | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Justification for Direct Procurement |  | Invitation to Supplier / Contractor |  | Draft Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[12 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
COVID19/G/DC-06 / Procurement of Hospital Equipment for four dedicated COVID-19 clinics: Rukhi Hospital, Batumi Hospital, Lisi Hospital and Infectious Disease Hospital | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 16231524 |  |  | Pending Implementation | Cleared | 2020/06/15 |  | 2020/06/20 |  | 2020/06/20 |  | 2020/07/04 |  | 2020/07/25 |  |  | 2021/01/21
COVID19/G/DC-13 / Procurement of Standard COVID-19 AG Tests | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 1300000 |  |  | Signed | Cleared | 2020/07/23 | 2020/07/23 | 2020/07/28 | 2020/07/24 | 2020/07/28 | 2020/07/24 | 2020/08/07 | 2020/08/03 | 2020/08/17 | 2020/08/03 |  | 2020/09/16
COVID19/G/DC-16 / Direct procurement of the Roboklon extraction kits | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 500000 |  |  | Pending Implementation | Cleared | 2020/08/15 |  | 2020/08/20 |  | 2020/08/20 |  | 2020/08/30 |  | 2020/09/14 |  |  | 2020/12/13
COMMANDER - 001 / Direct procurement of the Goggles, Protective | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 179820 |  |  | Pending Implementation | Cleared | 2020/08/04 |  | 2020/08/09 |  | 2020/08/09 |  | 2020/08/14 |  | 2020/08/19 |  |  | 2021/02/15
COVID19GDC- 21 / Procurement of the STANDARD Q COVID-19 Ag/Ab Total Test. | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 2000000 |  |  | Pending Implementation | Cleared | 2020/09/04 |  | 2020/09/09 |  | 2020/09/09 |  | 2020/09/19 |  | 2020/09/20 |  |  | 2020/10/10
COVID19/G/DC-08 / Procurement of In Vitro Diagnostic Medical Device | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 493980 |  |  | Under Implementation | Cleared | 2020/06/12 | 2020/05/22 | 2020/06/13 | 2020/06/19 | 2020/06/13 |  | 2020/06/20 |  | 2020/07/11 |  |  | 2021/01/07
COVID19/G/DC-02 / Procurement of Critical Care Ventilators and Related Services | Yes | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 405000 |  |  | Signed | Cleared | 2020/05/28 | 2020/05/04 | 2020/06/02 | 2020/05/11 | 2020/06/02 | 2020/05/19 | 2020/06/16 | 2020/05/21 | 2020/07/07 | 2020/05/21 |  | 2020/08/31
COVID19/G/DC-01 / Procurement of Rapid COVID-19 Test Cassette | Yes | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 504400 |  |  | Signed | Cleared | 2020/05/28 | 2020/05/13 | 2020/06/02 | 2020/05/13 | 2020/06/02 | 2020/05/17 | 2020/06/16 | 2020/05/17 | 2020/07/07 | 2020/05/17 | 2020/07/23 | 2021/01/03
COVID19/G/DC-14 / Procurement of Nucleic Acid Diagnostic Kit. | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 2520000 |  |  | Under Implementation | Cleared | 2020/07/23 | 2020/07/23 | 2020/07/28 | 2020/06/24 | 2020/07/28 | 2020/07/22 | 2020/08/11 |  | 2020/08/21 |  |  | 2020/09/20
COVID19/G/DC-09 / Procurement of Qiagen RNA Mini Kit | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 338708 |  |  | Signed | Cleared | 2020/06/25 | 2020/06/16 | 2020/06/30 | 2020/06/23 | 2020/06/30 | 2020/06/26 | 2020/07/14 | 2020/07/01 | 2020/08/04 | 2020/07/01 |  | 2021/01/31
COVID19/G/DC-07 / Procurement of Diagnostic Supplies | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 25000000 |  |  | Pending Implementation | Cleared | 2020/06/15 |  | 2020/06/20 |  | 2020/06/20 |  | 2020/07/04 |  | 2020/07/25 |  |  | 2021/01/21
COVID19/G/DC-17 / Direct Procurement of PCR tests for Procleix Panther System for Automated NAT ( Grifols device) | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 300000 |  |  | Pending Implementation | Cleared | 2020/08/15 |  | 2020/08/20 |  | 2020/08/20 |  | 2020/08/30 |  | 2020/09/14 |  |  | 2020/12/13
COVID19/G/DC-18 / Direct Procurement of saliva collection kits | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 385000 |  |  | Pending Implementation | Cleared | 2020/08/15 |  | 2020/08/20 |  | 2020/08/20 |  | 2020/08/30 |  | 2020/09/14 |  |  | 2020/12/13
COVID19/G/DC-10 / Procurement of Thersmo Scientifics COVID-19 tests | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 5685100 |  |  | Signed | Cleared | 2020/06/25 | 2020/06/16 | 2020/06/30 | 2020/06/23 | 2020/06/30 | 2020/06/26 | 2020/07/14 | 2020/07/01 | 2020/08/04 | 2020/07/01 |  | 2021/01/31
COVID19GDC-12 / Procurement of COBAS 6800/8800 SARS-COV-2 Tests | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 4100000 |  |  | Pending Implementation | Cleared | 2020/08/24 |  | 2020/08/29 |  | 2020/08/29 |  | 2020/09/08 |  | 2020/09/14 |  |  | 2021/03/13
COVID19/G/DC-19 / Direct Procurement of protective gloves | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 350000 |  |  | Pending Implementation | Cleared | 2020/08/15 |  | 2020/08/20 |  | 2020/08/20 |  | 2020/08/30 |  | 2020/09/14 |  |  | 2020/12/13
COVID19/G/DC-15 / Direct Procurement of the Qiagen extraction kits | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 500000 |  |  | Pending Implementation | Cleared | 2020/08/15 |  | 2020/08/20 |  | 2020/08/20 |  | 2020/08/30 |  | 2020/09/14 |  |  | 2020/11/13
COVID19/G/DC-04 / Procurement of Standard COVID-19 Antigen Tests | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 612200 |  |  | Signed | Cleared | 2020/06/12 | 2020/06/12 | 2020/06/13 | 2020/06/12 | 2020/06/13 | 2020/06/16 | 2020/06/20 | 2020/06/18 | 2020/06/21 | 2020/06/19 |  | 2020/07/21
COVID-19-G-DC-20 / procurement of the Second hand goods (CT scanner) | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 105000 |  |  | Pending Implementation | Cleared | 2020/09/04 |  | 2020/09/09 |  | 2020/09/09 |  | 2020/09/19 |  | 2020/10/10 |  |  | 2021/04/08
COVID19/G/DC-11 / Procurement of Nucleic Acid Diagnostic Kit | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 828000 |  |  | Canceled | Cleared | 2020/06/25 | 2020/06/16 | 2020/06/30 | 2020/06/24 | 2020/06/30 |  | 2020/07/03 |  | 2020/07/06 |  |  | 2020/09/04
COVID19/G/DC-03 / Procurement of Mobile Emergency Ventilators and Related Services | Yes | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 313476 |  |  | Signed | Cleared | 2020/05/28 | 2020/05/13 | 2020/06/02 | 2020/05/14 | 2020/06/02 | 2020/05/19 | 2020/06/16 | 2020/05/20 | 2020/07/07 | 2020/05/20 |  | 2020/08/31
COVID19/G/DC-05 / Procurement of Personal Protective Equipment | No | IBRD-91130 | Emergency COVID-19 Response | Post | Goods | Direct | 5000000 |  |  | Pending Implementation | Cleared | 2020/06/14 |  | 2020/06/19 |  | 2020/06/19 |  | 2020/07/03 |  | 2020/07/24 |  |  | 2021/01/20

## UN
UN Agencies (Direct) - *All Categories
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Procurement Category | Evaluation Options | Estimated Amount (US$) | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Justification for Direct Procurement |  | Invitation to Supplier / Contractor |  | Draft Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[12 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
COVID19/G/UN-01 / Procurement of Xpert (R) Xpress SARS-CoV-2 Diagnostic Test Kits | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Goods |  | 478240.4 |  |  | Signed | Cleared | 2020/06/25 | 2020/06/16 | 2020/06/30 | 2020/06/16 | 2020/06/30 | 2020/06/26 | 2020/07/14 | 2020/07/02 | 2020/08/04 | 2020/07/02 |  | 2021/01/31

## QBS
Quality Based Selection (QBS)
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Short List and Draft Request for Proposals |  | Request for Proposals as Issued |  | Amendments to Request for Proposals |  | Opening of Technical Proposals / Minutes |  | Evaluation of Technical Proposals |  | Combined Evaluation Report and Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[10 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
COVID19/CS/QBS-01 / Training and technical assistance to MoLSHA | No | IBRD-91130 | Emergency COVID-19 Response | Post | Consultant Services | Open - International | 300000 | Pending Implementation | Cleared | 2020/06/05 |  | 2020/06/26 |  | 2020/07/26 |  | 2020/08/09 |  |  |  | 2020/08/09 |  | 2020/09/06 |  | 2020/10/06 |  | 2020/11/05 |  | 2020/11/19 |  | 2020/12/10 |  |  | 2021/12/10

## CDS
Consultant Direct Selection (CDS)
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Justification for Direct Selection |  | Invitation to Identified/Selected Consultant |  | Amendments to Terms of Reference |  | Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[10 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
COVID19/CS/CDS-01 / Technical Assistance for post-crises COVID-19 strategy for Health Sector - Lead Consultant | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Consultant Services | Direct | 6250 | Signed | Cleared | 2020/06/25 | 2020/06/29 | 2020/06/28 | 2020/06/22 | 2020/06/28 | 2020/07/02 | 2020/06/28 |  | 2020/07/03 | 2020/07/02 | 2020/07/03 | 2020/07/02 | 2020/07/03 | 2020/07/02 |  | 2020/07/28
COVID19/CS/CDS-02 / Technical Assistance for post crises COVID-19 strategy for Health Sector - Assistant Consultant | No | COFN-C1670,IBRD-91130 | Emergency COVID-19 Response | Post | Consultant Services | Direct | 3125 | Signed | Cleared | 2020/06/25 | 2020/06/29 | 2020/06/28 | 2020/06/22 | 2020/06/28 | 2020/07/02 | 2020/06/28 |  | 2020/07/03 | 2020/07/02 | 2020/07/03 | 2020/07/02 | 2020/07/03 | 2020/07/02 |  | 2020/07/28
COVID19/CS/INDV-07 / Interpreter under the Project Implementation Unit (PIU) for Emergency COVID-19 Response Project | No | COFN-C1670,IBRD-91130 | Project Management | Post | Consultant Services | Direct | 1000 | Under Implementation | Cleared | 2020/07/24 | 2020/07/27 | 2020/07/29 | 2020/07/24 | 2020/08/03 | 2020/07/27 | 2020/08/03 |  | 2020/08/13 | 2020/07/27 | 2020/08/23 |  | 2020/09/02 |  |  | 2020/12/01

## INDV
Individual Consultant Selection
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Estimated Amount (US$) | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Justification for Direct Selection |  | Invitation to Identified / Selected Consultant |  | Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[10 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
COVID19/CS/INDV-01 / Procurement Manager | No | IBRD-91130 | Project Management | Post | Consultant Services | Open | 72000 | Signed | Cleared | 2020/05/25 | 2020/05/08 | 2020/06/08 |  | 2020/07/08 | 2020/06/05 |  |  | 2020/07/13 | 2020/05/21 | 2020/08/03 | 2020/06/16 | 2020/08/17 | 2020/06/16 | 2020/09/07 | 2020/06/16 |  | 2021/03/06
COVID19/CS/INDV-05 / Social Standards Specialist | No | IBRD-91130 | Project Management | Post | Consultant Services | Open | 38400 | Under Implementation | Cleared | 2020/05/25 | 2020/05/08 | 2020/06/08 |  | 2020/07/08 |  |  |  | 2020/07/13 |  | 2020/08/03 |  | 2020/08/17 |  | 2020/09/07 |  |  | 2021/03/06
COVID19/CS/INDV-02 / Financial Manager | No | IBRD-91130 | Project Management | Post | Consultant Services | Open | 60000 | Under Implementation | Cleared | 2020/05/25 | 2020/05/08 | 2020/06/08 |  | 2020/07/08 |  |  |  | 2020/07/13 |  | 2020/08/03 |  | 2020/08/17 |  | 2020/09/07 |  |  | 2021/03/06
COVID19/CS/INDV-06 / Environmental Standards Specialist | No | IBRD-91130 | Project Management | Post | Consultant Services | Open | 38400 | Signed | Cleared | 2020/05/25 | 2020/05/08 | 2020/06/08 |  | 2020/07/08 | 2020/06/05 |  |  | 2020/07/13 | 2020/05/21 | 2020/08/03 | 2020/06/16 | 2020/08/17 | 2020/06/16 | 2020/09/07 | 2020/06/16 |  | 2021/03/06
COVID19/CS/INDV-04 / Health Specialist | No | IBRD-91130 | Project Management | Post | Consultant Services | Open | 60000 | Signed | Cleared | 2020/05/25 | 2020/05/08 | 2020/06/08 |  | 2020/07/08 | 2020/06/05 |  |  | 2020/07/13 | 2020/05/21 | 2020/08/03 | 2020/06/16 | 2020/08/17 | 2020/06/16 | 2020/09/07 | 2020/06/16 |  | 2021/03/06
COVID19/CS/INDV-03 / Procurement Specialist | No | IBRD-91130 | Project Management | Post | Consultant Services | Open | 52800 | Signed | Cleared | 2020/05/25 | 2020/05/08 | 2020/06/08 |  | 2020/07/08 | 2020/06/05 |  |  | 2020/07/13 | 2020/05/21 | 2020/08/03 | 2020/06/16 | 2020/08/17 | 2020/06/16 | 2020/09/07 | 2020/06/16 |  | 2021/03/06