## Slide 1
EASTERN EUROPE AND SOUTH CAUCASUS INITIATIVE
EU4Business: From Policies to Action
Proposed methodology and work arrangements on costing of Georgia‘s SME Strategy / Action Plan
Videoconference
23.09.2020
Janez Šušteršič, independet expert

## Slide 2
Agenda
Basics on costing methodology
2. How we can support you in costing

## Slide 3
Why is costing important
more precision in planning of activities and resources;
avoids implementation delays caused by lack of funds;
helps prioritization of activities and measures;
provides a realistic base for additional funding requests;
enables comparison between costs and results;
increases transparency of budgets.

## Slide 4
The bottom-up approach to costing
Specify the activities and their outputs
Identify the inputs required by each output
Estimate the cost of each input
Sum up the costs by cost categories
Note that in some cases, the total cost is pre-determined by available resources,
for example the budget available for specific type of grant to SMEs.
Also in such cases, it is important to plan a rough number of SMEs that will be
supported, and account for other costs of implementation.

## Slide 5
Illustration: example of a costing table

## Slide 6
Organization of costing
The ministry/agency proposing the activity should also do the costing
Costing process should be coordinated and checked by the AP coordinator
Advisable cooperation with budget departments and MoF

## Slide 7
Question to be clarified before costing
Time horizon of costing
Classification of costs and funding sources
Format for presenting the costs and funding in the AP
Additional or full costs?
Are funding gaps (i.e. additional budget requests) allowed?
How to set the reference prices for typical inputs?
Format for reporting on actual costs
Any existing costing methodologies and practices?

## Slide 8
Agenda
Basics on costing methodology
2. How we can support you in costing

## Slide 9
General approach to support
Working closely with official(s) coordinating the costing
Supporting the costing coordinator to become a guide / instructor to other officials working on costing
Interactive webinars providing hands-on support on costing of selected measures
Extent of support: 10-12 expert workdays

## Slide 10
Proposed steps (1)
Online meeting with the coordinators of the strategy / AP
  Agreement on organization of work and timeline
  Clarification of open questions
  Requirement: appointment of a costing coordinator (CC) who will support and work closely with the expert
  Timing: as soon as possible
Webinar 1
  Presentation and discussion of methodology
  Group work of participants on exercises
  Requirement: support by the CC in organization of the webinar and selection of participants
  Timing: early in the preparation of the AP

## Slide 11
Proposed steps (2)
Webinars 2-3
  Joint work on improving costing of selected activities (up to 15 activities per webinar)
  Clarification of open questions
  Requirement: draft costing of selected activities submitted to the CC and expert
  Timing: to be agreed
In between and after webinars
  Remote support to the CC via email or short meetings
  Clarification of open questions
  Requirement: the CC acts as a guide/instructor to other officials working on costing
  Timing: as needed and agreed