PDO Indicators by Objectives / Outcomes

To prevent, detect, and respond to the threat posed by the COVID-19 pandemic.

IN00874620. ►1. Number of people tested for COVID-19 identification per MoILHSA protocol (Number, Custom). Baseline; Actual (Previous); Actual (Current); End Target. Value; 9,699.00; --; --; 100,000.00. Date; 24-Apr-2020; --; 20-Jul-2020; 05-May-2022. Comments:; Cumulative number of people tested for COVID-19. The technical specifications of the tests will be defined in the POM based on the international/national norms and standards for COVID-19 response.. IN00874636. ►2. Number of COVID-19 patients treated per SSA reimbursement guidelines. (Number, Custom). Baseline; Actual (Previous); Actual (Current); End Target. Value; 431.00; --; --; 2,000.00. Date; 24-Apr-2020; --; 20-Jul-2020; 05-May-2022. Comments:; Cumulative number of patients treated for COVID-19 in hospitals and other designated facilities reimbursed as per SSA guidelines.. IN3. 00874637. ►3. Share of the population in the poorest quintile who are receiving the COVID-19 pandemic related social assistance programs. (Percentage, Custom). Baseline; Actual (Previous); Actual (Current); End Target. Value; 36.00; --; --; 45.00. Date; 16-Apr-2020; --; 20-Jul-2020; 05-May-2022. Comments:; COVID-19 pandemic related social assistance programs refer to the emergency cash benefit, the temporary unemployment benefit, and the TSA. Quintile of the adult equivalent consumption distribution net of social assistance transfers...

Intermediate Results Indicators by Components

Emergency COVID-19 Response

IN00874639. ►4. Number of designated laboratories with COVID-19 diagnostic equipment, test kits, and reagents per MOILHSA guidelines. (Number, Custom). Baseline; Actual (Previous); Actual (Current); End Target. Value; 0.00; --; --; 4.00. Date; 16-Apr-2020; --; 20-Jul-2020; 05-May-2022. Comments:; Number of designated laboratories supported under the project with COVID-19 diagnostic equipment, test kits, and reagents per MoILHSA guidelines. The technical specifications of the tests will be defined in the Project Operation Manual based on the national norms and standards for COVID-19 response.. IN00874642. ►5. Number of personal protection equipment (PPE) purchased. (Number, Custom). Baseline; Actual (Previous); Actual (Current); End Target. Value; 0.00; --; --; 800,000.00. Date; 16-Apr-2020; --; 20-Jul-2020; 05-May-2022. Comments:; Cumulative number of personal protective equipment purchased, including gloves, protective goggles, surrgical masks/ear loop, face mask FF2, face mask N95, gown AAMI level 3, shoe covers, protection caps, scaffolders.. IN00874644. ►6. Number of designated public hospitals with fully equipped and functional intensive care units (ICUs) for COVID-19 patients (Number, Custom). Baseline; Actual (Previous); Actual (Current); End Target. Value; 0.00; --; --; 4.00. Date; 30-Apr-2020; --; 20-Jul-2020; 01-May-2022. Comments:; An ICU unit will be considered fully equipped and operational if two conditions are satisfied: (i) all individual beds in the ICU unit have the necessary equipment as per MoILHSA guidelines, and (ii) ICU unit (comprising of multiple beds) has all necessary shared equipment as per MoILHSA guidelines.. IN00874646. ►7. Number of designated public hospitals with isolation capacity. (Percentage, Custom). Baseline; Actual (Previous); Actual (Current); End Target. Value; 0.00; --; --; 4.00. Date; 16-Apr-2020; --; 20-Jul-2020; 05-May-2022. Comments:; Percentage of designated public hospitals that have operational isolation capacity (isolation rooms in admission departments and isolation wards in designated departments). Designated public facilities are those identified by the MoILHSA for observation of suspected cases and treatment of confirmed COVID-19 cases...

Enabling health measures to contain the COVID-19 outbreak through temporary income support for

IN00874638. ►8. Number of vulnerable households receiving temporary cash benefit. (Number, Custom). Baseline; Actual (Previous); Actual (Current); End Target. Value; 0.00; --; --; 70,000.00. Date; 16-Apr-2020; --; 20-Jul-2020; 05-May-2022. Comments:; “Vulnerable” households are defined as those households without formal labor income, households with children; households with at least one member with a disability. Data will be disaggregated by (i) households with at least one workable member without labor income; (ii) households with children (up to 18 years old); and (iii) households with at least a member with disabilities.. IN00874641. ►9. Number of formal private sector workers laid off because of COVID-related lock down who receive temporary unemployment benefits, by gender. (Number, Custom). Baseline; Actual (Previous); Actual (Current); End Target. Value; 0.00; --; --; 135,000.00. Date; 16-Apr-2020; --; 20-Jul-2020; 05-May-2022. Comments:; Formal private-sector workers are defined as workers appearing in Revenue Service Registry data (workers for which employers pay payroll taxes). Layoffs will be reported by employers and confirmed by Revenue Service based on their registry. Sex-disaggregated data will be monitored.. IN00874643. ►10. Number of TSA beneficiary households. (Number, Custom). Baseline; Actual (Previous); Actual (Current); End Target. Value; 118,100.00; --; --; 124,000.00. Date; 16-Apr-2020; --; 20-Jul-2020; 05-May-2022. Comments:; Number of TSA beneficiary households as per program administrative data. TSA beneficiary households are defined as households with a PMT score below 65,001 based on the existing scoring formula (determined by Res. 758 of December 31, 2014). The indicator will be disaggregated for female-headed households.. IN00874645. ►11. Complaints received related to COVID-related social assistance programs. (Percentage, Custom). Baseline; Actual (Previous); Actual (Current); End Target. Value; 0.00; --; --; 5.00. Date; 16-Apr-2020; --; 20-Jul-2020; 05-May-2022. Comments:; This indicator tracks the number of complaints received relating to COVID-19 related social assistance programs to help identify problems and address them as necessary. COVID-19 pandemic related social assistance programs refer to the emergency cash benefit, the temporary unemployment benefit, and the TSA.. IN00874647. ►12. Number of informal workers who receive the one-off benefit , by gender (Number (Thousand), Custom). Baseline; Actual (Previous); Actual (Current); End Target. Value; 0.00; --; --; 340,000.00. Date; 16-Apr-2020; --; 20-Jul-2020; 29-Apr-2022. Comments:; Number of informal workers who lose their activity because of COVID-related lockdown restrictions who receive a temporary unemployment benefit, by gender...

Project Management

IN00874640. ►13. Percentage of beneficiaries reporting that community engagement and outreach meet their needs. (Percentage, Custom). Baseline; Actual (Previous); Actual (Current); End Target. Value; 0.00; --; --; 70.00. Date; 16-Apr-2020; --; --; 05-May-2022. Comments:; This indicator tracks the number of complaints received relating to COVID-19 related social assistance programs to help identify problems and address them as necessary. COVID-19 pandemic related social assistance programs refer to the emergency cash benefit, the temporary unemployment benefit, and the TSA...