## Gantt Chart
Reporting Periods
|  | RP 2 | RP 3 | RP 4 | RP 5 | RP 6 | RP 7 | RP 8 | Comments
Component 1: National Sector Reform Policies
Output 1.1 | Updated national sector reform policies drafted
Indicator 1.1.1 | Status of drafts of updated sector reform policies, strategies and action plans
| - VET Strategy/AP (by end 2020, to be incorporated in overall education strategy by end 2021) | Situational analysis, goals/objectives for strategy drafted | [6 empty] | Decision should be made by MoESCS on how far VET strategy preparation should go before work is started on preparing overall education strategy
| - CG Strategy/AP (by end 2020) | 1st complete draft of strategy drafted
| - Youth Strategy/AP (Strategy by end 2020, AP by end of RP3 following election) | Situational analysis, goals/objectives drafted, completed draft expected by end 09.2020
- Law on Youth (by mid-2021)
- Labour/ Employment Strategy / AP (AP reviewed annually, strategy revised mid-B12023)
Indicator 1.1.2 | Status of proposals for improved policy coordination / monitoring | Drafting started
Output 1.2 | Capacities in sector reform policy development, implementation and monitoring enhanced
Indicator 1.2.1 | Implementation status of TA capacity building programme of the project
- Comprehensive TA capacity building programme developed, agreed, and completed (programme drafted by end 2020, implementation completed mid-2023)
| - Beneficiaries supported in meeting BS indicators (annual mid-2020, mid-2021, mid-2022, mid-2023) | MoESCS and MoIDPLHSA assisted, with some comments on indicators 05-07.2020
Indicator 1.2.2 | Number of officials trained (by mid-2023)
Output 1.3 | Enhanced capacity to provide visibility & communications for sector reform policies and specific services
Indicator 1.3.1 | Status of plans, tools, materials etc. developed for PR campaigns (Communications strategy by 02.2020, PR campaigns completed by mid-2023) | Banners, leaflets prepared, SESA and YA assisted in holding events
Indicator 1.3.2 | Number of stakeholder institutions participating in visibility and communications events (total by mid-2023)
Component 2: Skills Development and Entrepreneurship Learning
Output 2.1 | Enhanced capacity of MoESCS to develop/modernise skills devt/LLL
Indicator 2.1.1 | Status of analysis on access to VET/LLL (by end RP3, if not by end 2020) | Survey of supply/demand for VET in all regions (for expansionn of provider network) 50% completed
Indicator 2.1.2 | Status of measures to improve access to VET and LLL for targeted groups (by mid-2023)
Output 2.2 | Enhanced capacity of general, vocational and higher education to provide career orientation and guidance | [7 empty] | Awaiting approval of CG strategy/AP
Indicator 2.2.1 | Status of career education and guidance at all levels of education (by mid-2023)
Indicator 2.2.2 | Status of career education and guidance modules for general education teachers and VET college career managers (developed by end 2021, pilots completed by mid-2023)
Output 2.3 | Enhanced capacity to deliver entrepreneurship education in general, vocational and higher education and lifelong learning
Indicator 2.3.1 | Status of new entrepreneurship key competence training modules for teachers (developed by end 2021, pilots completed by 2023)
Indicator 2.3.2 | Status of review of entrepreneurship key competence and good practices in universities (by end 2022)
Component 3: Youth
Output 3.1 | Enhanced capacity of Youth Agency to develop and deliver effective youth services | [7 empty] | Awaiting approval of Youth strategy/AP
Indicator 3.1.1 | Status of institutional capacity building plan (Capacity building plan 2020, completed by mid-2023)
Indicator 3.1.2 | Number of Youth Agency staff trained (approx. 20 fully trained by mid-2023)
Indicator 3.1.3 | Status of draft youth services proposals and materials (completed by mid-2023)
Output 3.2 | Improved organizational and human capacities to deliver youth services at local level | [7 empty] | Awaiting approval of Youth Strategy/AP
Indicator 3.2.1 | Status of improvement and development plans of local providers of youth services (number/locations to be agreed with YA in RP3, completed by 2023)
Indicator 3.2.2 | Number of youth workers provided with basic training in delivery of youth services (at least 80 fully trained 2021-23)
Indicator 3.2.3 | Status of draft standards for youth workers (by end 2022)
Indicator 3.2.4 | Status of qualification for youth workers (by mid-2023 according to log frame, but indicator to be reviewed in consultation with YA - see comment) | [7 empty] | Training programme for youth workers already developed and authorized. New qualification may not be necessary.
Component 4: Employment Services
Output 4.1 | State Employment Support Agency (SESA) supported in its implementation of the Revised New Service Model (NSM)
Indicator 4.1.1 | Status of draft revisions to the NSM
- NSM assessment (by end 2020)
- NSM recommendations, handbooks, guidelines (by end 2021)
Indicator 4.1.2 | Status of proposals for SESA institutional development
| - Institutional development plan (by end 2020) | Outline plan drafted and sent to SESA for comment
- Plans for inclusion of remote areas (road map) (by end 2021)
Indicator 4.1.3 | Status of proposals for local employment policies (by end 2021)
Output 4.2 | SESA supported in designing and delivering more accessible, effective and comprehensive ALMP measures for all job seekers
Indicator 4.2.1 | Status of recommendations on improved ALMP measures
- ALMP measures assessment (by mid-2021)
- Recommendations on comprehensive measures (by end 2021)
- ALMP manuals, guidelines (by mid-2022)
- ALMP pilots (by mid-2023)
Output 4.3 | Capacity developed within the SESA staff to provide more effective employment services for jobseekers and employers
Indicator 4.3.1 | Number of SESA staff at different levels trained | Training plan drafted in RP1
| - Induction training (by end 2020 - provided that SESA staff recruitment process is completed) | Preparations for delivery of induction training in RP3
- Advanced and specialised training (by end 2021)
Component 5: Information Systems and Analysis
Output 5.1 | Improved integrity and compatibility of data and information systems for evidence-based policy making and implementation
Indicator 5.1.1 | Status of proposal for enhanced employment statistics resource
| - Elaborated proposals for employment statistics resource (by mid-2020) | Drafted RP1, submitted to beneficiaries for comment RP2
- Technical specifications (by mid-2021)
- Advisory support to implementation (if proposals are accepted) (by mid-2023)
- Training for users(by mid-2023)
Output 5.2 | LMIMS technically revised and upgraded
Indicator 5.2.1 | Status of recommendations on technical upgrading (by mid-2021)
Indicator 5.2.2 | Status of the guidelines on analytical use (assuming that the necessary decisions are made to upgrade system) (by end 2022)
Output 5.3 | Capacity of LMIS team enhanced in analysis, survey and anticipation methods
Indicator 5.3.1 | Level of capacity of LMIS team in labour market analyses and forecasting (capacity bulding started RP3, completed by mid-2023)
Indicator 5.3.2 | Status of draft guidelines on skills anticipation surveys and analysis (draft sector guidelines by end 2020, other guidelines on request by mid-2023) | Drafting of sector guidelines started, awaiting Geostat info on selected sectors
Indicator 5.3.3 | Status of concept notes for further developing the LMIS and LMIS web portal
- Concept note for upgrading LMIS (by end 2020)
- Proposals for upgrading LMIS web portal (by mid-2021)
- Advisory and technical support has been provided to upgrades of LMIS and LMIS web portal (as necessary, to mid-2023)
Output 5.4 | Enhanced capacity of EMIS to support evidence-based education and training policy making
Indicator 5.4.1 | Status of review report on content and capacity of EMIS (by end 2021)
Indicator 5.4.2 | Status of TA capacity building plan for using EMIS data in evidence-based policy-making (staff capacity bulidng plan by end 2021, completed by mid-2023)
Output 5.5 | Enhanced capacity of institutions to use LMIS, LMIMS and EMIS data in evidence-based policy making
Indicator 5.5.1 | Status of capacity assessment report and training plan (stakeholder capacity building plan by mid-2022, completed by mid-2023)
Indicator 5.5.2 | Status of the survey methodology and pilot surveys proposed for Enterprise Georgia (methodology elaborated by end 2021, 2 pilots completed by end 2022)
Component 6: Monitor Grant Scheme Implementation
Output 6.1 | Grant scheme implementation supported through the monitoring of grant projects
Indicator 6.1.1 | Status of monitoring reports / recommendations (six-monthly, approx. around the end of RP3, RP4, RP5, RP6, RP7, RP8)
Indicator 6.1.2 | Status of the compendium of grant project results and good practices (started in RP6, completed in RP8)