## Gantt Chart
[9 empty] | 2019 |  |  | 2020 | [11 empty] | 01-02.21 |  | 03-08.21 |  | 09.21-02.22 |  | 03-08.22 |  | 09.22 -02.23 |  | 03-08.23 |  | 09.23
|  | TOTAL | TL | KE2 | KE3 | JNKE |  | SNKE | Reporting Period 1 |  |  |  |  | Reporting Period 2 | [5 empty] | Reporting Period 3 | [5 empty] | RP 4 |  | RP 5 |  | RP 6 |  | RP 7 |  | RP 8
[6 empty] | LT | ST |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Q1 | Q2 | Q1 | Q2 | Q1 | Q2 | Q1 | Q2 | Q1 | Q2
Component 0: Project Management |  | 207 | 100 | 70 | 22 | 15 | 0 | 0
| Inception Phase, Management and Reporting | 194 | 100 | 62 | 22 | 10 | 0 | 0
Component 1: National Sector Reform Policies |  | 475 | 170 | 50 | 46 | 189 | 20 | 0
1.1 | National sector reform policies updated and improved | 239 | 80 | 50 | 0 | 89 | 20 | 0
1.1.1 | Analyse policies, strategies, action plans of the 3 ministries and Youth Agency in skills development and skills matching to identify gaps and propose improvements (completed)
1.1.2 | Support the updating and/or improvement of policies, strategies and/or action plans in line with national policy planning framework requirements
a) MoESCS, MoIDPLHSA and the Youth Agency in developing a concept and national strategy for career education and guidance (only for MoESCS, on time)
b) MoESCS in updating the national VET strategy and action plan in the context of the overall national education strategy (started, but overall education strategy scheduled for 2021)
c) MoIDPLHSA in updating the national labour and employment strategy and action plan (not due for updating until 2023)
d) The Youth Agency on developing a strategy/action plan for youth services in the context of the revised national Youth Policy and legislation (on time)
e) The Youth Agency in preparing a new youth law (to be started only after election, end 2020)
1.1.3 | Assist MoESCS in surveying geographical coverage of VET by municipality, identifying gaps, and recommending solutions and priorities for expanding availability (extended to Oct. 2020)
1.1.4 | Organize annual thematic workshops/events related to Sector Policy development to present/ discuss relevant Georgian and international experiences and practices (no change)
1.1.5 | Support strengthening of co-ordinating mechanisms between beneficiary ministries and institutions related to Sector Reform Policy development, implementation and monitoring (started later than planned, but on time)
1.1.6 | Support implementation/further development of monitoring arrangements for sector strategies/action plans, incl. annual reviews on progress in achieving SRPC targets (no change)
1.1.7 | Provide administrative and logistical support to EU missions and expert visits to Georgia related to the SRPC (ad hoc, no change, currently online only)
1.1.8 | Provide short update and progress reports to the EU Delegation related to the SRPC and its implementation (ad hoc, no change, currently online only)
1.2 | Capacities in National Sector Policy development, implementation, monitoring enhanced | 111 | 45 | 0 | 46 | 20 | 0 | 0
1.2.1 | Develop capacity building programme for beneficiaries related to the requirements of national sector policy development, implementation and monitoring (postponed to January 2021)
1.2.2 | Monitor and evaluate progress in capacity building for the project beneficiaries and periodically adjust the programme according to emerging needs
1.3 | Visibility/communications support for National Sector Policies and services of beneficiaries (no change) | 125 | 45 | 0 | 0 | 80 | 0 | 0
1.3.1 | Develop/implement communications and visibility plan incl.measures, tools, events to promote stakeholder engagement and raise public awareness
1.3.2 | Prepare communications and visibility materials to support the project communications and visibility plan
1.3.3 | Support and monitor communications between project beneficiaries and key stakeholders to ensure effective coordination of SRPC-related activities
1.3.4 | Coordinate, support, monitor external communications across all components to raise awareness of SRPC reforms/project results, specifically by:
a) Assisting MoESCS in enhancing awareness of opportunities and attractiveness of VET and LLL though targeted activities and events
b) Increasing public awareness of the youth services, and youth transition and activation measures including social entrepreneurship
c) Generating public awareness of employment services/ALMPs to provide visibility for SESA, advertising services esp. to young people, women, vulnerable groups, NEETs
d) Generating public awareness and visibility of labour market information
Component 2: Skills Development and Entrepreneurship Learning |  | 648 | 220 | 40 | 0 | 158 | 80 | 150
2.1 | Enhanced capacity of MoESCS to develop/modernise skills devtt/LLL | 144 | 90 | 0 | 0 | 54 | 0 | 0
2.1.1 | Assist MoESCS in developing legal, regulatory and financing framework for VET and LLL (no support requested so far)
2.1.2 | Assist MoESCS in improving access to, and participation in, VET and LLL (new start date Nov. 2020)
2.2 | Enhanced capacity to provide prof. orientation/career guidance | 204 | 60 | 40 | 0 | 54 | 0 | 50
2.2.1 | Assist MoESCS in developing/improving arrangements for career education/guidance
a) Review current situation, practices and quality in CEG, and capacity of institutions in genera, vocational and higher education to deliver effective services (included in situational analyis in CG strategy)
b) Prepare proposal/action plan on further development/improvement of career guidance, including institutional arrangements at national, regional and local levels (dependent on acceptance of CG strategy)
2.2.2 | Develop capacities in career education and guidance (no change)
a) Develop/pilot training course and materials for teachers in secondary schoolsto take on the career counsellor role, including local partnerships
b) Review/update existing training module and materials for career managers in VET colleges
2.3 | Enhanced capacity to deliver entrepreneurship education | 300 | 70 | 0 | 0 | 50 | 80 | 100
2.3.1 | Support MoESCS in developing a concept note on innovative learning practices in the context of the LLEL strategy (rescheduled Nov. 2020 to March 2021)
2.3.2 | Design and pilot training programme for upper secondary teachers on entrepreneurship key competence development within Nat. Curriculum
2.3.3 | Design and pilot an in-service training programme for VET teachers and managers on entrepreneurship key competence development in VET programmes
2.3.4 | Prepare guidance materials for teachers on new learning methods and approaches to enhance entrepreneurship key competence development
2.3.5 | Pilot entrepreneurial experience for students from general secondary education schools and VET colleges, and develop a model for replication in the education system
2.3.6 | Review entrepreneurship learning provision in universities/HE institutions based on a sample survey
2.3.7 | Organize pilots to enhance entrepreneurship learning in universities and disseminate results to the higher education community
Component 3: Youth |  | 684 | 206 | 40 | 0 | 158 | 80 | 200
3.1 | Enhanced capacity of Youth Agency to develop and deliver effective youth services (all subactivities rescheduled, starting only after Nov. 2020 / finalization of youth strategy) | 439 | 141 | 30 | 0 | 108 | 60 | 100
3.1.1 | Assist the Youth Agency in organizational development, national strategy and action planning, for improvement and delivery of youth services in the regions
3.1.2 | Assess capacity building and support needs of Youth Agency staff and design and deliver a training plan and coaching scheme
3.1.3 | Organize a study visit to EU member state(s) to observe best practices in the field of youth policy and youth services delivery
3.1.4 | Support the Youth Agency in Improving coordination and cooperation arrangements with other agencies and stakeholders
3.1.5 | Review current youth activation services delivery and support the Agency in revising/updating, implementing and monitoring youth activation measures across the regions in cooperation with relevant stakeholders
3.1.6 | Review career orientation and guidance services provision for youth across the regions, and support the Agency in revising/developing and piloting more effective services, with guidance materials for planning, implementing, monitoring and evaluating provision
3.1.7 | Review non-formal education and training provision for youth, and support the Youth Agency in developing high quality training courses targeting employability/social needs and improving access, supported by manuals and materials for planning, developing delivering and monitoring/evaluating training provision
3.1.8 | Review social entrepreneurship measures for youth and support the Youth Agency in developing and piloting innovative approaches to youth entrepreneurship
3.1.9 | Assist the Youth Agency and youth centres in selected regions to increase public awareness of youth services including youth activation measures and social entrepreneurship
3.2 | Improved organizational and human capacities to deliver youth services at local level (no change) | 245 | 65 | 10 | 0 | 50 | 20 | 100
3.2.1 | Organizational capacities of selected Youth Centres in targeted regions assessed, and institutional development and improvement plans prepared
3.2.2 | Capacity building and training needs of youth workers assessed, and appropriate arrangements put in place to ensure their training, qualifications and professionalization (because there is already an authorised basic training course, YA has requested possible change to developing a course at HE level)
Component 4: Employment Services |  | 1079 | 37 | 460 | 32 | 300 | 0 | 250
4.1 | State Employment Support Agency (SESA) supported in its implementation of the Revised New Service Model (NSM) | 370 | 13 | 160 | 7 | 100 | 0 | 90
4.1.1 | Assessment of current system of the NSM, recommendations (regional visits postponed by Covid, scheduled for October 2020)
4.1.2 | Institutional development of SESA
4.1.3 | Develop detailed instructional materials for NSM work methodology
4.1.4 | Strategy for improving links with local / regional stakeholders (delayed by Covid)
4.1.5 | Guidance for planning, implementing, monitoring and evaluation of measures
4.1.6 | Develop proposals for increasing public awareness of employment services (PR event held in August 2020)
4.2 | SESA supported in designing and delivering more accessible, effective and comprehensive ALMP measures for all job seekers (under review) | 337 | 12 | 150 | 5 | 100 | 0 | 70
4.2.1 | Assessment of current system of ALMP measures
4.2.2 | Proposal for the upgrade and revision of all types of ALMP measures
4.2.3 | Procedures and guidance materials for ALMP measures
4.2.4 | Proposal for revised/redesigned career guidance/ counselling for jobseekers
4.2.5 | Replicable pilot programmes of new ALMP measures
4.3 | Capacity (knowledge and expertise) developed within the ESA staff to provide more effective employment services for jobseekers and employers | 372 | 12 | 150 | 20 | 100 | 0 | 90
4.3.1 | Induction training and TNA of SESA (on schedule)
4.3.2 | Training plan for staff of SESA and other relevant institutions
4.3.3 | Training measures
4.3.4 | Study visit to EU member state(s)
4.3.5 | Exchange of experience with European peers and nationally (postponed to RP 4)
4.3.6 | Coaching scheme and pilot for the staff of SESA and other relevant institutions
Component 5: Information Systems and Analysis |  | 627 | 37 | 60 | 200 | 180 | 0 | 150
5.1 | Data and information systems linked to support evidence-based policy making and implementation | 111 | 0 | 0 | 25 | 36 | 0 | 50
5.1.1 | Analyse the specifications of the main information systems, assess their scope for inter-connectivity, prepare detailed proposals for sharing data (extended to end of RP 3 due to Covid)
5.1.2 | Provide advisory technical support to the up-grading of the data systems to achieve the necessary linking of main data systems
5.2 | LMIMS portal technically revised and upgraded to increase information content, usability and intranet use by staff | 141 | 0 | 20 | 35 | 36 | 0 | 50
5.2.1 | Develop detailed proposals to upgrade the LMIMS portal (software and hardware) including increased information content and enabling the unemployed to be distinguished from job-seekers (ongoing)
5.2.2 | Develop procedure and guidance manuals for use of LMIMS as intranet, as well as for analysis of public employment services data
5.3 | LMIS technically revised and upgraded, and capacity of LMIS team enhanced | 156 | 0 | 20 | 50 | 36 | 0 | 50
5.3.1 | Provide Guidelines and related capacity building to the LMIS team to collect, analyze and disseminate labour market information and monitor labour market developments (guidelines being developed, capacity building delayed due to Covid)
5.3.2 | Provide capacity building and support to the LMIS team (delayed due to Covid)
5.3.3 | Increase public awareness and visibility of the LMIS (delayed due to Covid)
5.4 | Enhanced capacity of EMIS to support education and training policy making on the basis of evidence-based analyses and policy briefs | 78 | 17 | 0 | 25 | 36 | 0 | 0
5.4.1 | Assess the capacity of the EMIS database to meet the requirements of evidence-based policy making
5.4.2 | Develop capacity of EMIS staff to support evidence-based policy making
5.5 | Enhanced capacity of other institutions to use LMIS, LMIMS and EMIS data in evidence-based policy making | 141 | 20 | 20 | 65 | 36 | 0 | 0
5.5.1 | Assess the capacity of potential data users to effectively use data in evidence-based policy
5.5.2 | Develop and implement training and coaching programme for data users
5.5.3 | Disseminate the results of data analyses to relevant stakeholders, through information workshops on use of data in evidence-based policy making
5.5.4 | Support Enterprise Georgia in analysing skill needs for SME development in selected sectors and link them with relevant training provision
5.5.5 | Support a comprehensive sector skill needs analysis for the health care sector, identification of sector skill needs and capacity of potential training provider (delayed due to Covid)
Component 6: Monitor Grant Scheme Implementation |  | 250 | 30 | 50 | 0 | 20 | 50 | 100
6.1 | Support grant scheme implementation through the monitoring of grant projects (no change) | 230 | 30 | 50 | 0 | 0 | 50 | 100
6.1.1 | Provide technical, implementation and monitoring support to the Grant Scheme
6.1.2 | Support preparation of a compendium of grant projects’ results
Total |  | 3970 | 800 | 770 | 300 | 1020 | 230 | 850