## Slide 1
Presentation to Skills4Jobs TA Project Third Steering Committee Meeting
TA TEAM
04.02.2021

## Slide 2
Technical and capacity building support through 6 components
Sector reform policy development and implementation (Component 1)
Skills development in VET, general & higher education (Component 2)
Youth policy and youth services development and implementation (Component 3)
Employment services and active labour market policy measures (Component 4)
Data systems and data sharing to support policy development and implementation (Component 5)
Skills4Jobs grant scheme implementation (Component 6)

## Slide 3
Overview of progress since 2nd Steering Committee Meeting, 29.05.2020
Reporting - June, July, August 2020 included in Progress Report 2, September 2020 to February 2021 will be covered in Progress report 3 which we are now working on
Implementation schedule was updated several times to take account of Covid-19 factors. Despite restrictions, implementation is still broadly on target
Non-key expert missions – no international experts came to Georgia – only tele-working was possible (NKEs for career guidance, youth, PES training) and the long-term Georgian NKEs played a key role
ROM M&E mission in October resulted in a positive monitoring report – recommended improvements have included more cross-component team working, greater involvement of Consortium partners, increased proactivity

## Slide 4
Component 1: Sector Policies
VET Strategy
Since last SC meeting: Preparatory workshop (July 2020), then a was coordination group supported in gathering/ analysing data incl. focus groups – situational analysis and problem trees prepared, goals/objectives are being drafted
For next period: Completion of Strategy drafting (April), development of Action Plan by mid-2021
Career Guidance Strategy
Since last SC meeting: Working group supported, complete draft Strategy already submitted to MoESCS. Action plan drafting has been started
For next period: Action plan to be completed
Youth Strategy
Since last SC meeting: Drafting support provided to expert group; Draft Strategy prepared, with final comments
For next period: Action Plan to be drafted
Survey of VET supply/demand in all municipalities
Since last SC meeting: Survey to support MoESCS in expanding the VET provider network, based on analysis of all available statistics supplemented by fieldwork and stakeholder consultations, was completed and submitted to MoESCS (in December)

## Slide 5
Capacity Building programme
Since last SC meeting: Consultations in progress with beneficiaries (SESA and Youth Agency completed). Other beneficiaries to be consulted in February 2021
For next period: Comprehensive capacity plan to be finalized and implementation started
Sector reform policy coordination mechanisms
The project is working on development of proposals for improved inter-agency coordination, with the aim of sharing an ideas paper for discussion with beneficiaries at end of the current reporting period
EU Budget Support indicators
Since last SC meeting: Support related to 2019/2020 indicators provided to EUD, MoESCS, MoESD and MoIDPLHSA in RP2, consultation with Review Team in RP3
For next period: Support related to 2021 indicators to be provided (May 2021)
Thematic workshops
For next period: 2 workshops, tentatively on gender issues and on social partnership
Communications
Since last SC meeting: Visibility support provided to SESA and Youth Agency events in August 2020. Organizational support provided to MoESCS for Skills Week (December,) including dedicated Skills4Jobs event and VET Donor event
For next period: Communications plan for 2021 developed/implementation begun, branding support to SESA

## Slide 6
Component 2: Skills Development
Innovative learning practices
For next period: We have agreed with MoESCS to recruit an international NKE to prepare a concept paper and action plan
Improved VET access measures for targeted groups
For next period: following on from the geographical survey, we will develop a set of measures to improve access for targeted groups, particularly in regions where current access is limited
Career guidance in schools, colleges, universities
For next period: following on from adoption of the Career Guidance Strategy and Action Plan, we will propose and support related implementation measures including piloting
Entrepreneurship key competence development
For next period: We are recruiting an international NKE to support MoESCS in piloting implementation in general, vocational and higher education programmes (This activity will also be linked with work on youth entrepreneurship with Youth Agency)
Identified implementation issue
As other large donor projects come on stream, MoESCS wishes EU to concentrate on supporting development of policies/concepts

## Slide 7
Component 3: Youth
Youth Agency staff development
For next period: We agreed with the Youth Agency to begin providing training and coaching in key areas of need including project management, monitoring & evaluation, career guidance, development of training courses etc.
Professional development for youth workers
For next period: Work will be started on developing a youth worker training programme at a more advanced level than the existing short course provision. Discussions with the Youth Agency under way about aims, objectives and possible content of the programme
Possible implementation issue
Will establishment of new MoCSY have any implications for project implementation?

## Slide 8
Component 4: Employment services
New service model
Since last SC meeting: Field visits to evaluate service delivery capacity of SESA offices started (all Tbilisi, Gori) but not completed because of travel restrictions; possible handbook content reviewed; various ad hoc reports prepared (qualitative surveys, PES outsourcing); coordination with SESA’s grant project
For next period: completion of field visits and evaluation of facilities, drafting of handbooks to be started, support to be provided to service delivery
ALMP measures
For next period: current implementation status to be reviewed, drafting of revised measures to be started
Capacity building
Since last SC meeting: Induction training provided for all SESA staff so far recruited (September 2020), institutional development workshops plan reviewed
For next period: Continuing of SESA staff training according to agreed plan, workshop delivery started
Issue to be resolved
Project no longer has office space in MoIDPLHSA/SESA, which may inhibit day-to-day contact

## Slide 9
Component 5: Data systems and analysis
Networking of data sources
Since last SC meeting: Data warehouse concept paper revised and submitted to MoESD. Dialogue started with other ministries. Assignment ToR drafted and possible international NKE identified to carry out technical evaluation
For next period: Needs evaluation to be carried out, with recommendations/draft specification
LMIMS portal/WorkNet
Since last SC meeting: Needs discussed with SESA and possible options identified
For next period: Needs evaluation to be carried out by technical expert, with recommendations/draft specification
LMIS
Since last SC meeting: Guidance for sector LM analyses drafted incl. specific approaches for energy/transport sectors. Possible methodologies for 5-year macroeconomic forecasting model investigated, including consultations with Cambridge Econometrics regarding use of CEDEFOP forecasting model and with EU twinning project in GEOSTAT
For next period: Support to sector analyses if implemented by MoESD, development of specific proposal for adaptation/use of CEDEFOP forecasting model
EMIS
For next period: Consultation and agreement on assistance to be provided on data networking and use in policy making

## Slide 10
Component 6: Grant Scheme
Support to Grantees
Since last SC meeting: Grant scheme contracts started between August and November 2021. First introductory information sharing event (September 2020). Public presentation of the 9 grant projects during Skills Week (December)
For next period: Individual support, information sharing event planned
Monitoring grant projects
Since last SC meeting: Monitoring approach and plan developed. Log frames and first quarterly reports are being checked, with feedback and recommendations provided. Monitoring teams to be identified and coached
For next period: First quarterly monitoring to be completed, second round of monitoring to be carried out, including field visits
Issue for discussion
How to involve representatives of beneficiary ministries in M&E team?

## Slide 11
Issues for the next progress report
After 18 months it is a good time to take stock of progress and review priorities for the remaining 30 months
Contract addendum under consideration:
Scope of many activities has grown without a corresponding increase in resources
Additional activities may be proposed, e.g. related to Skills Georgia or as follow-up to other EU projects
NKE working days are being used up very quickly, esp. for local experts
Use of incidentals budget e.g. for sub-contracting is currently restricted under the ToR
May involve:
Reallocation of resources between different budget categories or
Injection of additional resources
Beneficiaries will be consulted during February about current log frame and activity matrix, and the Third Progress Report will include recommendations for any changes that are considered necessary
If addendum is necessary, it will be proposed in March

## Slide 12
THANK YOU !
Skills4Jobs.TA@gopa.de
https://www.facebook.com/Skills4jobsTA