Terms of Reference

Development of Labour Legislation and Support Effective Enforcement of Labour Rights’ Protection in Georgia

| Technical Responsible | Project: Inclusive Labour Market for Job Creation in Georgia |
| --- | --- |
| Requirement: | National Consultant |
| Duty Station: | Tbilisi, Georgia / Home-based |
| Source of funding: | TC Danida |
| Duration: |  |

- Background

In November 2017 the International Labour Organization and the Government of Denmark signed four-year agreement for the implementation of the project “Inclusive Labour Market for Job Creation in Georgia”. The project aims at improving labour market institutions that encapsulate and/or have the capacity to develop legislative and policy frameworks, as well as deliver services, which will lead to a well-functioning labour market that generates decent work opportunities.

In line with its international commitments, Georgia has made a significant progress in adopting legislative changes and implementing policy reforms to promote safety at work and establish an effective enforcement mechanism.  On September 29 2020 the Parliament of Georgia voted for amendments to the Organic Law of Georgia “Georgian Labour Code” and adoption of the new Law of Georgia on “Labour Inspection”. Amendments to the Labour Code outstandingly strengthen the legal framework for the protection of the labour rights of Georgian workers by meeting the requirements of GSP (generalized system of preferences), EU-Georgia Association Agreement and International Labour Organization.

Georgian Labour Code defines that state supervision over labour legislation of Georgia is ensured by the LEPL Labour Inspection functions, authority and power of which is guaranteed by the newly adopted Law of Georgia on Labour Inspection.  Law of Georgia on “Labour Inspection” establishes an independent enforcement body, LEPL Labour Inspection Service and defines basic principles, authority and power of inspection, rights and obligations, and ensure effective implementation of labour norms.

In order to give effect to the above-mentioned laws a number of steps are to be taken by the Government of Georgia.

- Objectives

The first objective of the assignment is to elaborate bylaws that are determined by the transitional provisions in the recently amended Organic Law of Georgia “Georgian Labour Code”, in particular:

- The Government of Georgia shall, approve the List of fields of Specific Working Regimes;

- The Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health, and Social Affairs of Georgia shall ensure the approval of the rules of recording of working hours;

- The Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health, and Social Affairs of Georgia shall:

- ensure the approval of the rules for the regulation of working hours in the mining sector;

- ensure approval of the proportional rate of night work within the annual working hours;

- ensure the scope and intervals for health assessment for night-time employees;

- Ensure the approval of the list of vital jobs.

The second purpose of the assignment is to help the Ministry form a full-fledged labour inspection specially focusing on supervision over labour rights/norms protection.

- Expected Outputs

The National Consultant is expected to complete the following outputs: -

- Develop/elaborate relevant legislative acts envisaged in the labour legislation through consultations with the Ministry and social partners;

- Develop standard operating procedures for a complete inspection of labour rights’ protection; Develop a complete labour inspection visit manual (related to inspection of labour rights) and related necessary documents;

- Build the capacity of the staff of the labour inspection on all materials developed under this assignment

Besides the key outputs, the consultant expected to submit the deliverables as stated in section below.

- Deliverables

The expected contract period is from ------------. To complete the assignment, the Consultant, in close collaboration and consultation with Labour Inspection Service is expected to perform the following tasks:

and the ILO’s project

Chief Technical Adviser in Georgia and the Senior Labour Inspection and OSH specialist in Moscow,

| # | Deliverables | Deliverable document |  |
| --- | --- | --- | --- |
| 1 | Conduct desk research and analyze all necessary national regulations and working documents. | Background analysis and list of documents reviewed to undertake the required tasks to complete the assignment | 10Working days |
| 2 | Consultation meeting/Interviews with ILO specialists, government agencies, social partners and all other relevant stakeholders. Conduct briefing on the findings. | List of participants/interviewees with their title and work place | 5 Working days |
| 3 | Prepare amendments/drafts of bylaws determining: The List of fields of Specific Working Regimes; The rules of recording of working hours; The rules for the regulation of working hours in the mining sector; The rate of night work within the annual working hours; The scope and intervals for health assessment for night-time employees; The list of vital jobs. | Draft bylaws agreed with social partners and ready for adoption; Any other relevant document | 20 Working days |
| 4 | Prepare the draft SoP, manual and related necessary documents | Standard Operating Procedures Labour inspection visit manual | 20 Working days |
| 5 | Conduct a capacity building workshop | Workshop | 5 Working days |

- Required Qualifications

Qualification required to undertake the consultancy assignment:

- University Degree or equivalent in law, public administration or related fields; advanced degree is an asset;

- Experience in the labour inspection and public administration system;

- Experience working on similar assignments for international organisations or the public sector; previous work experience for the ILO or UN agencies is an advantage;

- Demonstrated knowledge of labour law and relevant International Labour Standards is an advantage;

- Strong speaking and writing skills in English

- Administration, Reporting and Coordination

The contract for this assignment will be issued by ILO Moscow Office. The Consultant will work closely with the project focal point of MoLHSA Labour Inspection and Policy Department and will report to the Chief Technical Advisor for the ILO project in Georgia. A technical backstopping will be provided by the ILO Senior Specialist on Labour Inspection and OSH.

Interested candidates are invited to submit an application package in English including the following documents by email to albahnasi@ilo.org

- A profile/CV demonstrating the consultant’s relevant experience and competencies;

- A brief technical proposal (maximum 4 pages) where the tentative methodologies and work plan are presented;

- A detailed financial proposal indicating the cost required for undertaking the assignment.

- In the subject line, please indicate “Application_Labour Inspection Planning and SoP_Name of the Consultant”.