## ActionPlan
Activity |  | Activity Output Indicator |  | Source of confirmation | Responsible Authority | Partner agency | Implementation time | Budget | Source of Financing |  |  |  |  | 2020 Report | Status
[9 empty] | State budget |  | Donor |  | Deficiency
[9 empty] | Amount | Code | Amount | Organization
1.1 | Managing and monitoring activities of the Action Plan by the Steering Committee; Developing recommendations as needed | 1.1.1 | Steering Committee is convened at least twice a year | Steering Committee minutes | IDPs, Eco-Migrants and Livelihoods Agency LEPL | Ministry of Internally Displaced Persons from the Occupied Territories, Labor, Health and Social Affairs of Georgia | 4th Quarter 2021 | Administrative resource | 0 | 27 01 07 | 0 | N/A | 0 | In 2020, one meeting of the steering committee was held | Partially implemented
1.2 | Training of the Ministry's Hotline and IDP Reception Center, as well as municipalities and representatives of livelihood programs providers | 1.2.1 | Employees of the Hotline and IDP reception center are trained / trained in livelihood programs; Representatives of the municipality and service providers are trained at least once a year | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | Ministry of Internally Displaced Persons from the Occupied Territories, Labor, Health and Social Affairs of Georgia; Local municipalities | 4th Quarter 2021 | Administrative resource | 0 | 27 01 07 | 0 | N/A | 0 | In 2020, 5 trainings were held, attendees were provided with complete information about livelihood programs. They also were provided information materials. | Implemented
2.1 | Involving IDPs and Eco-Migrants in State Program for Job Seekers Professional Retraining and Qualification | 2.1.1 | Number of IDPs and Eco-Migrants Involved in State Program for Job Seekers Professional Retraining and Qualification | LEPL - State Employment Promotion Agency Data | LEPL - State Employment Promotion Agency | IDPs, Eco-Migrants and Livelihoods Agency LEPL | 4th Quarter 2021 | 2020: 10% of Program budget 2021: 10% of Program budget; | 10% of Program budget | 27 05 03 | 0 | N/A | 0 | Number of IDPs involved in the program - 36. Among them - 23 famale; Number of eco-migrants - 3, among them 1 female. | Implemented
2.2 | Incolving the IDPs and eco-migrants in the State Program for the Development of Employment Support Services | 2.2.1 | The number of IDPs and eco-migrants involved in the State Program for Development of Employment Support Services | LEPL - State Employment Promotion Agency Data | LEPL - State Employment Promotion Agency | IDPs, Eco-Migrants and Livelihoods Agency LEPL | 4th Quarter 2021 | Administrative resource | 0 | 27 05 01 | 0 | N/A | 0 | In 2020, 486 IDPs and 49 eco-migrants underwent individual counseling to support employment, 110 IDPs and 8 eco-migrants received mediation services, 59 IDPs and 7 eco-migrants are employed within the employment support programs. | Implemented
2.3 | Facilitate enrollment of IDPs and eco-migrants in state vocational education institutions | 2.3.1 | Number of Enrolled in Public Vocational Education Institutions | Data from LEPL -Education Management Information System | Ministry of Education, Science, Culture and Sport of Georgia | IDPs, Eco-Migrants and Livelihoods Agency LEPL | 4th Quarter 2021 | 2020: 660 000; 2021: 660 000; | 1 320 000 | 32 03 01 | 0 | N/A | 0 | In 2020, 399 IDPs and 53 eco-migrants were enrolled in state vocational education programs. | Implemented
2.4 | Providing transportation of all IDP and Eco-Migrant students in need who are studying atstate vocational education institutions. | 2.4.1 | Number of all IDPs and eco-migrants in need of being financed for studying at state vocational education institutions; 40% of the sponsored are women | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | N/A | 4th Quarter 2021 | 2020: 100 000; 2021: 100 000 | 200 000 | 27 06 05 | 0 | N/A | 0 | In 2020, 205 IDPs and eco-migrants, including 103 (49.76%) women, were provided with transportation cost funding | Implemented
3.1 | Promoting self-employment for IDPs and eco-migrants by providing them with working tools | 3.1.1 | Up to 50 beneficiaries are funded, among them 40% are female; By cooperation with the Ministry of Education, Science, Culture and Sport of Georgia and other partner organizations Self-employment professions with high demand are identified | IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | Ministry of Education, Science, Culture and Sport of Georgia, LEPL State Employment Promotion Agency, LEPL Education Management Information System | 4th Quarter 2021 | 2020: 100 000; 2021: 100 000 | 200 000 | 27 06 05 | 0 | N/A | 0 | Due to the limitations caused by the pandemic, applications for the "Self-Employment Promotion Grant Program" started on December 15, so the winners will be identified in 2021 | Ongoing-Partially implemented
3.2 | Promoting of the integration process of IDPs and eco-migrants by providing grants | 3.2.1 | Needs are identified; A need-based grant program has been developed; 10 households are funded | IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | N/A | 4th Quarter 2021 | 2020: 100 000; 2021: 100 000; | 200 000 | 27 06 05 | 0 | N/A | 0 | Due to the limitations caused by the pandemic, applications were received from November to December 2020. 620 applications were submitted and the winners will be identified in 2021; | Ongoing-Partially implemented
3.3 | Support of IDPs and Eco-migrants by providing greenhouse program | 3.3.1 | Mnimum 15 projects are funded | IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | USAID Project Zrda Georgia | 4th Quarter 2021 | 2020: 200 000; 2021: 200 000 | 200 000 | 27 06 05 | 200 000 | USAID/ZRDA | 0 | In 2020, 15 greenhouses were organized within the "Greenhouse Support Grant Program". | Implemented
3.4 | Increasing access to livelihoods for vulnerable IDPs - a pilot project | 3.4.1 | Mnimum 200 Initiative are funded | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | LEPL Social Service Agency | 4th Quarter 2020 | 2020: 500 000 | 500 000 | 27 06 05 | 0 | N/A | 0 | In 2020, 342 applicants were received under the program, of which 169 applicants passed the qualification stage. 135 ideas were funded by the commission. | Partially implemented
3.5 | Entrepreneurship Supporting Program | 3.5.1 | 20 IDPs / eco-migrants entrepreneurs will be supported under the program | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | Movement Against Hunger (AAH); German Society for International Cooperation (GIZ) | 4th Quarter 2020 | 2020: 150 000 | 100000 | 27 06 05 | 50000 | Movement Against Hunger (AAH); | 0 | 20 entrepreneurs were provided with assistance under the program | Implemented
4.1 | Holding information meetings on livelihood programs into IDPs and eco-migrant settlements | 4.1.1 | Minimum 10 informational meetings annually | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | N/A | 4th Quarter 2021 | Administrative resource | 0 | 27 01 07 | 0 | N/A | 0 | The Agency staff held 43 information meetings on livelihood programs in IDP and eco-migrant settlements in the following cities and villages: Zugdidi, Kakhati, Jvari, Pakhulani, Chale, Zeda Etseri, Rukhi, Poti, Tskaltubo, Khobi, Terjola. Tkibuli, Chakvi, Baghdati, Batumi, Kutaisi, Vani, Khoni, Samtredia, Senaki, Gardabani, Rustavi, Bolnisi, Shaumiani, Koda, Tsinamdzgvriantkari, Tserovani, Akhalsopeli, Kareli, Shavshvebi, Khurvaleti, Berbuki, Gori. | Implemented
4.2 | Informing IDPs and Eco-Migrants about door-to-door livelihood programs, by volunteers | 4.2.1 | 6,000 informational materials are distributed annually; At least 40% of the informed population is female | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | USAID/ZRDA | 4th Quarter 2021 | 2020: 25000; 2021: 25000 | 0 | N/A | 50000 | USAID/ZRDA | 0 | No activity was carried out due to the pandemic and regulations set in place. | Not Started
4.3 | Livelihood Forums throughout Georgia | 4.3.1 | At least 3 livelihood forums in different regions of Georgia | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | Partner organizations specified in the strategy and action plan | 4th Quarter 2021 | Administrative resource | 0 | 27 01 07 | 0 | N/A | 0 | No activity was carried out due to the pandemic and regulations set in place. | Not Started
4.4 | Sending short text messages (SMS) to IDPs and eco-migrants about livelihood programs within the information campaign | 4.4.1 | 3,000,000 short text messages annually | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | N/A | 4th Quarter 2021 | 2020: 8000; 2021: 8000 | 16000 | 27 06 05 | 0 | N/A | 0 | In 2020, 86,882 short text messages were sent to IDPs and eco-migrants about livelihood programs. | Partially implemented
4.5 | Provide authorized agency staff with the tools needed to disseminate information | 4.5.1 | About 2,000 copies of livelihood information materials are transmitted to the territorial divisions of the Agency | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | N/A | 4th Quarter 2021 | Administrative resource | 0 | 27 01 07 | 0 | N/A | 0 | In 2020, the Agency's main office and regional divisions staff were provided with 2,000 brochures on livelihood programs, brochures were placed on information boards, and also distributed by Agency staff. | Implemented
4.6 | Information on livelihood programs is published on the Ministry's website | 4.6.1 | Information is avaiable at the web page of MoIPDsLHSA | Web Page Of MoIDPsLHSA | MoIDPsLHSA | IDPs, Eco-Migrants and Livelihoods Agency LEPL | 4th Quarter 2021 | Administrative resource | 0 | 27 01 01 | 0 | N/A | 0 | Information is posted on the website of the LEPL IDPs, EcoMigrants and Livelihoods agency | Implemented
4.7 | Production and distribution of informational material on livelihood programs | 4.7.1 | 10 000 booklets are produced and distributed annually | Report of the IDPs, Eco-Migrants and Livelihoods Agency LEPL | IDPs, Eco-Migrants and Livelihoods Agency LEPL | N/A | 4th Quarter 2021 | 2020: 15 000; 2021: 15 000 | 30 000 | 27 06 03 01 | 0 | N/A | 0 | In 2020, 5,100 information material were printed and distributed (3,800 brochures, 1,000 posters and 300 stickers). | Partially implemented
4.8 | Encouraging Involvement of IDPs and eco-migrants in the programs of LEPL Enterprise Georgia | 4.8.1 | Number of IDPs and Eco-Migrants Involved in the Program | LEPL "Enterprise Georgia" | IDPs, Eco-Migrants and Livelihoods Agency LEPL | N/A | 4th Quarter 2021 | 2020: 1 000 000; 2021: 1 000 000; | 1 020 000 | 24 07 | 0 | N/A | 0 | 263 people were trained under the program. | Implemented
4.9 | Involving IDPs and Eco-Migrants in State Program of NNLP Agricultural and Rural Development Agency | 4.9.1 | Number of IDPs and Eco-Migrants Involved in Agency's Program | NNLP Agricultural and Rural Development Agency | IDPs, Eco-Migrants and Livelihoods Agency LEPL | N/A | 4th Quarter 2021 | 2020: 480 750; 2021: 480 750; | 961 500 | 31 05 | 0 | N/A | 0 | 231 IDPs and 140 Ecomigrants were involved in the program. | Implemented