## Slide 1
Roadmap for Phased Implementation of Revised PHC Benefits Package and New Costing and Payment Model

## Slide 2: Revised PHC benefits package and costing model
November 2019 – WHO Mission invited to review Georgia's PHC reform plan
Month? 2020 – MoIDPLHSA requests WHO technical assistance to revise PHC benefits package and payment model
Month? 2020 - Technical assistance team established and meets 1-2 times weekly (local experts, ministry, WHO CO, WHO European Centre for Primary Health Care, WHO European Center for Health System Strengthening)
July 2020 – Revised benefits package and payment model presented to MoIDPLHSA
November 2020 – Draft roadmap and priority package options presented to MoIDPLHSA
January 2021 – Revised roadmap and phased implementation plan presented to MoIDPLHSA
February 2021 – Revised roadmap and phased implementation pan presented to PHC Board
Timeline

## Slide 3: Key challenges facing PHC strengthening
Lack of separately defined PHC benefits package
Highly fragmented PHC structures
Misaligned incentive structure
Poorly defined patient pathways
Low PHC payment rates
Variation in financing of rural, urban and priority diseases
Complicated coverage and eligibility criteria
Complex co-payment system hinders access to PHC services
Design and Structure
Financing and Coverage
Weak gatekeeping function (40% referral rate)
Narrow scope of practice among urban PHC
Inadequate/outdated clinical guidelines
Lack of accountability and performance oversight
Intensive reporting on inputs without data on performance outcomes (insufficient IT)
Poor regulation of pharmaceutical market
Limited nursing workforce
Lack of system for CME
Low quality of rural PHC facilities
Insufficient IT and digital health capacity
Regulation and Oversight
Workforce and Infrastructure
Limited public health/epidemiology capacity
Insufficient attention to population health needs and outcomes
Insufficient health education and health promotion
Public Health

## Slide 4: Georgia has the lowest public spending on PHC
Source: 2018 data, Global Health Expenditure Database
Chart: GDP (%)
| MDA | RUS | MKD | KAZ | TJK | ARM | UZB | GEO
#REF! | 0.012295 | 0.012123 | 0.011314 | 0.0070868 | 0.0069879 | 0.0052422 | 0.0047705 | 0.0033769
1.2% 1.2% 1.1% 0.7% 0.7% 0.5% 0.5%

## Slide 5: PHC not a priority for public spending on health
Chart: Public spending on primary health care as a share of public spending on health (%)
| ARM | KAZ | RUS | TJK | MDA | MKD | UZB | GEO
Public spending on primary health care as a share of government expenditure on health (%) | 0.42374 | 0.39864 | 0.38356 | 0.3569 | 0.3298 | 0.29982 | 0.2362 | 0.1203
Source: 2018 data, Global Health Expenditure Database

## Slide 6: Vision for PHC in Georgia
  High-quality, evidence-based, person-centred PHC services capable of managing up to 80% of an individual’s health needs throughout their lifetime including prevention, treatment, and management of long-term conditions
  PHC that is aligned with the needs of the target population and accessible equally to urban and rural populations
  Increased trust and confidence in PHC services
  This Roadmap aims to support:
Notes: RECONSIDERING THIS SLIDE

## Slide 7: Key goals for Revised PHC Benefit Package
  Community engagement and awareness
  Increase use of digital health services
  Strengthen PHC as first point of contact
  Transition to networks of multidisciplinary PHC teams accountable for performance outcomes
  Unified PHC model applied universally to urban and rural practices
  Some differences should be acceptable for better alignment of services to priority health needs of empaneled population
Holistic, people-centered PHC
Unified PHC model
  At least one family nurse per family doctor
  Enhance competences and increase autonomy
  Engage in individual risk assessment and brief interventions on behavioral change
  Enhanced role in preventive and patronage services
  Focus on better outcomes for priority conditions: hypertension, CVD, type 2 diabetes, mental health
  Evidence-based PHC interventions
  Introduce education and counselling services for better patient self-management
  Implement new patient pathways
Increased role of family nurse
Chronic diseases management
Notes: RECONSIDERING THIS SLIDE
Deleted the following:
Narrow specialists' services remain as a separate packages for out-patient specialized services

## Slide 8: Health system enablers
Adequate and sustainable funding
Better governance, leadership and participation
Services delivery and integration of care
Invest in healthcare workforce
Well-functioning HIS
Access to medicines and ancillary exams
PHC TRANSFORMATION
Notes: WE can delete this slide

## Slide 9
Better governance, leadership and participation
Adequate and sustainable funding
Services delivery and integration of care
Establish coordination structure (e.g. ministerial task force)
Develop phased implementation plan to manage transition
Develop national PHC facilities investment plan
Strengthen licensing requirements and/or selective contracting
Develop M&E plan for implementation of the new PHC service package
Develop long-term and prudent fiscal scenarios (with MoF)
Institutionalize NHA costing function and continuous revision of tariffs and payment methods
Develop patient pathways for the major conditions
Revise population empanelment and registration procedures
Revise referral mechanisms and promote PHC gatekeeper role

## Slide 10
Invest in healthcare workforce
Well-functioning HIS
Access to medicines and ancillary exams
Assess HRH and develop HRH strategic plan (including 1 nurse per doctor)
Prioritize training interventions aligned with the service delivery model (NCD management, ECD, PHC management)
Define core competences
Introduce mandatory continuing medical education
Develop CME strategy
Prioritize PHC specific HIS that features electronic health records, patient and population health management, and performance monitoring
Define minimum data set to support implementation of the refined PHC model and develop relevant IT system
Assess access to quality medicines and health products according to the PHC basket of services and introduce necessary amendments
Introduce price regulation for medicines and enhance the outpatient medicines benefit program to increase affordability of medicines
Notes: RECONSIDERING THIS SLIDE

## Slide 11: PHC services
  Retain current scope of services:
  Population health management and preventive services for adults
  Preventive services for children and adolescents
  Common acute health problems and urgent care
  Elder care
  Cancer and palliative care
  HIV/HCV/TB screenings and HIV/TB referral services
Integrate packages of priority services:
  Package B (2023-)
  Asthma
  COPD
  Management of outpatient TB/HCV cases
  Women’s health
  Antenatal care
  Package A (2021-)
  Early Child Development (ECD)
  Type II diabetes
  Hypertension and CVD
  Mental health

## Slide 12: Implementation Strategy
  Increase financing for Package A for Early Adopters
  Integrate and strengthen Package A services for Early Adopters:
  Early Child Development (0-5)
  Diabetes Care
  Hypertension and CVD
  Mental health
Phase 1A (2021-2022)
  Review and assess proposed services for Package B
  Increase financing for Package B services for Early Adopters
  Integrate and strengthen Package B services for Early Adopters
  Asthma and COPD
  Management of outpatient TB/HCV cases
  Women’s health and antenatal care
Phase 1B (2023-2025)
  Adopt universal payment model covering the basic costs of all providers offering the essential PHC package in rural and urban settings
  Increase financing for expansion of Package A to all PHC providers
  Integrate and strengthen Package A for all PHC providers nationwide:
  Early Child Development (0-5)
  Diabetes Care
  Hypertension and CVD
  Mental health
Phase 2A (2023-2025)
  Implementation of the refined PHC model is a complex task and requires Ministry leadership, a multidisciplinary task force (clinical, IT, financial, legal) and phased implementation plan with a primary focus on immediate-term activities (2021-2023)
Notes: To clarify the issue of different phases running simultaneously they are identified as phases 1 & 2 and packages A & B
Phase 1 is always Early Adopters (1a is early adopters implementing package A; 1b is Early adopters implementing package B)
Phase 2 is always National level (2a is nationwide implementation of package A; 2b is nationwide implementation of package B)

## Slide 13
Payment model

## Slide 14: Package A add-on capitation (Phase 1A)
Service | Included | Monthly Capitation
ECD | Visit costs for family doctor or nurse (on site, remote, or at home) according to guideline | 2.38 GEL
NDC | Costs of laboratory tests, procedures, one preventive nurse and specialist visit for eye examination provided to chronic patients (diabetes II, Hypertension and CVD) according to guidelines | 4.79 GEL
  Motivational add-on capitation component for Package A services to encourage use of PHC as first contact providers.
  National guidelines were used to calculate the add-on payments.
  The per capita costs were defined by dividing the cost of delivering the defined services to the target population by the total population in need.

## Slide 15: Early Adopters (Phase 1A)
Providers/patients | Phase 1A (Early Adopters) | Phase 1B/2A (Total)
Urban providers | 75 | 
Rural providers | 125 | 
FP/FN teams in Adjara ECD pilot | 105 | 
FP/FN teams (excl. Adjara) | 605 | 2,604
Children | 80,413 | 273,200
NCD patients | 471,531 | 1,602,000
Notes: The last row was missing from the table in the narrative but was included in an earlier presentation (keep or remove?)
Kaija: lets remove.

## Slide 16: Target populations and budget impact estimates (Phase 1A)
 | 1 Sept – 31 Dec 2021 (4 months) | 1 Jan – 31 Dec 2022 (12 months) | Annual cost of universal implementation after 1 January 2023
Annual budget ECD | 535,483 | 1,606,450 | 7,407,047
Annual budget NCD | 4,519,497 | 13,558,492 | 64,489,881
Upfront investments (training, equipment, transportation* etc) | 2,721,295 | 3,082,900 | 1,155,801
TOTAL (not including medications, digital solutions, engagement/comms)** | 7,776,275 | 18,247,842 | 73,052,729
*additional upfront investments may be needed for IT infrastructure, communication depending on the need and currently available solutions.
** The budget impact assessments are not adjusted to inflation (no increase in capitation amount is foreseen during the 3 year period)
Notes: Prevalence data from NCDC and possible coverage targets are taken into account in cost estimates, it is assumed that 70% of children will be covered and 50% of NCD patients will be covered in 2021/2022 from the target population in early adopters’ catchment area
The budget impact assessments are not adjusted to inflation (no increase in capitation amount is foreseen)

## Slide 17: Provider payment for Package A (Phase 1A)
Package A | Average population per FD/FN with patient list of 1,500 | Monthly capitation per enrollee | Average monthly sum if coverage is 70% for NCD and 95% for ECD | Average annual sum GEL
NCD services (diabetes, CVD and hypertension) | 646 | 4.79 | 1,548 | 18,573
ECD services (0-5) | 182 | 2.38 | 303 | 3,639
Average # of patients | 828 | Total GEL | 1,851 | 22,212
Notes: NOTES: I think we can delete the last column. Annual cost after universal implementation is the key but don’t think we need cumulative
Kaija: I would keep it. It shows th no of patients with whome the providers need to start working with. On average is more than a half of their patient list. Also they may be intrested in the toal monthly and annual sum.

## Slide 18: Prerequisites for phased implementation
  Before implementation of Phase 1A, it is essential to develop:
    new national guidelines (when necessary)
    system and criteria to define patients in the catchment area
    technical solutions/details for the add on payment instalments
  .. and define:
    budgetary space
    necessary changes in legislation and contracting process
    list of early adopters and selection process
    necessary upfront investments (equipment, IT-solutions, training)

## Slide 19: Principles of new payment model (Phase 2A)
  Phase 2A includes universal implementation of priority service Package A throughout Georgia
  The calculated rates cover all necessary costs for rural and urban providers working as single practitioner or in groups
  The costs of laboratory tests that minimally should be available at primary care level are considered
NB! Costing model is flexible to amend underlying assumptions
  The new payment model aims to be applicable for all PHC providers offering the essential PHC package in rural and urban settings

## Slide 20: Inputs for costing
  Service providers actual cost information (9 PHC providers)
  Expert opinion if accurate cost information was not available
  Market prices (lab tests) provided by local experts
  National guidelines
  Available standards for facilities and equipment
  Expert opinion
Cost information
Service standards
Next Steps:
  Develop a more detailed bottom-up costing for laboratory tests
  Set up a procedure for regular collection of cost information and renewal of the costing model

## Slide 21: Budget breakdown for Phase 2A (national expansion)
Notes: The budget impact assessments are not adjusted to inflation (no increase in capitation amount is foreseen

## Slide 22: Payment design for Phase 2A
Payment design for a single provider | Sub-packages | Average population per FD/FN | Monthly cost per enrollee | Monthly capitation or lump sum | Annual budget per FD/FN | % of total annual budget
Basic capitation | Minimum costs | 1,500 | 3.33 | 4,990 | 59,884 | 54%
 | Laboratory tests |  | 0.57 |  | 10,188 | 9%
Package A | NCD services | 646 |  | 4.79 | 26,003 | 24%
 | ECD services | 182 |  | 2.38 | 5,198 | 5%
Rent or capitalization allowance |  |  |  |  | 9,360 | 8%
Total annual budget |  |  |  |  | 110,633 | 
Payment design for a group practice (5 FD/FN teams | Sub-packages | Average population per provider | Monthly cost per enrollee | Unified monthly per capita cost | Annual budget per team | % of total annual budget
Basic capitation | Minimum costs | 10,000 | 2.21 | 2.78 | 333,241 | 45%
 | Laboratory tests |  | 0.57 |  |  | 3%
Package A | NCD services | 4,306 |  | 4.79 | 173,351 | 29%
 | ECD services | 734 |  | 2.38 | 19,910 | 3%
Rent or capitalization allowance |  |  |  |  | 67,200 | 11%
Total annual budget |  |  |  |  | 593,702 | 

## Slide 23: Discussion points
Strengthen continuity of care and population health management via empanelment
  The practice of empanelment supports delivery of primary care that is continuous, comprehensive, coordinated, and people-centred by entrusting the health of defined populations to specific PHC teams.
  Empanelment enables the transition from disease treatment to disease prevention and enables PHC systems to shift from reactive care to proactive care leading to improved population health outcomes
  Empanelment is a foundational strategy for strengthening PHC and achieving effective UHC
  Key in establishing stability and continuity of patient care
  Supports strengthening population health management
Notes: TO BE ADDED HERE

## Slide 24: Discussion points cont.
Approach and timeline
  Selected packages: ECD (0-5) and NCD (hypertension, CVD, type II diabetes, mental health);
  Early adopters from 1 September 2021 followed by national scale-up in 2023 (1A, 1B, 2A, 2B)
Number of early adopters/criteria for selection
  Number: approx. 200 rural providers chosen by the Ministry for digital infrastructure enhancement + 25-50 urban providers based on predefined criteria
  Criteria: participation in Adjara pilot; willingness; size of empaneled population (at least 13,000); staffing levels, including nurses; financial stability and ability to mobilize working capital; geographical coverage; etc.

## Slide 25: Discussion points cont.
Payment model and financing
  Add-on motivational capitation for ECD/NCD services;
  Upfront investments (equipment, training, coaches, communication, IT, etc.)
Pharmaceutical benefit expansion plan
  Start with existing scheme and expand the scope and scale of drug benefits for outpatient medicines for priority NCDs from 2022

## Slide 26
Thank you

## Slide 27: Discussion points cont.
3. Supporting selective contracting in urban areas
Adapt new payment model for urban PHC providers who:
  are identified as early adopters (offer essential services and priority services under Package A)
  Meet the selective contracting criteria
  The budget impact could be up to 48 million GEL depending on:
    Number of patients: the patient list is used as a basis to calculate the capitation amount
    Number of providers: how many providers meet the criteria and are ready to be early adopters
    Co-payment: whether co-payments are implemented for specialist services at PHC level

## Slide 28
Roadmap

## Slide 29: PHC Roadmap Implementation (2021)
# | Action | Timeframe | Lead
1 | Present revised PHC PB and Roadmap to PHC Board | February | 
2 | Adopt new ECD and NCD national guidelines and protocols | February | 
3 | Confirm Task Force (ToR, accountability framework) | February | 
4 | Agree on criteria for selection of Early Adopters | February | 
5 | Present finalized costing and budgeting for implementation of the new PHC model including upfront investment in infrastructure, equipment and capacity building | February | 
6 | Complete selection of Early Adopters – PHC providers who will implement the new PHC model with Package A (ECD, diabetes, hypertension, CVD management) | 15 April | 
7 | Define roles/responsibilities of Early Adopters (SOP) | April - May | 
8 | Map and assess PHC training resources (revise as needed) | April | 
9 | Assess training needs of Early Adopters (digital health/technology, change management, protocols/guidelines) | April - May | 
10 | Review/revise nursing competencies and develop strategy to increase role of nurses in PHC | May-June | 
Notes: I adjusted some of the dates/order

## Slide 30: Phase 1A Preparation (2021)
# | Action | Timeframe | Lead
11 | Community Focus Groups (identify perception/understanding of PHC, barriers, expectations, preferences, needs) | May- June | 
12 | Policy Roundtable Urban PHC (Key Stakeholders/Policy makers, local government and providers) | May | 
13 | Policy Roundtable Urban PHC (Key Stakeholders/Policy makers, local government and providers) | May | 
14 | Approve new contracting payment, reporting and verification mechanisms for Early Adopters (incl. motivational payment for Package A) | 1 June | 
15 | Establish criteria to define patients in catchment area | 15 June | 
16 | Approve revised legal and regulatory base – new national guidelines and protocols, changes to the state health programs, including changes to financing mechanism for the priority services packages and empanelment procedures for the target populations for early adopters | 15 June | 
17 | National Policy Roundtable II (Early Adopters/PHC managers and providers) | 30 June | 
18 | Procure and supply equipment to Early Adopters for office and home-based services under new PHC model | June - July | 
19 | Develop and implement community engagement (link to public health) strategy, communication, public awareness | 1 June ongoing | 

## Slide 31: Phase 1A Preparation Continued (2021)
# | Action | Timeframe | Lead
20 | Electronic Health Information System: Unified Management Information System (E-MIS): testing of e-module for patient flow, e-referral, telemedicine for PHC | 1 June – 1 September | 
21 | Register and empanel target populations (families with children under 6 years of age, patients with diabetes, hypertension and CVD) by the early adopters | 1 June – 1 August | 
22 | Establish mechanisms to ensure access to necessary diagnostics for all Early Adopters | June | 
23 | Develop monitoring and evaluation framework, tools and mechanism including digital platform for care coordination, monitoring and continuous improvement of services | June | 
24 | Train up to 60 Master trainers and 600 teams of FP and FN of the Early Adopters in the priority packages (Package A) | 1 June | 
25 | Set up mentoring system and train early adopter PHC workforce (managers, FP, FN) in delivery of Package A services, referrals/counter-referral in accordance with new/revised training module, digital platforms and monitoring and evaluation tools | July - August | 
26 | Contract early adopters for Phase 1A | July - August | 
27 | Initiate service provision by Early Adopters with ongoing supportive supervision and monitoring of implementation of Package A services | September | 

## Slide 32: PHC Roadmap Implementation (September 2021 – March 2023)
# | Action | Timeframe | Lead
27 | Initiate service provision by Early Adopters with ongoing supportive supervision and monitoring of implementation of Package A services | September | 
28 | PHC Implementation Roundtable I (lessons learned from Rural Early Adopters) | November | 
29 | PHC Implementation Roundtable I (lessons learned from Urban Early Adopters) | November | 
30 | PHC Implementation Roundtable II (lessons learned from Rural Early Adopters) | February | 
31 | PHC Implementation Roundtable II (lessons learned from Urban Early Adopters) | February | 
32 | Perform mid-term assessment of Package A implementation in Early Adopters to provide recommendations/refinements for national scale up | 1 July 2022– 1 Sept 2022 | 
33 | Train remaining PHC national workforce (managers, doctors, nurses) to deliver Package A services with the new/revised training module using the tools and coordination, monitoring and evaluation platform for Package A services | 1 Jan 2022 – 1 Dec 2022 | 
34 | Procure equipment (as required) for Phase 2 PHC facilities (not early adopters) implementing Package A under new PHC model | 1 December 2022 | 
35 | Initiate Phase 2A with integration of Package A services nationwide | 1 Jan 2023 | 
36 | Implement Phase 1B with integration of Package B among Early Adopters | 1 March 2023 |