## Cover
CCM Funding - Performance Framework
The indicators agreed for a specific year, are assessed at the end of the corresponding year and influence the next disbursement decision and/or envelope. The evaluation happens in two phases: 1. CCM self assessment by the CCM 2. GF assessment
The self-assessment consists in a desk review where the CCM, using the evaluation form, ensures that necessary documentation is available and ready to be provided (physically or electronically) when requested, in order to confirm the CCM’s and CCM Secretariat's level of compliance for each indicator. Once the self assessment phase is completed, CT and CCM hub will review the information and inform on the final results and their implications.
To complete the Self Assesment the CCM should take into account only the annual period covered by the performance framework (Year 1, Year 2 or Year 3) and ensure the compliance to the corresponding indicators. The column "CCM Self Assessment" has the options "Yes", "No" and "Pending". In case of "No" and "Pending" the CCM should provide more information on the reasons of this result or when the information will be provided.
Version August 2017

## Page de garde (hidden)
Financement des CCM - Cadre de performance (Performance Framework)
Les indicateurs convenus pour une année donnée sont évalués à la fin de l'année correspondante et influencent la prochaine décision de décaissement et/ou enveloppe. L'évaluation se déroule en deux phases: 1. L'auto-évaluation du CCM par le CCM 2. Evaluation par le Fonds mondial
L'auto-évaluation consiste en une revue où le CCM, en utilisant le formulaire d'évaluation, garantit que la documentation nécessaire est disponible et est prête à être fournie (physiquement ou électroniquement) sur demande, afin de confirmer le niveau de conformité du CCM et du Secrétariat du CCM pour chaque indicateur. Une fois la phase d'auto-évaluation terminée, l'Equipe pays et le CCM examineront les informations et partageront les résultats finaux ainsi que leurs implications.
Pour compléter l'auto-évaluation, le CCM ne doit prendre en compte que la période annuelle couverte par le cadre de performance (Année 1, Année 2 ou Année 3) et s'assurer de la conformité des indicateurs correspondants. La colonne "CCM Self Assessment" a les options "Oui", "Non" et "En attente". Dans le cas de "Non" et "en attente", le CCM devra fournir plus d'informations sur les raisons de ce résultat ou la date à laquelle les informations seront fournies.
Version Août 2017

## Página de cubierta (hidden)
Financiamiento del MCP - Marco de desempeño
Los indicadores acordados para un año determinado se evalúan al final del año correspondiente e influyen en la próxima decisión de desembolso y/o sobre ("enveloppe"). La evaluación se realiza en dos fases: 1. Autoevaluación del MCP por el MCP 2. Evaluación del Fondo Mundial
La autoevaluación consiste en una revisión en la que el MCP, mediante el formulario de evaluación, garantiza que la documentación necesaria este disponible y lista para ser suministrada (físicamante o electrónicamente) cuando se solicite, para confirmar el nivel de cumplimiento del MCP y la Secretaría del MCP para cada indicador. Una vez finalizada la fase de autoevaluación, el Equipo de País y el MCP revisarán la información y se informará sobre los resultados finales y sus implicaciones.
Para completar la Autoevaluación, el MCP debe tener en cuenta solamente el período anual cubierto por el marco de desempeño (Año 1, Año 2 o Año 3) y asegurar el cumplimiento de los indicadores correspondientes. La columna "Autoevaluación CCM" tiene las opciones "Sí", "No" y "Pendiente". En el caso de "No" y "Pendiente", el MCP debe proporcionar más información sobre las razones de este resultado o cuándo se proporcionará dicha información.
Versión Agosto 2017

## PerformanceFrameworkYear1 (hidden)
CCM Funding - Performance Framework
CCM Name: | CCM Georgia
CCM Agreement No: | GEO-CFUND-1708
Starting Date: | 2017-03-01
Year of Agreement: | Year 1
The indicators below can influence the disbursement amount.
CCM Performance |  | Evaluation Source | Comments
Indicator 1: | (CCM0) Latest Eligibility and Performance Assessment (EPA) overall ratings is at least at 90% compliance. OR Latest EPA has improved at least 30% since last assessement. (MANDATORY) | Latest EPA submitted to the Global Fund
Indicator 2: | (CCM1) CCM documents evidence that they are making all the necessary efforts to avoid stock-outs of key drugs AND 'emergency disbursement' to prevent them. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters)
Indicator 3: | (CCM2) CCM documents evidence that they are making all the necessary efforts to avoid grants in the portfolio which receive two consecutive B2/C ratings. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters)
Indicator 4: | (CCM3) Number of CCM documents developed and shared with regard to the development of Transition Plans to sustain the National TB and HIV Strategies 2016 - 2020. | (CCM3) CCM has developed: 2 Transition and Readiness Assessment activities and reports 4 National workshops on development of Transition Plans 2 Joint meetings of CCM 's TWG to discuss the final drafts of the Transition Plans 1 CCM meeting to endorse the Transition Plan
CCM Secretariat Performance |  | Evaluation Source
Indicator 1: | CCM assesses annually the overall CCM Secretariat Performance. Assessment outcome should be one of those four values: "Exceptional", "Performing well", "A few minor issues", "Serious Issues". | CCM Secretariat assessment results, including the CCM meeting minutes with the discussion about the assesment's results
Indicator 2: | 100% of the agenda/meeting minutes of CCM meetings (plenary and Oversight Committee) in the next 12 months circulated to all CCM members/alternates and GF Secretariat (FPM, CCM Hub). For the Agenda within less than 7 calendar days before the meeting and for the meeting minutes 7 calendar days after. | Emails shared with the CCM Hub (ccm@theglobalfund.org)
Indicator 3: | In the context of CCM Funding, annual work plan and financial reports are submitted to GF (FPM, CCM Hub) within one month after the end of the (funding) year. | Emails shared with the CCM Hub (ccm@theglobalfund.org)
Indicator 4: | Eligibility and Performance Assessment (EPA) Improvement plan and CCM Contacts are updated at least every 3 months. | Data in the systems, which should not be outdated for more than 3 months, at any given time.
Indicator 5: | CCM Secretariat is facilitating the information sharing between country level activities and GF Secretariat as well as supporting Country Teams when in countries. | Using the same scales as #1, assessed by the Global Fund.
Version August 2017

## PerformanceFrameworkYear2 (hidden)
CCM Funding - Performance Framework
CCM Name: | CCM Georgia
CCM Agreement No: | GEO-CFUND-1708
Starting Date: | 2017-03-01
Year of Agreement: | Year 2
The indicators below can influence the disbursement amount.
CCM Performance |  | Evaluation Source | Comments
Indicator 1: | (CCM0) Latest Eligibility and Performance Assessment (EPA) overall ratings is at least at 90% compliance. OR Latest EPA has improved at least 30% since last assessement. (MANDATORY) | Latest EPA submitted to the Global Fund
Indicator 2: | (CCM1) CCM documents evidence that they are making all the necessary efforts to avoid stock-outs of key drugs AND 'emergency disbursement' to prevent them. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters)
Indicator 3: | (CCM2) CCM documents evidence that they are making all the necessary efforts to avoid grants in the portfolio which receive two consecutive B2/C ratings. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters)
Indicator 4: | (CCM3) Number of CCM documents developed and shared with regard to the development of Transition Plans to sustain the National TB and HIV Strategies 2016 - 2020. | (CCM3) CCM has developed: 2 Transition and Readiness Assessment activities and reports 4 National workshops on development of Transition Plans 2 Joint meetings of CCM 's TWG to discuss the final drafts of the Transition Plans 1 CCM meeting to endorse the Transition Plan
CCM Secretariat Performance |  | Evaluation Source
Indicator 1: | CCM assesses annually the overall CCM Secretariat Performance. Assessment outcome should be one of those four values: "Exceptional", "Performing well", "A few minor issues", "Serious Issues". | CCM Secretariat assessment results, including the CCM meeting minutes with the discussion about the assesment's results
Indicator 2: | 100% of the agenda/meeting minutes of CCM meetings (plenary and Oversight Committee) in the next 12 months circulated to all CCM members/alternates and GF Secretariat (FPM, CCM Hub). For the Agenda within less than 7 calendar days before the meeting and for the meeting minutes 7 calendar days after. | Emails shared with the CCM Hub (ccm@theglobalfund.org)
Indicator 3: | In the context of CCM Funding, annual work plan and financial reports are submitted to GF (FPM, CCM Hub) within one month after the end of the (funding) year. | Emails shared with the CCM Hub (ccm@theglobalfund.org)
Indicator 4: | Eligibility and Performance Assessment (EPA) Improvement plan and CCM Contacts are updated at least every 3 months. | Data in the systems, which should not be outdated for more than 3 months, at any given time.
Indicator 5: | CCM Secretariat is facilitating the information sharing between country level activities and GF Secretariat as well as supporting Country Teams when in countries. | Using the same scales as #1, assessed by the Global Fund.
Version August 2017

## PerformanceFrameworkYear3 (hidden)
CCM Funding - Performance Framework
CCM Name: | CCM Georgia
CCM Agreement No: | GEO-CFUND-1708
Starting Date: | 2017-03-01
Year of Agreement: | Year 3
The indicators below can influence the disbursement amount.
CCM Performance |  | Evaluation Source | Comments
Indicator 1: | (CCM0) Latest Eligibility and Performance Assessment (EPA) overall ratings is at least at 90% compliance. OR Latest EPA has improved at least 30% since last assessement. (MANDATORY) | Latest EPA submitted to the Global Fund
Indicator 2: | (CCM1) CCM documents evidence that they are making all the necessary efforts to avoid stock-outs of key drugs AND 'emergency disbursement' to prevent them. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters)
Indicator 3: | (CCM2) CCM documents evidence that they are making all the necessary efforts to avoid grants in the portfolio which receive two consecutive B2/C ratings. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters)
Indicator 4: | (CCM3) Number of CCM documents developed and shared with regard to the development of Transition Plans to sustain the National TB and HIV Strategies 2016 - 2020. | (CCM3) CCM has developed: 2 Transition and Readiness Assessment activities and reports 4 National workshops on development of Transition Plans 2 Joint meetings of CCM 's TWG to discuss the final drafts of the Transition Plans 1 CCM meeting to endorse the Transition Plan
CCM Secretariat Performance |  | Evaluation Source
Indicator 1: | CCM assesses annually the overall CCM Secretariat Performance. Assessment outcome should be one of those four values: "Exceptional", "Performing well", "A few minor issues", "Serious Issues". | CCM Secretariat assessment results, including the CCM meeting minutes with the discussion about the assesment's results
Indicator 2: | 100% of the agenda/meeting minutes of CCM meetings (plenary and Oversight Committee) in the next 12 months circulated to all CCM members/alternates and GF Secretariat (FPM, CCM Hub). For the Agenda within less than 7 calendar days before the meeting and for the meeting minutes 7 calendar days after. | Emails shared with the CCM Hub (ccm@theglobalfund.org)
Indicator 3: | In the context of CCM Funding, annual work plan and financial reports are submitted to GF (FPM, CCM Hub) within one month after the end of the (funding) year. | Emails shared with the CCM Hub (ccm@theglobalfund.org)
Indicator 4: | Eligibility and Performance Assessment (EPA) Improvement plan and CCM Contacts are updated at least every 3 months. | Data in the systems, which should not be outdated for more than 3 months, at any given time.
Indicator 5: | CCM Secretariat is facilitating the information sharing between country level activities and GF Secretariat as well as supporting Country Teams when in countries. | Using the same scales as #1, assessed by the Global Fund.
Version August 2017

## Evaluation_Y1
CCM Funding - Performance Framework
Evaluation
CCM Name: | CCM Georgia
CCM Agreement No: | GEO-CFUND-1708
Starting Date: | 2017-03-01
Year of Agreement: | Year 1
Column1 | CCM PERFORMANCE Indicators | Evaluation Source | CCM Self Assessment | Comments | CT Assessment (Please comment if not in agreement with CCM Self-assessment) | CCM Hub
Indicator 1: | (CCM0) Latest Eligibility and Performance Assessment (EPA) overall ratings is at least at 90% compliance. OR Latest EPA has improved at least 30% since last assessement. (MANDATORY) | Did the EPA submitted show an improvement of at least 30%? | Yes | The CCM was fully compliant with 9 indicators out of 18 during the assessment. Now it shows full comliance with 16 indicators out of 18. Thus significant improvement in percentage is shown.
Indicator 2: | (CCM1) CCM documents evidence that they are making all the necessary efforts to avoid stock-outs of key drugs AND 'emergency disbursement' to prevent them. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters) | Yes | Oversight Commettee regularly reviews dashboards and issues the reccomnedations; the site visits including those to the regions are regularly conducted. During the site visits special attention is goven to meeting ith SR-s, SSR-s, progrma beneficaries. The results of OC activities including dashboards are presented to the CCM; GF program implementation is regularly presented at every CCM meeting by the PR
Indicator 3: | (CCM2) CCM documents evidence that they are making all the necessary efforts to avoid grants in the portfolio which receive two consecutive B2/C ratings. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters) | Yes | Principal Recipient of the Global Fund grants - Natinal Center for disease Control and Publiac Heath achieved and sustains high performance rate - A2.
Indicator 4: | (CCM3) Number of CCM documents developed and shared with regard to the development of Transition Plans to sustain the National TB and HIV Strategies 2016 - 2020. | (CCM3) CCM has developed: 2 Transition and Readiness Assessment activities and reports 4 National workshops on development of Transition Plans 2 Joint meetings of CCM 's TWG to discuss the final drafts of the Transition Plans 1 CCM meeting to endorse the Transition Plan | Yes | This indicator has been achieved during the previous reporting period. During the current reporting period 4 meetings of the CCM , 5 meetings of the PAAC - main consultative platform for the CCM - and CSO forum were conducted: 1) 86th CCM meeting, April 10, 2017. Main topics for discussion: to present and discuss the current status of implementation of the Global Fund’s projects, the report of the Oversight Committee, EHRN Initiative on establishment of community-level M&E for NSP and OST in Georgia, Information on the Global Fund Regional Program Community Actions to Increase Access of MSM and TG People to HIV Services in Eastern Europe and Central Asia, Outcomes of the meetings of community organizations aimed at better engagement in the processes of development of funding request. 2) PAAC Meeting 8. May 11, 2017. Objectives: to discuss the feedback to Georgian Transitional Plan comments on TSP and elaborate the comments of PAAC on proposed amendments and recommendations 3) PAAC Meeting 9. June 28, 2017. Objectives: to inform the group members and discuss on the CCM transition plan outline presented by the Euro Health Group (EHG) consultants; to define the PAAC role in the development of the CCM transition plan and outline modus operandi of the group 4) 87th CCM meeting, August 7, 2017. Main topics of the meeting: The current status of implementation of the Global Fund’s projects, the report of the Oversight Committee, dashboards recommendations, the Global Fund Allocation Letter, funding application approaches, the role of the PAAC in the process of preparation of funding requests, assigning to the PAAC a role of the platform in the development of the requests. In order to ensure broad country dialogue with an active involvement of all stakeholders, especially those representing KAPs and vulnerable populations in the working process of preparation of programs continuation requests it was decided to expand the composition of the PAAC. The members were requested to disseminate this information among interested parties; the corresponding announcement was published on the CCM web-site. 5) PAAC Meeting 10. August 11, 2017. Objectives: to discuss the main strategic scenarios/options for CCM transition; to discuss the draft outline for CCM transition plan developed by the EHG consultants, concerning the future regulatory framework, structure, functions and financial mechanisms of the CCM 6) PAAC Meeting 11. November 7, 2017. Objectives: to discuss the Funding Request preparation process. 7) PAAC Meeting 12. November 22, 2017. Objectives: to meet with EHG consultants to discuss the draft CCM Transition Plan 8) 88th CCM meeting. November 24, 2017. Main topics of the meeting: Programs implementation status including planned reallocation/reprogramming activities, timelines of the submission to the GF of the continuation request (decision - August 6); the new initiative called end AIDS epidemic in Georgia; reselection of the PR; brief outline of the first draft CCM transition plan; 9) 89th CCM meeting. Main topics of the meeting: HIV and TB grants implementation status/ The process of preparation of funding requests; Savings under current programs/Reprogramming proposals; report of the OC; 10) On February 20, 2018 Civil Society Forum organized by Georgia CCM was conducted. The concept of the forum was developed by the representatives of Civil Sector of Georgia CCM. The forum was very representative. More than 100 participants attended including broad representation of community organizations, KAPs, local NGOs, representatives of the Government Sector and International Organizations. The forum was covered by mass-media. The following topics were presented and discussed: The state support for the transition period / Trends in growth of state funding, the Global Fund current grants, the process of preparation of programs continuation request, HIV/AIDS and TB control current initiatives and the role of the CSOs in their implementation. The notes of special gratitude were received by the Georgia CCM Secretariat from community organizations for organizing such an important and successful event.
Column1 | CCM SECRETARIAT Indicators | Evaluation Source | CCM Self Assessment | Comments | CT Assessment (Please comment if not in agreement with CCM Self-assessment) | CCM Hub
Indicator 1: | CCM assesses annually the overall CCM Secretariat Performance. Assessment outcome should be one of those four values: "Exceptional", "Performing well", "A few minor issues", "Serious Issues". | Did the CCM provide to ccm@theglobalfund.org the CCM Secretariat assessment results, including the CCM meeting minutes with the discussion about the assesment's results? | Exceptional | The CCM provided the results of the assessment and desciption of the process to FPM and CCM Hub on March 6, 2018
Indicator 2: | 100% of the agenda/meeting minutes of CCM meetings (plenary and Oversight Committee) in the next 12 months circulated to all CCM members/alternates and GF Secretariat (FPM, CCM Hub). For the Agenda within less than 7 calendar days before the meeting and for the meeting minutes 7 calendar days after. | Has the CCM Secretariat shared the agenda/meeting minutes of CCM meeting, as agreed? | Yes | The CCM MoMs are shared with the CCM as per regulations of the Geo CCM Governance Manual (two weeks ). They are are unprecendentally precize, comprehensive, with high attention to all details. They are developed in two languages (Georgian and English). The MoMs, including the reports on OC activities and dashboards are placed on the CCM web-site. The latter represents an effectiive information resource hub and maintained directly by the CCM Secretariat. Thus this is conditional "yes". In new reporting period the Secretariat will stick more to the finally agreed indicator.
Indicator 3: | In the context of CCM Funding, annual work plan and financial reports submitted to GF (FPM, CCM Hub) within one month after the end of the (funding) year. | Has the CCM Secretariat provided CCM Funding documentation as requested? | Yes | The deadlines are strictly observed
Indicator 4: | Eligibility and Performance Assessment (EPA) Improvement plan and CCM Contacts are updated at least every 3 months. | Has the CCM Secretariat updated the Improvement Plan and CCM Contacts every 3 months, as agreed? | Yes | Starting from November 2017 the improvement plan has been updated even on a monthly basis
Indicator 5: | CCM Secretariat is facilitating the information sharing between country level activities and GF Secretariat as well as supporting Country Teams when in countries. | Has the CCM Secretariat provided the necessary support to GF Secretariat and CTs, including the information sharing incountry, as requested? |  | Exceptional
Yes
Version August 2017

## Evaluation_Y2 (hidden)
CCM Funding - Performance Framework
Evaluation
CCM Name: | CCM Georgia
CCM Agreement No: | GEO-CFUND-1708
Starting Date: | 2017-03-01
Year of Agreement: | Year 2
Column1 | CCM PERFORMANCE Indicators | Evaluation Source | CCM Self Assessment | Comments | CT Assessment (Please comment if not in agreement with CCM Self-assessment) | CCM Hub
Indicator 1: | (CCM0) Latest Eligibility and Performance Assessment (EPA) overall ratings is at least at 90% compliance. OR Latest EPA has improved at least 30% since last assessement. (MANDATORY) | Did the EPA submitted show an improvement of at least 30%?
Indicator 2: | (CCM1) CCM documents evidence that they are making all the necessary efforts to avoid stock-outs of key drugs AND 'emergency disbursement' to prevent them. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters)
Indicator 3: | (CCM2) CCM documents evidence that they are making all the necessary efforts to avoid grants in the portfolio which receive two consecutive B2/C ratings. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters)
Indicator 4: | (CCM3) Number of CCM documents developed and shared with regard to the development of Transition Plans to sustain the National TB and HIV Strategies 2016 - 2020. | (CCM3) CCM has developed: 2 Transition and Readiness Assessment activities and reports 4 National workshops on development of Transition Plans 2 Joint meetings of CCM 's TWG to discuss the final drafts of the Transition Plans 1 CCM meeting to endorse the Transition Plan
Column1 | CCM SECRETARIAT Indicators | Evaluation Source | CCM Self Assessment | Comments | CT Assessment (Please comment if not in agreement with CCM Self-assessment) | CCM Hub
Indicator 1: | CCM assesses annually the overall CCM Secretariat Performance. Assessment outcome should be one of those four values: "Exceptional", "Performing well", "A few minor issues", "Serious Issues". | Did the CCM provide to ccm@theglobalfund.org the CCM Secretariat assessment results, including the CCM meeting minutes with the discussion about the assesment's results?
Indicator 2: | 100% of the agenda/meeting minutes of CCM meetings (plenary and Oversight Committee) in the next 12 months circulated to all CCM members/alternates and GF Secretariat (FPM, CCM Hub). For the Agenda within less than 7 calendar days before the meeting and for the meeting minutes 7 calendar days after. | Has the CCM Secretariat shared the agenda/meeting minutes of CCM meeting, as agreed?
Indicator 3: | In the context of CCM Funding, annual work plan and financial reports submitted to GF (FPM, CCM Hub) within one month after the end of the (funding) year. | Has the CCM Secretariat provided CCM Funding documentation as requested?
Indicator 4: | Eligibility and Performance Assessment (EPA) Improvement plan and CCM Contacts are updated at least every 3 months. | Has the CCM Secretariat updated the Improvement Plan and CCM Contacts every 3 months, as agreed?
Indicator 5: | CCM Secretariat is facilitating the information sharing between country level activities and GF Secretariat as well as supporting Country Teams when in countries. | Has the CCM Secretariat provided the necessary support to GF Secretariat and CTs, including the information sharing incountry, as requested?
Version August 2017

## Evaluation_Y3 (hidden)
CCM Funding - Performance Framework
Evaluation
CCM Name: | CCM Georgia
CCM Agreement No: | GEO-CFUND-1708
Starting Date: | 2017-03-01
Year of Agreement: | Year 3
Column1 | CCM PERFORMANCE Indicators | Evaluation Source | CCM Self Assessment | Comments | CT Assessment (Please comment if not in agreement with CCM Self-assessment) | CCM Hub
Indicator 1: | (CCM0) Latest Eligibility and Performance Assessment (EPA) overall ratings is at least at 90% compliance. OR Latest EPA has improved at least 30% since last assessement. (MANDATORY) | Did the EPA submitted show an improvement of at least 30%?
Indicator 2: | (CCM1) CCM documents evidence that they are making all the necessary efforts to avoid stock-outs of key drugs AND 'emergency disbursement' to prevent them. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters)
Indicator 3: | (CCM2) CCM documents evidence that they are making all the necessary efforts to avoid grants in the portfolio which receive two consecutive B2/C ratings. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters)
Indicator 4: | (CCM3) Number of CCM documents developed and shared with regard to the development of Transition Plans to sustain the National TB and HIV Strategies 2016 - 2020. | (CCM3) CCM has developed: 2 Transition and Readiness Assessment activities and reports 4 National workshops on development of Transition Plans 2 Joint meetings of CCM 's TWG to discuss the final drafts of the Transition Plans 1 CCM meeting to endorse the Transition Plan
Column1 | CCM SECRETARIAT Indicators | Evaluation Source | CCM Self Assessment | Comments | CT Assessment (Please comment if not in agreement with CCM Self-assessment) | CCM Hub
Indicator 1: | CCM assesses annually the overall CCM Secretariat Performance. Assessment outcome should be one of those four values: "Exceptional", "Performing well", "A few minor issues", "Serious Issues". | Did the CCM provide to ccm@theglobalfund.org the CCM Secretariat assessment results, including the CCM meeting minutes with the discussion about the assesment's results?
Indicator 2: | 100% of the agenda/meeting minutes of CCM meetings (plenary and Oversight Committee) in the next 12 months circulated to all CCM members/alternates and GF Secretariat (FPM, CCM Hub). For the Agenda within less than 7 calendar days before the meeting and for the meeting minutes 7 calendar days after. | Has the CCM Secretariat shared the agenda/meeting minutes of CCM meeting, as agreed?
Indicator 3: | In the context of CCM Funding, annual work plan and financial reports submitted to GF (FPM, CCM Hub) within one month after the end of the (funding) year. | Has the CCM Secretariat provided CCM Funding documentation as requested?
Indicator 4: | Eligibility and Performance Assessment (EPA) Improvement plan and CCM Contacts are updated at least every 3 months. | Has the CCM Secretariat updated the Improvement Plan and CCM Contacts every 3 months, as agreed?
Indicator 5: | CCM Secretariat is facilitating the information sharing between country level activities and GF Secretariat as well as supporting Country Teams when in countries. | Has the CCM Secretariat provided the necessary support to GF Secretariat and CTs, including the information sharing incountry, as requested?
Version August 2017

## Lookup (hidden)
YesNo | Indicator | Evaluation Source | Assessment | Assessment | Year
Yes | (CCM1) CCM documents evidence that they are making all the necessary efforts to avoid stock-outs of key drugs AND 'emergency disbursement' to prevent them. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters) | Yes | Exceptional | Year 1
No | (CCM2) CCM documents evidence that they are making all the necessary efforts to avoid grants in the portfolio which receive two consecutive B2/C ratings. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters) | No | Performing well | Year 2
| (CCM3) The CCM is working with the government at the necessary levels in order to secure the required Counter-Part Financing. CCM documents evidence that they are making all the necessary efforts to ensure governement honors it commitments. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters) | Pending | Minor issues | Year 3
| (CCM4) The CCM supports the Host Country in its obligation to take all appropriate and necessary actions to ensure that the Global Fund is accorded with privileges and immunities. CCM documents evidence that they are supporting the Host Country in its obligation to take all appropriate and necessary actions to ensure that the Global Fund is accorded with privileges and immunities. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters) |  | Serious Issues
| (CCM5) The CCM is negotiating with the government and municipalities to take over all activities currently supported from the Global Fund grant. CCM documents evidence that they are making all the necessary efforts to secure government/municipality financing of all activities currently supported from the Global Fund grant. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters)
| (CCM6) % of CCM activities organized to develop the Transition Plans to sustain the National TB Program 2016-2020. CCM will develop: - Preparation of Transition and Readiness Assessment report. - Joint meetings of CCM 's TWG to discuss the final drafts of the Transition Plans CCM meeting to endorse the Transition Plan” with “Preparation of Transition Plan. - Joint meetings of CCM 's TWG to discuss the final drafts of the Transition Plans CCM meeting to endorse the Transition Plan” | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters)
| (CCM7) Number of CCM documents developed and shared with regard to the development of Transition Plans to sustain the National TB Strategy 2016 - 2020. CCM will develop: - Transition and Readiness Assessment report. - The final drafts of the Transition Plan. - Endorsement of the Transition Plan. | Can the CCM provide on demand the evidence they have done necessary efforts to reach the objective? (meeting minutes, emails, letters)

## ListCCM (hidden)
OrganizationID | OrganizationName | OrganizationAcronym | Type
96 | CCM Afghanistan | AFG | CCM
196 | CCM Albania | ALB | CCM
78 | CCM Algeria | DZA | CCM
98 | CCM Angola | AGO | CCM
99 | CCM Armenia | ARM | CCM
100 | CCM Azerbaijan | AZE | CCM
101 | CCM Bangladesh | BAN | CCM
102 | CCM Belarus | BLR | CCM
190 | CCM Belize | BEL | CCM
103 | CCM Benin | BEN | CCM
104 | CCM Bhutan | BTN | CCM
189 | CCM Bolivia | BOL | CCM
105 | CCM Bosnia and Herzegovina | BIH | CCM
106 | CCM Botswana | BOT | CCM
107 | CCM Bulgaria | BUL | CCM
108 | CCM Burkina Faso | BUR | CCM
109 | CCM Burundi | BRN | CCM
110 | CCM Cambodia | CAM | CCM
201 | CCM Cameroon | CMR | CCM
111 | CCM Cape Verde | CAP | CCM
112 | CCM Central African Republic | CAF | CCM
113 | CCM Chad | TCD | CCM
115 | CCM Colombia | COL | CCM
116 | CCM Comoros | COM | CCM
121 | CCM Congo (Democratic Republic) | ZAR | CCM
118 | CCM Congo (Republic of) | COG | CCM
83 | CCM Costa Rica | COR | CCM
119 | CCM Cote d'Ivoire | CIV | CCM
95 | CCM Croatia | HRV | CCM
120 | CCM Cuba | CUB | CCM
122 | CCM Djibouti | DJB | CCM
123 | CCM Dominican Republic | DMR | CCM
84 | CCM Ecuador | ECU | CCM
124 | CCM Egypt | EGY | Non-CCM
125 | CCM El Salvador | SLV | CCM
76 | CCM Equatorial Guinea | GNQ | CCM
126 | CCM Eritrea | ERT | CCM
127 | CCM Ethiopia | ETH | CCM
194 | CCM Fiji | FJI | CCM
128 | CCM Gabon | GAB | CCM
129 | CCM Gambia | GMB | CCM
663 | CCM Georgia | GEO | CCM
85 | CCM Ghana | GHN | CCM
131 | CCM Guatemala | GUA | CCM
132 | CCM Guinea | GIN | CCM
197 | CCM Guinea-Bissau | GNB | CCM
86 | CCM Guyana | GYA | CCM
97 | CCM Haiti | HTI | CCM
133 | CCM Honduras | HND | CCM
134 | CCM India | IDA | CCM
135 | CCM Indonesia | IND | CCM
136 | CCM Iran (Islamic Republic of) | IRN | CCM
137 | CCM Iraq | IRQ | CCM
87 | CCM Jamaica | JAM | CCM
139 | CCM Kazakhstan | KAZ | CCM
140 | CCM Kenya | KEN | CCM
141 | CCM Kosovo | KOS | CCM
142 | CCM Kyrgyzstan | KGZ | CCM
193 | CCM Lao PDR | LAO | CCM
143 | CCM Lesotho | LSO | CCM
144 | CCM Liberia | LBR | CCM
145 | CCM Macedonia | MKD | CCM
146 | CCM Madagascar | MDG | CCM
147 | CCM Malawi | MLW | CCM
1249 | CCM Malaysia | MYS | CCM
149 | CCM Mali | MAL | CCM
150 | CCM Mauritania | MRT | CCM
208 | CCM Mauritius | MVS | CCM
164 | CCM Moldova | MOL | CCM
151 | CCM Mongolia | MON | CCM
152 | CCM Montenegro | MNT | CCM
153 | CCM Morocco | MOR | CCM
154 | CCM Mozambique | MOZ | CCM
88 | CCM Myanmar | MYN | CCM
155 | CCM Namibia | NMB | CCM
156 | CCM Nepal | NEP | Non-CCM
89 | CCM Nicaragua | NIC | CCM
157 | CCM Niger | NGR | CCM
158 | CCM Nigeria | NGA | CCM
159 | CCM Pakistan | PKS | CCM
90 | CCM Panama | PAN | CCM
160 | CCM Papua New Guinea | PNG | CCM
161 | CCM Paraguay | PRY | CCM
162 | CCM Peru | PER | CCM
163 | CCM Philippines | PHL | CCM
165 | CCM Romania | ROM | CCM
166 | CCM Rwanda | RWN | CCM
91 | CCM São Tomé and Príncipe | STP | CCM
167 | CCM Senegal | SNG | CCM
168 | CCM Serbia | SRB | CCM
169 | CCM Sierra Leone | SLE | CCM
210 | CCM Solomon Islands | SLB | CCM
171 | CCM South Africa | SAF | CCM
199 | CCM South Sudan | SSD | Non-CCM
172 | CCM Sri Lanka | SRL | CCM
94 | CCM Sudan | SUD | CCM
173 | CCM Suriname | SUR | CCM
174 | CCM Swaziland | SWZ | CCM
671 | CCM Syria | SYR | CCM
175 | CCM Tajikistan | TAJ | CCM
670 | CCM Tanzania | TNZ | CCM
176 | CCM Thailand | THA | CCM
200 | CCM Timor Leste | TMP | CCM
177 | CCM Togo | TGO | CCM
178 | CCM Tunisia | TUN | CCM
179 | CCM Turkmenistan | TKM | CCM
180 | CCM Uganda | UGD | CCM
181 | CCM Ukraine | UKR | CCM
183 | CCM Uzbekistan | UZB | CCM
184 | CCM Viet Nam | VTN | CCM
185 | CCM Yemen | YEM | CCM
186 | CCM Zambia | ZAM | CCM
187 | CCM Zanzibar | ZAN | CCM
188 | CCM Zimbabwe | ZIM | CCM
1428 | Non-CCM Coordination Committee for Prevention and Fight with HIV/AIDS | CCRF | Non-CCM
209 | Non-CCM DPR of Korea | PRK | Non-CCM
1433 | Non-CCM Palestine | PSE | Non-CCM
170 | Non-CCM Somalia | SACBHSC | Non-CCM
44 | Non-CCM West Bank and Gaza Strip | UNTG | Non-CCM
636 | RCM Abidjan-Lagos Corridor Organisation | OCAL | RCM
204 | RCM Elimination of Malaria in Mesoamerica and Hispaniola Island (EMMIE) | EMMIE | RCM
205 | RCM Organisation of Eastern Caribbean States | OECS | RCM
81 | RCM Pan Caribbean Partnership against HIV/AIDS (PANCAP) | PANCAP | RCM
1348 | RCM Regional Steering Committee for the Regional Artemisinin Initiative (RAI) | RCM SEA | RCM
4234 | RCM Southern Africa Regional Coordinating Mechanism (SARCM) | SARCM | RCM
195 | RCM Western Pacific | PIRMCCM | RO
3881 | RO African Network for the Care of Children Affected by HIV/AIDS (ANECCA) | ANECCA | RO
3988 | RO AIDS and Rights Alliance for Southern Africa and Enda Santé (ARASA-ENDA) | ARASA | RO
5556 | RO Alliance Nationale Contre le Sida (ANCS) | ANCS | RO
19 | RO Asia Pacific Network of People Living with HIV/AIDS (APN+) | APN | RO
5557 | RO Australian Federation of AIDS Organisations (AFAO) | AFAO | RO
5171 | RO Caribbean Vulnerable Communities Coalition (CVC) and El Centro de Orientación e Investigación Integral (COIN) | CVCCOIN | RO
555 | RO Center for Health Policies and Studies (PAS Center) | PAS | RO
206 | RO Central American Network of People with HIV (REDCA+) | REDCA+ | RO
3920 | RO East Europe and Central Asia Union of PLHIV (ECUO) | ECUO | RO
5555 | RO East, Central and Southern Africa Health Community (ECSA-HC) | ECSA | RO
3882 | RO Elimination 8 (E8) | E8 | RO
5558 | RO Eurasian Coalition on Male Health (ECOM) | ECOM | RO
1418 | RO Eurasian Harm Reduction Network (EHRN) | EHRN | RO
5559 | RO Handicap International (HI) | HI | RO
66 | RO Humanist Institute for Cooperation with Developing Countries, Southern Africa (HIVOS) | HIVOS | RO
5561 | RO Intergovernmental Authority on Development (IGAD) | IGAD | RO
61 | RO International Community of Women Living with HIV/AIDS (ICW Latina) | ICW | RO
5560 | RO International HIV/AIDS Alliance (IHAA) | IHAA | RO
5562 | RO International HIV/AIDS Alliance in Ukraine (IHAU) | IHAU | RO
3441 | RO International Organization for Migration (IOM) | IOM | RO
5563 | RO International Treatment Preparedness Coalition - West Africa (ITPC-WA) | ITPC-WA | RO
1926 | RO Kenya AIDS NGOs Consortium (KANCO) | KANCO | RO
67 | RO Latin American and Caribbean Network of Transgender People (REDLACTRANS) | REDLACTRANS | RO
5564 | RO Lubombo Spatial Development Initiative 2 (LSDI-2) | LSDI-2 | RO
5565 | RO Middle East and North Africa Harm Reduction Association (MENAHRA) | MENAHRA | RO
5058 | RO Organismo Andino de Salud - Convenio Hipólito Unanue (ORAS CONHU) | ORAS-CONHU | RO
22 | RO RedTraSex | REDTRSX | RO
5253 | RO Regional Oversight Mechanism for Latin America | ROMLAM | RO
207 | RO Southern African Development Community Secretariat | SADC | RO
5566 | RO Youth Leadership, Education, Advocacy and Development (Youth LEAD) | Youth LEAD | RO
| RCM Africa Regional Coordinating Mechanism |  | RCM